## New Production Status Summary
New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04 | New Production Status Summary 2022-11-04
Project Name | Project Id | PM Project Name | PM Project Id | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM
Rally X10 Family | 1135 | Rally X10 Family | 16349 | Product Development Plan | Fitness | 2024-12-20 | [7 empty] | 2025-01-31 | 1 | 0
Force Kayak Propulsion System | 1134 | Force Kayak Propulsion System | 10617 | Top Level Design | Marine | 2024-09-23 | 2022-05-05 | 2022-05-26 | 2023-05-18 | 2023-06-01 | 2023-06-12 |  |  | 2024-11-04 | 1 | 0
Xero B60i Laser Navigation Binoculars | 1119 | Xero B60i Laser Navigation Binoculars | 13229 | Detailed Design | Outdoor | 2024-09-16 | 2022-03-17 | 2022-04-07 | 2023-09-07 | 2023-09-21 | 2023-09-28 |  |  | 2024-10-28 | 1 | 0
TGWW25 | 1138 | TGWW25 | 16227 | Top Level Design | OEM Auto | 2024-08-31 | [7 empty] | 2024-10-11 | 1 | 0
LYWW24 | 1113 | LYWW24 | 15976 | Top Level Design | OEM Auto | 2024-08-05 | 2022-05-20 | 2022-06-10 | [5 empty] | 2024-09-16 | 1 | 0
Tread 10" OEM - Kawasaki CAN | 1142 | Tread 10" OEM - Kawasaki CAN | 16584 | Pilot Run | Automotive | 2024-05-27 | [7 empty] | 2024-07-08 | 1 | 0
Edge 1050 | 1137 | Edge 1050 | 16197 | Product Development Plan | Fitness | 2024-03-04 | [7 empty] | 2024-04-15 | 1 | 0
dezl headset (2nd Gen) | 1132 | dezl headset (2nd Gen) | 16249 | Top Level Design | Automotive | 2024-02-12 | 2022-08-11 | 2022-09-01 | [5 empty] | 2024-03-25 | 1 | 0
LED Control Module | 1066 | LED Control Module | 13134 | Detailed Design | Marine | 2024-01-08 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  |  |  | 2024-02-19 | 1 | 0
Product - GDU147XW | 1049 | Product - GDU147XW | 12509 | Product Development Plan | Aviation | 2024-01-03 | [7 empty] | 2024-02-14 | 1 | 0
Approach R50 | 1012 | Approach R50 | 10926 | Detailed Design | Outdoor | 2023-12-25 | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 |  |  |  | 2024-02-05 | 1 | 0
Forerunner 165 and 165 Music | 1145 | Forerunner 165 and 165 Music | 16437 | Detailed Design | Fitness | 2023-12-18 | 2022-07-25 | 2022-08-15 | 2022-11-04 | 2022-11-18 | 2022-11-23 |  |  | 2024-01-29 | 1 | 0
Lily 2 | 1123 | Lily 2 | 15993 | Detailed Design | Fitness | 2023-10-30 | [7 empty] | 2023-12-11 | 1 | 0
ECHOMAP Ultra 2 | 1147 | ECHOMAP Ultra 2 | 16483 | Detailed Design | Marine | 2023-10-23 |  |  | 2023-01-04 | 2023-01-18 | 2023-01-26 |  |  | 2023-12-04 | 1 | 0
Prop Drive Cost Down | 1115 | Prop Drive Cost Down | 16233 | Detailed Design | Marine | 2023-10-16 | 2022-02-14 | 2022-03-07 | 2022-07-08 | 2022-07-22 | 2022-08-08 |  |  | 2023-11-27 | 1 | 0
GPSMAP 9500 | 1141 | GPSMAP 9500 | 16616 | Detailed Design | Marine | 2023-10-02 |  |  | 2023-01-13 | 2023-01-27 | 2023-02-03 |  |  | 2023-11-13 | 1 | 0
Descent Mk3 Series - Large | 1057 | Descent Mk3 Series | 12994 | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-07-20 | 2022-08-03 | 2022-08-26 | 2023-04-19 |  | 2023-11-13 | 1 | 0
Xero L60i Laser Navigator | 1016 | Xero L60i Laser Navigator | 8510 | Detailed Design | Outdoor | 2023-09-18 | 2021-02-25 | 2021-03-18 | 2022-11-07 | 2022-11-21 | 2022-11-21 |  |  | 2023-10-30 | 1 | 3
Descent Mk3 Series - Small | 1058 | Descent Mk3 Series | 16205 | Detailed Design | Outdoor | 2023-09-18 | 2021-08-13 | 2021-09-03 | 2022-07-14 | 2022-07-28 | 2022-08-26 | 2023-04-14 | 2023-07-03 | 2023-10-30 | 1 | 0
IMWW23 | 1084 | IMWW23 | 14434 | Top Level Design | OEM Auto | 2023-09-18 |  |  | 2021-11-05 | 2021-11-19 |  | 2022-09-27 |  | 2023-10-30 | 1 | 0
BMW Motorrad Nav VI Production Support | 1140 | BMW Motorrad Nav VI Production Support | 10170 | Pilot Run | OEM Auto | 2023-09-04 | [5 empty] | 2022-10-19 | 2023-04-21 | 2023-10-16 | 1 | 0
Connect 50 transition to Taiwan Manufacturing | 1127 | Connect 50 transition to Taiwan Manufacturing | 16347 | Pilot Run | Marine | 2023-08-21 | [7 empty] | 2023-10-02 | 1 | 0
eTrex Solar | 1065 | eTrex Solar | 10901 | Detailed Design | Outdoor | 2023-08-21 | 2021-10-14 | 2021-11-04 | 2022-12-07 | 2022-12-21 | 2023-01-13 |  |  | 2023-10-02 | 1 | 0 |  | PeiRu.Tsai | Willycw.Wu Viola.Kao | Tina.Yang Franksl.Chen
DC-2023 Premium Dash Cameras | 1130 | DC-2023 Premium Dash Cameras | 16199 | Detailed Design | Automotive | 2023-08-14 | 2022-07-15 | 2022-08-05 | 2023-01-19 | 2023-02-02 | 2023-02-03 |  |  | 2023-09-25 | 1 | 0
GSD28 | 1068 | GSD28 | 15876 | Detailed Design | Marine | 2023-08-07 | 2021-10-07 | 2021-10-28 | 2022-11-03 | 2022-11-17 | 2022-12-01 |  | 2023-02-14 | 2023-09-18 | 1 | 0
vivoactive 5 | 1146 | vivoactive 5 | 16388 | Detailed Design | Fitness | 2023-07-31 | [7 empty] | 2023-09-11 | 1 | 0
Descent S1 Buoy | 1006 | Descent S1 Buoy | 12799 | Detailed Design | Outdoor | 2023-07-31 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 | 2022-08-15 | 2022-11-14 | 2023-09-11 | 1 | 0
GPSMAP 9000 - 19" | 1051 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-07-24 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-04 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 - 24" | 1053 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-07-24 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-04 | 1 | 2 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 -27" | 1054 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-07-24 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-04 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 - 22" | 1052 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-07-24 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-04 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
Catalyst KMR - Hub | 1111 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-24 | 2021-09-20 | 2021-10-11 | 2022-02-04 | 2022-02-18 | 2022-06-27 |  |  | 2023-09-04 | 1 | 1
TWIN23 | 1144 | TWIN23 | 16503 | Detailed Design | OEM Auto | 2023-07-17 | [7 empty] | 2023-08-28 | 1 | 2
Catalyst KMR - Display | 1120 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-10 | 2021-09-20 | 2021-10-11 | 2022-02-04 | 2022-02-18 | 2022-06-27 |  |  | 2023-08-21 | 1 | 1
Catalyst KMR - Camera | 1110 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-10 | 2021-09-20 | 2021-10-11 | 2022-02-04 | 2022-02-18 | 2022-06-27 |  |  | 2023-08-21 | 1 | 1
Force Kraken Trolling Motor | 978 | Force Kraken Trolling Motor | 12789 | Factory Prototype | Marine | 2023-07-10 | 2019-12-17 | 2020-01-07 | 2022-02-08 | 2022-02-22 | 2022-07-18 | 2022-08-15 | 2023-04-11 | 2023-08-21 | 1 | 2
TXTW22_Drive+3.0 (Taroko) -12.3 DA | 964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Product Launch | OEM Auto | 2023-07-03 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 |  | 2023-08-14 | 1 | 0 |  | Wells.Yu Davidsd.Lin | Zack.Lin Colby.Ren Jeff.Lin | Nick.Yen
Product - G3X/G500TXi Hybrid | 1050 | Product - G3X/G500TXi Hybrid | 12717 | Product Development Plan | Aviation | 2023-07-01 | [7 empty] | 2023-08-11 | 1 | 0
Product - 1.3\" GTR/GNC | 984 | Product - 1.3\" GTR/GNC | 12164 | Development | Aviation | 2023-07-01 | [7 empty] | 2023-08-11 | 1 | 0
BlueNET Gateway | 961 | BlueNET Gateway | 9756 | Factory Prototype | Marine | 2023-06-26 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-04-21 | 2022-12-28 | 2023-08-07 | 1 | 0
BlueNET Switch | 962 | BlueNET Switch | 9755 | Factory Prototype | Marine | 2023-06-26 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-05-19 | 2022-12-28 | 2023-08-07 | 1 | 0
GT15M Thru-Hull Flush | 1129 | GT15M Thru-Hull Flush | 16387 | Detailed Design | Marine | 2023-06-19 |  |  |  |  | 2022-07-26 |  |  | 2023-07-31 | 1 | 0
Venu 3 | 1089 | Venu 3 | 15520 | Factory Prototype | Fitness | 2023-05-29 | 2021-09-09 | 2021-09-30 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-08-03 |  | 2023-07-10 | 1 | 3
Venu 3S | 1090 | Venu 3S | 15519 | Factory Prototype | Fitness | 2023-05-29 |  |  | 2021-12-01 | 2021-12-15 | 2022-07-19 |  |  | 2023-07-10 | 1 | 1
Xero C1 Chronograph | 989 | Xero C1 Chronograph | 12253 | Factory Prototype | Outdoor | 2023-05-08 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-24 | 2022-05-25 | 2022-10-14 | 2023-06-19 | 1 | 0
GMR xHD3 Domes (18/24xHD replacement) | 1126 | GMR xHD3 Domes (18/24xHD replacement) | 16246 | Factory Prototype | Marine | 2023-04-24 | 2022-04-01 | 2022-04-22 | 2022-08-30 | 2022-09-13 | 2022-10-04 |  |  | 2023-06-05 | 1 | 0
Approach S70 | 1088 | Approach S70 | 16176 | Detailed Design | Outdoor | 2023-04-10 | 2021-08-05 | 2021-08-26 | 2022-03-15 | 2022-03-29 | 2022-07-22 | 2022-09-07 |  | 2023-05-22 | 1 | 0
Instinct 2X Solar | 1112 | Instinct 2X Solar | 16020 | Detailed Design | Outdoor | 2023-04-10 | 2022-02-04 | 2022-02-25 | 2022-07-29 | 2022-08-12 | 2022-04-01 |  |  | 2023-05-22 | 1 | 0
Serv+ - 10" | 1081 | Serv+ (7"/10") | 14554 | Factory Prototype | Marine | 2023-04-03 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-07-20 | 2022-08-26 |  | 2023-05-15 | 1 | 0
Serv+ - 7" | 1080 | Serv+ (7"/10") | 14554 | Factory Prototype | Marine | 2023-04-03 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-08-03 | 2022-08-26 |  | 2023-05-15 | 1 | 1
BMW MGU22/IDC | 815 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2023-04-01 |  | 2019-08-30 | 2020-04-10 | 2020-04-24 | 2020-04-24 |  |  | 2023-05-12 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Sandy.Lee
fenix 7X Pro | 1077 | fenix 7X Pro | 16112 | Detailed Design | Outdoor | 2023-03-27 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 |  |  | 2023-05-08 | 1 | 3
GMR xHD3 Magnetron Open Arrays | 1105 | GMR xHD3 Magnetron Open Arrays | 15804 | Factory Prototype | Marine | 2023-03-27 |  |  | 2022-05-06 | 2022-05-20 | 2022-08-03 |  |  | 2023-05-08 | 1 | 0
fenix 7 Pro | 1075 | fenix 7 Pro | 14729 | Factory Prototype | Outdoor | 2023-03-27 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-23 | 2022-12-30 | 2023-05-08 | 1 | 1
fenix 7S Pro (2022) | 1076 | fenix 7S Pro (2022) | 16108 | Factory Prototype | Outdoor | 2023-03-20 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-26 | 2022-11-14 | 2023-05-01 | 1 | 1
Approach S70s | 1036 | Approach S70S | 15419 | Detailed Design | Outdoor | 2023-03-20 | 2021-08-05 | 2021-08-26 | 2022-03-15 | 2022-03-29 | 2022-08-01 | 2022-09-07 |  | 2023-05-01 | 1 | 1
Panoptix PS70 - (SSMB) | 833 | Panoptix PS70 - (SSMB) | 10091 | Factory Prototype | Marine | 2023-03-13 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-09-05 | 2022-11-28 | 2023-04-24 | 1 | 0
EPIX PRO (Gen 2) 51mm | 1094 | EPIX PRO (Gen 2) 51mm | 16218 | Detailed Design | Outdoor | 2023-03-06 | [5 empty] | 2022-08-31 |  | 2023-04-17 | 1 | 0
zumo XT2 | 1101 | zumo XT2 | 16069 | Detailed Design | Automotive | 2023-03-06 | 2021-09-15 | 2021-10-06 | 2022-03-08 | 2022-03-22 | 2022-04-14 |  |  | 2023-04-17 | 1 | 3
Varia eBike Radar Tail Light (eRTL615) | 1102 | Varia eBike Radar Tail Light (eRTL615) | 15837 | Factory Prototype | Fitness | 2023-03-06 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-17 | 1 | 0
EPIX PRO (Gen 2) 47mm | 1093 | EPIX PRO (Gen 2) 47mm | 16217 | Detailed Design | Outdoor | 2023-03-01 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 |  |  | 2023-04-12 | 1 | 0
EPIX PRO (Gen 2) 42mm | 1092 | EPIX PRO (Gen 2) 42mm | 15803 | Factory Prototype | Outdoor | 2023-02-13 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 | 2022-09-01 | 2022-11-28 | 2023-03-27 | 1 | 0
Foretrex 801/901 | 1078 | Foretrex 801/901 | 14769 | Factory Prototype | Outdoor | 2023-02-06 | 2021-10-01 | 2021-10-22 | 2022-03-11 | 2022-03-25 | 2022-07-22 | 2022-09-23 |  | 2023-03-20 | 1 | 0
Edge 540 840 | 1069 | Edge 540 840 | 14509 | Factory Prototype | Fitness | 2023-01-30 | 2021-03-11 | 2021-04-01 | 2021-04-14 | 2021-04-28 | 2022-02-07 | 2022-06-03 | 2022-10-14 | 2023-03-13 | 1 | 0
Forerunner 965 | 1103 | Forerunner 965 | 16002 | Pilot Run | Fitness | 2023-01-09 | 2021-12-17 | 2022-01-07 | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-02-20 | 1 | 0
Tread 8" OEM w/ CAN | 1063 | Tread 8" OEM w/ CAN | 15955 | Pilot Run | Automotive | 2023-01-09 | [6 empty] | 2022-03-16 | 2023-02-20 | 1 | 0
Forerunner 265 | 1107 | Forerunner 265 | 14529 | Pilot Run | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 0
Forerunner 265s | 1118 | Forerunner 265 | 14529 | Pilot Run | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 0
eTrex SE | 1044 | eTrex SE | 15843 | Detailed Design | Outdoor | 2022-12-19 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 | 2022-05-23 |  | 2023-01-30 | 1 | 1
ECHOMAP UHD2 (Touch) 7" | 1059 | ECHOMAP UHD2 (Touch) | 13095 | Pilot Run | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  | 2022-10-07 | 2023-01-30 | 1 | 0
ECHOMAP UHD2 (Touch) 6" | 1018 | ECHOMAP UHD2 (Touch) | 13095 | Pilot Run | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2021-11-23 | 2022-05-06 | 2022-10-07 | 2023-01-30 | 1 | 0
ECHOMAP UHD2 (Touch) 9" | 1041 | ECHOMAP UHD2 (Touch) | 13095 | Pilot Run | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  | 2022-10-07 | 2023-01-30 | 1 | 0
FUSION - WB675 Hide Away Stereo | 1043 | FUSION - WB675 Hide Away Stereo | 15524 | Pilot Run | Marine | 2022-12-16 | [7 empty] | 2023-01-27 | 1 | 0
Alpha Dog Collar | 856 | Alpha Dog Collar | 7029 | Factory Prototype | Outdoor | 2022-12-09 | 2021-03-15 | 2021-04-05 | 2021-08-09 | 2021-08-23 | 2022-01-10 | 2022-01-25 |  | 2023-01-20 | 1 | 0
Dash Cam Live (LTE) | 990 | Dash Cam Live (LTE) | 13009 | Factory Prototype | Automotive | 2022-11-21 | 2020-09-18 | 2020-10-09 | 2020-11-30 | 2020-12-14 | 2021-06-14 | 2022-01-07 | 2022-07-28 | 2023-01-02 | 1 | 1
vivomove Trend (previously "4") | 1030 | vivomove Trend (previously "4") | 14004 | Product Launch | Fitness | 2022-11-14 | 2020-11-13 | 2020-12-04 | 2021-10-01 | 2021-10-15 | 2021-11-03 | 2022-04-18 | 2022-08-05 | 2022-12-26 | 1 | 0
Bounce(Waldo) | 862 | Bounce | 10919 | Product Launch | Fitness | 2022-10-24 | 2019-09-03 | 2019-09-24 | 2019-10-22 | 2019-11-05 | 2020-04-30 |  | 2022-01-03 | 2022-12-05 | 1 | 0
Tread - XL (10") | 948 | Tread XL - Baja Race Edition | 12983 | Product Launch | Automotive | 2022-10-17 | 2020-02-11 | 2020-03-03 | 2020-06-29 | 2020-07-13 | 2020-12-11 | 2021-08-11 | 2021-10-01 | 2022-11-28 | 1 | 0
LIIN22 | 1108 | LIIN22 | 16129 | Top Level Design | OEM Auto | 2022-10-11 | [7 empty] | 2022-11-22 | 1 | 0
Instinct Hybrid Analog/Digital(Ripley) | 1029 | Instinct Hybrid Analog/Digital | 13084 | Pilot Run | Outdoor | 2022-10-11 |  |  | 2021-12-01 | 2021-12-15 |  | 2022-01-05 |  | 2022-11-22 | 1 | 0 |  | Anton.Lin | Eric.Chiang Viola.Kao | Robben.Liu Alexty.Chang
Marq (Gen 2) | 972 | Marq (Gen 2) | 13004 | Detailed Design | Outdoor | 2022-10-10 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-11-21 | 1 | 2
DriveSmart76 Synaptics Redesigns | 1098 | DriveSmart Synaptics Redesigns | 16182 | Production | Automotive | 2022-10-03 | [7 empty] | 2022-11-14 | 1 | 0
DriveSmart66 Synaptics Redesigns | 1097 | DriveSmart Synaptics Redesigns | 16182 | Production | Automotive | 2022-10-03 | [7 empty] | 2022-11-14 | 1 | 0
GST - MCU 2.0 | 966 | GST - MCU 2.0 | 12155 | Production | Marine | 2022-09-19 | [7 empty] | 2022-10-31 | 1 | 0
Alpha 200/200i Plus (i.MX7 Platform) | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | 16195 | Pilot Run | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 1 | 0
TXTW22_Drive+3.0 (Taroko)-9 DA | 953 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Product Launch | OEM Auto | 2022-08-24 |  |  | 2021-05-28 | 2021-06-11 | 2021-06-18 | 2021-09-02 |  | 2022-10-05 | 1 | 0 |  | Davidsd.Lin Wells.Yu | Jeff.Lin Zack.Lin Colby.Ren | Nick.Yen
Venu Sq 2(IMP) | 1023 | Venu Sq 2 | 14949 | Production | Fitness | 2022-08-01 | 2021-04-29 | 2021-03-10 |  |  |  | 2021-11-23 |  | 2022-09-12 | 1 | 0
Tacx NEO Bike Plus_Shifter | 986 | Tacx NEO Bike Plus | 13644 | Product Launch | Fitness | 2022-06-27 | [5 empty] | 2021-12-01 |  | 2022-08-08 | 1 | 0
IXWW22 | 985 | IXWW22 | 11792 | Production | OEM Auto | 2022-06-27 | 2020-04-01 | 2020-04-22 |  |  | 2021-07-12 |  | 2021-12-28 | 2022-08-08 | 1 | 0
BMW MGU22_PL1 | 1028 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0 |  |  |  | Mark.Chang
BMW MGU22_G1 | 1079 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0
Tread Audio System | 1009 | Tread Audio System | 12874 | Production | Automotive | 2022-06-13 | 2020-11-24 | 2020-12-15 | 2021-03-17 | 2021-03-31 | 2021-07-19 | 2021-08-23 | 2022-01-14 | 2022-07-25 | 1 | 0
Edge Explore 2 | 1045 | Edge Explore 2 | 14994 | Production | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0
Forerunner 955 and 955 Solar | 967 | Forerunner 955 and 955 Solar | 12875 | Production | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-05-30 | 0 | 0
2022 vivofit jr. 3 SKUs | 1095 | 2022 vivofit jr. 3 SKUs | 15907 | Production | Fitness | 2022-04-11 |  |  |  |  | 2021-09-13 |  |  | 2022-05-23 | 0 | 0
quatix 7x Solar | 1086 | quatix 7x Solar | 16113 | Production | Marine | 2022-04-06 | [7 empty] | 2022-05-18 | 1 | 0
Tacx Vortex 2M | 1070 | Tacx Vortex 2M | 13589 | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1
Tactix 7 | 1087 | Tactix 7 | 14754 | Production | Outdoor | 2022-03-07 | [7 empty] | 2022-04-18 | 0 | 0
BMW MGU22-RSE | 895 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-03-07 |  | 2019-10-31 | 2020-05-15 | 2020-05-29 | 2020-05-29 |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang | Sandy.Lee
quatix 7 Sapphire | 1104 | quatix 7 Sapphire | 16114 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0
quatix 7 | 1085 | quatix 7 | 15801 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0
D2 Echo (EPIX) | 1040 | D2 Echo (EPIX) | 13079 | Production | Outdoor | 2022-01-17 | [7 empty] | 2022-02-28 | 0 | 0
vivomove "Lite" | 979 | vivomove Sport (previously "Lite") | 12989 | Production | Fitness | 2021-11-08 | [7 empty] | 2021-12-20 | 1 | 0
"Austin" | 983 | "Austin" | 13684 | Production | Outdoor | 2021-11-01 | 2020-03-05 | 2020-03-26 | 2020-08-31 | 2020-09-14 | 2020-09-15 |  |  | 2021-12-13 | 1 | 0
Venu 2 Plus | 879 | Venu 2 Plus | 12514 | Production | Fitness | 2021-10-18 | 2020-01-01 | 2020-01-22 | 2020-02-07 | 2020-02-21 | 2020-06-05 |  |  | 2021-11-29 | 1 | 0
fenix 7S | 959 | fenix 7S | 13824 | Production | Outdoor | 2021-10-04 | [7 empty] | 2021-11-15 | 1 | 0
Battery Charger | 998 | Battery Charger | 14544 | Production | Outdoor | 2021-04-26 | [7 empty] | 2021-06-07 | 1 | 0
Xero G2i SatCom Scouting Camera | 826 | Xero G2i SatCom Scouting Camera | 7011 | Top Level Design | Outdoor |  |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  |  | 0 | 0 |  | Derek.Cheng | Frankie.Lee | Ken.Kuo
PGWW23 | 1136 | PGWW23 | 16590 | Product Development Plan | OEM Auto | [9 empty] | 0 | 0
Drive 53 | 1131 | Drive 53 | 16467 | Pilot Run | Automotive |  | 2022-06-08 | 2022-06-29 |  |  |  | 2022-08-08 |  |  | 0 | 2
Tacx FLUX 3M | 1148 | Tacx FLUX 3M | 16250 | Product Development Plan | Fitness | [9 empty] | 0 | 0
GPSMAP 66sr/66i Plus (i.MX7 Platform) | 1116 | GPSMAP 67/67i (i.MX7 Platform) | 16211 | Pilot Run | Outdoor | [9 empty] | 0 | 0
GPSMAP 68 | 1091 | GPSMAP 68 | 16137 | Product Development Plan | Outdoor | [9 empty] | 0 | 0
Cellular Tracking Module | 1139 | Cellular Tracking Module | 16095 | Detailed Design | Outdoor | [9 empty] | 0 | 0
Tacx NEO 3M | 1109 | Tacx NEO 3M | 15808 | Detailed Design | Fitness | [9 empty] | 0 | 0
Descent X1i | 1121 | Descent X1i | 15469 | Detailed Design | Outdoor | [9 empty] | 0 | 0
Tacx Motion Plates | 1082 | Tacx Motion Plates | 14854 | Production | Fitness | [9 empty] | 1 | 1
Enduro 2023 | 1047 | Enduro 2023 | 14704 | Detailed Design | Outdoor |  | 2021-09-15 | 2021-10-06 | 2022-08-30 | 2022-09-13 | 2021-11-09 |  |  |  | 0 | 0
Tacx Sports bottle | 1128 | Tacx Sports bottle | 14164 | Pilot Run | Fitness | [9 empty] | 0 | 0
Product - Flight Stream Redesign | 977 | Product - Flight Stream Redesign | 13634 | Derivative Product Concept | Aviation | [9 empty] | 0 | 0
Product - GDU77XW | 1048 | Product - GDU77XW | 12510 | Product Development Plan | Aviation | [9 empty] | 0 | 0
Tire Temp Sensor | 1114 | Tire Temp Sensor | 11778 | Detailed Design | Automotive |  | 2021-12-22 | 2022-01-12 | [6 empty] | 0 | 0
MARQ Carbon | 904 | MARQ Carbon | 11252 | Detailed Design | Outdoor |  | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 |  |  |  | 0 | 0