## Sheet1
Project ID | Project Name | Working Prototype Built and Tested | Final Factory Prototypes Built | MP Date | PR Date | Global/Asia | PDP/Form107 | Status | Develop Product QE (DPQE)
2854 | Product - GDC 7500 | 2013-04-30 |  | 2019-07-01 | 2018-10-12 | Global | PDP | Development | Kuo, Chris
2914 | Product - GTN 6xx/7xx |  |  |  |  | Global | PDP | Development
2930 | Product - GWX 7000 | 2019-03-22 |  | 2021-09-09 | 2021-06-04 | Global | PDP | Concepts
3753 | Product - GDU 7XX | 2015-08-14 |  | 2018-01-26 | 2017-01-05 | Global | PDP | Development
3767 | HIRF & Lightning System Cert |  |  |  |  | Global | PDP | Development
5710 | Product - GFS 83 | 2015-06-12 |  | 2018-06-11 | 2018-05-31 | Global | PDP | Development
5711 | Product - GLA 85 | 2014-10-30 |  | 2018-12-07 | 2016-08-31 | Global | PDP | Development | Kuo, Chris
6352 | G5 | 2015-07-31 |  | 2016-04-25 | 2016-03-28 | Global | PDP | Development
6465 | Industrial Design |  |  |  |  | Global | PDP | Development
6539 | Product - AFCS |  |  |  |  | Global | PDP | Development
6606 | Product - GAP 52 | 2015-03-26 |  | 2018-07-23 | 2015-12-01 | Global | PDP | Development
6614 | ACO Priority List |  |  |  |  | Global | PDP | Development
6616 | AvnServices - ACARS |  |  |  |  | Global | PDP | Development
6651 | Non-Certified Aviation Software |  |  |  |  | Global | PDP | Development
6680 | Product - Transponder |  |  |  |  | Global | PDP | Development
6755 | Salem SW LRU Status |  |  |  |  | Global | PDP | Development
6775 | STC - G500/G600 P23 AML |  |  |  |  | Global | PDP | Development
6779 | STC - GTX 3x5 P23 AML |  |  |  |  | Global | PDP | Development
6782 | STC - GFC 500/600 Management |  |  |  |  | Global | PDP | Development
6810 | Salem Aircraft Cert Status |  |  |  |  | Global | PDP | Development
6886 | Product - GWX 75/75R/80 | 2015-10-22 |  | 2018-04-10 | 2017-10-20 | Global | PDP | Development
6901 | STC - G500H P27 AML |  |  |  |  | Global | PDP | Development
6915 | STC - GTX 3x5 P27 AML |  |  |  |  | Global | PDP | Development
7011 | Xero G2i SatCom Scouting Camera |  |  |  |  | Global | PDP | Development | Kuo, Chris
7029 | Alpha Dog Collar | 2021-11-18 | 2022-08-18 | 2023-02-27 | 2022-10-28 | Global | PDP | Development | Kuo, Chris
7058 | BMW MGU MY20 |  |  | 2020-09-01 |  | Global | PDP | Development | Chen, Tiffany(QA); Puder, Kristi; Kelly, Joan; Santos, Mila; Holland, Wendy; Bennett, Travis; Tugui, Susanne; Sauer, Stefanie; Bruns, Melanie; Tsai, Cherry
7145 | STC - TXi P23 AML |  |  |  |  | Global | PDP | Development
7563 | Mercury |  |  | 2022-01-17 | 2021-04-23 | Global | PDP | Development | Fu, Ernest
7891 | Product - GIN 6000 |  |  |  |  | Global | PDP | Concepts
7893 | Emergency Approach and Autolanding |  |  | 2018-02-15 |  | Global | PDP | Development
7894 | Product - GRA 15 |  |  |  |  | Global | PDP | Development
7899 | Product - GI 275 | 2018-04-04 |  | 2019-04-02 | 2019-03-22 | Global | PDP | Development | Kuo, Chris
7900 | Product - GPD 3125HE | 2018-12-28 |  | 2020-04-30 | 2019-10-11 | Global | PDP | Development
7901 | Feature - Data Driven Charts |  |  | 2019-09-01 |  | Global | PDP | Development
7903 | Product - GTN Xi Series |  |  | 2020-02-25 | 2020-02-04 | Global | PDP | Development | Dong, Reta
7961 | Feature - Throttle Quadrant |  |  |  |  | Global | PDP | Concepts
7974 | Custom - MechEng Initiatives |  |  |  |  | Global | PDP | Concepts
8220 | Product - NexGen GPS |  |  |  |  | Global | PDP | Development
8227 | Product - MEMS INS |  |  |  |  | Global | PDP | Concepts
8510 | Xero L60i Laser Navigator | 2022-09-21 | 2023-03-23 | 2023-09-18 | 2023-07-13 | Global | PDP | Development | Kuo, Chris
9196 | GIFD 3.0 Technologies |  |  |  |  | Global | PDP | Concepts
9666 | Ford SYNC4 Navigation |  |  | 2020-12-01 |  | Global | PDP | Development | Not Applicable
9755 | BlueNET Switch | 2022-02-17 | 2022-09-16 | 2023-06-26 | 2023-02-10 | Global | PDP | Development | Ni, Wendy
9756 | BlueNET Gateway | 2022-02-17 | 2022-09-27 | 2023-06-26 | 2023-02-10 | Global | PDP | Development | Ni, Wendy
9946 | GPSMAP 9000 | 2022-06-08 | 2023-01-30 | 2023-07-10 | 2023-05-11 | Global | PDP | Development | Hsu, Jason(PQE); Wang, Evelyn
10016 | Connect IQ 3.x |  |  |  |  | Global | PDP | Concepts | Kuo, Chris
10091 | Panoptix PS70 - (SSMB) | 2022-01-21 | 2022-10-10 | 2023-03-13 | 2023-01-02 | Global | PDP | Development | Wang, Evelyn
10205 | GPCN Tracking |  |  |  |  | Asia | PDP | Concepts
10240 | System Release Status |  |  |  |  | Global | PDP | Development
10291 | TestPlan_AOEM_EE |  |  |  |  | Asia | PDP | Concepts
10340 | TXTW22_Drive+3.0 (Taroko) | 2021-01-25 | 2021-09-20 | 2022-08-24 | 2022-05-09 | Asia | PDP | Development | Hu, Ray; Ko, Simon
10341 | Product - GVS 2020 |  |  |  |  | Global | PDP | Concepts
10496 | Product - GDL 60 (LTE) |  |  |  |  | Global | PDP | Development
10617 | Force Kayak Propulsion System | 2023-05-25 | 2024-03-01 | 2024-09-23 | 2024-06-21 | Global | PDP | Development | Hsu, Jason(PQE)
10620 | DGCN20 | 2018-10-12 | 2020-07-24 | 2021-03-08 | 2020-12-28 | Asia | PDP | Development | Chen, Tiffany(QA); Yu, Arthur
10692 | SaMD Sleep Apnea Risk Assessment |  |  |  |  | Global | PDP | Concepts | Fu, Ernest
10693 | SaMD PPG Atrial Fibrillation Detection |  |  |  |  | Global | PDP | Concepts | Fu, Ernest
10718 | BMW MGU22 |  |  | 2023-03-01 |  | Global | PDP | Development | Chen, Tiffany(QA); Kelly, Joan; Bruns, Melanie; Kocon, Andy; Yamnitz, Ryan; Jundi, Ramzi; Overzier, Martin; Keller, Marina; Hu, Ray; Hu, Ray; Tsai, Cherry; Hsu, Jessie; Lee, Lewis
10728 | European UAT Trials |  |  |  |  | Global | PDP | Concepts
10762 | Honda MKSA Maintenance |  |  | 2020-06-01 | 2018-12-24 | Global | PDP | Development | Chen, Tiffany(QA); Yu, Arthur
10847 | AOEM Technical Roadmap Development and Demo Plan | 2018-05-04 | 2018-07-20 |  |  | Asia | PDP | Concepts
10901 | eTrex Solar | 2022-12-14 | 2023-04-24 | 2023-08-21 | 2023-06-27 | Global | PDP | Development | Kuo, Chris
10919 | Bounce |  | 2020-10-26 | 2022-10-24 |  | Global | PDP | Development | Fu, Ernest
10926 | Approach R50 | 2023-01-04 | 2023-07-21 | 2023-12-25 | 2023-11-03 | Global | PDP | Development | Kuo, Chris
11020 | Geely Early Engagement |  |  |  |  | Asia | PDP | Concepts
11022 | STC - GPS 175/375/355 P23 AML |  |  |  |  | Global | PDP | Development
11043 | ARINC Projects |  |  |  |  | Global | PDP | Concepts
11088 | UAS Products |  |  |  |  | Global | PDP | Concepts
11249 | Product - GTX Miniaturized |  |  |  |  | Global | PDP | Concepts
11252 | MARQ Carbon (Gen 2) |  | 2022-08-23 |  |  | Global | PDP | Development | Fu, Ernest
11304 | Daimler_VIS20_2020 |  |  | 2020-05-25 |  | Global | PDP | Development | Tsai, Cherry; Peranovic, Predrag; Nefzger, Bernadette; Kelly, Joan; Pinte, Marius; Jones, Rachel; Yamnitz, Ryan; Bruns, Melanie
11403 | 7.1 SW Features |  |  |  |  | Global | PDP | Development
11577 | Product - Head Mounted Display |  |  |  |  | Global | PDP | Concepts
11778 | Tire Temp Sensor | 2022-08-26 |  | 2023-04-10 | 2023-02-10 | Global | PDP | Development | Ni, Wendy
11825 | Product - GCD 1600 |  |  |  |  | Global | PDP | Concepts
11922 | CES2021/Roadmap |  |  |  |  | Global | PDP | Concepts
11979 | Honda Talon HU RFQ |  |  |  |  | Global | PDP | Concepts
11984 | Product - Fixed Mount HUD |  |  |  |  | Global | PDP | Concepts
12141 | JLR NAV SW Solution - RFI |  |  |  |  | Global | PDP | Concepts
12164 | Product - 1.3\" GTR/GNC |  |  |  |  | Global | PDP | Development | Wang, Evelyn
12253 | Xero C1 Chronograph | 2022-02-04 | 2022-06-30 | 2023-05-08 | 2023-03-08 | Global | PDP | Development | Kuo, Chris
12258 | Product - Scanning DME |  |  |  |  | Global | PDP | Concepts
12264 | BMW NAV X |  |  |  |  | Global | PDP | Concepts
12279 | Marq Hybrid |  |  |  |  | Global | PDP | Concepts | Wang, Cooper
12284 | GSS Integrated Surveillance System |  |  |  |  | Global | PDP | Concepts
12408 | GC 300 (PTZ) Camera | 2021-06-09 | 2021-12-27 | 2023-02-21 | 2023-02-01 | Global | PDP | Development | Hsu, Jason(PQE)
12509 | Product - GDU147XW |  |  |  |  | Global | PDP | Concepts | Wang, Evelyn
12510 | Product - GDU77XW |  |  |  |  | Global | PDP | Concepts | Wang, Evelyn
12539 | Product - GSR 56C |  |  |  |  | Global | PDP | Concepts
12549 | Ford Off-Road App RFI |  |  |  |  | Global | PDP | Concepts
12705 | Approach Z50 | 2022-01-31 | 2022-11-24 | 2023-05-01 | 2023-03-02 | Global | PDP | Development | Kuo, Chris
12717 | Product - G3X/G500TXi Hybrid |  |  |  |  | Global | PDP | Concepts
12789 | Force Kraken Trolling Motor | 2022-02-22 | 2023-02-10 | 2023-07-10 | 2023-05-12 | Global | PDP | Development | Hsu, Jason(PQE)
12799 | Descent S1 Buoy | 2022-11-04 | 2022-11-04 | 2023-07-31 | 2023-04-14 | Global | PDP | Development | Lo, Aalto
12844 | Cartography - Chart Subscriptions |  |  |  |  | Global | PDP | Development | Hsu, Jason(PQE)
12910 | Product - FCC Concept |  |  |  |  | Global | PDP | Concepts
12983 | Tread XL - Baja Race Edition | 2020-12-17 | 2021-08-05 | 2022-10-17 | 2021-12-27 | Global | PDP | Development | Hsu, Jason(PQE)
12994 | Descent Mk3 | 2022-12-05 | 2023-05-05 | 2023-10-02 | 2023-08-04 | Global | PDP | Development | Wang, Cooper
13004 | Marq (Gen 2) | 2022-01-11 | 2022-08-05 | 2022-10-11 | 2022-08-15 | Global | PDP | Development | Wang, Cooper
13009 | Dash Cam Live (LTE) | 2021-06-25 | 2022-02-25 | 2022-11-21 | 2022-08-24 | Global | PDP | Development | Kuo, Chris
13034 | Companion Dog Tracking Collar |  |  |  |  | Global | PDP | Concepts | Kuo, Chris
13084 | Instinct Crossover | 2021-11-05 |  | 2022-10-11 | 2022-08-26 | Global | PDP | Development | Lo, Aalto
13095 | ECHOMAP UHD2 (Touch) | 2021-12-03 | 2022-06-03 | 2022-12-19 | 2022-11-04 | Global | PDP | Development | Hsu, Jason(PQE)
13099 | Product - D2 Air |  |  |  |  | Global | PDP | Development
13126 | Product - GDL 59 Replace |  |  |  |  | Global | PDP | Concepts
13134 | LED Control Module | 2023-03-02 | 2023-08-24 | 2024-01-08 | 2023-11-07 | Global | PDP | Development | Wang, Evelyn
13149 | BRP Cluster Head Unit |  |  |  |  | Global | PDP | Concepts
13229 | Xero B60i Laser Navigation Binoculars | 2023-09-14 | 2024-03-08 | 2024-09-16 | 2024-07-12 | Global | PDP | Development | Kuo, Chris
13249 | GBB 40 |  |  |  |  | Global | PDP | Concepts
13479 | Honda MLFA Maintenance |  |  |  |  | Global | PDP | Development | Yu, Arthur
13529 | Custom - 7800 New Sensors |  |  |  |  | Global | PDP | Concepts
13584 | ENG-0276 |  |  |  |  | Global | PDP | Concepts
13644 | Tacx NEO Bike Plus |  | 2022-01-28 | 2022-10-04 | 2022-05-27 | Global | PDP | Development | Kuo, Chris
13719 | Probe Heater Coiling and Brazing |  |  |  |  | Global | PDP | Concepts
13759 | Product - GDL 5X Redesign |  |  |  |  | Global | PDP | Concepts
13834 | Aviation inReach |  |  |  |  | Global | PDP | Concepts
13913 | Product - GTE 1x0 |  |  |  |  | Global | PDP | Concepts
13920 | Approach Z50, Asia |  |  | 2023-05-01 | 2023-03-17 | Asia | PDP | Development | Kuo, Chris
14004 | vivomove Trend |  | 2022-06-17 | 2022-11-14 |  | Global | PDP | Development | Lo, Aalto
14069 | Descent S1 Buoy, Asia (previously: Descent Topside Box) |  | 2022-12-16 | 2023-07-31 | 2023-03-24 | Asia | PDP | Development | Lo, Aalto
14140 | Feature - GTX Mode 1/2 |  |  |  |  | Global | PDP | Concepts
14194 | GVM 53 |  |  |  |  | Global | PDP | Concepts
14374 | BMW Motorrad Cluster RFI |  |  |  |  | Global | PDP | Concepts
14434 | IMWW23 | 2021-11-24 | 2022-08-01 | 2023-09-18 | 2023-02-08 | Asia | PDP | Development | Tsai, Cherry; Ko, Simon
14449 | LTDM20 |  |  | 2022-02-14 | 2020-08-17 | Asia | PDP | Development | Ko, Simon
14509 | Edge 540 840 |  |  | 2023-01-30 |  | Global | PDP | Development | Kuo, Chris
14529 | Forerunner 265 |  | 2022-09-21 | 2023-01-03 | 2022-11-29 | Global | PDP | Development | Fu, Ernest
14554 | Serv+ (7"/10") | 2022-07-20 | 2022-10-07 | 2023-03-20 | 2023-01-26 | Global | PDP | Development | Hsu, Jason(PQE)
14604 | L20 Laser Range Finder |  |  |  |  | Global | PDP | Concepts | Kuo, Chris
14704 | Next Gen Fenix Dev Platform |  |  |  |  | Global | PDP | Development | Wang, Cooper
14729 | fenix 7 Pro | 2022-09-09 | 2022-10-04 | 2023-03-27 | 2023-02-10 | Global | PDP | Development | Fu, Ernest
14739 | inReach Certus IoT |  |  |  |  | Global | PDP | Concepts | Kuo, Chris
14749 | inReach Mini 2, Asia |  | 2021-06-10 | 2022-02-21 | 2021-11-10 | Asia | PDP | Development | Kuo, Chris
14764 | All_Garmin_meter | 2021-09-13 |  | 2021-12-31 |  | Asia | PDP | Development
14769 | Foretrex 801/901 | 2022-08-24 | 2022-10-07 | 2023-02-06 | 2022-12-23 | Global | PDP | Development | Fu, Ernest
14879 | Android Automotive Research AOEM |  |  |  |  | Global | PDP | Concepts
14925 | Taiwan to US Production Move |  |  |  |  | Global | PDP | Development
14949 | Venu Sq 2 |  |  | 2022-08-01 |  | Global | PDP | Development | Lo, Aalto
14959 | Garmin OnStar |  |  |  |  | Global | PDP | Concepts
14960 | Helicopter Emergency Autoland |  |  |  |  | Global | PDP | Concepts
14984 | Dash Cam Live (LTE), ASIA |  | 2022-03-31 | 2023-02-13 | 2022-11-11 | Asia | PDP | Development | Kuo, Chris
15074 | Connected Cockpit |  |  |  |  | Global | PDP | Development
15284 | Kenwood SW-Only 2023 DNX&Truck |  |  |  |  | Global | PDP | Concepts
15285 | Kenwood SW-Only 2022 Truck |  |  |  |  | Global | PDP | Concepts
15419 | Approach S70S | 2022-07-20 | 2022-10-27 | 2023-03-20 | 2023-01-26 | Global | PDP | Development | Wang, Cooper
15435 | Product - GIFD3 Data Loader |  |  |  |  | Global | PDP | Concepts
15436 | Product - GIFD3 Controller |  |  |  |  | Global | PDP | Concepts
15464 | Touchscreen Technologies |  |  |  |  | Global | PDP | Concepts
15469 | Descent X1i | 2024-01-05 |  | 2024-11-18 | 2024-09-20 | Global | PDP | Development | Kuo, Chris
15475 | LTE Outlet |  |  |  |  | Global | PDP | Concepts
15499 | MARQ (Gen 2), Asia |  | 2022-07-29 | 2022-11-21 | 2022-10-14 | Asia | PDP | Development | Wang, Cooper
15505 | vivomove Trend, Asia (previously vivomove 4) |  |  | 2022-11-21 | 2022-10-28 | Asia | PDP | Development | Lo, Aalto
15509 | Approach R50, Asia |  |  | 2023-12-25 | 2023-11-03 | Asia | PDP | Development | Kuo, Chris
15519 | Venu 3S |  | 2022-12-07 | 2023-05-29 |  | Global | PDP | Development | Fu, Ernest
15520 | Venu 3 |  | 2022-12-07 | 2023-05-29 |  | Global | PDP | Development | Wang, Cooper
15524 | FUSION - WB675 Hide Away Stereo | 2021-08-31 |  | 2022-12-16 | 2022-10-31 | Global | PDP | Development | Hsu, Jason(PQE)
15574 | GSR 56C Services |  |  |  |  | Global | PDP | Concepts
15619 | Approach G20 |  |  |  |  | Global | PDP | Concepts | Kuo, Chris
15624 | Catalyst Kart/Moto/Auto | 2022-06-24 | 2023-01-09 | 2023-07-24 | 2023-05-10 | Global | PDP | Development | Lo, Aalto
15634 | Honda RSE |  |  |  |  | Global | PDP | Concepts
15654 | Waveguide HUD |  |  |  |  | Global | PDP | Concepts
15664 | GFC 600 for Part 25 Aircraft |  |  |  |  | Global | PDP | Concepts
15665 | Smart Rudder Bias |  |  |  |  | Global | PDP | Concepts
15669 | AvnServices - ACARS Host (Ground Services) |  |  |  |  | Global | PDP | Concepts
15798 | X.3/G3X Power Module |  |  |  |  | Global | PDP | Concepts
15800 | Fusion - Signature Series 4 Speakers and Subs | 2022-09-01 |  | 2023-07-28 | 2023-06-21 | Global | PDP | Development | Hsu, Jason(PQE)
15803 | EPIX PRO (Gen 2) 42mm | 2022-08-05 | 2022-10-06 | 2023-03-01 | 2023-01-05 | Global | PDP | Development | Lo, Aalto
15804 | GMR xHD3 Magnetron Open Arrays | 2022-06-13 | 2022-11-15 | 2023-03-27 | 2023-02-10 | Global | PDP | Development | Hsu, Jason(PQE)
15808 | Tacx NEO 3M | 2022-11-10 |  | 2023-07-14 | 2023-06-12 | Global | PDP | Development | Kuo, Chris
15814 | LWIN21 |  | 2021-04-12 | 2021-10-20 | 2021-08-30 | Asia | PDP | Development | Hu, Ray; Ko, Simon
15816 | GSU 25C/D New Gyro |  |  |  |  | Global | PDP | Concepts
15818 | GDL59 - WiFi Refresh |  |  |  |  | Global | PDP | Concepts
15825 | NX5 |  |  |  |  | Global | PDP | Concepts
15826 | Glide Assist |  |  |  |  | Global | PDP | Concepts
15827 | Venu Sq 2, Asia |  | 2022-03-21 | 2022-08-12 | 2022-07-15 | Asia | PDP | Development | Lo, Aalto
15828 | Instinct Crossover, Asia (PDP) |  | 2022-06-10 | 2022-10-11 | 2022-09-02 | Asia | PDP | Development | Lo, Aalto
15837 | Varia eBike Radar Tail Light (eRTL615) | 2022-06-28 | 2022-10-21 | 2023-03-06 | 2022-12-27 | Global | PDP | Development | Kuo, Chris
15841 | Aquarius |  |  |  |  | Global | PDP | Concepts
15843 | eTrex SE | 2022-05-02 | 2022-07-25 | 2022-11-21 | 2022-10-21 | Global | PDP | Development | Kuo, Chris
15859 | Yoxi Navigation RFQ |  |  | 2022-01-03 |  | Asia | PDP | Concepts
15876 | GSD28 | 2022-10-17 | 2023-03-14 | 2023-07-24 | 2023-06-09 | Global | PDP | Development | Hsu, Jason(PQE)
15883 | Edge 540 840 ASIA |  |  |  |  | Asia | PDP | Development | Kuo, Chris
15884 | Security |  |  |  |  | Global | PDP | Concepts
15892 | MARQ (Gen 2) Carbon, Asia |  |  | 2023-05-22 | 2023-01-30 | Asia | PDP | Development | Fu, Ernest
15915 | Aera 660 Screen Replacement |  |  |  |  | Global | PDP | Concepts
15917 | inReach Messenger, Asia |  |  | 2022-12-19 | 2022-07-06 | Asia | PDP | Development | Kuo, Chris
15924 | Cert Gain Tool |  |  |  |  | Global | PDP | Concepts
15925 | GADGET |  |  |  |  | Global | PDP | Concepts
15926 | HUD Applications |  |  |  |  | Global | PDP | Concepts
15927 | GFC 500/600 |  |  |  |  | Global | PDP | Concepts
15928 | Initial Development |  |  |  |  | Global | PDP | Concepts
15931 | Helicopter Simulation Environment: A109 |  |  |  |  | Global | PDP | Concepts
15932 | Current Development |  |  |  |  | Global | PDP | Concepts
15938 | Smart Rudder Bias (GIFD) |  |  |  |  | Global | PDP | Concepts
15939 | Smart Glide (GIFD) |  |  |  |  | Global | PDP | Concepts
15955 | Tread 8" OEM - Honda | 2021-12-24 |  | 2023-01-09 | 2022-03-30 | Global | PDP | Development | Ni, Wendy
15962 | GTE 200 |  |  |  |  | Global | PDP | Concepts
15970 | Approach S70s, Asia |  | 2022-10-27 | 2023-04-10 | 2023-02-06 | Asia | PDP | Development | Wang, Cooper
15976 | LYWW24 |  | 2022-05-18 | 2024-08-05 | 2023-06-08 | Asia | PDP | Development | Ko, Simon
15984 | CJ Autothrottle |  |  |  |  | Global | PDP | Concepts
15987 | Descent Subwave Solar |  |  |  |  | Global | PDP | Concepts
15988 | Xero A2i Bow Sight |  |  |  |  | Global | PDP | Concepts
15990 | Xero X20 Crossbow Scope |  |  |  |  | Global | PDP | Concepts
15993 | Lily 2 |  |  | 2023-10-30 |  | Global | PDP | Development | Fu, Ernest
15994 | GEA 24B |  |  |  |  | Global | PDP | Concepts
16002 | Forerunner 965 |  | 2022-10-24 | 2023-01-09 | 2022-11-29 | Global | PDP | Development | Lo, Aalto
16005 | HRM6-Advanced |  |  |  |  | Global | PDP | Concepts
16020 | Instinct 2X Solar | 2022-11-04 | 2022-12-02 | 2023-03-20 | 2023-02-07 | Global | PDP | Development | Lo, Aalto
16023 | eTrex SE, Asia |  | 2022-07-13 | 2023-09-18 | 2023-08-04 | Asia | PDP | Development | Kuo, Chris
16027 | AvnServices - ATSB2 |  |  |  |  | Global | PDP | Concepts
16029 | GIFD 3.0 SW |  |  |  |  | Global | PDP | Concepts
16036 | Low-End GIFD Trainer |  |  |  |  | Global | PDP | Concepts
16037 | M60i Laser Navigation Binoculars 15/18x56mm |  |  |  |  | Global | PDP | Concepts
16044 | K60i Compact Laser Navigation Binocular 8/10x32mm |  |  |  |  | Global | PDP | Concepts
16046 | STC - TXi v3.4x P23 AML |  |  |  |  | Global | PDP | Concepts
16053 | HRM-Hera |  |  |  |  | Global | PDP | Development | Kuo, Chris
16054 | Wingtip Proximity Sensor |  |  |  |  | Global | PDP | Concepts
16061 | Fitness Gamification |  |  |  |  | Global | PDP | Concepts
16066 | P23 FBW |  |  |  |  | Global | PDP | Concepts
16069 | zumo XT2 | 2022-05-11 | 2022-10-13 | 2023-03-06 | 2022-12-30 | Global | PDP | Development | Ni, Wendy
16074 | Descent Mk3, Asia |  | 2023-05-05 | 2023-10-30 | 2023-08-18 | Asia | PDP | Development | Wang, Cooper
16077 | CES/Roadmap 2022 AOEM |  |  |  |  | Global | PDP | Concepts
16086 | Product - GAT 89 |  |  |  |  | Global | PDP | Concepts
16087 | STC - TXi v3.5x P23 AML |  |  |  |  | Global | PDP | Concepts
16093 | GMA x4x BT Redesign |  |  |  |  | Global | PDP | Concepts
16094 | inReach Fishing Scale (Major League Fishing) |  |  |  |  | Global | PDP | Concepts
16095 | Cellular Tracking Module |  | 2023-04-13 | 2023-09-07 | 2023-07-13 | Global | PDP | Development | Fu, Ernest
16099 | GI 275 AT Computer |  |  |  |  | Global | PDP | Concepts
16105 | fenix 7 PRO Asia |  | 2022-11-02 | 2023-03-27 | 2023-02-10 | Asia | PDP | Development | Fu, Ernest
16108 | fenix 7S Pro | 2022-09-09 | 2022-10-06 | 2023-03-27 | 2023-02-10 | Global | PDP | Development | Wang, Cooper
16112 | fenix 7X Pro | 2022-09-13 | 2022-11-09 | 2023-04-10 | 2023-02-17 | Global | PDP | Development | Fu, Ernest
16115 | fenix 7S PRO Asia |  | 2022-10-28 | 2023-03-27 | 2023-02-10 | Asia | PDP | Development | Wang, Cooper
16117 | GPD 3200 |  |  |  |  | Global | PDP | Concepts
16129 | LIIN22 | 2022-02-07 | 2022-04-25 | 2022-09-19 | 2022-07-11 | Asia | PDP | Development | Ko, Simon
16134 | Instinct Lite |  |  |  |  | Global | PDP | Concepts
16136 | Large Format TXi |  |  |  |  | Global | PDP | Concepts
16137 | GPSMAP 68 |  |  |  |  | Global | PDP | Concepts
16152 | Garmin Wallet |  |  |  |  | Global | PDP | Development
16157 | eTrex Solar, Asia |  | 2023-04-24 | 2023-12-18 | 2023-11-03 | Asia | PDP | Development | Kuo, Chris
16158 | GDL 60 Chart Streaming |  |  |  |  | Global | PDP | Concepts
16176 | Approach S70 | 2022-07-22 | 2022-10-28 | 2023-03-20 | 2023-01-27 | Global | PDP | Development | Wang, Cooper
16183 | Varia Headlight Camera |  |  |  |  | Global | PDP | Concepts
16185 | GI 4700 |  |  |  |  | Global | PDP | Concepts
16190 | Approach S70, Asia |  | 2022-10-28 | 2023-04-10 | 2023-02-10 | Asia | PDP | Development | Wang, Cooper
16197 | Edge 1050 |  |  |  |  | Global | PDP | Concepts
16198 | MOB/ECOS System |  |  |  |  | Global | PDP | Concepts
16199 | DC-2023 Premium Dash Cameras | 2023-02-02 | 2023-05-10 | 2023-08-14 | 2023-06-15 | Global | PDP | Development | Ni, Wendy
16204 | Secure Config Module |  |  |  |  | Global | PDP | Concepts
16205 | Descent Mk3s | 2022-11-18 | 2023-04-20 | 2023-09-18 | 2023-07-20 | Global | PDP | Development | Wang, Cooper
16212 | Marq (Gen 3) |  |  |  |  | Global | PDP | Concepts
16215 | eTrex Touch Gen 2 |  |  |  |  | Global | PDP | Concepts
16216 | inReach Messenger 2 |  |  |  |  | Global | PDP | Concepts
16217 | EPIX PRO (Gen 2) 47mm | 2022-09-13 | 2022-10-06 | 2023-03-01 | 2023-01-05 | Global | PDP | Development | Wang, Cooper
16218 | EPIX PRO (Gen 2) 51mm | 2022-07-28 | 2022-10-17 | 2023-03-06 | 2023-01-17 | Global | PDP | Development | Wang, Cooper
16220 | GTN Xi FPGA Replacement |  |  |  |  | Global | PDP | Concepts
16227 | TGWW25 |  |  | 2024-08-31 |  | Asia | PDP | Development | Hu, Ray
16229 | GPD 3150 |  |  |  |  | Global | PDP | Concepts
16230 | Dive Light with Sonar |  |  |  |  | Global | PDP | Concepts
16231 | Descent Mk3s, Asia |  | 2023-04-21 | 2023-10-16 | 2023-08-04 | Asia | PDP | Development | Wang, Cooper
16233 | Prop Drive Cost Down | 2022-10-07 | 2023-04-07 | 2023-11-27 | 2023-08-11 | Global | PDP | Development | Hsu, Jason(PQE)
16242 | 5G Rad Alt Solutions/Activities |  |  |  |  | Global | PDP | Concepts
16244 | EPIX (Gen 3) |  |  |  |  | Global | PDP | Concepts
16246 | GMR xHD3 Domes (18/24xHD replacement) | 2022-09-14 | 2022-11-28 | 2023-04-24 | 2023-02-27 | Global | PDP | Development | Hsu, Jason(PQE)
16248 | Lily Athlete |  |  |  |  | Global | PDP | Concepts
16249 | dezl headset (2nd Gen) | 2023-04-24 |  | 2024-02-12 | 2023-12-08 | Global | PDP | Development
16250 | Tacx FLUX 3M |  |  |  |  | Global | PDP | Concepts
16260 | Venu 3, ASIA |  | 2022-12-07 | 2023-05-29 | 2023-04-28 | Asia | PDP | Development | Wang, Cooper
16261 | Venu 3S, ASIA |  | 2022-12-07 | 2023-05-29 | 2023-04-28 | Asia | PDP | Development | Fu, Ernest
16262 | Forerunner 265, ASIA |  | 2022-08-29 |  | 2022-11-28 | Asia | PDP | Development | Fu, Ernest
16263 | Forerunner 965, ASIA |  | 2022-08-23 |  | 2022-11-28 | Asia | PDP | Development | Lo, Aalto
16264 | fenix 7X PRO Asia |  | 2022-11-09 | 2023-04-10 | 2023-02-17 | Asia | PDP | Development | Fu, Ernest
16275 | Audi Oneinfotainment BtP RFQ |  |  |  |  | Global | PDP | Concepts
16279 | Thin Watch |  |  |  |  | Global | PDP | Concepts
16287 | GMC 805 IBEX |  |  |  |  | Global | PDP | Concepts
16288 | IBEX GI 275 Remount Mount Unit |  |  |  |  | Global | PDP | Concepts
16289 | GSG - Air Transport |  |  |  |  | Global | PDP | Concepts
16290 | BA TOLD |  |  |  |  | Global | PDP | Concepts
16291 | CA Mobile App |  |  |  |  | Global | PDP | Concepts
16292 | D2 Mach 2 |  |  |  |  | Global | PDP | Concepts
16293 | D2 Air X15 |  |  |  |  | Global | PDP | Concepts
16294 | CAP010 New Hardware Reporting |  |  |  |  | Global | PDP | Concepts
16298 | Instinct 3 Series |  |  |  |  | Global | PDP | Concepts
16300 | Flush Mount Stainless Steel Camera |  |  |  |  | Global | PDP | Concepts | Wang, Evelyn
16306 | GRA 6500 |  |  |  |  | Global | PDP | Concepts
16319 | Aviation Headset - |  |  |  |  | Global | PDP | Concepts
16335 | SafeTaxi 3.0 |  |  |  |  | Global | PDP | Concepts
16336 | GWX Interface Unit |  |  |  |  | Global | PDP | Concepts
16345 | Tacx Climbing Accessory |  |  |  |  | Global | PDP | Concepts
16348 | Alternate Actuators |  |  |  |  | Global | PDP | Concepts
16349 | Rally X10 Family |  |  |  |  | Global | PDP | Concepts
16365 | Surface Mount Camera |  |  |  |  | Global | PDP | Concepts
16367 | EPIX PRO (Gen 2) 51mm, Asia |  | 2022-10-18 |  | 2023-01-17 | Asia | PDP | Development | Wang, Cooper
16368 | EPIX PRO (Gen 2) 47mm, Asia |  | 2022-10-06 | 2023-03-01 | 2023-01-05 | Asia | PDP | Development | Wang, Cooper
16369 | EPIX PRO (Gen 2) 42mm, Asia |  | 2022-10-06 | 2023-03-01 | 2023-01-05 | Asia | PDP | Development | Lo, Aalto
16370 | Instinct 2X Solar, Asia |  |  |  |  | Asia | PDP | Development | Lo, Aalto
16373 | IDC23vo |  |  |  |  | Global | PDP | Concepts
16382 | Descent X1i Series, Asia |  |  | 2024-07-01 |  | Asia | PDP | Development | Kuo, Chris
16384 | Large Display Smartwatch |  |  |  |  | Global | PDP | Concepts
16387 | GT12M & GT15M Thru-Hull Flush | 2022-11-28 | 2023-03-07 | 2023-06-19 | 2023-05-02 | Global | PDP | Development
16388 | vivoactive 5 | 2022-12-12 | 2023-02-23 | 2023-07-31 | 2023-06-02 | Global | PDP | Development
16392 | Honda PowerSports Capacitive Touch Dev |  |  |  |  | Global | PDP | Concepts
16396 | GMU 44B New Processor |  |  |  |  | Global | PDP | Concepts
16397 | GAD 27 - New CPU |  |  |  |  | Global | PDP | Concepts
16398 | inReach Fly Mini |  |  |  |  | Global | PDP | Concepts
16399 | inReach Fly Max |  |  |  |  | Global | PDP | Concepts
16405 | GMI 50 (Next Gen) |  |  |  |  | Global | PDP | Concepts
16411 | Fusion - RA800 |  |  |  |  | Global | PDP | Concepts
16412 | Blue Jay |  |  |  |  | Global | PDP | Concepts
16414 | Lily 2, Asia |  |  | 2023-10-30 | 2023-09-08 | Asia | PDP | Development | Fu, Ernest
16437 | Forerunner 165 and 165 Music | 2023-02-27 | 2023-07-13 | 2023-12-18 | 2023-10-20 | Global | PDP | Development | Wang, Cooper
16445 | Next Gen Fenix Dev Platform Asia |  | 2023-02-24 | 2023-08-14 | 2023-06-06 | Asia | PDP | Development | Wang, Cooper
16447 | T1-Tx adapter |  |  |  |  | Global | PDP | Concepts
16448 | GTS Processor (ACAS Xa) |  |  |  |  | Global | PDP | Concepts
16449 | GCU 485, Gray, 3 Button |  |  |  |  | Global | PDP | Concepts
16455 | STC - GTN Xi GDL 60 Installation |  |  |  |  | Global | PDP | Concepts
16456 | Descent T2 Transceiver | 2023-02-10 |  | 2023-07-31 | 2023-06-09 | Global | PDP | Development | Fu, Ernest
16467 | Drive 53 |  | 2022-08-26 | 2022-12-26 | 2022-11-11 | Global | PDP | Development | Ni, Wendy
16483 | ECHOMAP Ultra 2 | 2023-04-25 | 2023-06-23 | 2023-10-23 | 2023-09-01 | Global | PDP | Development | Hsu, Jason(PQE)
16487 | GA 26X |  |  |  |  | Global | PDP | Concepts
16488 | AFCS SYS REL 5.1.X |  |  |  |  | Global | PDP | Concepts
16489 | GMC 605C - AFCS SYS & SW |  |  |  |  | Global | PDP | Concepts
16490 | AFCS SYS REL 6.2.X |  |  |  |  | Global | PDP | Concepts
16491 | AFCS SYS REL 7.2.X |  |  |  |  | Global | PDP | Concepts
16493 | AFCS SYS REL 7.3.X |  |  |  |  | Global | PDP | Concepts
16495 | Software - GDU 7xx - SW v3.15 |  |  |  |  | Global | PDP | Concepts
16498 | BMW Motorrad Instrument Cluster_RFQ |  |  |  |  | Asia | PDP | Concepts
16499 | BMW Motorrad Connectivity unit RFQ |  |  | 2025-12-31 |  | Asia | PDP | Concepts
16500 | ACADIA |  |  |  |  | Global | PDP | Concepts
16501 | Panoptix Ice Fishing Bundle and Transducer |  |  |  |  | Global | PDP | Concepts | Hsu, Jason(PQE)
16503 | TWIN23 | 2022-09-29 | 2022-12-19 | 2023-07-17 | 2023-04-24 | Asia | PDP | Development | Ko, Simon; Hu, Ray
16514 | fenix 8 Series |  |  |  |  | Global | PDP | Concepts
16516 | Marine WW SKU Asia Compliance Tracking |  |  |  |  | Asia | PDP | Concepts
16539 | Motorcycle Radar 2023 |  |  |  |  | Global | PDP | Concepts
16547 | DC-2023 Premium Dash Cameras, Asia |  |  | 2023-09-04 | 2023-05-31 | Asia | PDP | Development
16554 | Mid-Market Trolling Motor |  |  |  |  | Global | PDP | Concepts
16555 | HRM6-Basic |  |  |  |  | Global | PDP | Concepts
16559 | GA 26MCX |  |  |  |  | Global | PDP | Concepts
16561 | Garmin Display Driver |  |  |  |  | Global | PDP | Concepts
16562 | Garmin Yoke |  |  |  |  | Global | PDP | Concepts
16578 | GDU 46x KOE-JDI |  |  |  |  | Global | PDP | Concepts
16579 | GA 62 |  |  |  |  | Global | PDP | Concepts
16580 | Garmin Trim Switch |  |  |  |  | Global | PDP | Concepts
16588 | GPSMAP 16X3 Chartplotters |  |  |  |  | Global | PDP | Concepts
16590 | PGWW23 |  |  | 2023-09-25 |  | Asia | PDP | Concepts
16592 | Alpha 5 |  |  |  |  | Global | PDP | Concepts
16602 | Marine and Powersports Amplifiers |  |  |  |  | Global | PDP | Concepts
16604 | GMA 35xc Refresh |  |  |  |  | Global | PDP | Concepts
16616 | GPSMAP 9500 | 2023-01-10 | 2023-05-23 | 2023-10-02 | 2023-08-10 | Global | PDP | Development
16617 | Forerunner 165 and 165 Music, Asia |  | 2023-07-25 | 2023-12-18 | 2023-10-25 | Asia | PDP | Development
16619 | vivoactive 5, Asia |  | 2023-03-07 | 2023-07-31 | 2023-06-07 | Asia | PDP | Development
16621 | Tactical MEMS Gyro |  |  |  |  | Global | PDP | Concepts
16623 | GTR 200 Redesign |  |  |  |  | Global | PDP | Concepts