## overview
DPQE | 2023-06 | 2023-07 | 2023-08 | 2023-09 | 2023-10 | 2023-11 | 2023-12 | 2024-01 | 2024-02 | 2024-03 | 2024-04 | 2024-05 | 2024-06 | 2024-07 | 2024-08 | 2024-09 | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-04 | 2025-10 | 2026-01
Chen, Leo(PQE) | 0 | 2 | 0 | 0 | 1 | 2 | 1 | 3 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Fu, Ernest | 1 | 0 | 2 | 1 | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1
Hsu, Jason(PQE) | 7 | 4 | 7 | 7 | 3 | 3 | 4 | 3 | 1 | 2 | 2 | 2 | 0 | 1 | 2 | 3 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0
Jen, Howard | 0 | 1 | 0 | 4 | 0 | 3 | 1 | 6 | 0 | 0 | 6 | 1 | 6 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Kuo, Chris | 3 | 1 | 3 | 2 | 9 | 1 | 3 | 6 | 1 | 4 | 3 | 0 | 2 | 3 | 1 | 3 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
Lo, Aalto | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 3 | 1 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Wang, Cooper | 0 | 2 | 0 | 2 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0
Wang, Evelyn | 3 | 1 | 4 | 2 | 1 | 4 | 1 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0

## overview_weighted
DPQE | 2023-06 | 2023-07 | 2023-08 | 2023-09 | 2023-10 | 2023-11 | 2023-12 | 2024-01 | 2024-02 | 2024-03 | 2024-04 | 2024-05 | 2024-06 | 2024-07 | 2024-08 | 2024-09 | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-04 | 2025-10 | 2026-01
Chen, Leo(PQE) | 0 | 8 | 0 | 0 | 2 | 2 | 1 | 6 | 0 | 4 | 6 | 7 | 8 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Fu, Ernest | 1 | 0 | 6 | 4 | 8 | 0 | 1 | 0 | 5 | 4 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 4
Hsu, Jason(PQE) | 20 | 10 | 27 | 17 | 11 | 6 | 9 | 8 | 4 | 6 | 8 | 6 | 0 | 3 | 5 | 10 | 0 | 0 | 3 | 7 | 0 | 4 | 4 | 0
Jen, Howard | 0 | 3 | 0 | 7 | 0 | 3 | 1 | 12 | 0 | 0 | 18 | 2 | 24 | 0 | 3 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Kuo, Chris | 5 | 2 | 9 | 2 | 23 | 1 | 8 | 17 | 4 | 14 | 8 | 0 | 8 | 9 | 4 | 12 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0
Lo, Aalto | 3 | 4 | 0 | 1 | 0 | 0 | 5 | 2 | 3 | 8 | 4 | 0 | 10 | 0 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Wang, Cooper | 0 | 4 | 0 | 6 | 8 | 3 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 3 | 0 | 4 | 8 | 4 | 0 | 0 | 0
Wang, Evelyn | 7 | 4 | 13 | 5 | 1 | 14 | 2 | 2 | 3 | 4 | 6 | 13 | 4 | 4 | 0 | 2 | 0 | 3 | 0 | 7 | 0 | 4 | 0 | 0

## detail
DPQE | Project Name | MP_Date | 1_NoDate(count) | 2023-06 | 2023-07 | 2023-08 | 2023-09 | 2023-10 | 2023-11 | 2023-12 | 2024-01 | 2024-02 | 2024-03 | 2024-04 | 2024-05 | 2024-06 | 2024-07 | 2024-08 | 2024-09 | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-04 | 2025-10 | 2026-01
Chen, Leo(PQE) | Venu 3 | 2023-07-03 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Venu 3S | 2023-07-03 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Instinct Y | 2024-03-04 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Edge 1050 | 2024-05-13 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIX (Gen 3) 43mm | 2024-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| fenix 8 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Instinct SE | 2024-07-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Forerunner 270 | 2024-12-02 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Fu, Ernest | Alpha LTE | 2023-09-18 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Descent T2 Transceiver | 2023-10-02 | 1 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lily 2 | 2023-10-30 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Approach Z30 | 2024-03-18 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Equine Wellness System | 2024-08-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HRM6-Advanced | 2024-08-14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HRM6-Basic | 2025-01-13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| 1_NoPRweb_Approach Z84 | 2025-01-20 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| 1_NoPRweb_LiDAR Lite v5 | 2026-01-01 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Hsu, Jason(PQE) | Serv - 10" | 2023-06-26 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Serv - 7" | 2023-06-26 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Force Kraken Trolling Motor | 2023-07-17 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GMR xHD3 Domes (18/24xHD replacement) | 2023-08-07 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BlueNet Gateway | 2023-08-14 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BlueNet Switch | 2023-08-14 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 9000 - 22" | 2023-08-21 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 9000 - 24" | 2023-08-21 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 9000 -27" | 2023-08-21 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GSD28 | 2023-09-25 | 0 | 2 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ECHOMAP Ultra 2 - 10" | 2023-10-23 | 0 | 0 | 2 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ECHOMAP Ultra 2 - 12" | 2023-10-23 | 0 | 0 | 2 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Fusion - Apollo Speakers and Subs (SS4) | 2023-11-24 | 0 | 0 | 2 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_GC 300 (PTZ) Camera | 2024-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 16X3 Chartplotters | 2024-02-05 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GT17M-THF | 2024-04-08 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 9500 | 2024-04-22 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prop Drive Cost Down | 2024-05-06 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tacx FLUX 3M | 2024-09-27 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Engine Cut-Off System (ECOS/MOB) | 2024-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fusion - RA800 | 2025-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0
| Force Kayak Propulsion System | 2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0
| 1_NoPRweb_Fusion - 80 Series Marine Stereos | 2025-10-25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Jen, Howard | MARQ Carbon | 2023-09-04 | 1 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEZL 2024 - OTR620/720 | 2024-06-10 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEZL 2024 - OTR725 | 2024-06-10 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEZL 2024 - OTR820/1020 | 2024-06-10 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIX (Gen 3) 47mm | 2024-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIX (Gen 3) 51mm | 2024-06-13 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| fenix 8X | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP H1/H1i | 2024-10-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEZL Sideview | 2024-11-04 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Kuo, Chris | Xero C1 Chronograph | 2023-08-28 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HRM-Fit | 2023-10-02 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| eTrex Solar | 2023-10-11 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DC-2023 Premium Dash Cameras | 2023-12-04 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Xero L60i Laser Navigator | 2024-01-08 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Xero G2i Scouting Camera | 2024-02-09 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Approach R50 | 2024-03-04 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2024 Value Dash Cams(DC48) | 2024-03-18 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2024 Value Dash Cams(Mini3) | 2024-03-18 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Approach G20 | 2024-06-17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Descent X1i | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tread 6" plus optional handlebar controller | 2024-08-19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| eTrex Touch | 2024-09-09 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Xero B60i Laser Navigation Binoculars | 2024-09-16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Varia Headlight Camera | 2024-09-30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_2" Thin Watch | 2024-11-18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Rally 110/210 Family | 2025-01-06 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Lo, Aalto | vivoactive 5 | 2023-07-31 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Descent S1 Buoy | 2024-03-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Motorcycle Radar 2023 | 2024-04-29 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Dive Light with Sonar | 2024-06-30 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Instinct 3 OLED | 2024-08-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instinct 3 Series | 2024-08-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Forerunner 970 | 2024-12-30 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Wang, Cooper | Descent Mk3 Series - Large | 2023-10-23 | 0 | 0 | 2 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Descent Mk3 Series - Small | 2023-10-30 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Forerunner 165 and 165 Music | 2024-01-02 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HRM6-Advanced | 2024-08-14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Approach G82 | 2024-12-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 1_NoPRweb_Approach S50 | 2025-01-01 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| HRM6-Basic | 2025-01-13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| 1_NoPRweb_Edge MTB | 2025-02-18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Wang, Evelyn | GT12M & GT15M Thru-Hull Flush | 2023-07-24 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GPSMAP 9000 - 19" | 2023-08-21 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Panoptix PS70 - (SSMB) | 2023-09-18 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Catalyst KMR - Camera | 2023-11-13 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Catalyst KMR - Display | 2023-11-13 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Catalyst KMR - Hub | 2023-11-13 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| dezl headset (2nd Gen) | 2024-05-06 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GC 255 and GC 245 | 2024-05-27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lily 2 Active | 2024-05-27 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LED Control Module | 2024-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| inReach Messenger 2 | 2024-07-15 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Garmin Fixed Mount VHF with AIS | 2025-01-08 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0
| Large Format TXi = GDU1210 | TBD
| Aviation Headset - | 2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0
Note on B95: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: No project

## MPdate_from_now
Category | Project ID | Project Name | MP Date | Global/Asia | PDP/Form107 | Status
Automotive | 15624 | Catalyst Kart/Auto | 2023-11-13 | Global | PDP | Development
Automotive | 16199 | DC-2023 Premium Dash Cameras | 2023-12-04 | Global | PDP | Development
Automotive | 16544 | 2024 Value Dash Cams | 2024-03-18 | Global | PDP | Development
Automotive | 16539 | Motorcycle Radar 2023 | 2024-04-29 | Global | PDP | Development
Automotive | 16249 | dezl headset (2nd Gen) | 2024-05-06 | Global | PDP | Development
Automotive | 16718 | DEZL 2024 | 2024-06-10 | Global | PDP | Development
Automotive | 16319 | Aviation Headset | 2025-04-21 | Global | PDP | Development
Fitness | 16053 | HRM-Fit | 2023-10-02 | Global | PDP | Development
Fitness | 15808 | Tacx NEO 3M | 2023-10-02 | Global | PDP | Development
Fitness | 15993 | Lily 2 | 2023-10-30 | Global | PDP | Development
Fitness | 16437 | Forerunner 165 and 165 Music | 2024-01-02 | Global | PDP | Development
Fitness | 16197 | Edge 1050 Luxe | 2024-05-13 | Global | PDP | Development
Fitness | 16248 | Lily 2 Active | 2024-05-27 | Global | PDP | Development
Fitness | 16345 | Tacx ALPINE | 2024-08-27 | Global | PDP | Development
Fitness | 16250 | Tacx FLUX 3M | 2024-09-27 | Global | PDP | Development
Fitness | 16183 | Varia Headlight Camera | 2024-09-30 | Global | PDP | Development
Fitness | 16349 | Rally 110/210 Family | 2025-01-06 | Global | PDP | Development
Garmin Labs | 16140 | Equine Wellness System | 2024-08-07 | Global | PDP | Development
Marine | 9755 | BlueNet 20 Switch | 2023-08-14 | Global | PDP | Development
Marine | 9756 | BlueNet 30 Gateway | 2023-08-14 | Global | PDP | Development
Marine | 9946 | GPSMAP 9000 | 2023-08-21 | Global | PDP | Development
Marine | 10091 | Panoptix PS70 - (SSMB) | 2023-09-18 | Global | PDP | Development
Marine | 15876 | GSD28 | 2023-09-25 | Global | PDP | Development
Marine | 16483 | ECHOMAP Ultra 2 | 2023-10-23 | Global | PDP | Development
Marine | 15800 | Fusion - Apollo Speakers and Subs (SS4) | 2023-11-24 | Global | PDP | Development
Marine | 12408 | GC 300 (PTZ) Camera | 2024-01-09 | Global | PDP | Development
Marine | 16588 | GPSMAP 16X3 Chartplotters | 2024-02-05 | Global | PDP | Development
Marine | 16706 | GT17M-THF | 2024-04-08 | Global | PDP | Development
Marine | 16616 | GPSMAP 9500 | 2024-04-22 | Global | PDP | Development
Marine | 16233 | Prop Drive Cost Down | 2024-05-06 | Global | PDP | Development
Marine | 16707 | Fusion - Apollo 6.5in & 8.8in Tower Speakers | 2024-05-16 | Global | PDP | Development
Marine | 16300 | GC 255 and GC 245 | 2024-05-27 | Global | PDP | Development
Marine | 13134 | LED Control Module | 2024-06-18 | Global | PDP | Development
Marine | 16198 | Engine Cut-Off System (ECOS/MOB) | 2024-09-30 | Global | PDP | Development
Marine | 16411 | Fusion - RA800 | 2025-01-06 | Global | PDP | Development
Marine | 16743 | Garmin Fixed Mount VHF with AIS | 2025-01-08 | Global | PDP | Development
Marine | 10617 | Force Kayak Propulsion System | 2025-04-21 | Global | PDP | Development
OEM Auto | 10718 | BMW MGU22 | 2024-01-15 | Global | PDP | Development
Outdoor | 12253 | Xero C1 Chronograph | 2023-08-28 | Global | PDP | Development
Outdoor | 11252 | MARQ Carbon (Gen 2) | 2023-09-04 | Global | PDP | Development
Outdoor | 16095 | Alpha LTE | 2023-09-18 | Global | PDP | Development
Outdoor | 16456 | Descent T2 Transceiver | 2023-10-02 | Global | PDP | Development
Outdoor | 10901 | eTrex Solar | 2023-10-11 | Global | PDP | Development
Outdoor | 12994 | Descent Mk3 51mm | 2023-10-23 | Global | PDP | Development
Outdoor | 16205 | Descent Mk3 43mm | 2023-10-30 | Global | PDP | Development
Outdoor | 8510 | Xero L60i Laser Navigator | 2024-01-08 | Global | PDP | Development
Outdoor | 16543 | Xero G2i Scouting Camera | 2024-02-09 | Global | PDP | Development
Outdoor | 10926 | Approach R50 | 2024-03-04 | Global | PDP | Development
Outdoor | 12799 | Descent S1 Buoy | 2024-03-11 | Global | PDP | Development
Outdoor | 16740 | Approach Z30 | 2024-03-18 | Global | PDP | Development
Outdoor | 14704 | Enduro 3 (Pando) | 2024-06-10 | Global | PDP | Development
Outdoor | 16244 | EPIX (Gen 3) 43mm | 2024-06-10 | Global | PDP | Development
Outdoor | 16802 | EPIX (Gen 3) 47mm | 2024-06-10 | Global | PDP | Development
Outdoor | 16801 | EPIX (Gen 3) 51mm | 2024-06-13 | Global | PDP | Development
Outdoor | 15619 | Approach G20 | 2024-06-17 | Global | PDP | Development
Outdoor | 15469 | Descent X1i | 2024-06-17 | Global | PDP | Development
Outdoor | 16514 | fenix 8 Solar 47mm | 2024-06-17 | Global | PDP | Development
Outdoor | 17001 | fenix 8 Solar 51mm | 2024-06-17 | Global | PDP | Development
Outdoor | 17075 | Instinct SE | 2024-07-02 | Global | PDP | Development
Outdoor | 16216 | inReach Messenger Plus | 2024-07-15 | Global | PDP | Development
Outdoor | 17074 | Instinct 3 OLED | 2024-08-05 | Global | PDP | Development
Outdoor | 16298 | Instinct 3 Solar | 2024-08-05 | Global | PDP | Development
Outdoor | 16215 | eTrex Touch | 2024-09-09 | Global | PDP | Development
Outdoor | 13229 | Xero B60i Laser Navigation Binoculars | 2024-09-16 | Global | PDP | Development
Outdoor | 16137 | GPSMAP H1 | 2024-10-07 | Global | PDP | Development
Outdoor | 16736 | Approach G82 | 2024-12-02 | Global | PDP | Development

## No_MPdate_count
Category | Count
Automotive | 6
Fitness | 13
Marine | 14
OEM Auto | 21
Outdoor | 30

## No_MPdate
Category | Project ID | Project Name | MP Date | Global/Asia | PDP/Form107 | Status
Automotive | 17038 | Dash Cam Lineup (Gen 7) |  | Global | PDP | Concepts
Automotive | 16808 | DEZL Sideview |  | Global | PDP | Concepts
Automotive | 16717 | DriveSmart 67/77/87 |  | Global | PDP | Concepts
Automotive | 16949 | Garmin zumo XS |  | Global | PDP | Concepts
Automotive | 16866 | Tread 6" plus optional handlebar controller |  | Global | PDP | Concepts
Automotive | 17176 | Tread 8" Overland Edition (entry level) |  | Global | PDP | Concepts
Fitness | 16384 | 2" Thin Watch |  | Global | PDP | Development
Fitness | 16005 | HRM6-Advanced |  | Global | PDP | Development
Fitness | 17053 | Bounce 2 |  | Global | PDP | Concepts
Fitness | 16987 | Edge MTB |  | Global | PDP | Concepts
Fitness | 17021 | Edge X50 |  | Global | PDP | Concepts
Fitness | 16810 | Forerunner 270 |  | Global | PDP | Concepts
Fitness | 16809 | Forerunner 970 |  | Global | PDP | Concepts
Fitness | 16033 | Garmband |  | Global | PDP | Concepts
Fitness | 16555 | HRM6-Basic |  | Global | PDP | Concepts
Fitness | 17231 | RTL520 |  | Global | PDP | Concepts
Fitness | 10692 | SaMD Sleep Apnea Risk Assessment |  | Global | PDP | Concepts
Fitness | 16119 | Venu 4 (41mm, 45mm) |  | Global | PDP | Concepts
Fitness | 16236 | vivoactive 6 |  | Global | PDP | Concepts
Marine | 16501 | Panoptix PS22-IF Transducer and Ice Fishing Bundles |  | Global | PDP | Development
Marine | 17232 | Autopilot Keypad |  | Global | PDP | Concepts
Marine | 16927 | Force Foot Pedal Gen 2 |  | Global | PDP | Concepts
Marine | 16753 | Fusion - 80 Series Marine Stereos |  | Global | PDP | Concepts
Marine | 17202 | Garmin 360 Sonar |  | Global | PDP | Concepts
Marine | 16858 | GMI 40 Marine Instrument |  | Global | PDP | Concepts
Marine | 16405 | GMI 50 (Next Gen) |  | Global | PDP | Concepts
Marine | 17079 | GPSMAP 9000xsv |  | Global | PDP | Concepts
Marine | 17002 | Kawasaki PWC Chartplotter (RFQ) |  | Global | PDP | Concepts
Marine | 8752 | Marine inReach Antenna |  | Global | PDP | Concepts
Marine | 16554 | Mid-Market Trolling Motor |  | Global | PDP | Concepts
Marine | 17131 | quatix 8 |  | Global | PDP | Concepts
Marine | 16727 | Reactor40 Autopilot - Commercial |  | Global | PDP | Concepts
Marine | 16909 | Steerable LiveScope |  | Global | PDP | Concepts
OEM Auto | 16500 | ACADIA |  | Global | PDP | Concepts
OEM Auto | 15841 | Aquarius |  | Global | PDP | Concepts
OEM Auto | 16275 | Audi Oneinfotainment BtP RFQ |  | Global | PDP | Concepts
OEM Auto | 16412 | Blue Jay |  | Global | PDP | Concepts
OEM Auto | 16675 | BMW IDCevo Build to Print RFQ |  | Global | PDP | Concepts
OEM Auto | 17025 | BMW Me & We |  | Global | PDP | Concepts
OEM Auto | 12264 | BMW NAV X |  | Global | PDP | Concepts
OEM Auto | 13149 | BRP Cluster Head Unit |  | Global | PDP | Concepts
OEM Auto | 11922 | CES2021/Roadmap |  | Global | PDP | Concepts
OEM Auto | 16659 | Daimler Gen20x.i3 B2P RFI/RFQ |  | Global | PDP | Concepts
OEM Auto | 16900 | Epoch |  | Global | PDP | Concepts
OEM Auto | 12549 | Ford Off-Road App RFI |  | Global | PDP | Concepts
OEM Auto | 16732 | Gray Hawk |  | Global | PDP | Concepts
OEM Auto | 16823 | HCP3 Gen2 |  | Global | PDP | Concepts
OEM Auto | 11979 | Honda Talon HU RFQ |  | Global | PDP | Concepts
OEM Auto | 16373 | IDC23vo |  | Global | PDP | Concepts
OEM Auto | 12141 | JLR NAV SW Solution - RFI |  | Global | PDP | Concepts
OEM Auto | 15285 | Kenwood SW-Only 2022 Truck |  | Global | PDP | Concepts
OEM Auto | 15284 | Kenwood SW-Only 2023 DNX&Truck |  | Global | PDP | Concepts
OEM Auto | 17101 | Mercedes-Benz CarComputer |  | Global | PDP | Concepts
OEM Auto | 17166 | Porsche Platform Proof of Concept |  | Global | PDP | Concepts
Outdoor | 16935 | EPIX (Gen 3) Connected |  | Global | PDP | Development
Outdoor | 16152 | Garmin Wallet |  | Global | PDP | Development
Outdoor | 16592 | Alpha 5 |  | Global | PDP | Concepts
Outdoor | 13036 | Alpha Max |  | Global | PDP | Concepts
Outdoor | 17212 | Approach R12 |  | Global | PDP | Concepts
Outdoor | 17214 | Approach S14 |  | Global | PDP | Concepts
Outdoor | 17029 | Approach S50 |  | Global | PDP | Concepts
Outdoor | 16673 | Approach Z84 |  | Global | PDP | Concepts
Outdoor | 16653 | Automated Device Testing Farm |  | Global | PDP | Concepts
Outdoor | 17190 | Battery Box Accessory - Sound |  | Global | PDP | Concepts
Outdoor | 13034 | Companion Dog Tracking Collar |  | Global | PDP | Concepts
Outdoor | 10016 | Connect IQ 3.x |  | Global | PDP | Concepts
Outdoor | 17064 | Descent G2 |  | Global | PDP | Concepts
Outdoor | 17260 | Descent X30i |  | Global | PDP | Concepts
Outdoor | 16230 | Dive Light with Sonar |  | Global | PDP | Concepts
Outdoor | 16536 | Enduro XT |  | Global | PDP | Concepts
Outdoor | 14739 | inReach Certus IoT |  | Global | PDP | Concepts
Outdoor | 16825 | inReach Mini 3 |  | Global | PDP | Concepts
Outdoor | 17178 | Instinct 3 OLED - 50mm |  | Global | PDP | Concepts
Outdoor | 16134 | Instinct Lite |  | Global | PDP | Concepts
Outdoor | 16597 | Instinct Y |  | Global | PDP | Concepts
Outdoor | 16044 | K60i Compact Laser Navigation Binocular 8/10x32mm |  | Global | PDP | Concepts
Outdoor | 14604 | L20 Laser Range Finder |  | Global | PDP | Concepts
Outdoor | 16791 | LiDAR Lite v5 |  | Global | PDP | Concepts
Outdoor | 16037 | M60i Laser Navigation Binoculars 15/18x56mm |  | Global | PDP | Concepts
Outdoor | 16212 | Marq (Gen 3) |  | Global | PDP | Concepts
Outdoor | 17061 | MicroLED Adventure Watch (51mm) |  | Global | PDP | Concepts
Outdoor | 17099 | Rino 8xx |  | Global | PDP | Concepts
Outdoor | 15988 | Xero A2i Bow Sight |  | Global | PDP | Concepts
Outdoor | 15990 | Xero X2c Crossbow Scope |  | Global | PDP | Concepts

## pmsystem_project_wo_any_date
Develop Product QE (DPQE) | Project ID | Project Name | Working Prototype Built and Tested | Final Factory Prototypes Built | MP Date | PR Date | Global/Asia | PDP/Form107 | Status
Fu, Ernest | 16414 | Lily 2, Asia |  |  |  |  | Asia | PDP | Development
Fu, Ernest | 10692 | SaMD Sleep Apnea Risk Assessment |  |  |  |  | Global | PDP | Concepts
Hsu, Jason(PQE) | 8752 | Marine inReach Antenna |  |  |  |  | Global | PDP | Concepts
Hsu, Jason(PQE) | 16501 | Panoptix PS22-IF Transducer and Ice Fishing Bundles |  |  |  |  | Global | PDP | Development
Jen, Howard | 16935 | EPIX (Gen 3) Connected |  |  |  |  | Global | PDP | Development
Kuo, Chris | 13036 | Alpha Max |  |  |  |  | Global | PDP | Concepts
Kuo, Chris | 13034 | Companion Dog Tracking Collar |  |  |  |  | Global | PDP | Concepts
Kuo, Chris | 14604 | L20 Laser Range Finder |  |  |  |  | Global | PDP | Concepts
Kuo, Chris | 14739 | inReach Certus IoT |  |  |  |  | Global | PDP | Concepts
Lo, Aalto | 17178 | Instinct 3 OLED - 50mm |  |  |  |  | Global | PDP | Concepts
Wang, Evelyn | 16136 | Large Format TXi |  |  |  |  | Global | PDP | Concepts
Wang, Evelyn | 12164 | Product - 1.3\" GTR/GNC |  |  |  |  | Global | PDP | Development
Wang, Evelyn | 12509 | Product - GDU147XW |  |  |  |  | Global | PDP | Concepts
Wang, Evelyn | 12510 | Product - GDU77XW |  |  |  |  | Global | PDP | Concepts

## ww_asia_diff_DPQE
Project ID | Project Name | Develop Product QE (DPQE) | Global/Asia | MP Date
15519 | Venu 3S | Chen, Leo(PQE) | Global | 2023-07-03
15520 | Venu 3 | Chen, Leo(PQE) | Global | 2023-07-03
16005 | HRM6-Advanced | Fu, Ernest | Global | 2024-08-14
16005 | HRM6-Advanced | Wang, Cooper | Global | 2024-08-14
16260 | Venu 3 | Wang, Cooper | Asia | 2023-07-03
16261 | Venu 3S | Fu, Ernest | Asia | 2023-07-03
16555 | HRM6-Basic | Fu, Ernest | Global | 2025-01-13
16555 | HRM6-Basic | Wang, Cooper | Global | 2025-01-13

## projects_wo_DPQE
Project ID | Project Name | Working Prototype Built and Tested | Final Factory Prototypes Built | MP Date | PR Date | Global/Asia | PDP/Form107 | Status | Develop Product QE (DPQE)

## multi_dpqe
Project ID | Project Name | Global/Asia | Develop Product QE (DPQE) | MP Date
9946 | GPSMAP 9000 | Global | Hsu, Jason(PQE); Wang, Evelyn | 2023-08-21
9946 | GPSMAP 9000 | Global | Hsu, Jason(PQE); Wang, Evelyn | 2023-08-21

## Aviation_PRweb
| Project Name | Project Id | Category | MP Date
78 | Product - Flight Stream Redesign | 977 | Aviation | 2023-05-15
36 | Large Format TXi | 1155 | Aviation | 2024-01-01
37 | Product - G3X/G500TXi Hybrid | 1050 | Aviation | 2024-01-01
38 | Product - GDU77XW | 1048 | Aviation | 2024-01-01
35 | Product - GDU147XW | 1049 | Aviation | 2024-01-03
130 | Product - 1.3\" GTR/GNC | 984 | Aviation