## overall_fixtureVV
| projectSizeId | Project_Name | Segment | Phase | status | actualGMLASubmitDate | targetGMLASubmitDate | no | Judgement | reviewerFeedBack | reviewer
0 | 766 | GAD 13 | Aviation | GMLA1 | Incomplete
1 | 766 | GAD 13 | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
2 | 766 | GAD 13 | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
3 | 766 | GAD 13 | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
4 | 766 | GAD 13 | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
5 | 909 | One Battery Bike Project | Fitness | GMLA3 | Complete | 2021-03-04 | 2021-02-17 | 3.C-2 | 1 | Fixtures are ready for PR | nixon.pan@garmin.com
6 | 909 | One Battery Bike Project | Fitness | GMLA3 | Complete | 2021-03-04 | 2021-02-17 | 3.D-5 | 1 | DPQE confirmed | jasoncy.hsu@garmin.com
7 | 936 | Edge 1040 | Fitness | GMLA1 | Complete | 2021-02-19 | 2021-02-17
8 | 936 | Edge 1040 | Fitness | GMLA2 | Complete | 2021-11-16 | 2021-11-17 | 2.C-2 | 1 | Fixture list ready and released | chris.kuo@garmin.com
9 | 936 | Edge 1040 | Fitness | GMLA2 | Complete | 2021-11-16 | 2021-11-17 | 2.D-5 | 1 | No issue found | chris.kuo@garmin.com
10 | 936 | Edge 1040 | Fitness | GMLA3 | Complete | 2022-02-25 | 2022-02-25 | 3.C-2 | 1 | Fixture ETA ready | chris.kuo@garmin.com
11 | 936 | Edge 1040 | Fitness | GMLA3 | Complete | 2022-02-25 | 2022-02-25 | 3.D-5 | 1 | No critical equipment/fixture | chris.kuo@garmin.com
12 | 937 | Drive 56 | Automotive | GMLA2 | Incomplete |  | 2021-03-30 | 2.C-2 | 0
13 | 937 | Drive 56 | Automotive | GMLA2 | Incomplete |  | 2021-03-30 | 2.D-5 | 0
14 | 937 | Drive 56 | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
15 | 937 | Drive 56 | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
16 | 955 | Varia Radar Camera (RCT715) | Fitness | GMLA2 | Complete | 2021-09-23 | 2021-09-09 | 2.C-2 | 1 | Fixtures are prepared on time without affecting FFP schedule | sherry.shih@garmin.com
17 | 955 | Varia Radar Camera (RCT715) | Fitness | GMLA2 | Complete | 2021-09-23 | 2021-09-09 | 2.D-5 | 1 | Universal glue dispensing machine | chris.kuo@garmin.com
18 | 955 | Varia Radar Camera (RCT715) | Fitness | GMLA3 | Complete | 2021-12-16 | 2021-12-20 | 3.C-2 | 1 | Fixture all ready | chris.kuo@garmin.com
19 | 955 | Varia Radar Camera (RCT715) | Fitness | GMLA3 | Complete | 2021-12-16 | 2021-12-20 | 3.D-5 | 1 | All fixture/equipment were verified | chris.kuo@garmin.com
20 | 964 | TXTW22_Drive+3.0 (Taroko) -12.3 DA | OEM Auto | GMLA1 | Complete | 2021-10-22 | 2021-10-26
21 | 964 | TXTW22_Drive+3.0 (Taroko) -12.3 DA | OEM Auto | GMLA2 | Complete | 2022-08-12 | 2022-08-12 | 2.C-2 | 1 | Checked | jason.fan@garmin.com
22 | 964 | TXTW22_Drive+3.0 (Taroko) -12.3 DA | OEM Auto | GMLA2 | Complete | 2022-08-12 | 2022-08-12 | 2.D-5 | 0 | Rear case auto screw machine need to modify the fixture. Aim to complete modification and verification on 9/E | jason.fan@garmin.com
23 | 964 | TXTW22_Drive+3.0 (Taroko) -12.3 DA | OEM Auto | GMLA3 | Complete | 2023-05-31 | 2023-05-31 | 3.C-2 | 1 | Update fixture list for PR | jim.shen@garmin.com
24 | 964 | TXTW22_Drive+3.0 (Taroko) -12.3 DA | OEM Auto | GMLA3 | Complete | 2023-05-31 | 2023-05-31 | 3.D-5 | 1 | Front case touch fixture add protective for level A serface, | simon.ko@garmin.com
25 | 983 | "Austin" | Outdoor | GMLA2 | Complete | 2021-03-26 | 2021-03-29 | 2.C-2 | 1 | fixtures meet FFP schedule | nixon.pan@garmin.com
26 | 983 | "Austin" | Outdoor | GMLA2 | Complete | 2021-03-26 | 2021-03-29 | 2.D-5 | 1 | confirmed by DPQE | cooper.wang@garmin.com
27 | 983 | "Austin" | Outdoor | GMLA3 | Complete | 2021-10-01 | 2021-10-06 | 3.C-2 | 1 | All fixtures meet PR schedule | nixon.pan@garmin.com
28 | 983 | "Austin" | Outdoor | GMLA3 | Complete | 2021-10-01 | 2021-10-06 | 3.D-5 | 1 | Confirmed by DPQE | aalto.lo@garmin.com
29 | 1004 | GPSMAP 79 Series | Marine | GMLA1 | Complete | 2021-03-03 | 2021-03-03
30 | 1004 | GPSMAP 79 Series | Marine | GMLA2 | Complete | 2021-06-16 | 2021-06-16 | 2.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
31 | 1004 | GPSMAP 79 Series | Marine | GMLA2 | Complete | 2021-06-16 | 2021-06-16 | 2.D-5 | 1 | Done for ASSY | daniel.lee@garmin.com
32 | 1004 | GPSMAP 79 Series | Marine | GMLA3 | Complete | 2021-09-08 | 2021-09-08 | 3.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
33 | 1004 | GPSMAP 79 Series | Marine | GMLA3 | Complete | 2021-09-08 | 2021-09-08 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
34 | 1005 | Next Generation Low-Cost Smartband | Fitness | GMLA1 | Incomplete |  | 2021-05-14
35 | 1005 | Next Generation Low-Cost Smartband | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
36 | 1005 | Next Generation Low-Cost Smartband | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
37 | 1005 | Next Generation Low-Cost Smartband | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
38 | 1005 | Next Generation Low-Cost Smartband | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
39 | 1009 | Tread Audio System | Automotive | GMLA3 | Complete | 2022-03-11 | 2022-03-14 | 3.C-2 | 1 | The fixture list is as the attachment. Confirmed by DPQE. | wendy.ni@garmin.com
40 | 1009 | Tread Audio System | Automotive | GMLA3 | Complete | 2022-03-11 | 2022-03-14 | 3.D-5 | 1 | Confirmed OK | isaac.wang@garmin.com
41 | 1009 | Tread Audio System | Automotive | GMLA1 | Complete | 2021-06-21 | 2021-06-29
42 | 1009 | Tread Audio System | Automotive | GMLA2 | Complete | 2022-01-05 | 2022-01-05 | 2.C-2 | 1 | At build beginning, it is determined to use SMT. Due to the bad quality of SMT power post. Hand soldering is applied for the rest units. Hand soldering fixture will be ready before PR build. | wendy.ni@garmin.com
43 | 1009 | Tread Audio System | Automotive | GMLA2 | Complete | 2022-01-05 | 2022-01-05 | 2.D-5 | 1 | ASSY fixture is verified at FFP without issue. SMT hand soldering fixture will be verified at PR build. | wendy.ni@garmin.com
44 | 1012 | Approach R50 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
45 | 1012 | Approach R50 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
46 | 1012 | Approach R50 | Outdoor | GMLA1 | Complete | 2021-12-07 | 2021-12-16
47 | 1012 | Approach R50 | Outdoor | GMLA2 | Incomplete |  | 2023-12-01 | 2.C-2 | 0
48 | 1012 | Approach R50 | Outdoor | GMLA2 | Incomplete |  | 2023-12-01 | 2.D-5 | 0
49 | 1017 | LiveScope XR (LVS62) | Marine | GMLA1 | Complete | 2021-07-29 | 2021-08-04
50 | 1017 | LiveScope XR (LVS62) | Marine | GMLA2 | Complete | 2021-12-06 | 2021-12-15 | 2.C-2 | 0 | (DPQE Confirmed) FT2 tank readiness need to be tracked | jasoncy.hsu@garmin.com
51 | 1017 | LiveScope XR (LVS62) | Marine | GMLA2 | Complete | 2021-12-06 | 2021-12-15 | 2.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
52 | 1017 | LiveScope XR (LVS62) | Marine | GMLA3 | Complete | 2022-04-07 | 2022-04-07 | 3.C-2 | 1 | (DPQE Confirmed) No delay on fixture readiness | jasoncy.hsu@garmin.com
53 | 1017 | LiveScope XR (LVS62) | Marine | GMLA3 | Complete | 2022-04-07 | 2022-04-07 | 3.D-5 | 1 | (DPQE Confirmed) Checked | jasoncy.hsu@garmin.com
54 | 1023 | Venu Sq 2(IMP) | Fitness | GMLA1 | Complete | 2021-10-26 | 2021-10-26
55 | 1023 | Venu Sq 2(IMP) | Fitness | GMLA2 | Complete | 2022-04-08 | 2022-04-11 | 2.C-2 | 1 | All FFP fixtures have been reviewed. | jackhl.chen@garmin.com
56 | 1023 | Venu Sq 2(IMP) | Fitness | GMLA2 | Complete | 2022-04-08 | 2022-04-11 | 2.D-5 | 1 | (Confirmed by DPQE) Based on DFM, no critical equipment is identified. | aalto.lo@garmin.com
57 | 1023 | Venu Sq 2(IMP) | Fitness | GMLA3 | Complete | 2022-07-06 | 2022-07-08 | 3.C-2 | 1 | All fixtures will be ready before MP. | jackhl.chen@garmin.com
58 | 1023 | Venu Sq 2(IMP) | Fitness | GMLA3 | Complete | 2022-07-06 | 2022-07-08 | 3.D-5 | 1 | (Confirmed by DPQE) Based on DFM, no critical equipment is identified. | aalto.lo@garmin.com
59 | 1028 | BMW MGU22_PL1 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
60 | 1028 | BMW MGU22_PL1 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
61 | 1028 | BMW MGU22_PL1 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
62 | 1028 | BMW MGU22_PL1 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
63 | 1028 | BMW MGU22_PL1 | OEM Auto | GMLA1 | Incomplete
64 | 1032 | Forerunner 255 | Fitness | GMLA1 | Complete | 2021-04-18 | 2021-04-19
65 | 1032 | Forerunner 255 | Fitness | GMLA2 | Complete | 2021-12-21 | 2021-12-22 | 2.C-2 | 1 | Fixture ready for FFP build | alexty.chang@garmin.com
66 | 1032 | Forerunner 255 | Fitness | GMLA2 | Complete | 2021-12-21 | 2021-12-22 | 2.D-5 | 1 | No requirement | alexty.chang@garmin.com
67 | 1032 | Forerunner 255 | Fitness | GMLA3 | Complete | 2022-03-30 | 2022-03-31 | 3.C-2 | 1 | Fixtures can be arrival before MP | robben.liu@garmin.com
68 | 1032 | Forerunner 255 | Fitness | GMLA3 | Complete | 2022-03-30 | 2022-03-31 | 3.D-5 | 0 | Need to provide report for verification. | pattie.lan@garmin.com
69 | 1036 | Approach S70s | Outdoor | GMLA1 | Complete | 2022-07-04 | 2022-07-05
70 | 1036 | Approach S70s | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 2.C-2 | 0 | Confirmed by DPQE Sampling 3 fixture(36339,36555,34529), all of them do not have TM0362. | cooper.wang@garmin.com
71 | 1036 | Approach S70s | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 2.D-5 | 1 | confirmed | cooper.wang@garmin.com
72 | 1036 | Approach S70s | Outdoor | GMLA3 | Complete | 2023-03-28 | 2023-03-28 | 3.C-2 | 1 | (Confirmed by DPQE) | leoyt.chen@garmin.com
73 | 1036 | Approach S70s | Outdoor | GMLA3 | Complete | 2023-03-28 | 2023-03-28 | 3.D-5 | 1 | No related issue cause by fixture | leoyt.chen@garmin.com
74 | 1037 | GHC 50 | Marine | GMLA2 | Incomplete |  | 2021-11-10 | 2.C-2 | 0
75 | 1037 | GHC 50 | Marine | GMLA2 | Incomplete |  | 2021-11-10 | 2.D-5 | 0
76 | 1037 | GHC 50 | Marine | GMLA3 | Incomplete |  | 2022-02-04 | 3.C-2 | 0
77 | 1037 | GHC 50 | Marine | GMLA3 | Incomplete |  | 2022-02-04 | 3.D-5 | 0
78 | 1037 | GHC 50 | Marine | GMLA1 | Incomplete
79 | 1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA1 | Incomplete |  | 2021-09-03
80 | 1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.C-2 | 0
81 | 1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.D-5 | 0
82 | 1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-24 | 3.C-2 | 0
83 | 1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-24 | 3.D-5 | 0
84 | 1057 | Descent Mk3 Series - Large | Outdoor | GMLA1 | Complete | 2023-01-18 | 2023-01-19
85 | 1057 | Descent Mk3 Series - Large | Outdoor | GMLA2 | Complete | 2023-08-10 | 2023-08-14 | 2.C-2 | 0 | ATE fixture all have TM0362 and interferance check.However, the smt and assy ixture do not have TM0362 | admin
86 | 1057 | Descent Mk3 Series - Large | Outdoor | GMLA2 | Complete | 2023-08-10 | 2023-08-14 | 2.D-5 | 1 | These issues didn't really cause quality issues. It's test accuracy. | cooper.wang@garmin.com
87 | 1057 | Descent Mk3 Series - Large | Outdoor | GMLA3 | Complete | 2023-10-04 | 2023-10-04 | 3.C-2 | 1 | 29 fixtures can't meet requirement. | cooper.wang@garmin.com
88 | 1057 | Descent Mk3 Series - Large | Outdoor | GMLA3 | Complete | 2023-10-04 | 2023-10-04 | 3.D-5 | 1 | Can't find any quality related fixture issue on PRissue | cooper.wang@garmin.com
89 | 1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 2.C-2 | 1 | All fixtures will share with DriveSmart 76. | stephanie.yang@garmin.com
90 | 1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 2.D-5 | 1 | Have verified the result (2-D-3), others are same with dezl OTR 700 | wilson.chen@garmin.com
91 | 1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA1 | Complete | 2021-11-02 | 2021-11-04
92 | 1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-11 | 3.C-2 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
93 | 1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-11 | 3.D-5 | 1 | Checked | wilson.chen@garmin.com
94 | 1083 | Approach S42 | Outdoor | GMLA1 | Incomplete
95 | 1083 | Approach S42 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
96 | 1083 | Approach S42 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
97 | 1083 | Approach S42 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
98 | 1083 | Approach S42 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
99 | 1089 | Venu 3 | Fitness | GMLA1 | Complete | 2022-07-07 | 2022-07-12
100 | 1089 | Venu 3 | Fitness | GMLA2 | Complete | 2023-02-06 | 2023-02-09 | 2.C-2 | 0 | Following fixtures have no verification result uploaded: 1.37896 2.37897 3.38524 4.38736 5.37896 6.37897 | cooper.wang@garmin.com
101 | 1089 | Venu 3 | Fitness | GMLA2 | Complete | 2023-02-06 | 2023-02-09 | 2.D-5 | 0 | Fixture may cause 100% no feeling scratch. | cooper.wang@garmin.com
102 | 1089 | Venu 3 | Fitness | GMLA3 | Complete | 2023-05-23 | 2023-05-24 | 3.C-2 | 0 | 37897 心跳版漏光 no newTM0362 38524 螢幕軟排connecotr鎖副 無干涉檢察 38736 軟排預摺無實體干涉檢察 38886 前殼LCM電測治具無干涉檢察 38890無實體干涉檢察 40959 螢幕軟排CONNECTOR鎖附TM0362無內容 41403 SUB-ppg TM0362無內容 (Confirmed by DPQE) | leoyt.chen@garmin.com
103 | 1089 | Venu 3 | Fitness | GMLA3 | Complete | 2023-05-23 | 2023-05-24 | 3.D-5 | 0 | Issue: OHRM FPC connector damage was detected at -1X unit assy RTESN. Fail rate: 1.36% (5/368 pcs) Root cause: No alignment feature of -4X PPG test fixture causing connector damaged once the operator didn't well place FPC on fixture. Action: Fixture modification to add alignment feature and keep monitor this issue in PR2. | leoyt.chen@garmin.com
104 | 1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA1 | Complete | 2022-07-25 | 2022-08-04
105 | 1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA2 | Complete | 2022-10-24 | 2022-10-28 | 2.C-2 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
106 | 1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA2 | Complete | 2022-10-24 | 2022-10-28 | 2.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
107 | 1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA3 | Complete | 2023-02-23 | 2023-02-24 | 3.C-2 | 0 | 38215 no TM0362 39271 no TM0362 39549 no TM0362 39652 no TM0362 | howard.jen@garmin.com
108 | 1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA3 | Complete | 2023-02-23 | 2023-02-24 | 3.D-5 | 1 | FPC Pre-bending fixture lead IC crack , have been modified immedaitely | howard.jen@garmin.com
109 | 1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA1 | Incomplete
110 | 1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
111 | 1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
112 | 1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
113 | 1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
114 | 1112 | Instinct 2X Solar | Outdoor | GMLA1 | Complete | 2022-10-27 | 2022-11-09
115 | 1112 | Instinct 2X Solar | Outdoor | GMLA2 | Complete | 2022-12-31 | 2023-01-03 | 2.C-2 | 0 | No TM0362 | aalto.lo@garmin.com
116 | 1112 | Instinct 2X Solar | Outdoor | GMLA2 | Complete | 2022-12-31 | 2023-01-03 | 2.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
117 | 1112 | Instinct 2X Solar | Outdoor | GMLA3 | Complete | 2023-02-01 | 2023-02-03 | 3.C-2 | 0 | No TM0362 | aalto.lo@garmin.com
118 | 1112 | Instinct 2X Solar | Outdoor | GMLA3 | Complete | 2023-02-01 | 2023-02-03 | 3.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
119 | 1113 | LYWW24 | OEM Auto | GMLA1 | Incomplete
120 | 1113 | LYWW24 | OEM Auto | GMLA2 | Incomplete |  | 2022-10-12 | 2.C-2 | 0
121 | 1113 | LYWW24 | OEM Auto | GMLA2 | Incomplete |  | 2022-10-12 | 2.D-5 | 0
122 | 1113 | LYWW24 | OEM Auto | GMLA3 | Incomplete |  | 2023-12-19 | 3.C-2 | 0
123 | 1113 | LYWW24 | OEM Auto | GMLA3 | Incomplete |  | 2023-12-19 | 3.D-5 | 0
124 | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA1 | Incomplete
125 | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
126 | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
127 | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
128 | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
129 | 1118 | Forerunner 265s | Fitness | GMLA1 | Complete | 2022-06-27 | 2022-07-06
130 | 1118 | Forerunner 265s | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 2.C-2 | 1 | ready before FFP | nixon.pan@garmin.com
131 | 1118 | Forerunner 265s | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 2.D-5 | 1 | No category A fixture by 7/20 | amyry.chen@garmin.com
132 | 1118 | Forerunner 265s | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-22 | 3.C-2 | 0 | No verification result update: 1. Router fixture 2. Paste tape fixture 3. PCB screwing fixture 4. Carrier fixture | amyry.chen@garmin.com
133 | 1118 | Forerunner 265s | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-22 | 3.D-5 | 1 | No PR issued | chris.kuo@garmin.com
134 | 1122 | GPSMAP 9000_Black Box | Marine | GMLA1 | Incomplete |  | 2022-12-14
135 | 1122 | GPSMAP 9000_Black Box | Marine | GMLA2 | Incomplete |  | 2023-06-02 | 2.C-2 | 0
136 | 1122 | GPSMAP 9000_Black Box | Marine | GMLA2 | Incomplete |  | 2023-06-02 | 2.D-5 | 0
137 | 1122 | GPSMAP 9000_Black Box | Marine | GMLA3 | Incomplete |  | 2023-08-28 | 3.C-2 | 0
138 | 1122 | GPSMAP 9000_Black Box | Marine | GMLA3 | Incomplete |  | 2023-08-28 | 3.D-5 | 0
139 | 1123 | Lily 2 | Fitness | GMLA1 | Complete | 2023-01-06 | 2023-01-06
140 | 1123 | Lily 2 | Fitness | GMLA2 | Complete | 2023-07-19 | 2023-07-20 | 2.C-2 | 0 | 43251 fixture no TM0362 document and interference check | ernest.fu@garmin.com
141 | 1123 | Lily 2 | Fitness | GMLA2 | Complete | 2023-07-19 | 2023-07-20 | 2.D-5 | 1 | No equipment & fixture design issued on FFP | ernest.fu@garmin.com
142 | 1123 | Lily 2 | Fitness | GMLA3 | Complete | 2023-10-04 | 2023-10-04 | 3.C-2 | 1 | DPQE comment on 10/4: All fixtures preparation and verification results are PASS PDO fixture preparation and verification result are checked | ernest.fu@garmin.com
143 | 1123 | Lily 2 | Fitness | GMLA3 | Complete | 2023-10-04 | 2023-10-04 | 3.D-5 | 1 | No equipment & fixture design issued on PR | ernest.fu@garmin.com
144 | 1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA1 | Incomplete
145 | 1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
146 | 1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
147 | 1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
148 | 1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
149 | 1132 | dezl headset (2nd Gen) | Automotive | GMLA3 | Incomplete |  | 2024-03-22 | 3.C-2 | 0
150 | 1132 | dezl headset (2nd Gen) | Automotive | GMLA3 | Incomplete |  | 2024-03-22 | 3.D-5 | 0
151 | 1132 | dezl headset (2nd Gen) | Automotive | GMLA1 | Complete | 2023-05-15 | 2023-05-16
152 | 1132 | dezl headset (2nd Gen) | Automotive | GMLA2 | Incomplete |  | 2023-12-11 | 2.C-2 | 0
153 | 1132 | dezl headset (2nd Gen) | Automotive | GMLA2 | Incomplete |  | 2023-12-11 | 2.D-5 | 0
154 | 1134 | Force Kayak Propulsion System | Marine | GMLA1 | Incomplete |  | 2023-12-29
155 | 1134 | Force Kayak Propulsion System | Marine | GMLA2 | Incomplete |  | 2024-10-22 | 2.C-2 | 0
156 | 1134 | Force Kayak Propulsion System | Marine | GMLA2 | Incomplete |  | 2024-10-22 | 2.D-5 | 0
157 | 1134 | Force Kayak Propulsion System | Marine | GMLA3 | Incomplete |  | 2025-01-28 | 3.C-2 | 0
158 | 1134 | Force Kayak Propulsion System | Marine | GMLA3 | Incomplete |  | 2025-01-28 | 3.D-5 | 0
159 | 1065 | eTrex Solar | Outdoor | GMLA1 | Complete | 2022-09-02 | 2022-09-07
160 | 1065 | eTrex Solar | Outdoor | GMLA2 | Complete | 2023-06-29 | 2023-06-29 | 2.C-2 | 1 | 1. No new equipment 2. All Assy Fixture no risk with PCBA | chris.kuo@garmin.com
161 | 1065 | eTrex Solar | Outdoor | GMLA2 | Complete | 2023-06-29 | 2023-06-29 | 2.D-5 | 1 | No fixture design issue on FFP build | chris.kuo@garmin.com
162 | 1065 | eTrex Solar | Outdoor | GMLA3 | Complete | 2023-09-07 | 2023-09-14 | 3.C-2 | 1 | [8/1] Review all fixture verification result PASS , Complete rate:100% (14/14) | chris.kuo@garmin.com
163 | 1065 | eTrex Solar | Outdoor | GMLA3 | Complete | 2023-09-07 | 2023-09-14 | 3.D-5 | 1 | Check by DPQE | chris.kuo@garmin.com
164 | 1069 | Edge 540 840 | Fitness | GMLA1 | Complete | 2021-12-06 | 2021-12-13
165 | 1069 | Edge 540 840 | Fitness | GMLA2 | Complete | 2022-08-22 | 2022-08-22 | 2.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
166 | 1069 | Edge 540 840 | Fitness | GMLA2 | Complete | 2022-08-22 | 2022-08-22 | 2.D-5 | 1 | No critical equipment | chris.kuo@garmin.com
167 | 1069 | Edge 540 840 | Fitness | GMLA3 | Complete | 2022-12-08 | 2022-12-12 | 3.C-2 | 0 | No verification result update to the PCBA screwing fixture | chris.kuo@garmin.com
168 | 1069 | Edge 540 840 | Fitness | GMLA3 | Complete | 2022-12-08 | 2022-12-12 | 3.D-5 | 0 | The screwing fixture will press the frame on the PCB | chris.kuo@garmin.com
169 | 1103 | Forerunner 965 | Fitness | GMLA1 | Complete | 2022-07-06 | 2022-07-18
170 | 1103 | Forerunner 965 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-15 | 2.C-2 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
171 | 1103 | Forerunner 965 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-15 | 2.D-5 | 1 | Verification of critical process (gluing process) is pass since no water leak issue after ELOT test. | aalto.lo@garmin.com
172 | 1103 | Forerunner 965 | Fitness | GMLA3 | Complete | 2022-12-15 | 2022-12-19 | 3.C-2 | 0 | Do not have TM0362 for level A fixture. | aalto.lo@garmin.com
173 | 1103 | Forerunner 965 | Fitness | GMLA3 | Complete | 2022-12-15 | 2022-12-19 | 3.D-5 | 1 | (Confirmed by DPQE) The breaking line appeared on the display. [12/5] The adjustment of fixture is finished, PE already use some material to make sure it works. | aalto.lo@garmin.com
174 | 1147 | ECHOMAP Ultra 2 - 12" | Marine | GMLA1 | Complete | 2023-04-26 | 2023-04-26
175 | 1147 | ECHOMAP Ultra 2 - 12" | Marine | GMLA3 | Incomplete |  | 2023-09-27 | 3.C-2 | 0
176 | 1147 | ECHOMAP Ultra 2 - 12" | Marine | GMLA3 | Incomplete |  | 2023-09-27 | 3.D-5 | 0
177 | 1149 | Fusion - RA800 | Marine | GMLA2 | Incomplete |  | 2024-09-27 | 2.C-2 | 0
178 | 1149 | Fusion - RA800 | Marine | GMLA2 | Incomplete |  | 2024-09-27 | 2.D-5 | 0
179 | 1149 | Fusion - RA800 | Marine | GMLA3 | Incomplete |  | 2024-12-18 | 3.C-2 | 0
180 | 1149 | Fusion - RA800 | Marine | GMLA3 | Incomplete |  | 2024-12-18 | 3.D-5 | 0
181 | 1149 | Fusion - RA800 | Marine | GMLA1 | Incomplete |  | 2023-10-26
182 | 1151 | GC 255 and GC 245 | Marine | GMLA1 | Complete | 2023-10-02 | 2023-10-04
183 | 1151 | GC 255 and GC 245 | Marine | GMLA3 | Incomplete |  | 2024-04-25 | 3.C-2 | 0
184 | 1151 | GC 255 and GC 245 | Marine | GMLA3 | Incomplete |  | 2024-04-25 | 3.D-5 | 0
185 | 1151 | GC 255 and GC 245 | Marine | GMLA2 | Incomplete |  | 2023-12-06 | 2.C-2 | 0
186 | 1151 | GC 255 and GC 245 | Marine | GMLA2 | Incomplete |  | 2023-12-06 | 2.D-5 | 0
187 | 1152 | Varia Headlight Camera | Fitness | GMLA2 | Incomplete |  | 2024-06-03 | 2.C-2 | 0
188 | 1152 | Varia Headlight Camera | Fitness | GMLA2 | Incomplete |  | 2024-06-03 | 2.D-5 | 0
189 | 1152 | Varia Headlight Camera | Fitness | GMLA3 | Incomplete |  | 2024-08-12 | 3.C-2 | 0
190 | 1152 | Varia Headlight Camera | Fitness | GMLA3 | Incomplete |  | 2024-08-12 | 3.D-5 | 0
191 | 1152 | Varia Headlight Camera | Fitness | GMLA1 | Incomplete
192 | 1155 | Large Format TXi | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
193 | 1155 | Large Format TXi | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
194 | 1155 | Large Format TXi | Aviation | GMLA1 | Complete | 2023-03-24 | 2023-03-29
195 | 1155 | Large Format TXi | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
196 | 1155 | Large Format TXi | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
197 | 1157 | Descent T2 Transceiver | Outdoor | GMLA1 | Complete | 2023-02-18 | 2023-03-01
198 | 1157 | Descent T2 Transceiver | Outdoor | GMLA2 | Complete | 2023-06-05 | 2023-06-07 | 2.C-2 | 1 | Fixture list / ATE fixture list were checked and all passed | ernest.fu@garmin.com
199 | 1157 | Descent T2 Transceiver | Outdoor | GMLA2 | Complete | 2023-06-05 | 2023-06-07 | 2.D-5 | 0 | ANT connection issue for Dive equipment , FT and VT_11arm | ernest.fu@garmin.com
200 | 1157 | Descent T2 Transceiver | Outdoor | GMLA3 | Complete | 2023-09-20 | 2023-09-20 | 3.C-2 | 1 | DPQE comment on 7/26: Fixture preparation and verification result is PASS | ernest.fu@garmin.com
201 | 1157 | Descent T2 Transceiver | Outdoor | GMLA3 | Complete | 2023-09-20 | 2023-09-20 | 3.D-5 | 1 | No equipment & fixture design issued | ernest.fu@garmin.com
202 | 1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA1 | Complete | 2023-06-19 | 2023-06-23
203 | 1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA3 | Incomplete |  | 2024-01-31 | 3.C-2 | 0
204 | 1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA3 | Incomplete |  | 2024-01-31 | 3.D-5 | 0
205 | 1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA2 | Incomplete |  | 2023-11-06 | 2.C-2 | 0
206 | 1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA2 | Incomplete |  | 2023-11-06 | 2.D-5 | 0
207 | 1173 | fenix 8 47mm | Outdoor | GMLA1 | Incomplete |  | 2023-11-20
208 | 1173 | fenix 8 47mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-02 | 2.C-2 | 0
209 | 1173 | fenix 8 47mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-02 | 2.D-5 | 0
210 | 1173 | fenix 8 47mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-08 | 3.C-2 | 0
211 | 1173 | fenix 8 47mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-08 | 3.D-5 | 0
212 | 1174 | fenix 8 51mm | Outdoor | GMLA1 | Incomplete |  | 2023-05-26
213 | 1174 | fenix 8 51mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-07 | 2.C-2 | 0
214 | 1174 | fenix 8 51mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-07 | 2.D-5 | 0
215 | 1174 | fenix 8 51mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-13 | 3.C-2 | 0
216 | 1174 | fenix 8 51mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-13 | 3.D-5 | 0
217 | 1175 | Instinct 3 Solar - 45mm | Outdoor | GMLA1 | Incomplete
218 | 1175 | Instinct 3 Solar - 45mm | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
219 | 1175 | Instinct 3 Solar - 45mm | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
220 | 1175 | Instinct 3 Solar - 45mm | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
221 | 1175 | Instinct 3 Solar - 45mm | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
222 | 1176 | Enduro 3 47mm | Outdoor | GMLA1 | Incomplete |  | 2023-10-25
223 | 1176 | Enduro 3 47mm | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
224 | 1176 | Enduro 3 47mm | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
225 | 1176 | Enduro 3 47mm | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
226 | 1176 | Enduro 3 47mm | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
227 | 1177 | LWIN23 | OEM Auto | GMLA1 | Incomplete
228 | 1177 | LWIN23 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
229 | 1177 | LWIN23 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
230 | 1177 | LWIN23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
231 | 1177 | LWIN23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
232 | 1180 | Engine Cut-Off System (ECOS/MOB) | Marine | GMLA1 | Incomplete |  | 2023-12-27
233 | 1180 | Engine Cut-Off System (ECOS/MOB) | Marine | GMLA2 | Incomplete |  | 2024-08-13 | 2.C-2 | 0
234 | 1180 | Engine Cut-Off System (ECOS/MOB) | Marine | GMLA2 | Incomplete |  | 2024-08-13 | 2.D-5 | 0
235 | 1180 | Engine Cut-Off System (ECOS/MOB) | Marine | GMLA3 | Incomplete |  | 2024-11-15 | 3.C-2 | 0
236 | 1180 | Engine Cut-Off System (ECOS/MOB) | Marine | GMLA3 | Incomplete |  | 2024-11-15 | 3.D-5 | 0
237 | 1181 | Xero G2i Scouting Camera | Outdoor | GMLA1 | Incomplete
238 | 1181 | Xero G2i Scouting Camera | Outdoor | GMLA2 | Incomplete |  | 2023-10-25 | 2.C-2 | 0
239 | 1181 | Xero G2i Scouting Camera | Outdoor | GMLA2 | Incomplete |  | 2023-10-25 | 2.D-5 | 0
240 | 1181 | Xero G2i Scouting Camera | Outdoor | GMLA3 | Incomplete |  | 2024-01-09 | 3.C-2 | 0
241 | 1181 | Xero G2i Scouting Camera | Outdoor | GMLA3 | Incomplete |  | 2024-01-09 | 3.D-5 | 0
242 | 1184 | Garmin Fixed Mount VHF with AIS | Marine | GMLA1 | Incomplete
243 | 1184 | Garmin Fixed Mount VHF with AIS | Marine | GMLA2 | Incomplete |  | 2024-10-03 | 2.C-2 | 0
244 | 1184 | Garmin Fixed Mount VHF with AIS | Marine | GMLA2 | Incomplete |  | 2024-10-03 | 2.D-5 | 0
245 | 1184 | Garmin Fixed Mount VHF with AIS | Marine | GMLA3 | Incomplete |  | 2024-11-20 | 3.C-2 | 0
246 | 1184 | Garmin Fixed Mount VHF with AIS | Marine | GMLA3 | Incomplete |  | 2024-11-20 | 3.D-5 | 0
247 | 1188 | zumo XS | Automotive | GMLA1 | Incomplete
248 | 1188 | zumo XS | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
249 | 1188 | zumo XS | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
250 | 1188 | zumo XS | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
251 | 1188 | zumo XS | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
252 | 1191 | DEZL Sideview | Automotive | GMLA1 | Incomplete
253 | 1191 | DEZL Sideview | Automotive | GMLA2 | Incomplete |  | 2024-09-04 | 2.C-2 | 0
254 | 1191 | DEZL Sideview | Automotive | GMLA2 | Incomplete |  | 2024-09-04 | 2.D-5 | 0
255 | 1191 | DEZL Sideview | Automotive | GMLA3 | Incomplete |  | 2024-11-27 | 3.C-2 | 0
256 | 1191 | DEZL Sideview | Automotive | GMLA3 | Incomplete |  | 2024-11-27 | 3.D-5 | 0
257 | 1193 | LXMY24 | OEM Auto | GMLA1 | Incomplete
258 | 1193 | LXMY24 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
259 | 1193 | LXMY24 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
260 | 1193 | LXMY24 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
261 | 1193 | LXMY24 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
262 | 780 | Dash Cam Tandem | Automotive | GMLA1 | Incomplete |  | 2019-04-03
263 | 780 | Dash Cam Tandem | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
264 | 780 | Dash Cam Tandem | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
265 | 780 | Dash Cam Tandem | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
266 | 780 | Dash Cam Tandem | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
267 | 783 | MKSA | OEM Auto | GMLA1 | Incomplete
268 | 783 | MKSA | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
269 | 783 | MKSA | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
270 | 783 | MKSA | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
271 | 783 | MKSA | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
272 | 785 | DGCN20 | OEM Auto | GMLA3 | Complete | 2021-02-22 | 2021-02-05 | 3.C-2 | 1 | review per pilot run kick-off meeting | nick.yen@garmin.com
273 | 785 | DGCN20 | OEM Auto | GMLA3 | Complete | 2021-02-22 | 2021-02-05 | 3.D-5 | 1 | The cycle test of critical fixtures are done. | zack.lin@garmin.com
274 | 874 | 2020 RV Series - Unit 7" | Marine | GMLA1 | Incomplete |  | 2019-07-01
275 | 874 | 2020 RV Series - Unit 7" | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
276 | 874 | 2020 RV Series - Unit 7" | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
277 | 874 | 2020 RV Series - Unit 7" | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
278 | 874 | 2020 RV Series - Unit 7" | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
279 | 987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA1 | Complete | 2021-01-27 | 2021-01-27
280 | 987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 2.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
281 | 987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 2.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
282 | 987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 3.C-2 | 1 | ((DPQE Confirmed) Fixture is ready and meet the ETA | jasoncy.hsu@garmin.com
283 | 987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 3.D-5 | 1 | (DPQE Confirmed) According to DFM report and fixture list, there is no critical equipment | jasoncy.hsu@garmin.com
284 | 988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA1 | Complete | 2021-02-01 | 2021-02-03
285 | 988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 2.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
286 | 988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 2.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
287 | 988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 3.C-2 | 1 | ((DPQE Confirmed) Fixture is ready and meet the ETA | jasoncy.hsu@garmin.com
288 | 988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 3.D-5 | 1 | (DPQE Confirmed) According to DFM report and fixture list, there is no critical equipment | jasoncy.hsu@garmin.com
289 | 1016 | Xero L60i Laser Navigator | Outdoor | GMLA1 | Complete | 2022-08-11 | 2022-08-15
290 | 1016 | Xero L60i Laser Navigator | Outdoor | GMLA2 | Complete | 2023-08-16 | 2023-08-16 | 2.C-2 | 1 | [7/28] Fixture complete rate: 62.9%(17/27) Not complete fixture ID:41931/41932/41935/41938/41946/42015/42163/42166/43142/43631 | chris.kuo@garmin.com
291 | 1016 | Xero L60i Laser Navigator | Outdoor | GMLA2 | Complete | 2023-08-16 | 2023-08-16 | 2.D-5 | 1 | No fixture & equipment design issue | chris.kuo@garmin.com
292 | 1016 | Xero L60i Laser Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-11-07 | 3.C-2 | 0
293 | 1016 | Xero L60i Laser Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-11-07 | 3.D-5 | 0
294 | 1027 | inReach Messenger | Outdoor | GMLA1 | Complete | 2021-09-01 | 2021-09-02
295 | 1027 | inReach Messenger | Outdoor | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 2.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
296 | 1027 | inReach Messenger | Outdoor | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 2.D-5 | 1 | No critical process need | chris.kuo@garmin.com
297 | 1027 | inReach Messenger | Outdoor | GMLA3 | Complete | 2022-05-16 | 2022-05-17 | 3.C-2 | 1 | Fixture ETA meet PR schedule | chris.kuo@garmin.com
298 | 1027 | inReach Messenger | Outdoor | GMLA3 | Complete | 2022-05-16 | 2022-05-17 | 3.D-5 | 1 | No critical equipment and fixture | chris.kuo@garmin.com
299 | 1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA1 | Complete | 2021-12-13 | 2021-12-13
300 | 1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.C-2 | 1 | (DPQE Confirmed) Fixture is ready for FFP | jasoncy.hsu@garmin.com
301 | 1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.D-5 | 1 | (DPQE Confirmed) Verification result checked | jasoncy.hsu@garmin.com
302 | 1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.C-2 | 1 | (DPQE Confirmed) Critical fixture (Class A) is only keypad board screwing fixture. The status is ongoing and wait for PDO, so there is no verification result needs to be checked | jasoncy.hsu@garmin.com
303 | 1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.D-5 | 1 | No fixture design issue according to PR issue and production report | jasoncy.hsu@garmin.com
304 | 1075 | fenix 7 Pro | Outdoor | GMLA1 | Complete | 2022-07-13 | 2022-07-18
305 | 1075 | fenix 7 Pro | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-22 | 2.C-2 | 0 | Check 4 fixture, none of them have TM0362 | howard.jen@garmin.com
306 | 1075 | fenix 7 Pro | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-22 | 2.D-5 | 1 | No issue related to fixture and equipment | howard.jen@garmin.com
307 | 1075 | fenix 7 Pro | Outdoor | GMLA3 | Complete | 2023-03-21 | 2023-03-21 | 3.C-2 | 0 | No verification result update (TM0362) : 40140、40581、40798、40812 | ernest.fu@garmin.com
308 | 1075 | fenix 7 Pro | Outdoor | GMLA3 | Complete | 2023-03-21 | 2023-03-21 | 3.D-5 | 1 | No PR issued | ernest.fu@garmin.com
309 | 1078 | Foretrex 801/901 | Outdoor | GMLA1 | Complete | 2022-07-01 | 2022-07-04
310 | 1078 | Foretrex 801/901 | Outdoor | GMLA2 | Complete | 2022-11-03 | 2022-11-03 | 2.C-2 | 1 | ready before FFP | amyry.chen@garmin.com
311 | 1078 | Foretrex 801/901 | Outdoor | GMLA2 | Complete | 2022-11-03 | 2022-11-03 | 2.D-5 | 1 | No equipment & fixture design issued on FFP build | ernest.fu@garmin.com
312 | 1078 | Foretrex 801/901 | Outdoor | GMLA3 | Complete | 2023-02-12 | 2023-02-17 | 3.C-2 | 0 | No verification result update: PCB screwing fixture | ernest.fu@garmin.com
313 | 1078 | Foretrex 801/901 | Outdoor | GMLA3 | Complete | 2023-02-12 | 2023-02-17 | 3.D-5 | 1 | No PR issued | ernest.fu@garmin.com
314 | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA1 | Incomplete
315 | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
316 | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
317 | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
318 | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
319 | 1161 | eTrex Touch | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
320 | 1161 | eTrex Touch | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
321 | 1161 | eTrex Touch | Outdoor | GMLA1 | Complete | 2023-08-23 | 2023-08-23
322 | 1161 | eTrex Touch | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
323 | 1161 | eTrex Touch | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
324 | 1162 | GT17M-THF | Marine | GMLA1 | Complete | 2023-09-26 | 2023-09-26
325 | 1162 | GT17M-THF | Marine | GMLA2 | Incomplete |  | 2024-01-03 | 2.C-2 | 0
326 | 1162 | GT17M-THF | Marine | GMLA2 | Incomplete |  | 2024-01-03 | 2.D-5 | 0
327 | 1162 | GT17M-THF | Marine | GMLA3 | Incomplete |  | 2024-02-26 | 3.C-2 | 0
328 | 1162 | GT17M-THF | Marine | GMLA3 | Incomplete |  | 2024-02-26 | 3.D-5 | 0
329 | 1185 | Equine Dynamics System | Outdoor | GMLA1 | Incomplete
330 | 1185 | Equine Dynamics System | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
331 | 1185 | Equine Dynamics System | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
332 | 1185 | Equine Dynamics System | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
333 | 1185 | Equine Dynamics System | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
334 | 826 | Xero G1 SatCom Scouting Camera | Outdoor | GMLA3 | Complete | 2021-08-12 | 2021-10-01 | 3.C-2 | 1 | Fixture ready for PR2 | chris.kuo@garmin.com
335 | 826 | Xero G1 SatCom Scouting Camera | Outdoor | GMLA3 | Complete | 2021-08-12 | 2021-10-01 | 3.D-5 | 1 | Check the equipment and fixture from Pilot run build. Need PDO provide the verification report to NPI. | chris.kuo@garmin.com
336 | 917 | Dash Cam 47 / 57 / 67W | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-24 | 3.C-2 | 1 | Checked with PE. Some of fixtures applied for DCx6 | robben.liu@garmin.com
337 | 917 | Dash Cam 47 / 57 / 67W | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-24 | 3.D-5 | 1 | equipment/fixture finished | cherry.lee@garmin.com
338 | 921 | Surround View Camera System | Marine | GMLA2 | Complete | 2021-05-25 | 2021-05-25 | 2.C-2 | 1 | Fixture & equipment ETA for FFP is fine but SW issue happened in FFP, factory have no chnace to finish verification | ken.kuo@garmin.com
339 | 921 | Surround View Camera System | Marine | GMLA2 | Complete | 2021-05-25 | 2021-05-25 | 2.D-5 | 1 | Done | frankie.lee@garmin.com
340 | 921 | Surround View Camera System | Marine | GMLA3 | Complete | 2021-09-01 | 2021-09-01 | 3.C-2 | 1 | (Confirmed by DPQE) Done | jasoncy.hsu@garmin.com
341 | 921 | Surround View Camera System | Marine | GMLA3 | Complete | 2021-09-01 | 2021-09-01 | 3.D-5 | 1 | (Confirmed by DPQE) Done | jasoncy.hsu@garmin.com
342 | 953 | TXTW22_Drive+3.0 (Taroko)-9 DA | OEM Auto | GMLA1 | Complete | 2021-06-01 | 2021-06-02
343 | 953 | TXTW22_Drive+3.0 (Taroko)-9 DA | OEM Auto | GMLA2 | Complete | 2022-03-20 | 2022-03-18 | 2.C-2 | 1 | regular meeting tracking | nick.yen@garmin.com
344 | 953 | TXTW22_Drive+3.0 (Taroko)-9 DA | OEM Auto | GMLA2 | Complete | 2022-03-20 | 2022-03-18 | 2.D-5 | 1 | checked | nick.yen@garmin.com
345 | 953 | TXTW22_Drive+3.0 (Taroko)-9 DA | OEM Auto | GMLA3 | Complete | 2022-06-10 | 2022-06-10 | 3.C-2 | 1 | checked. | nick.yen@garmin.com
346 | 953 | TXTW22_Drive+3.0 (Taroko)-9 DA | OEM Auto | GMLA3 | Complete | 2022-06-10 | 2022-06-10 | 3.D-5 | 1 | checked | wells.yu@garmin.com
347 | 967 | Forerunner 955 and 955 Solar | Fitness | GMLA1 | Complete | 2021-04-07 | 2021-04-08
348 | 967 | Forerunner 955 and 955 Solar | Fitness | GMLA2 | Complete | 2021-11-15 | 2021-11-17 | 2.C-2 | 1 | Check, also the Automation project. | alexty.chang@garmin.com
349 | 967 | Forerunner 955 and 955 Solar | Fitness | GMLA2 | Complete | 2021-11-15 | 2021-11-17 | 2.D-5 | 0 | Confirmed by DPQE | ernest.fu@garmin.com
350 | 967 | Forerunner 955 and 955 Solar | Fitness | GMLA3 | Complete | 2022-03-09 | 2022-03-09 | 3.C-2 | 1 | Meet the target | alexty.chang@garmin.com
351 | 967 | Forerunner 955 and 955 Solar | Fitness | GMLA3 | Complete | 2022-03-09 | 2022-03-09 | 3.D-5 | 1 | checked | calvinyt.hsu@garmin.com
352 | 970 | Approach G12 | Outdoor | GMLA2 | Complete | 2020-12-25 | 2020-12-31 | 2.C-2 | 1 | Fixtures are ready for FFP | sherry.shih@garmin.com
353 | 970 | Approach G12 | Outdoor | GMLA2 | Complete | 2020-12-25 | 2020-12-31 | 2.D-5 | 1 | Check verification result | chris.kuo@garmin.com
354 | 970 | Approach G12 | Outdoor | GMLA3 | Complete | 2021-03-04 | 2021-03-04 | 3.C-2 | 1 | Confirmed by DPQE | chris.kuo@garmin.com
355 | 970 | Approach G12 | Outdoor | GMLA3 | Complete | 2021-03-04 | 2021-03-04 | 3.D-5 | 1 | no fixture issue | chris.kuo@garmin.com
356 | 971 | Instinct 2S | Outdoor | GMLA2 | Complete | 2021-05-12 | 2021-05-12 | 2.C-2 | 1 |  | franksl.chen@garmin.com
357 | 971 | Instinct 2S | Outdoor | GMLA2 | Complete | 2021-05-12 | 2021-05-12 | 2.D-5 | 1 | No critical equipment (confirmed by DPQE) | cooper.wang@garmin.com
358 | 971 | Instinct 2S | Outdoor | GMLA3 | Complete | 2021-07-26 | 2021-07-28 | 3.C-2 | 1 | MPM confirmed | franksl.chen@garmin.com
359 | 971 | Instinct 2S | Outdoor | GMLA3 | Complete | 2021-07-26 | 2021-07-28 | 3.D-5 | 1 | No critical equipment (DPQE confirmed) | cooper.wang@garmin.com
360 | 972 | Marq (Gen 2) | Outdoor | GMLA1 | Complete | 2022-02-10 | 2022-02-10
361 | 972 | Marq (Gen 2) | Outdoor | GMLA2 | Complete | 2022-09-14 | 2022-09-14 | 2.C-2 | 1 | No impact to FFP build. | alexty.chang@garmin.com
362 | 972 | Marq (Gen 2) | Outdoor | GMLA2 | Complete | 2022-09-14 | 2022-09-14 | 2.D-5 | 1 | No category A fixture by 7/16 (confirmed by DPQE) | cooper.wang@garmin.com
363 | 972 | Marq (Gen 2) | Outdoor | GMLA3 | Complete | 2022-09-29 | 2022-09-29 | 3.C-2 | 1 | No impact to Job Start Date | alexty.chang@garmin.com
364 | 972 | Marq (Gen 2) | Outdoor | GMLA3 | Complete | 2022-09-29 | 2022-09-29 | 3.D-5 | 1 | No category A fixture by 7/16 (confirmed by DPQE) | cooper.wang@garmin.com
365 | 981 | Xero A1i PRO Bow Sight | Outdoor | GMLA2 | Complete | 2021-01-08 | 2021-01-11 | 2.C-2 | 1 | Confirmed | lori.tsai@garmin.com
366 | 981 | Xero A1i PRO Bow Sight | Outdoor | GMLA2 | Complete | 2021-01-08 | 2021-01-11 | 2.D-5 | 1 | Fixtures of RH were verified in FFP. | lori.tsai@garmin.com
367 | 981 | Xero A1i PRO Bow Sight | Outdoor | GMLA3 | Complete | 2021-07-15 | 2021-07-15 | 3.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
368 | 981 | Xero A1i PRO Bow Sight | Outdoor | GMLA3 | Complete | 2021-07-15 | 2021-07-15 | 3.D-5 | 1 | No PVP review for bow sight pro since the unit is the same as the previous version | chris.kuo@garmin.com
369 | 984 | Product - 1.3\" GTR/GNC | Aviation | GMLA1 | Complete | 2023-03-06 | 2023-03-20
370 | 984 | Product - 1.3\" GTR/GNC | Aviation | GMLA2 | Complete | 2023-05-02 | 2023-05-10 | 2.C-2 | 1 | Fixtures for the PR phase have been completed. | steve.chiang@garmin.com
371 | 984 | Product - 1.3\" GTR/GNC | Aviation | GMLA2 | Complete | 2023-05-02 | 2023-05-10 | 2.D-5 | 1 | (1) No equipment requirement (2) No fixture issue | evelyn.wang@garmin.com
372 | 1015 | Dezl Headset | Automotive | GMLA1 | Complete | 2021-05-25 | 2021-05-31
373 | 1015 | Dezl Headset | Automotive | GMLA2 | Complete | 2021-11-18 | 2021-11-22 | 2.C-2 | 1 | Also equipment of vendor sealing check was not ready in FFP. Will keep tracking and implement before PR. | lori.tsai@garmin.com
374 | 1015 | Dezl Headset | Automotive | GMLA2 | Complete | 2021-11-18 | 2021-11-22 | 2.D-5 | 0 | The limited position of the Headset/ Slider/ ST fixture should be modified to improve the retry rate. | wendy.ni@garmin.com
375 | 1015 | Dezl Headset | Automotive | GMLA3 | Complete | 2022-02-08 | 2022-02-08 | 3.C-2 | 1 | Machine and fixtures are ready for PR2 on time. Second set of ST and ANC will be ready by 3/17, initial MP UPH will be re-evaluated. | lori.tsai@garmin.com
376 | 1015 | Dezl Headset | Automotive | GMLA3 | Complete | 2022-02-08 | 2022-02-08 | 3.D-5 | 1 | Confirmed by NPI PE | chloe.lin2@garmin.com
377 | 1026 | dezl watch | Automotive | GMLA2 | Complete | 2021-05-14 | 2021-05-14 | 2.C-2 | 1 | FFP fixtures are ready in time for FFP | robben.liu@garmin.com
378 | 1026 | dezl watch | Automotive | GMLA2 | Complete | 2021-05-14 | 2021-05-14 | 2.D-5 | 1 | No critical equipment (confirmed by DPQE) | wendy.ni@garmin.com
379 | 1026 | dezl watch | Automotive | GMLA3 | Complete | 2021-10-20 | 2021-10-20 | 3.C-2 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
380 | 1026 | dezl watch | Automotive | GMLA3 | Complete | 2021-10-20 | 2021-10-20 | 3.D-5 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
381 | 1055 | dezl OTR Series 2022-10" | Automotive | GMLA1 | Complete | 2021-11-17 | 2021-11-29
382 | 1055 | dezl OTR Series 2022-10" | Automotive | GMLA2 | Complete | 2022-02-09 | 2022-02-09 | 2.C-2 | 1 | Fixture is the same as dezl 1000. Confirmed by DPQE. | wendy.ni@garmin.com
383 | 1055 | dezl OTR Series 2022-10" | Automotive | GMLA2 | Complete | 2022-02-09 | 2022-02-09 | 2.D-5 | 1 | Same as last Gen. | isaac.wang@garmin.com
384 | 1055 | dezl OTR Series 2022-10" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 3.C-2 | 1 | Need to track ATE2.0 verification plan. | stephanie.yang@garmin.com
385 | 1055 | dezl OTR Series 2022-10" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 3.D-5 | 1 | There is no critical process. Confimed by DPQE. | wendy.ni@garmin.com
386 | 1081 | Serv - 10" | Marine | GMLA1 | Complete | 2022-03-01 | 2022-03-02
387 | 1081 | Serv - 10" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 2.C-2 | 1 | Confirmed by DPQE. Focus on verification result by PDO. The fixture is pass. | jasoncy.hsu@garmin.com
388 | 1081 | Serv - 10" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 2.D-5 | 1 | According to the questionnaire and criteria. There is no quality issue is caused by fixture in FFP build. It should be complete. | jasoncy.hsu@garmin.com
389 | 1081 | Serv - 10" | Marine | GMLA3 | Complete | 2023-03-13 | 2023-03-13 | 3.C-2 | 1 | Done | ruby.chang@garmin.com
390 | 1081 | Serv - 10" | Marine | GMLA3 | Complete | 2023-03-13 | 2023-03-13 | 3.D-5 | 1 | No fixture design issue from PR1 | jasoncy.hsu@garmin.com
391 | 1131 | Drive 53 | Automotive | GMLA2 | Complete | 2022-09-26 | 2022-09-27 | 2.C-2 | 1 | Fixture list is as the attachment. Confirmed by DPQE. | wendy.ni@garmin.com
392 | 1131 | Drive 53 | Automotive | GMLA2 | Complete | 2022-09-26 | 2022-09-27 | 2.D-5 | 0 | Attach GPS fixture height needs to be modified. | wendy.ni@garmin.com
393 | 1131 | Drive 53 | Automotive | GMLA3 | Complete | 2022-12-01 | 2022-12-01 | 3.C-2 | 0 | There are no TM0362 for lid assembly fixture、MPM solder printing fixture. | wendy.ni@garmin.com
394 | 1131 | Drive 53 | Automotive | GMLA3 | Complete | 2022-12-01 | 2022-12-01 | 3.D-5 | 0 | Scratches on the front of the device(fixed position/bottom left corner): 50% (5/10) ->Modify LCM attachment fixture chamfer. | wendy.ni@garmin.com
395 | 1192 | Aviation Headset - | Automotive | GMLA1 | Incomplete |  | 2023-11-28
396 | 1192 | Aviation Headset - | Automotive | GMLA2 | Incomplete |  | 2024-11-04 | 2.C-2 | 0
397 | 1192 | Aviation Headset - | Automotive | GMLA2 | Incomplete |  | 2024-11-04 | 2.D-5 | 0
398 | 1192 | Aviation Headset - | Automotive | GMLA3 | Incomplete |  | 2025-02-12 | 3.C-2 | 0
399 | 1192 | Aviation Headset - | Automotive | GMLA3 | Incomplete |  | 2025-02-12 | 3.D-5 | 0
400 | 775 | zumo X | Automotive | GMLA1 | Incomplete |  | 2019-04-25
401 | 775 | zumo X | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
402 | 775 | zumo X | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
403 | 775 | zumo X | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
404 | 775 | zumo X | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
405 | 779 | Approach Z82 | Outdoor | GMLA1 | Incomplete |  | 2019-06-06
406 | 779 | Approach Z82 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
407 | 779 | Approach Z82 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
408 | 779 | Approach Z82 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
409 | 779 | Approach Z82 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
410 | 814 | Varia Radar-Only (RVR315) | Fitness | GMLA1 | Incomplete |  | 2019-03-14
411 | 814 | Varia Radar-Only (RVR315) | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
412 | 814 | Varia Radar-Only (RVR315) | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
413 | 814 | Varia Radar-Only (RVR315) | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
414 | 814 | Varia Radar-Only (RVR315) | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
415 | 824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA2 | Complete | 2021-05-13 | 2021-05-13 | 2.C-2 | 1 | As attached. | audon.peng@garmin.com
416 | 824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA2 | Complete | 2021-05-13 | 2021-05-13 | 2.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
417 | 824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA3 | Complete | 2021-06-23 | 2021-07-05 | 3.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
418 | 824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA3 | Complete | 2021-06-23 | 2021-07-05 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
419 | 979 | vivomove "Lite" | Fitness | GMLA2 | Complete | 2021-05-03 | 2021-05-03 | 2.C-2 | 1 | fixtures for FFP are completed in time | sherry.shih@garmin.com
420 | 979 | vivomove "Lite" | Fitness | GMLA2 | Complete | 2021-05-03 | 2021-05-03 | 2.D-5 | 0 | 1. "-" type screwing machine is under verification 2. Gearbox electrical fixture is under verification (ETA 5/7) | sherry.shih@garmin.com
421 | 979 | vivomove "Lite" | Fitness | GMLA3 | Complete | 2021-09-27 | 2021-09-23 | 3.C-2 | 0 | No PR build SMT fixture list | sherry.shih@garmin.com
422 | 979 | vivomove "Lite" | Fitness | GMLA3 | Complete | 2021-09-27 | 2021-09-23 | 3.D-5 | 0 | No Auto screw machine verification report | ernest.fu@garmin.com
423 | 1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA2 | Complete | 2021-03-18 | 2021-03-18 | 2.C-2 | 1 | All uploaded finished, fixtures are ready for MP. | audon.peng@garmin.com
424 | 1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA2 | Complete | 2021-03-18 | 2021-03-18 | 2.D-5 | 1 | All sharing with CLx, no new request for MP. | audon.peng@garmin.com
425 | 1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA3 | Complete | 2021-06-16 | 2021-06-16 | 3.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
426 | 1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA3 | Complete | 2021-06-16 | 2021-06-16 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
427 | 1048 | Product - GDU77XW | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
428 | 1048 | Product - GDU77XW | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
429 | 1048 | Product - GDU77XW | Aviation | GMLA1 | Complete | 2022-11-08 | 2022-11-15
430 | 1048 | Product - GDU77XW | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
431 | 1048 | Product - GDU77XW | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
432 | 1050 | Product - G3X/G500TXi Hybrid | Aviation | GMLA1 | Incomplete
433 | 1050 | Product - G3X/G500TXi Hybrid | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
434 | 1050 | Product - G3X/G500TXi Hybrid | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
435 | 1050 | Product - G3X/G500TXi Hybrid | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
436 | 1050 | Product - G3X/G500TXi Hybrid | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
437 | 1051 | GPSMAP 9000 - 19" | Marine | GMLA1 | Complete | 2022-05-09 | 2022-05-09
438 | 1051 | GPSMAP 9000 - 19" | Marine | GMLA2 | Complete | 2023-03-16 | 2023-03-16 | 2.C-2 | 0 | (DPQE Confirmed) (1)No new equipment, LCM assistant carrying in DFM is carrier fixture. (2) Fixture V&V NOT implement well as attachment. | evelyn.wang@garmin.com
439 | 1051 | GPSMAP 9000 - 19" | Marine | GMLA2 | Complete | 2023-03-16 | 2023-03-16 | 2.D-5 | 1 | No equipment & fixture design issue | evelyn.wang@garmin.com
440 | 1051 | GPSMAP 9000 - 19" | Marine | GMLA3 | Complete | 2023-07-17 | 2023-07-14 | 3.C-2 | 1 | Was ready for PR build. (DPQE Comment) After reviewing the fixture verification result, there are some fixture didn't have the interference inspection result (see attachment) | jasoncy.hsu@garmin.com
441 | 1051 | GPSMAP 9000 - 19" | Marine | GMLA3 | Complete | 2023-07-17 | 2023-07-14 | 3.D-5 | 1 | No issue related to fixture/equipment | evelyn.wang@garmin.com
442 | 1053 | GPSMAP 9000 - 24" | Marine | GMLA1 | Complete | 2022-03-07 | 2022-03-07
443 | 1054 | GPSMAP 9000 -27" | Marine | GMLA1 | Complete | 2022-05-09 | 2022-05-09
444 | 1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA1 | Incomplete
445 | 1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA2 | Incomplete |  | 2022-02-08 | 2.C-2 | 0
446 | 1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA2 | Incomplete |  | 2022-02-08 | 2.D-5 | 0
447 | 1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA3 | Incomplete |  | 2022-03-15 | 3.C-2 | 0
448 | 1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA3 | Incomplete |  | 2022-03-15 | 3.D-5 | 0
449 | 1183 | DEZL 2024 - OTR725 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.C-2 | 0
450 | 1183 | DEZL 2024 - OTR725 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.D-5 | 0
451 | 1183 | DEZL 2024 - OTR725 | Automotive | GMLA1 | Complete | 2023-09-30 | 2023-10-02
452 | 1183 | DEZL 2024 - OTR725 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.C-2 | 0
453 | 1183 | DEZL 2024 - OTR725 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.D-5 | 0
454 | 990 | Dash Cam Live (LTE) | Automotive | GMLA1 | Complete | 2021-01-18 | 2021-01-18
455 | 990 | Dash Cam Live (LTE) | Automotive | GMLA2 | Complete | 2022-04-26 | 2022-04-26 | 2.C-2 | 1 | Fixture list complete | chris.kuo@garmin.com
456 | 990 | Dash Cam Live (LTE) | Automotive | GMLA2 | Complete | 2022-04-26 | 2022-04-26 | 2.D-5 | 1 | No verification report update. PDO is still reviewing the process of V&V. Bypass the fixture verification result this time. | chris.kuo@garmin.com
457 | 990 | Dash Cam Live (LTE) | Automotive | GMLA3 | Complete | 2022-09-26 | 2022-09-26 | 3.C-2 | 0 | No fixture list update for Assy | chris.kuo@garmin.com
458 | 990 | Dash Cam Live (LTE) | Automotive | GMLA3 | Complete | 2022-09-26 | 2022-09-26 | 3.D-5 | 1 | No critical Equipment/Fixture | chris.kuo@garmin.com
459 | 1024 | Forerunner 255 Basic | Fitness | GMLA1 | Incomplete |  | 2021-04-19
460 | 1024 | Forerunner 255 Basic | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
461 | 1024 | Forerunner 255 Basic | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
462 | 1024 | Forerunner 255 Basic | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
463 | 1024 | Forerunner 255 Basic | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
464 | 1061 | RV/Camper 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.C-2 | 0
465 | 1061 | RV/Camper 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.D-5 | 0
466 | 1061 | RV/Camper 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.C-2 | 0
467 | 1061 | RV/Camper 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.D-5 | 0
468 | 1061 | RV/Camper 2022 - 8" | Automotive | GMLA1 | Incomplete
469 | 1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA1 | Complete | 2022-07-25 | 2022-07-26
470 | 1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA2 | Complete | 2022-10-31 | 2022-10-31 | 2.C-2 | 1 | Confirmed by DPQE | howard.jen@garmin.com
471 | 1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA2 | Complete | 2022-10-31 | 2022-10-31 | 2.D-5 | 1 | (Confirmed by DPQE) | howard.jen@garmin.com
472 | 1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA3 | Complete | 2023-02-22 | 2023-02-23 | 3.C-2 | 0 | 38214,38304,40224,40339,40657 do not have TM0362 | howard.jen@garmin.com
473 | 1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA3 | Complete | 2023-02-22 | 2023-02-23 | 3.D-5 | 1 | confirmed | cooper.wang@garmin.com
474 | 1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA1 | Complete | 2023-04-26 | 2023-04-26
475 | 1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA2 | Complete | 2023-07-27 | 2023-07-27 | 2.C-2 | 1 | (DPQE Confirmed) 1. Fixture: 42023 TM0362 verification is incomplete (6/7, 85.7%) 2. ATE: All pass (5/5, 100%) | jasoncy.hsu@garmin.com
476 | 1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA2 | Complete | 2023-07-27 | 2023-07-27 | 2.D-5 | 1 | No fixture design issue on FFP | jasoncy.hsu@garmin.com
477 | 1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA3 | Complete | 2023-10-05 | 2023-10-16 | 3.C-2 | 1 | (DPQE Confirmed) 8/14: TM0360 and TM0362 are completed | jasoncy.hsu@garmin.com
478 | 1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA3 | Complete | 2023-10-05 | 2023-10-16 | 3.D-5 | 1 | No equipment and fixture design issue | jasoncy.hsu@garmin.com
479 | 806 | OEM GPS Sensor | Marine | GMLA1 | Incomplete
480 | 806 | OEM GPS Sensor | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
481 | 806 | OEM GPS Sensor | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
482 | 806 | OEM GPS Sensor | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
483 | 806 | OEM GPS Sensor | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
484 | 856 | Alpha Dog Collar | Outdoor | GMLA1 | Complete | 2022-01-07 | 2022-01-14
485 | 856 | Alpha Dog Collar | Outdoor | GMLA2 | Complete | 2022-09-27 | 2022-09-29 | 2.C-2 | 1 | All fixtures ready in time | robben.liu@garmin.com
486 | 856 | Alpha Dog Collar | Outdoor | GMLA2 | Complete | 2022-09-27 | 2022-09-29 | 2.D-5 | 1 | No critical equipment/ fixture need update | chris.kuo@garmin.com
487 | 856 | Alpha Dog Collar | Outdoor | GMLA3 | Complete | 2023-02-10 | 2023-02-10 | 3.C-2 | 1 | 1. No new equipment 2. TM0362 has been update | chris.kuo@garmin.com
488 | 856 | Alpha Dog Collar | Outdoor | GMLA3 | Complete | 2023-02-10 | 2023-02-10 | 3.D-5 | 1 | No fixture design issue | chris.kuo@garmin.com
489 | 858 | Approach R10 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-05 | 3.C-2 | 1 | Fixtures met build plan but are likely to be adjusted before preMP because BOM changed | robben.liu@garmin.com
490 | 858 | Approach R10 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-05 | 3.D-5 | 1 | All confirmed. | pattie.lan@garmin.com
491 | 879 | Venu 2 Plus | Fitness | GMLA2 | Complete | 2021-03-17 | 2021-03-17 | 2.C-2 | 1 | confirmed by DPQE | cooper.wang@garmin.com
492 | 879 | Venu 2 Plus | Fitness | GMLA2 | Complete | 2021-03-17 | 2021-03-17 | 2.D-5 | 1 | "5 atm sub-assembly waterproof test", "ST" and "ECG test" verification is on-going, we plan verification them by golden sample. | cooper.wang@garmin.com
493 | 879 | Venu 2 Plus | Fitness | GMLA3 | Complete | 2021-07-30 | 2021-07-29 | 3.C-2 | 1 |  | cooper.wang@garmin.com
494 | 879 | Venu 2 Plus | Fitness | GMLA3 | Complete | 2021-07-30 | 2021-07-29 | 3.D-5 | 1 |  | cooper.wang@garmin.com
495 | 881 | fenix 7 | Outdoor | GMLA2 | Complete | 2021-01-11 | 2021-01-08 | 2.C-2 | 1 | Fixture list complete with specific L/T | nixon.pan@garmin.com
496 | 881 | fenix 7 | Outdoor | GMLA2 | Complete | 2021-01-11 | 2021-01-08 | 2.D-5 | 1 | included in PVP | nixon.pan@garmin.com
497 | 881 | fenix 7 | Outdoor | GMLA3 | Complete | 2021-05-05 | 2021-05-05 | 3.C-2 | 1 | fixtures / equipment ready before PR | nixon.pan@garmin.com
498 | 881 | fenix 7 | Outdoor | GMLA3 | Complete | 2021-05-05 | 2021-05-05 | 3.D-5 | 0 | Cpk of lens rotation angle < 1 | cooper.wang@garmin.com
499 | 882 | fenix 6 Solar (2020) | Outdoor | GMLA1 | Incomplete |  | 2019-08-07
500 | 882 | fenix 6 Solar (2020) | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
501 | 882 | fenix 6 Solar (2020) | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
502 | 882 | fenix 6 Solar (2020) | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
503 | 882 | fenix 6 Solar (2020) | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
504 | 947 | Tread 8" | Automotive | GMLA2 | Incomplete |  | 2021-08-04 | 2.C-2 | 0
505 | 947 | Tread 8" | Automotive | GMLA2 | Incomplete |  | 2021-08-04 | 2.D-5 | 0
506 | 947 | Tread 8" | Automotive | GMLA3 | Incomplete |  | 2021-10-06 | 3.C-2 | 0
507 | 947 | Tread 8" | Automotive | GMLA3 | Incomplete |  | 2021-10-06 | 3.D-5 | 0
508 | 948 | Tread - XL (10") | Automotive | GMLA2 | Complete | 2021-09-07 | 2021-09-07 | 2.C-2 | 1 | (Confirmed by DPQE) Fixture is ready | jasoncy.hsu@garmin.com
509 | 948 | Tread - XL (10") | Automotive | GMLA2 | Complete | 2021-09-07 | 2021-09-07 | 2.D-5 | 1 | (Confirmed by DPQE) | jasoncy.hsu@garmin.com
510 | 948 | Tread - XL (10") | Automotive | GMLA3 | Complete | 2021-11-17 | 2021-11-17 | 3.C-2 | 1 | (DPQE confirmed) Checked | jasoncy.hsu@garmin.com
511 | 948 | Tread - XL (10") | Automotive | GMLA3 | Complete | 2021-11-17 | 2021-11-17 | 3.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
512 | 989 | Xero C1 Chronograph | Outdoor | GMLA1 | Complete | 2022-01-13 | 2022-01-17
513 | 989 | Xero C1 Chronograph | Outdoor | GMLA2 | Complete | 2022-07-21 | 2022-07-25 | 2.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
514 | 989 | Xero C1 Chronograph | Outdoor | GMLA2 | Complete | 2022-07-21 | 2022-07-25 | 2.D-5 | 1 | No critical equipment | chris.kuo@garmin.com
515 | 989 | Xero C1 Chronograph | Outdoor | GMLA3 | Complete | 2023-07-10 | 2023-07-10 | 3.C-2 | 1 | [5/11] Fixture ID: 43069/43071/43073/43074 no fixture verification | chris.kuo@garmin.com
516 | 989 | Xero C1 Chronograph | Outdoor | GMLA3 | Complete | 2023-07-10 | 2023-07-10 | 3.D-5 | 1 | NO issue found | chris.kuo@garmin.com
517 | 1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA1 | Complete | 2021-12-13 | 2021-12-13
518 | 1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.C-2 | 1 | (DPQE Confirmed) Fixture is ready for FFP | jasoncy.hsu@garmin.com
519 | 1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.D-5 | 1 | (DPQE Confirmed) Verification result checked | jasoncy.hsu@garmin.com
520 | 1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.C-2 | 1 | (DPQE Confirmed) Critical fixture (Class A) is only keypad board screwing fixture. The status is ongoing and wait for PDO, so there is no verification result needs to be checked | jasoncy.hsu@garmin.com
521 | 1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.D-5 | 1 | No fixture design issue according to PR issue and production report | jasoncy.hsu@garmin.com
522 | 1019 | Forerunner 255S | Fitness | GMLA1 | Incomplete |  | 2021-02-04
523 | 1019 | Forerunner 255S | Fitness | GMLA2 | Incomplete |  | 2021-11-24 | 2.C-2 | 0
524 | 1019 | Forerunner 255S | Fitness | GMLA2 | Incomplete |  | 2021-11-24 | 2.D-5 | 0
525 | 1019 | Forerunner 255S | Fitness | GMLA3 | Incomplete |  | 2022-03-10 | 3.C-2 | 0
526 | 1019 | Forerunner 255S | Fitness | GMLA3 | Incomplete |  | 2022-03-10 | 3.D-5 | 0
527 | 1101 | zumo XT2 | Automotive | GMLA1 | Complete | 2022-05-25 | 2022-06-02
528 | 1101 | zumo XT2 | Automotive | GMLA2 | Complete | 2022-11-15 | 2022-11-15 | 2.C-2 | 1 | There is no TM0362 of 105-04577-00 router 2.0 fixture. This fixture is for PR and MP. | wendy.ni@garmin.com
529 | 1101 | zumo XT2 | Automotive | GMLA2 | Complete | 2022-11-15 | 2022-11-15 | 2.D-5 | 1 | No fixture design issue. The root cause for VT fail are FPC assembly method and mechanical design. | wendy.ni@garmin.com
530 | 1101 | zumo XT2 | Automotive | GMLA3 | Complete | 2023-01-10 | 2023-01-10 | 3.C-2 | 0 | There is no TM0362 of 105-04577-00 MPM fixture. | wendy.ni@garmin.com
531 | 1101 | zumo XT2 | Automotive | GMLA3 | Complete | 2023-01-10 | 2023-01-10 | 3.D-5 | 1 | There is no fixture-related quality issue. | wendy.ni@garmin.com
532 | 1145 | Forerunner 165 and 165 Music | Fitness | GMLA1 | Complete | 2023-03-22 | 2023-03-23
533 | 1145 | Forerunner 165 and 165 Music | Fitness | GMLA2 | Complete | 2023-09-01 | 2023-09-01 | 2.C-2 | 1 | All Class B fixture before May no need interferamce check A class fixture will be finished before August | howard.jen@garmin.com
534 | 1145 | Forerunner 165 and 165 Music | Fitness | GMLA2 | Complete | 2023-09-01 | 2023-09-01 | 2.D-5 | 1 | No fixture issue is highlighted in PRissue | cooper.wang@garmin.com
535 | 1145 | Forerunner 165 and 165 Music | Fitness | GMLA3 | Incomplete |  | 2023-11-10 | 3.C-2 | 1 | All fixtures V&V are completed in FFP | cooper.wang@garmin.com
536 | 1145 | Forerunner 165 and 165 Music | Fitness | GMLA3 | Incomplete |  | 2023-11-10 | 3.D-5 | 1 | The potential root cause of LCM crack may be fixture, waiting for validation | cooper.wang@garmin.com
537 | 1170 | DEZL 2024 - OTR820/1020 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.C-2 | 0
538 | 1170 | DEZL 2024 - OTR820/1020 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.D-5 | 0
539 | 1170 | DEZL 2024 - OTR820/1020 | Automotive | GMLA1 | Complete | 2023-08-31 | 2023-09-05
540 | 1170 | DEZL 2024 - OTR820/1020 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.C-2 | 0
541 | 1170 | DEZL 2024 - OTR820/1020 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.D-5 | 0
542 | 1171 | DEZL 2024 - OTR620/720 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.C-2 | 0
543 | 1171 | DEZL 2024 - OTR620/720 | Automotive | GMLA3 | Incomplete |  | 2024-05-01 | 3.D-5 | 0
544 | 1171 | DEZL 2024 - OTR620/720 | Automotive | GMLA1 | Complete | 2023-09-03 | 2023-09-08
545 | 1171 | DEZL 2024 - OTR620/720 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.C-2 | 0
546 | 1171 | DEZL 2024 - OTR620/720 | Automotive | GMLA2 | Incomplete |  | 2024-02-14 | 2.D-5 | 0
547 | 1172 | fenix 8 43mm | Outdoor | GMLA1 | Incomplete |  | 2023-11-10
548 | 1172 | fenix 8 43mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-02 | 2.C-2 | 0
549 | 1172 | fenix 8 43mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-02 | 2.D-5 | 0
550 | 1172 | fenix 8 43mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-07 | 3.C-2 | 0
551 | 1172 | fenix 8 43mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-07 | 3.D-5 | 0
552 | 1189 | Tread 6" plus optional handlebar controller | Automotive | GMLA1 | Incomplete |  | 2023-09-28
553 | 1189 | Tread 6" plus optional handlebar controller | Automotive | GMLA2 | Incomplete |  | 2024-05-08
554 | 1189 | Tread 6" plus optional handlebar controller | Automotive | GMLA3 | Incomplete |  | 2024-07-17
555 | 793 | Occupancy Sensor | Fitness | GMLA1 | Incomplete
556 | 793 | Occupancy Sensor | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
557 | 793 | Occupancy Sensor | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
558 | 793 | Occupancy Sensor | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
559 | 793 | Occupancy Sensor | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
560 | 815 | BMW MGU22/IDC | OEM Auto | GMLA2 | Complete | 2021-01-27 | 2020-12-30 | 2.C-2 | 1 | Keep track on the list for D sample. | jamesjj.huang@garmin.com
561 | 815 | BMW MGU22/IDC | OEM Auto | GMLA2 | Complete | 2021-01-27 | 2020-12-30 | 2.D-5 | 1 | Will according to D sample PFMEA & CP, re-evaluated again | jamesjj.huang@garmin.com
562 | 815 | BMW MGU22/IDC | OEM Auto | GMLA3 | Complete | 2022-08-05 | 2022-08-05 | 3.C-2 | 1 | Machine/Fixtures were ready for D sample build. | sandy.lee@garmin.com
563 | 815 | BMW MGU22/IDC | OEM Auto | GMLA3 | Complete | 2022-08-05 | 2022-08-05 | 3.D-5 | 1 | Done | shawnch.huang@garmin.com
564 | 837 | ECHOMAP 2020 UHD 6" | Marine | GMLA1 | Incomplete |  | 2019-07-01
565 | 837 | ECHOMAP 2020 UHD 6" | Marine | GMLA2 | Incomplete |  | 2019-09-12 | 2.C-2 | 0
566 | 837 | ECHOMAP 2020 UHD 6" | Marine | GMLA2 | Incomplete |  | 2019-09-12 | 2.D-5 | 0
567 | 837 | ECHOMAP 2020 UHD 6" | Marine | GMLA3 | Incomplete |  | 2019-11-08 | 3.C-2 | 0
568 | 837 | ECHOMAP 2020 UHD 6" | Marine | GMLA3 | Incomplete |  | 2019-11-08 | 3.D-5 | 0
569 | 838 | ECHOMAP 2020 UHD 7" | Marine | GMLA1 | Incomplete |  | 2019-06-24
570 | 838 | ECHOMAP 2020 UHD 7" | Marine | GMLA2 | Incomplete |  | 2019-11-07 | 2.C-2 | 0
571 | 838 | ECHOMAP 2020 UHD 7" | Marine | GMLA2 | Incomplete |  | 2019-11-07 | 2.D-5 | 0
572 | 838 | ECHOMAP 2020 UHD 7" | Marine | GMLA3 | Incomplete |  | 2019-12-30 | 3.C-2 | 0
573 | 838 | ECHOMAP 2020 UHD 7" | Marine | GMLA3 | Incomplete |  | 2019-12-30 | 3.D-5 | 0
574 | 941 | Forerunner 55 | Fitness | GMLA2 | Complete | 2021-02-02 | 2021-02-02 | 2.C-2 | 1 | Confirmed by DPQE. | ernest.fu@garmin.com
575 | 941 | Forerunner 55 | Fitness | GMLA2 | Complete | 2021-02-02 | 2021-02-02 | 2.D-5 | 1 | See the comment | alexty.chang@garmin.com
576 | 941 | Forerunner 55 | Fitness | GMLA3 | Complete | 2021-04-12 | 2021-04-13 | 3.C-2 | 1 | Confirmed by DPQE | ernest.fu@garmin.com
577 | 941 | Forerunner 55 | Fitness | GMLA3 | Complete | 2021-04-12 | 2021-04-13 | 3.D-5 | 1 | Confirmed by DPQE | ernest.fu@garmin.com
578 | 1034 | vivosmart 5 (Franklin) | Fitness | GMLA1 | Complete | 2021-05-17 | 2021-05-24
579 | 1034 | vivosmart 5 (Franklin) | Fitness | GMLA2 | Complete | 2021-10-18 | 2021-10-20 | 2.C-2 | 1 | they are ready. | daniel.tsai@garmin.com
580 | 1034 | vivosmart 5 (Franklin) | Fitness | GMLA2 | Complete | 2021-10-18 | 2021-10-20 | 2.D-5 | 0 | Confirmed by DPQE | ernest.fu@garmin.com
581 | 1034 | vivosmart 5 (Franklin) | Fitness | GMLA3 | Complete | 2021-12-27 | 2021-12-27 | 3.C-2 | 1 | Fixture met PR schedule | nixon.pan@garmin.com
582 | 1034 | vivosmart 5 (Franklin) | Fitness | GMLA3 | Complete | 2021-12-27 | 2021-12-27 | 3.D-5 | 0 | Sam will provide the modified fixtures for verification. If it pass, he will duplicate the rest fixtures. | daniel.tsai@garmin.com
583 | 1040 | D2 Echo (EPIX) | Outdoor | GMLA1 | Incomplete
584 | 1040 | D2 Echo (EPIX) | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
585 | 1040 | D2 Echo (EPIX) | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
586 | 1040 | D2 Echo (EPIX) | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
587 | 1040 | D2 Echo (EPIX) | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
588 | 1047 | Enduro 3 Sport (Pando) | Outdoor | GMLA1 | Incomplete |  | 2022-09-02
589 | 1047 | Enduro 3 Sport (Pando) | Outdoor | GMLA2 | Incomplete |  | 2024-02-12 | 2.C-2 | 0
590 | 1047 | Enduro 3 Sport (Pando) | Outdoor | GMLA2 | Incomplete |  | 2024-02-12 | 2.D-5 | 0
591 | 1047 | Enduro 3 Sport (Pando) | Outdoor | GMLA3 | Incomplete |  | 2024-05-08 | 3.C-2 | 0
592 | 1047 | Enduro 3 Sport (Pando) | Outdoor | GMLA3 | Incomplete |  | 2024-05-08 | 3.D-5 | 0
593 | 1062 | RV/Camper 2022-10" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.C-2 | 0
594 | 1062 | RV/Camper 2022-10" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.D-5 | 0
595 | 1062 | RV/Camper 2022-10" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.C-2 | 0
596 | 1062 | RV/Camper 2022-10" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.D-5 | 0
597 | 1062 | RV/Camper 2022-10" | Automotive | GMLA1 | Incomplete
598 | 1070 | Tacx Vortex 2M | Fitness | GMLA1 | Incomplete
599 | 1070 | Tacx Vortex 2M | Fitness | GMLA2 | Incomplete |  | 2021-12-06 | 2.C-2 | 0
600 | 1070 | Tacx Vortex 2M | Fitness | GMLA2 | Incomplete |  | 2021-12-06 | 2.D-5 | 0
601 | 1070 | Tacx Vortex 2M | Fitness | GMLA3 | Incomplete |  | 2022-02-17 | 3.C-2 | 0
602 | 1070 | Tacx Vortex 2M | Fitness | GMLA3 | Incomplete |  | 2022-02-17 | 3.D-5 | 0
603 | 1085 | quatix 7 | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 2.C-2 | 0
604 | 1085 | quatix 7 | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 2.D-5 | 0
605 | 1085 | quatix 7 | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 3.C-2 | 0
606 | 1085 | quatix 7 | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 3.D-5 | 0
607 | 1085 | quatix 7 | Marine | GMLA1 | Incomplete
608 | 1091 | GPSMAP H1/H1i | Outdoor | GMLA2 | Incomplete |  | 2024-06-11 | 2.C-2 | 0
609 | 1091 | GPSMAP H1/H1i | Outdoor | GMLA2 | Incomplete |  | 2024-06-11 | 2.D-5 | 0
610 | 1091 | GPSMAP H1/H1i | Outdoor | GMLA3 | Incomplete |  | 2024-09-04 | 3.C-2 | 0
611 | 1091 | GPSMAP H1/H1i | Outdoor | GMLA3 | Incomplete |  | 2024-09-04 | 3.D-5 | 0
612 | 1091 | GPSMAP H1/H1i | Outdoor | GMLA1 | Incomplete |  | 2023-12-13
613 | 1107 | Forerunner 265 | Fitness | GMLA1 | Complete | 2022-06-27 | 2022-07-06
614 | 1107 | Forerunner 265 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 2.C-2 | 1 | ready before FFP | nixon.pan@garmin.com
615 | 1107 | Forerunner 265 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 2.D-5 | 1 | No category A fixture by 7/20 | amyry.chen@garmin.com
616 | 1107 | Forerunner 265 | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-21 | 3.C-2 | 0 | No verification result update: 1. Router fuxtre 2. Paste tape fixture | amyry.chen@garmin.com
617 | 1107 | Forerunner 265 | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-21 | 3.D-5 | 1 | No equipment &fixture issue on PR build. | evelyn.wang@garmin.com
618 | 1135 | Rally 110/210 Family | Fitness | GMLA3 | Incomplete |  | 2024-11-15 | 3.C-2 | 0
619 | 1135 | Rally 110/210 Family | Fitness | GMLA3 | Incomplete |  | 2024-11-15 | 3.D-5 | 0
620 | 1135 | Rally 110/210 Family | Fitness | GMLA1 | Complete | 2023-09-01 | 2023-09-01
621 | 1135 | Rally 110/210 Family | Fitness | GMLA2 | Incomplete |  | 2024-07-26 | 2.C-2 | 0
622 | 1135 | Rally 110/210 Family | Fitness | GMLA2 | Incomplete |  | 2024-07-26 | 2.D-5 | 0
623 | 1140 | BMW Motorrad Nav VI Production Support | OEM Auto | GMLA1 | Incomplete
624 | 1140 | BMW Motorrad Nav VI Production Support | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
625 | 1140 | BMW Motorrad Nav VI Production Support | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
626 | 1140 | BMW Motorrad Nav VI Production Support | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
627 | 1140 | BMW Motorrad Nav VI Production Support | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
628 | 1148 | Tacx FLUX 3M | Fitness | GMLA1 | Incomplete
629 | 1148 | Tacx FLUX 3M | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
630 | 1148 | Tacx FLUX 3M | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
631 | 1148 | Tacx FLUX 3M | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
632 | 1148 | Tacx FLUX 3M | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
633 | 1163 | Lily 2 Active | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
634 | 1163 | Lily 2 Active | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
635 | 1163 | Lily 2 Active | Fitness | GMLA1 | Complete | 2023-08-24 | 2023-08-30
636 | 1163 | Lily 2 Active | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
637 | 1163 | Lily 2 Active | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
638 | 1167 | Large Format TXi | Aviation | GMLA1 | Incomplete
639 | 1167 | Large Format TXi | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
640 | 1167 | Large Format TXi | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
641 | 1167 | Large Format TXi | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
642 | 1167 | Large Format TXi | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
643 | 1168 | Approach G20 | Outdoor | GMLA1 | Incomplete |  | 2023-06-08
644 | 1168 | Approach G20 | Outdoor | GMLA2 | Incomplete |  | 2024-02-19 | 2.C-2 | 0
645 | 1168 | Approach G20 | Outdoor | GMLA2 | Incomplete |  | 2024-02-19 | 2.D-5 | 0
646 | 1168 | Approach G20 | Outdoor | GMLA3 | Incomplete |  | 2024-05-14 | 3.C-2 | 0
647 | 1168 | Approach G20 | Outdoor | GMLA3 | Incomplete |  | 2024-05-14 | 3.D-5 | 0
648 | 855 | RTL515 - Varia Radar Tail light | Fitness | GMLA1 | Incomplete |  | 2019-11-04
649 | 855 | RTL515 - Varia Radar Tail light | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
650 | 855 | RTL515 - Varia Radar Tail light | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
651 | 855 | RTL515 - Varia Radar Tail light | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
652 | 855 | RTL515 - Varia Radar Tail light | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
653 | 862 | Bounce(Waldo) | Fitness | GMLA2 | Complete | 2021-05-06 | 2021-05-17 | 2.C-2 | 1 | no issue in FFP | franksl.chen@garmin.com
654 | 862 | Bounce(Waldo) | Fitness | GMLA2 | Complete | 2021-05-06 | 2021-05-17 | 2.D-5 | 1 | Critical equipment/ fixture verification result PASS | franksl.chen@garmin.com
655 | 862 | Bounce(Waldo) | Fitness | GMLA3 | Complete | 2021-07-12 | 2021-07-13 | 3.C-2 | 1 | MPM confirmed | franksl.chen@garmin.com
656 | 862 | Bounce(Waldo) | Fitness | GMLA3 | Complete | 2021-07-12 | 2021-07-13 | 3.D-5 | 0 | Need to provide the information of verification report | annie.wang@garmin.com
657 | 905 | Instinct 2 | Outdoor | GMLA2 | Complete | 2021-05-11 | 2021-05-11 | 2.C-2 | 1 | FFP fixtures are ready in time for FFP | robben.liu@garmin.com
658 | 905 | Instinct 2 | Outdoor | GMLA2 | Complete | 2021-05-11 | 2021-05-11 | 2.D-5 | 1 | No critical equipment (confirmed by DPQE) | cooper.wang@garmin.com
659 | 905 | Instinct 2 | Outdoor | GMLA3 | Complete | 2021-07-19 | 2021-07-16 | 3.C-2 | 1 | No schedule delayed by fixtures. | robben.liu@garmin.com
660 | 905 | Instinct 2 | Outdoor | GMLA3 | Complete | 2021-07-19 | 2021-07-16 | 3.D-5 | 1 | No critical equipment (confirmed by DPQE) | cooper.wang@garmin.com
661 | 929 | FUSION - RA60 | Marine | GMLA2 | Complete | 2021-02-06 | 2021-02-09 | 2.C-2 | 1 | DPQE confirmed | jasoncy.hsu@garmin.com
662 | 929 | FUSION - RA60 | Marine | GMLA2 | Complete | 2021-02-06 | 2021-02-09 | 2.D-5 | 1 | DPQE confirmed | jasoncy.hsu@garmin.com
663 | 929 | FUSION - RA60 | Marine | GMLA3 | Complete | 2021-04-07 | 2021-04-07 | 3.C-2 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
664 | 929 | FUSION - RA60 | Marine | GMLA3 | Complete | 2021-04-07 | 2021-04-07 | 3.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
665 | 946 | Overlander 10" | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
666 | 946 | Overlander 10" | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
667 | 946 | Overlander 10" | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
668 | 946 | Overlander 10" | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
669 | 985 | IXWW22 | OEM Auto | GMLA2 | Complete | 2021-12-20 | 2021-12-20 | 2.C-2 | 1 | only 1 set color test rank arrive to C5, needs NPI PE to check rest rank arrive date. | nick.yen@garmin.com
670 | 985 | IXWW22 | OEM Auto | GMLA2 | Complete | 2021-12-20 | 2021-12-20 | 2.D-5 | 1 | Known | jeff.lin@garmin.com
671 | 985 | IXWW22 | OEM Auto | GMLA3 | Complete | 2022-03-18 | 2022-03-17 | 3.C-2 | 1 | Fixtures are ready in C5. | nick.yen@garmin.com
672 | 985 | IXWW22 | OEM Auto | GMLA3 | Complete | 2022-03-18 | 2022-03-17 | 3.D-5 | 0 | checked. | jeff.lin@garmin.com
673 | 1060 | RV/Camper 2022 - 7" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.C-2 | 0
674 | 1060 | RV/Camper 2022 - 7" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 2.D-5 | 0
675 | 1060 | RV/Camper 2022 - 7" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.C-2 | 0
676 | 1060 | RV/Camper 2022 - 7" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 3.D-5 | 0
677 | 1060 | RV/Camper 2022 - 7" | Automotive | GMLA1 | Incomplete
678 | 1100 | Tacx NEO Bike Plus | Fitness | GMLA1 | Incomplete |  | 2020-04-27
679 | 1100 | Tacx NEO Bike Plus | Fitness | GMLA2 | Incomplete |  | 2022-03-03 | 2.C-2 | 0
680 | 1100 | Tacx NEO Bike Plus | Fitness | GMLA2 | Incomplete |  | 2022-03-03 | 2.D-5 | 0
681 | 1100 | Tacx NEO Bike Plus | Fitness | GMLA3 | Incomplete |  | 2022-05-06 | 3.C-2 | 0
682 | 1100 | Tacx NEO Bike Plus | Fitness | GMLA3 | Incomplete |  | 2022-05-06 | 3.D-5 | 0
683 | 1139 | Alpha LTE | Outdoor | GMLA1 | Complete | 2023-02-24 | 2023-02-13
684 | 1139 | Alpha LTE | Outdoor | GMLA2 | Complete | 2023-06-01 | 2023-06-02 | 2.C-2 | 1 | Fixture list / ATE fixture list were checked and all passed | ernest.fu@garmin.com
685 | 1139 | Alpha LTE | Outdoor | GMLA2 | Complete | 2023-06-01 | 2023-06-02 | 2.D-5 | 0 | Screw LTE fixture need to be modified since there is potential risk to make LTE broken | ernest.fu@garmin.com
686 | 1139 | Alpha LTE | Outdoor | GMLA3 | Complete | 2023-09-19 | 2023-09-19 | 3.C-2 | 1 | Equipment & fixture preparation and verification results are PASS | ernest.fu@garmin.com
687 | 1139 | Alpha LTE | Outdoor | GMLA3 | Complete | 2023-09-19 | 2023-09-19 | 3.D-5 | 1 | No equipment & fixture design issued on PR | ernest.fu@garmin.com
688 | 1144 | TWIN23 | OEM Auto | GMLA1 | Incomplete
689 | 1144 | TWIN23 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
690 | 1144 | TWIN23 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
691 | 1144 | TWIN23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
692 | 1144 | TWIN23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
693 | 1150 | Motorcycle Radar 2023 | Automotive | GMLA1 | Complete | 2023-05-23 | 2023-05-25
694 | 1150 | Motorcycle Radar 2023 | Automotive | GMLA3 | Incomplete |  | 2024-03-27 | 3.C-2 | 0
695 | 1150 | Motorcycle Radar 2023 | Automotive | GMLA3 | Incomplete |  | 2024-03-27 | 3.D-5 | 0
696 | 1150 | Motorcycle Radar 2023 | Automotive | GMLA2 | Incomplete |  | 2024-02-15 | 2.C-2 | 0
697 | 1150 | Motorcycle Radar 2023 | Automotive | GMLA2 | Incomplete |  | 2024-02-15 | 2.D-5 | 0
698 | 1186 | HRM6-600 (Adv.) | Fitness | GMLA1 | Incomplete
699 | 1186 | HRM6-600 (Adv.) | Fitness | GMLA2 | Incomplete |  | 2024-08-14 | 2.C-2 | 0
700 | 1186 | HRM6-600 (Adv.) | Fitness | GMLA2 | Incomplete |  | 2024-08-14 | 2.D-5 | 0
701 | 1186 | HRM6-600 (Adv.) | Fitness | GMLA3 | Incomplete |  | 2024-11-08 | 3.C-2 | 0
702 | 1186 | HRM6-600 (Adv.) | Fitness | GMLA3 | Incomplete |  | 2024-11-08 | 3.D-5 | 0
703 | 1187 | HRM6-200 (Basic) | Fitness | GMLA1 | Incomplete
704 | 1187 | HRM6-200 (Basic) | Fitness | GMLA2 | Incomplete |  | 2024-11-05 | 2.C-2 | 0
705 | 1187 | HRM6-200 (Basic) | Fitness | GMLA2 | Incomplete |  | 2024-11-05 | 2.D-5 | 0
706 | 1187 | HRM6-200 (Basic) | Fitness | GMLA3 | Incomplete |  | 2025-02-04 | 3.C-2 | 0
707 | 1187 | HRM6-200 (Basic) | Fitness | GMLA3 | Incomplete |  | 2025-02-04 | 3.D-5 | 0
708 | 820 | FUSION - RA210 | Marine | GMLA1 | Incomplete |  | 2019-01-18
709 | 820 | FUSION - RA210 | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
710 | 820 | FUSION - RA210 | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
711 | 820 | FUSION - RA210 | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
712 | 820 | FUSION - RA210 | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
713 | 821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA2 | Complete | 2021-02-08 | 2021-02-18 | 2.C-2 | 1 | Confirmed by DPQE | chris.kuo@garmin.com
714 | 821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA2 | Complete | 2021-02-08 | 2021-02-18 | 2.D-5 | 1 | Confirmed by DPQE | chris.kuo@garmin.com
715 | 821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA3 | Complete | 2021-04-26 | 2021-04-23 | 3.C-2 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
716 | 821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA3 | Complete | 2021-04-26 | 2021-04-23 | 3.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
717 | 823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA1 | Incomplete |  | 2019-07-24
718 | 823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
719 | 823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
720 | 823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
721 | 823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
722 | 866 | Descent Mk2s | Outdoor | GMLA3 | Complete | 2020-12-29 | 2020-12-22 | 3.C-2 |  | need to follow the battery wire AOI equipment/fixture readiness | abner.tsai@garmin.com
723 | 866 | Descent Mk2s | Outdoor | GMLA3 | Complete | 2020-12-29 | 2020-12-22 | 3.D-5 | 1 | DPQE confirmed. | abner.tsai@garmin.com
724 | 868 | Venu 2S | Fitness | GMLA3 | Complete | 2021-01-27 | 2021-01-27 | 3.C-2 | 1 | Pls refer the to attached. | alexty.chang@garmin.com
725 | 868 | Venu 2S | Fitness | GMLA3 | Complete | 2021-01-27 | 2021-01-27 | 3.D-5 | 1 | confirmed | ming.shen@garmin.com
726 | 870 | Forerunner 945 LTE | Fitness | GMLA3 | Complete | 2020-12-28 | 2020-12-28 | 3.C-2 | 1 | DPQE confrimed. | abner.tsai@garmin.com
727 | 870 | Forerunner 945 LTE | Fitness | GMLA3 | Complete | 2020-12-28 | 2020-12-28 | 3.D-5 | 1 | DPQE confirmed. | abner.tsai@garmin.com
728 | 895 | BMW MGU22-RSE | OEM Auto | GMLA2 | Complete | 2021-02-06 | 2020-12-30 | 2.C-2 | 1 | All equipment /fixture is ready for C sample. | sandy.lee@garmin.com
729 | 895 | BMW MGU22-RSE | OEM Auto | GMLA2 | Complete | 2021-02-06 | 2020-12-30 | 2.D-5 | 1 | Will reevaluate again according to D sample PFMEA & CP | valentina.tsai@garmin.com
730 | 895 | BMW MGU22-RSE | OEM Auto | GMLA3 | Complete | 2021-10-19 | 2021-10-06 | 3.C-2 | 1 | 1. Cleaning booth and robot are under development ETA 10/B | sandy.lee@garmin.com
731 | 895 | BMW MGU22-RSE | OEM Auto | GMLA3 | Complete | 2021-10-19 | 2021-10-06 | 3.D-5 | 1 | OK | jack.yang@garmin.com
732 | 962 | BlueNet Switch | Marine | GMLA1 | Complete | 2021-09-23 | 2021-09-30
733 | 962 | BlueNet Switch | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 2.C-2 | 1 | Only the bending fixture needs to be slightly modified, and the modification is completed by PDO. | chloe.lin2@garmin.com
734 | 962 | BlueNet Switch | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 2.D-5 | 0 | 12.30% scratch caused by the fixture. NPI adds rubber to protect DUT. Texture parts will be verified at the PR phase. (FFP parts without texture) | wendy.ni@garmin.com
735 | 962 | BlueNet Switch | Marine | GMLA3 | Complete | 2023-04-06 | 2023-04-06 | 3.C-2 | 0 | Class A TM00362 not released: 38593, 39404, 40152, 41010. For the Nut install fixture modified, it will be verified after getting the fixture. (4/12) | wendy.ni@garmin.com
736 | 962 | BlueNet Switch | Marine | GMLA3 | Complete | 2023-04-06 | 2023-04-06 | 3.D-5 | 1 | 1. Screw nut fixture scratch has been solved. (refer switch PRissue ID 8894) 2. Nut install fixture will be modified for appearance alignment issue. There is no quality concern, thus define as complete. It is low risk and will be completed on 4/12. | wendy.ni@garmin.com
737 | 963 | Malibu Display | Marine | GMLA3 | Complete | 2021-02-03 | 2021-02-03 | 3.C-2 | 1 | DPQE confirmed | jasoncy.hsu@garmin.com
738 | 963 | Malibu Display | Marine | GMLA3 | Complete | 2021-02-03 | 2021-02-03 | 3.D-5 | 1 | DPQE confirmed. No critical equipment | jasoncy.hsu@garmin.com
739 | 1006 | Descent S1 Buoy | Outdoor | GMLA1 | Complete | 2021-03-04 | 2021-03-10
740 | 1006 | Descent S1 Buoy | Outdoor | GMLA2 | Complete | 2023-05-17 | 2023-05-23 | 2.C-2 | 0 | Do not have relevant verification result | aalto.lo@garmin.com
741 | 1006 | Descent S1 Buoy | Outdoor | GMLA2 | Complete | 2023-05-17 | 2023-05-23 | 2.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
742 | 1006 | Descent S1 Buoy | Outdoor | GMLA3 | Incomplete |  | 2023-10-11 | 3.C-2 | 0
743 | 1006 | Descent S1 Buoy | Outdoor | GMLA3 | Incomplete |  | 2023-10-11 | 3.D-5 | 0
744 | 1046 | GHP Reactor Kicker_Sunray redesign | Marine | GMLA1 | Incomplete
745 | 1046 | GHP Reactor Kicker_Sunray redesign | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
746 | 1046 | GHP Reactor Kicker_Sunray redesign | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
747 | 1046 | GHP Reactor Kicker_Sunray redesign | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
748 | 1046 | GHP Reactor Kicker_Sunray redesign | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
749 | 1068 | GSD28 | Marine | GMLA1 | Complete | 2022-07-28 | 2022-08-01
750 | 1068 | GSD28 | Marine | GMLA2 | Complete | 2023-06-12 | 2023-06-12 | 2.C-2 | 0 | (DPQE Confirmed) 1. Fixture (1) 38756 MPM printing: No interference inspection result (2) 38762 MPS: No interference inspection result 2. ATE (1) 9587 v05: No interference inspection result and TM0362 3. No new equipment according to DFM report | jasoncy.hsu@garmin.com
751 | 1068 | GSD28 | Marine | GMLA2 | Complete | 2023-06-12 | 2023-06-12 | 2.D-5 | 1 | No fixture design issue from PR issue records | jasoncy.hsu@garmin.com
752 | 1068 | GSD28 | Marine | GMLA3 | Complete | 2023-09-11 | 2023-09-11 | 3.C-2 | 1 | (DPQE Confirmed) PDO has provided the interference result and TM0362 for fixture and ATE | jasoncy.hsu@garmin.com
753 | 1068 | GSD28 | Marine | GMLA3 | Complete | 2023-09-11 | 2023-09-11 | 3.D-5 | 1 | No fixture design related issue in PR | jasoncy.hsu@garmin.com
754 | 1072 | Enduro 2022 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
755 | 1072 | Enduro 2022 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
756 | 1072 | Enduro 2022 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
757 | 1072 | Enduro 2022 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
758 | 1084 | IMWW23 | OEM Auto | GMLA1 | Complete | 2021-12-14 | 2021-12-14
759 | 1084 | IMWW23 | OEM Auto | GMLA2 | Complete | 2022-11-09 | 2022-11-09 | 2.C-2 | 1 | Fixture ETA meet schedule. | jason.fan@garmin.com
760 | 1084 | IMWW23 | OEM Auto | GMLA2 | Complete | 2022-11-09 | 2022-11-09 | 2.D-5 | 1 | Checked | jeff.lin@garmin.com
761 | 1084 | IMWW23 | OEM Auto | GMLA3 | Complete | 2023-07-06 | 2023-07-06 | 3.C-2 | 1 | TEST : FT1 4ports & FT2 4ports completed. | jim.shen@garmin.com
762 | 1084 | IMWW23 | OEM Auto | GMLA3 | Complete | 2023-07-06 | 2023-07-06 | 3.D-5 | 1 | FT fixture modified in 7/4, will check in PR2 | simon.ko@garmin.com
763 | 1086 | quatix 7x Solar | Marine | GMLA1 | Incomplete
764 | 1086 | quatix 7x Solar | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
765 | 1086 | quatix 7x Solar | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
766 | 1086 | quatix 7x Solar | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
767 | 1086 | quatix 7x Solar | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
768 | 1129 | GT12M & GT15M Thru-Hull Flush | Marine | GMLA1 | Complete | 2022-11-21 | 2022-11-21
769 | 1129 | GT12M & GT15M Thru-Hull Flush | Marine | GMLA2 | Complete | 2023-04-13 | 2023-04-13 | 2.C-2 | 0 | (1) No new equipment (2) Fixture V&V not implement well as attachment. | evelyn.wang@garmin.com
770 | 1129 | GT12M & GT15M Thru-Hull Flush | Marine | GMLA2 | Complete | 2023-04-13 | 2023-04-13 | 2.D-5 | 1 | No equipment & fixture design issued on FFP build | evelyn.wang@garmin.com
771 | 1129 | GT12M & GT15M Thru-Hull Flush | Marine | GMLA3 | Complete | 2023-06-28 | 2023-06-28 | 3.C-2 | 1 | (1) No new equipment (2)2023-40922 熱敏電阻焊接holder 干涉檢查未完成 --> 5/18已補上 | evelyn.wang@garmin.com
772 | 1129 | GT12M & GT15M Thru-Hull Flush | Marine | GMLA3 | Complete | 2023-06-28 | 2023-06-28 | 3.D-5 | 1 | No fixture design issue | evelyn.wang@garmin.com
773 | 1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
774 | 1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
775 | 1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
776 | 1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
777 | 1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA1 | Incomplete
778 | 794 | FUSION - ERX400 | Marine | GMLA1 | Incomplete |  | 2019-02-27
779 | 794 | FUSION - ERX400 | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
780 | 794 | FUSION - ERX400 | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
781 | 794 | FUSION - ERX400 | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
782 | 794 | FUSION - ERX400 | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
783 | 893 | PGWW20 | OEM Auto | GMLA3 | Complete | 2021-09-07 | 2021-10-12 | 3.C-2 | 1 | LCM alignment assembly fixture will ready in June/M. | nick.yen@garmin.com
784 | 893 | PGWW20 | OEM Auto | GMLA3 | Complete | 2021-09-07 | 2021-10-12 | 3.D-5 | 1 | check completed before audit activity. | colby.ren@garmin.com
785 | 944 | Pet Tracker | Outdoor | GMLA1 | Incomplete
786 | 944 | Pet Tracker | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
787 | 944 | Pet Tracker | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
788 | 944 | Pet Tracker | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
789 | 944 | Pet Tracker | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
790 | 954 | Dash Cam Mini 2 | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-21 | 3.C-2 | 1 | All fixtures were verified in PR | lori.tsai@garmin.com
791 | 954 | Dash Cam Mini 2 | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-21 | 3.D-5 | 1 | ASSY: all the fixture have been introduced in FFP and PR, all work and have no fixture related appearance issue. | daniel.lee@garmin.com
792 | 976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA2 | Complete | 2021-04-13 | 2021-04-13 | 2.C-2 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
793 | 976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA2 | Complete | 2021-04-13 | 2021-04-13 | 2.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
794 | 976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA3 | Complete | 2021-06-01 | 2021-06-04 | 3.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
795 | 976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA3 | Complete | 2021-06-01 | 2021-06-04 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
796 | 1014 | GMR Fantom 18x/24x | Marine | GMLA2 | Complete | 2021-06-22 | 2021-06-22 | 2.C-2 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
797 | 1014 | GMR Fantom 18x/24x | Marine | GMLA2 | Complete | 2021-06-22 | 2021-06-22 | 2.D-5 | 1 | Confirmed by DPQE. | jasoncy.hsu@garmin.com
798 | 1014 | GMR Fantom 18x/24x | Marine | GMLA3 | Complete | 2021-09-14 | 2021-09-15 | 3.C-2 | 1 | (Confirmed by DPQE) No delay for PR schedule | jasoncy.hsu@garmin.com
799 | 1014 | GMR Fantom 18x/24x | Marine | GMLA3 | Complete | 2021-09-14 | 2021-09-15 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
800 | 1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA1 | Complete | 2021-11-17 | 2021-11-29
801 | 1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 2.C-2 | 1 | ASSY fixtures are the same as dezl 800. Confirmed by DPQE. | wendy.ni@garmin.com
802 | 1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 2.D-5 | 1 | ATE fixture will be adjusted and do the cycle test before PR. | wendy.ni@garmin.com
803 | 1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 3.C-2 | 1 | Need to track ATE2.0 verification plan. | stephanie.yang@garmin.com
804 | 1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 3.D-5 | 1 | Done | frankie.lee@garmin.com
805 | 1067 | LXTW19 - SCR | OEM Auto | GMLA1 | Incomplete
806 | 1067 | LXTW19 - SCR | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
807 | 1067 | LXTW19 - SCR | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
808 | 1067 | LXTW19 - SCR | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
809 | 1067 | LXTW19 - SCR | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
810 | 1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA1 | Complete | 2022-07-04 | 2022-07-11
811 | 1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA2 | Complete | 2022-11-03 | 2022-11-09 | 2.C-2 | 1 | Review pass. All fixture accept by NPI | chris.kuo@garmin.com
812 | 1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA2 | Complete | 2022-11-03 | 2022-11-09 | 2.D-5 | 1 | No fixture design issued on FFP | chris.kuo@garmin.com
813 | 1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA3 | Complete | 2023-01-31 | 2023-02-01 | 3.C-2 | 1 | Fixture had been verified | chris.kuo@garmin.com
814 | 1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA3 | Complete | 2023-01-31 | 2023-02-01 | 3.D-5 | 1 | No fixture issue in PR. | chris.kuo@garmin.com
815 | 1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA1 | Complete | 2022-04-28 | 2022-04-28
816 | 1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA2 | Complete | 2022-12-09 | 2022-12-16 | 2.C-2 | 1 | (DPQE Confirmed) MB screwing fixture and motor board screwing fixture: TM0362 doc are completed | jasoncy.hsu@garmin.com
817 | 1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA2 | Complete | 2022-12-09 | 2022-12-16 | 2.D-5 | 1 | No fixture design issue | jasoncy.hsu@garmin.com
818 | 1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA3 | Complete | 2023-04-24 | 2023-05-10 | 3.C-2 | 1 | (DPQE Confirmed) After reviewing the fixture list, there is no Class A fixture for GMR OA | jasoncy.hsu@garmin.com
819 | 1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA3 | Complete | 2023-04-24 | 2023-05-10 | 3.D-5 | 1 | No quality issue from fixture design | jasoncy.hsu@garmin.com
820 | 1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA1 | Incomplete |  | 2024-08-19
821 | 1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA2 | Incomplete |  | 2024-04-10 | 2.C-2 | 0
822 | 1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA2 | Incomplete |  | 2024-04-10 | 2.D-5 | 0
823 | 1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA3 | Incomplete |  | 2024-08-02 | 3.C-2 | 0
824 | 1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA3 | Incomplete |  | 2024-08-02 | 3.D-5 | 0
825 | 1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA1 | Incomplete
826 | 1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
827 | 1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
828 | 1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
829 | 1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
830 | 1160 | HRM-Fit | Fitness | GMLA1 | Complete | 2023-04-14 | 2023-04-25
831 | 1160 | HRM-Fit | Fitness | GMLA2 | Complete | 2023-06-01 | 2023-06-05 | 2.C-2 | 1 | 1. No New equipment 2. All fixture release TM0362 | chris.kuo@garmin.com
832 | 1160 | HRM-Fit | Fitness | GMLA2 | Complete | 2023-06-01 | 2023-06-05 | 2.D-5 | 0 | 2 fixture issue on FFP 1. Pin assembly fixture (ID:42638) 2. VT2 fixture (ID:42632) | chris.kuo@garmin.com
833 | 1160 | HRM-Fit | Fitness | GMLA3 | Complete | 2023-07-28 | 2023-08-01 | 3.C-2 | 1 | [6/28 review] 1.Check all the fixture has bee verified. 2. No new equipment for HRM FIT | chris.kuo@garmin.com
834 | 1160 | HRM-Fit | Fitness | GMLA3 | Complete | 2023-07-28 | 2023-08-01 | 3.D-5 | 1 | Same fixture issue as FFP | chris.kuo@garmin.com
835 | 1197 | Instinct SE (40 mm) | Outdoor | GMLA1 | Incomplete
836 | 1197 | Instinct SE (40 mm) | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
837 | 1197 | Instinct SE (40 mm) | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
838 | 1197 | Instinct SE (40 mm) | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
839 | 1197 | Instinct SE (40 mm) | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
840 | 844 | dezl OTR/LGV 700 | Automotive | GMLA1 | Incomplete |  | 2019-05-09
841 | 844 | dezl OTR/LGV 700 | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
842 | 844 | dezl OTR/LGV 700 | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
843 | 844 | dezl OTR/LGV 700 | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
844 | 844 | dezl OTR/LGV 700 | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
845 | 845 | dezl OTR/LGV 800 | Automotive | GMLA1 | Incomplete |  | 2019-05-09
846 | 845 | dezl OTR/LGV 800 | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
847 | 845 | dezl OTR/LGV 800 | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
848 | 845 | dezl OTR/LGV 800 | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
849 | 845 | dezl OTR/LGV 800 | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
850 | 1008 | Venu H(Asia ISO13485 Certification) | Fitness | GMLA3 | Complete | 2021-01-29 | 2021-04-08 | 3.C-2 | 1 | Pls refer the to attached. | ernest.fu@garmin.com
851 | 1008 | Venu H(Asia ISO13485 Certification) | Fitness | GMLA3 | Complete | 2021-01-29 | 2021-04-08 | 3.D-5 | 1 | Np Critical equipment. | alexty.chang@garmin.com
852 | 1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA2 | Incomplete |  | 2021-11-29 | 2.C-2 | 0
853 | 1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA2 | Incomplete |  | 2021-11-29 | 2.D-5 | 0
854 | 1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA3 | Incomplete |  | 2022-02-23 | 3.C-2 | 0
855 | 1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA3 | Incomplete |  | 2022-02-23 | 3.D-5 | 0
856 | 1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA1 | Incomplete
857 | 1049 | Product - GDU147XW | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
858 | 1049 | Product - GDU147XW | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
859 | 1049 | Product - GDU147XW | Aviation | GMLA1 | Complete | 2023-03-03 | 2023-03-03
860 | 1049 | Product - GDU147XW | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
861 | 1049 | Product - GDU147XW | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
862 | 1052 | GPSMAP 9000 - 22" | Marine | GMLA1 | Complete | 2021-12-09 | 2021-12-07
863 | 1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA1 | Complete | 2021-12-13 | 2021-12-13
864 | 1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.C-2 | 1 | (DPQE Confirmed) Fixture is ready for FFP | jasoncy.hsu@garmin.com
865 | 1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 2.D-5 | 1 | (DPQE Confirmed) Verification result checked | jasoncy.hsu@garmin.com
866 | 1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.C-2 | 1 | (DPQE Confirmed) Critical fixture (Class A) is only keypad board screwing fixture. The status is ongoing and wait for PDO, so there is no verification result needs to be checked | jasoncy.hsu@garmin.com
867 | 1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 3.D-5 | 1 | No fixture design issue according to PR issue and production report | jasoncy.hsu@garmin.com
868 | 1066 | LED Control Module | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
869 | 1066 | LED Control Module | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
870 | 1066 | LED Control Module | Marine | GMLA1 | Complete | 2023-05-11 | 2023-05-15
871 | 1066 | LED Control Module | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
872 | 1066 | LED Control Module | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
873 | 1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA1 | Incomplete
874 | 1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
875 | 1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
876 | 1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
877 | 1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
878 | 1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA1 | Incomplete
879 | 1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
880 | 1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
881 | 1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
882 | 1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
883 | 1108 | LIIN22 | OEM Auto | GMLA1 | Incomplete
884 | 1108 | LIIN22 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
885 | 1108 | LIIN22 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
886 | 1108 | LIIN22 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
887 | 1108 | LIIN22 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
888 | 1138 | TGWW25 | OEM Auto | GMLA3 | Incomplete |  | 2024-08-21 | 3.C-2 | 0
889 | 1138 | TGWW25 | OEM Auto | GMLA3 | Incomplete |  | 2024-08-21 | 3.D-5 | 0
890 | 1138 | TGWW25 | OEM Auto | GMLA1 | Complete | 2023-07-27 | 2023-07-27
891 | 1138 | TGWW25 | OEM Auto | GMLA2 | Incomplete |  | 2023-12-14 | 2.C-2 | 0
892 | 1138 | TGWW25 | OEM Auto | GMLA2 | Incomplete |  | 2023-12-14 | 2.D-5 | 0
893 | 1190 | Blaze | Fitness | GMLA1 | Incomplete
894 | 1190 | Blaze | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
895 | 1190 | Blaze | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
896 | 1190 | Blaze | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
897 | 1190 | Blaze | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
898 | 1190 | Blaze | Fitness | GMLA1 | Incomplete
899 | 1190 | Blaze | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
900 | 1190 | Blaze | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
901 | 1190 | Blaze | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
902 | 1190 | Blaze | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
903 | 786 | GI 275 | Aviation | GMLA1 | Incomplete
904 | 786 | GI 275 | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
905 | 786 | GI 275 | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
906 | 786 | GI 275 | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
907 | 786 | GI 275 | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
908 | 816 | GPSMAP 7x2 Plus | Marine | GMLA1 | Incomplete |  | 2019-05-09
909 | 816 | GPSMAP 7x2 Plus | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
910 | 816 | GPSMAP 7x2 Plus | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
911 | 816 | GPSMAP 7x2 Plus | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
912 | 816 | GPSMAP 7x2 Plus | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
913 | 912 | Approach S12 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-04 | 3.C-2 | 1 | Confirmed by DPQE. | ernest.fu@garmin.com
914 | 912 | Approach S12 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-04 | 3.D-5 | 1 | No issue | maggie.chang@garmin.com
915 | 949 | Approach Z50 | Outdoor | GMLA1 | Complete | 2021-03-03 | 2021-03-04
916 | 949 | Approach Z50 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
917 | 949 | Approach Z50 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
918 | 949 | Approach Z50 | Outdoor | GMLA2 | Incomplete |  | 2022-11-04 | 2.C-2 | 0
919 | 949 | Approach Z50 | Outdoor | GMLA2 | Incomplete |  | 2022-11-04 | 2.D-5 | 0
920 | 986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA1 | Complete | 2021-07-12 | 2021-07-21
921 | 986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA2 | Complete | 2022-02-07 | 2022-02-04 | 2.C-2 | 1 | MPM confirmed | franksl.chen@garmin.com
922 | 986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA2 | Complete | 2022-02-07 | 2022-02-04 | 2.D-5 | 0 | No button test fixture verification report from PDO | chris.kuo@garmin.com
923 | 986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA3 | Complete | 2022-05-17 | 2022-05-17 | 3.C-2 | 1 | Fixture meet PR | chris.kuo@garmin.com
924 | 986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA3 | Complete | 2022-05-17 | 2022-05-17 | 3.D-5 | 1 | Need PDO update the TM0347 & TM0349 for verification report | chris.kuo@garmin.com
925 | 1021 | NEO 2T Taiwan Production | Fitness | GMLA3 | Complete | 2021-03-31 | 2021-03-31 | 3.C-2 | 0 | PDO has not provided equipment operation manual yet. Confirmed by DPQE. | wendy.ni@garmin.com
926 | 1021 | NEO 2T Taiwan Production | Fitness | GMLA3 | Complete | 2021-03-31 | 2021-03-31 | 3.D-5 | 0 | PDO is still improving equipment and related equipment documents have not yet been established | vincent.chou@garmin.com
927 | 1087 | Tactix 7 | Outdoor | GMLA1 | Incomplete
928 | 1087 | Tactix 7 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
929 | 1087 | Tactix 7 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
930 | 1087 | Tactix 7 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
931 | 1087 | Tactix 7 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
932 | 1088 | Approach S70 | Outdoor | GMLA1 | Complete | 2022-07-06 | 2022-07-11
933 | 1088 | Approach S70 | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 2.C-2 | 0 | Confirmed by DPQE Sampling three fixtures (344523,36555,34527) all of them do not have TM0362. | cooper.wang@garmin.com
934 | 1088 | Approach S70 | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 2.D-5 | 1 | confirmed | cooper.wang@garmin.com
935 | 1088 | Approach S70 | Outdoor | GMLA3 | Complete | 2023-03-28 | 2023-03-28 | 3.C-2 | 0 | PCB assembly fixture, display & bezel dispensing alignment fixture no TM0362 (Confirmed by DPQE) | leoyt.chen@garmin.com
936 | 1088 | Approach S70 | Outdoor | GMLA3 | Complete | 2023-03-28 | 2023-03-28 | 3.D-5 | 1 | Confirmed by DPQE | leoyt.chen@garmin.com
937 | 1121 | Descent X1i | Outdoor | GMLA2 | Incomplete |  | 2024-02-19 | 2.C-2 | 0
938 | 1121 | Descent X1i | Outdoor | GMLA2 | Incomplete |  | 2024-02-19 | 2.D-5 | 0
939 | 1121 | Descent X1i | Outdoor | GMLA3 | Incomplete |  | 2024-05-21 | 3.C-2 | 0
940 | 1121 | Descent X1i | Outdoor | GMLA3 | Incomplete |  | 2024-05-21 | 3.D-5 | 0
941 | 1121 | Descent X1i | Outdoor | GMLA1 | Incomplete |  | 2022-11-30
942 | 1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA3 | Incomplete |  | 2024-01-31 | 3.C-2 | 0
943 | 1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA3 | Incomplete |  | 2024-01-31 | 3.D-5 | 0
944 | 1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA1 | Complete | 2023-08-22 | 2023-08-28
945 | 1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA2 | Incomplete |  | 2023-11-08 | 2.C-2 | 0
946 | 1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA2 | Incomplete |  | 2023-11-08 | 2.D-5 | 0
947 | 802 | CL5 with monitor _YAMAHA | Marine | GMLA1 | Incomplete |  | 2018-10-23
948 | 802 | CL5 with monitor _YAMAHA | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
949 | 802 | CL5 with monitor _YAMAHA | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
950 | 802 | CL5 with monitor _YAMAHA | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
951 | 802 | CL5 with monitor _YAMAHA | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
952 | 803 | CL0/G W/O Display_YAMAHA | Marine | GMLA1 | Incomplete |  | 2018-10-23
953 | 803 | CL0/G W/O Display_YAMAHA | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
954 | 803 | CL0/G W/O Display_YAMAHA | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
955 | 803 | CL0/G W/O Display_YAMAHA | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
956 | 803 | CL0/G W/O Display_YAMAHA | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
957 | 903 | Venu 2 | Fitness | GMLA3 | Complete | 2020-12-30 | 2020-12-30 | 3.C-2 | 1 | Check! | alexty.chang@garmin.com
958 | 903 | Venu 2 | Fitness | GMLA3 | Complete | 2020-12-30 | 2020-12-30 | 3.D-5 | 1 | Battery soldering : no fixture, Bezel sealing : use current fixture (confirmed by DPQE) | cooper.wang@garmin.com
959 | 945 | Tread - SXS (8") | Automotive | GMLA2 | Complete | 2021-07-26 | 2021-07-26 | 2.C-2 | 1 | The list is as the attachment. Confirmed by DPQE. | wendy.ni@garmin.com
960 | 945 | Tread - SXS (8") | Automotive | GMLA2 | Complete | 2021-07-26 | 2021-07-26 | 2.D-5 | 1 | comfirmed | jimmy.kuo@garmin.com
961 | 945 | Tread - SXS (8") | Automotive | GMLA3 | Complete | 2021-10-29 | 2021-11-03 | 3.C-2 | 1 | 1. Need to track Barometer verification plan 2. Could have VT sellable build prior to pre-MP. | lori.tsai@garmin.com
962 | 945 | Tread - SXS (8") | Automotive | GMLA3 | Complete | 2021-10-29 | 2021-11-03 | 3.D-5 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
963 | 969 | Delta Simple | Outdoor | GMLA1 | Complete | 2021-04-26 | 2021-04-29
964 | 969 | Delta Simple | Outdoor | GMLA2 | Complete | 2021-12-02 | 2021-12-02 | 2.C-2 | 1 | Fixture list update for FFP | chris.kuo@garmin.com
965 | 969 | Delta Simple | Outdoor | GMLA2 | Complete | 2021-12-02 | 2021-12-02 | 2.D-5 | 1 | No fixture issue found | chris.kuo@garmin.com
966 | 969 | Delta Simple | Outdoor | GMLA3 | Complete | 2022-04-21 | 2022-04-25 | 3.C-2 | 1 | Fixture list update. all under schedule | chris.kuo@garmin.com
967 | 969 | Delta Simple | Outdoor | GMLA3 | Complete | 2022-04-21 | 2022-04-25 | 3.D-5 | 1 | No critical equipment/ fixture | chris.kuo@garmin.com
968 | 1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA1 | Complete | 2021-10-08 | 2021-10-20
969 | 1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 2.C-2 | 1 | All fixtures ready. | tim.wu@garmin.com
970 | 1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 2.D-5 | 1 | NPI checked all good. | allen.chu@garmin.com
971 | 1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA3 | Complete | 2022-05-24 | 2022-05-24 | 3.C-2 | 1 | All fixture ETA match | tim.wu@garmin.com
972 | 1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA3 | Complete | 2022-05-24 | 2022-05-24 | 3.D-5 | 0 | Some fixtures would need to be modified. 1. Battery pressure fixture will remove battery PCB area to prevent breaking battery. 2. Modify unit holder to prevent tilt during assembly. 3. Change DA5x RTESN rack to share with dezlcam. 4. Modify MTF fixture to fit hot unit. | allen.chu@garmin.com
973 | 1076 | fenix 7S Pro (2022) | Outdoor | GMLA1 | Complete | 2022-07-22 | 2022-07-25
974 | 1076 | fenix 7S Pro (2022) | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-21 | 2.C-2 | 0 | 所有A級治具TM0362表單無內容 | howard.jen@garmin.com
975 | 1076 | fenix 7S Pro (2022) | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-21 | 2.D-5 | 1 | No related issue cause by fixture | howard.jen@garmin.com
976 | 1076 | fenix 7S Pro (2022) | Outdoor | GMLA3 | Complete | 2023-03-22 | 2023-03-22 | 3.C-2 | 1 | TM0362 will be finished in this week, all fixture has confirmed these item with PDO 1.Interferance check 2.Characteristic limit 3.Durable of fixture | howard.jen@garmin.com
977 | 1076 | fenix 7S Pro (2022) | Outdoor | GMLA3 | Complete | 2023-03-22 | 2023-03-22 | 3.D-5 | 1 | No issue | howard.jen@garmin.com
978 | 1077 | fenix 7X Pro | Outdoor | GMLA1 | Complete | 2022-07-18 | 2022-07-25
979 | 1077 | fenix 7X Pro | Outdoor | GMLA2 | Complete | 2022-12-01 | 2022-12-01 | 2.C-2 | 0 | No verification result (TM0362) on Fenix 7X Pro but pass for Gen 5 | ernest.fu@garmin.com
980 | 1077 | fenix 7X Pro | Outdoor | GMLA2 | Complete | 2022-12-01 | 2022-12-01 | 2.D-5 | 1 | White LED Current: The testing positioning is not stable, the fixture will be adjusted before PR. | ernest.fu@garmin.com
981 | 1077 | fenix 7X Pro | Outdoor | GMLA3 | Complete | 2023-03-29 | 2023-03-29 | 3.C-2 | 1 | Checked | ernest.fu@garmin.com
982 | 1077 | fenix 7X Pro | Outdoor | GMLA3 | Complete | 2023-03-29 | 2023-03-29 | 3.D-5 | 1 | No PR issued | ernest.fu@garmin.com
983 | 1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA1 | Incomplete
984 | 1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
985 | 1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
986 | 1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
987 | 1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
988 | 1120 | Catalyst KMR - Display | Automotive | GMLA1 | Complete | 2022-06-08 | 2022-06-20
989 | 1120 | Catalyst KMR - Display | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.C-2 | 0 | (Confirmed by DPQE) 1. No new equipment. 2. Fixture V&V is not implement well as attachement. | evelyn.wang@garmin.com
990 | 1120 | Catalyst KMR - Display | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.D-5 | 1 | No equipment & fixture design issued on PR issue. | evelyn.wang@garmin.com
991 | 1120 | Catalyst KMR - Display | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.C-2 | 0
992 | 1120 | Catalyst KMR - Display | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.D-5 | 0
993 | 1136 | PGWW23 | OEM Auto | GMLA1 | Complete | 2022-09-22 | 2022-09-26
994 | 1136 | PGWW23 | OEM Auto | GMLA2 | Complete | 2023-06-17 | 2023-06-20 | 2.C-2 | 1 | 音箱 arrival to C5 before 6/16. | nick.yen@garmin.com
995 | 1136 | PGWW23 | OEM Auto | GMLA2 | Complete | 2023-06-17 | 2023-06-20 | 2.D-5 | 1 | Checked | simon.ko@garmin.com
996 | 1136 | PGWW23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
997 | 1136 | PGWW23 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
998 | 1137 | Edge 1050 | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
999 | 1137 | Edge 1050 | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1000 | 1137 | Edge 1050 | Fitness | GMLA1 | Complete | 2023-05-11 | 2023-05-12
1001 | 1137 | Edge 1050 | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1002 | 1137 | Edge 1050 | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1003 | 831 | Fantom 254 / 256 | Marine | GMLA1 | Incomplete |  | 2019-07-10
1004 | 831 | Fantom 254 / 256 | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1005 | 831 | Fantom 254 / 256 | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1006 | 831 | Fantom 254 / 256 | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1007 | 831 | Fantom 254 / 256 | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1008 | 833 | Panoptix PS70 - (SSMB) | Marine | GMLA1 | Complete | 2021-12-23 | 2021-12-23
1009 | 833 | Panoptix PS70 - (SSMB) | Marine | GMLA2 | Complete | 2022-11-28 | 2022-11-28 | 2.C-2 | 1 | Done | jimmy.kuo@garmin.com
1010 | 833 | Panoptix PS70 - (SSMB) | Marine | GMLA2 | Complete | 2022-11-28 | 2022-11-28 | 2.D-5 | 1 | No fixture & equipment issue. | evelyn.wang@garmin.com
1011 | 833 | Panoptix PS70 - (SSMB) | Marine | GMLA3 | Complete | 2023-05-05 | 2023-05-08 | 3.C-2 | 0 | (1) no new equipment (2) Fixture V&V not implement completely. | evelyn.wang@garmin.com
1012 | 833 | Panoptix PS70 - (SSMB) | Marine | GMLA3 | Complete | 2023-05-05 | 2023-05-08 | 3.D-5 | 1 | Array bonding fixture have no foolproof of direction, but no quality issue, will track with PR issue-8935. | evelyn.wang@garmin.com
1013 | 834 | MSC-10 [Marine Satellite Compass] | Marine | GMLA3 | Complete | 2021-02-02 | 2021-02-01 | 3.C-2 | 1 | All fixture & equipment arrive and meet PR build | ken.kuo@garmin.com
1014 | 834 | MSC-10 [Marine Satellite Compass] | Marine | GMLA3 | Complete | 2021-02-02 | 2021-02-01 | 3.D-5 | 1 | DPQE confirmed | jasoncy.hsu@garmin.com
1015 | 842 | Xero L40i Laser Range Navigator | Outdoor | GMLA1 | Incomplete |  | 2021-11-29
1016 | 842 | Xero L40i Laser Range Navigator | Outdoor | GMLA2 | Incomplete |  | 2023-02-02 | 2.C-2 | 0
1017 | 842 | Xero L40i Laser Range Navigator | Outdoor | GMLA2 | Incomplete |  | 2023-02-02 | 2.D-5 | 0
1018 | 842 | Xero L40i Laser Range Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-05-17 | 3.C-2 | 0
1019 | 842 | Xero L40i Laser Range Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-05-17 | 3.D-5 | 0
1020 | 956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA1 | Incomplete
1021 | 956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1022 | 956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1023 | 956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1024 | 956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1025 | 978 | Force Kraken Trolling Motor | Marine | GMLA2 | Complete | 2023-03-15 | 2023-03-15 | 2.C-2 | 0 | (DPQE Confirmed) GPSBOX: Screw PCB to rear case fixture (36117). There is no verification result (TM0362) for Class A fixture | jasoncy.hsu@garmin.com
1026 | 978 | Force Kraken Trolling Motor | Marine | GMLA2 | Complete | 2023-03-15 | 2023-03-15 | 2.D-5 | 1 | No quality issue caused by fixture design problem | jasoncy.hsu@garmin.com
1027 | 978 | Force Kraken Trolling Motor | Marine | GMLA3 | Complete | 2023-06-21 | 2023-06-21 | 3.C-2 | 0 | (DPQE Confirmed) 5/2: Review verification result of class A fixture. 1. Servo antenna board pressing fixture: No interference checking result 2. GPSBOX antenna pressing fixture: No interference checking result 6/20: All interference inspection have been reviewed. 2 new equipments didn't be verified before PR. Servo shaft gear lubricate potting machine and Servo top housing lubricate dispensing machine | jasoncy.hsu@garmin.com
1028 | 978 | Force Kraken Trolling Motor | Marine | GMLA3 | Complete | 2023-06-21 | 2023-06-21 | 3.D-5 | 1 | No quality issue related to equipment/ fixture design, but some fixtures still need to be modified for production line | jasoncy.hsu@garmin.com
1029 | 1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA1 | Complete | 2021-11-08 | 2021-11-10
1030 | 1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA2 | Complete | 2022-06-27 | 2022-06-29 | 2.C-2 | 1 | Fixtures are ready for FFP | robben.liu@garmin.com
1031 | 1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA2 | Complete | 2022-06-27 | 2022-06-29 | 2.D-5 | 1 | (Confirmed by DPQE) No new critical equipment | aalto.lo@garmin.com
1032 | 1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA3 | Complete | 2022-09-16 | 2022-09-19 | 3.C-2 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
1033 | 1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA3 | Complete | 2022-09-16 | 2022-09-19 | 3.D-5 | 1 | (Confirmed by DPQE) No new critical equipment | aalto.lo@garmin.com
1034 | 1030 | vivomove Trend (previously "4") | Fitness | GMLA1 | Complete | 2021-10-22 | 2021-10-22
1035 | 1030 | vivomove Trend (previously "4") | Fitness | GMLA2 | Complete | 2022-07-04 | 2022-07-06 | 2.C-2 | 1 | All fixture are available in time. | leol.chen@garmin.com
1036 | 1030 | vivomove Trend (previously "4") | Fitness | GMLA2 | Complete | 2022-07-04 | 2022-07-06 | 2.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
1037 | 1030 | vivomove Trend (previously "4") | Fitness | GMLA3 | Complete | 2022-10-14 | 2022-10-19 | 3.C-2 | 1 | No new critical equipment and fixture is identified. | aalto.lo@garmin.com
1038 | 1030 | vivomove Trend (previously "4") | Fitness | GMLA3 | Complete | 2022-10-14 | 2022-10-19 | 3.D-5 | 1 | (Confirmed by DPQE) | aalto.lo@garmin.com
1039 | 1044 | eTrex SE | Outdoor | GMLA1 | Complete | 2021-12-20 | 2022-04-21
1040 | 1044 | eTrex SE | Outdoor | GMLA2 | Complete | 2022-08-04 | 2022-08-10 | 2.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
1041 | 1044 | eTrex SE | Outdoor | GMLA2 | Complete | 2022-08-04 | 2022-08-10 | 2.D-5 | 1 | No critical equipment | chris.kuo@garmin.com
1042 | 1044 | eTrex SE | Outdoor | GMLA3 | Complete | 2022-11-08 | 2022-11-08 | 3.C-2 | 0 | No verification result (TM0362) on the PCBA screwing fixture | chris.kuo@garmin.com
1043 | 1044 | eTrex SE | Outdoor | GMLA3 | Complete | 2022-11-08 | 2022-11-08 | 3.D-5 | 1 | No equipment & fixture issue on PR phase | chris.kuo@garmin.com
1044 | 1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 2.C-2 | 1 | Use the same fixtures as DS66. | wendy.ni@garmin.com
1045 | 1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 2.D-5 | 1 | All the fixtures and equipment are the same as DS66. | wendy.ni@garmin.com
1046 | 1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA1 | Complete | 2021-11-01 | 2021-11-04
1047 | 1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA3 | Complete | 2022-04-08 | 2022-04-11 | 3.C-2 | 1 | Use the same fixtures as DS66. | wendy.ni@garmin.com
1048 | 1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA3 | Complete | 2022-04-08 | 2022-04-11 | 3.D-5 | 1 | All the fixture is same as DS66. Confirmed by DPQE. | wendy.ni@garmin.com
1049 | 1079 | BMW MGU22_G1 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1050 | 1079 | BMW MGU22_G1 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1051 | 1079 | BMW MGU22_G1 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1052 | 1079 | BMW MGU22_G1 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1053 | 1079 | BMW MGU22_G1 | OEM Auto | GMLA1 | Incomplete
1054 | 1164 | inReach Messenger 2 | Outdoor | GMLA2 | Incomplete |  | 2024-02-21 | 2.C-2 | 0
1055 | 1164 | inReach Messenger 2 | Outdoor | GMLA2 | Incomplete |  | 2024-02-21 | 2.D-5 | 0
1056 | 1164 | inReach Messenger 2 | Outdoor | GMLA3 | Incomplete |  | 2024-06-12 | 3.C-2 | 0
1057 | 1164 | inReach Messenger 2 | Outdoor | GMLA3 | Incomplete |  | 2024-06-12 | 3.D-5 | 0
1058 | 1164 | inReach Messenger 2 | Outdoor | GMLA1 | Incomplete |  | 2023-10-26
1059 | 1169 | Tacx Climbing Accessory | Fitness | GMLA1 | Incomplete
1060 | 1169 | Tacx Climbing Accessory | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1061 | 1169 | Tacx Climbing Accessory | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1062 | 1169 | Tacx Climbing Accessory | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1063 | 1169 | Tacx Climbing Accessory | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1064 | 782 | LYWW20 | OEM Auto | GMLA3 | Complete | 2021-04-09 | 2021-04-08 | 3.C-2 | 1 | per review in pilot run. | nick.yen@garmin.com
1065 | 782 | LYWW20 | OEM Auto | GMLA3 | Complete | 2021-04-09 | 2021-04-08 | 3.D-5 | 1 | No critical equipment/ fixture defined in DFM report | cherry.tsai@garmin.com
1066 | 828 | aera 760 | Aviation | GMLA1 | Incomplete
1067 | 828 | aera 760 | Aviation | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1068 | 828 | aera 760 | Aviation | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1069 | 828 | aera 760 | Aviation | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1070 | 828 | aera 760 | Aviation | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1071 | 899 | DAB+ for multiple ALJ projects | OEM Auto | GMLA1 | Incomplete
1072 | 899 | DAB+ for multiple ALJ projects | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1073 | 899 | DAB+ for multiple ALJ projects | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1074 | 899 | DAB+ for multiple ALJ projects | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1075 | 899 | DAB+ for multiple ALJ projects | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1076 | 904 | MARQ Carbon | Outdoor | GMLA1 | Complete | 2023-03-21 | 2021-08-26
1077 | 904 | MARQ Carbon | Outdoor | GMLA2 | Complete | 2023-04-11 | 2023-04-11 | 2.C-2 | 1 | Fixture all have TM0362, Screw fixture and Screw display fixture is modified now, will be back in 4/14 , have already check the interferance check | howard.jen@garmin.com
1078 | 904 | MARQ Carbon | Outdoor | GMLA2 | Complete | 2023-04-11 | 2023-04-11 | 2.D-5 | 1 | No fixture related design issue | howard.jen@garmin.com
1079 | 904 | MARQ Carbon | Outdoor | GMLA3 | Complete | 2023-07-12 | 2023-07-19 | 3.C-2 | 1 | All 2023/2 before fixture has interferance check,After has TM0362 | howard.jen@garmin.com
1080 | 904 | MARQ Carbon | Outdoor | GMLA3 | Complete | 2023-07-12 | 2023-07-19 | 3.D-5 | 1 | 1.The screw rear case Fixture scratch the LCM(2.71%), but with protective film, do not have scratch 2.Fixture scratch lug appearance(1.47%) concenrated in lug, due to the fixture material, POM can totally avoid the scratch | howard.jen@garmin.com
1081 | 959 | fenix 7S | Outdoor | GMLA2 | Complete | 2020-12-28 | 2021-01-04 | 2.C-2 | 1 | Confirmed | abbie.chang@garmin.com
1082 | 959 | fenix 7S | Outdoor | GMLA2 | Complete | 2020-12-28 | 2021-01-04 | 2.D-5 | 1 |  | abbie.chang@garmin.com
1083 | 959 | fenix 7S | Outdoor | GMLA3 | Complete | 2021-04-13 | 2021-04-13 | 3.C-2 | 1 | Confirmed fixture list | abbie.chang@garmin.com
1084 | 959 | fenix 7S | Outdoor | GMLA3 | Complete | 2021-04-13 | 2021-04-13 | 3.D-5 | 1 | OBVP have included verification result | cooper.wang@garmin.com
1085 | 960 | fenix 7X | Outdoor | GMLA2 | Complete | 2021-01-15 | 2021-01-11 | 2.C-2 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
1086 | 960 | fenix 7X | Outdoor | GMLA2 | Complete | 2021-01-15 | 2021-01-11 | 2.D-5 |  | Confirmed by DPQE. | wendy.ni@garmin.com
1087 | 960 | fenix 7X | Outdoor | GMLA3 | Complete | 2021-05-24 | 2021-05-20 | 3.C-2 | 1 | All fixtures have meet PR schedule. For MP, some fixtures are under duplicating, keep track on the complete rate. | sherry.shih@garmin.com
1088 | 960 | fenix 7X | Outdoor | GMLA3 | Complete | 2021-05-24 | 2021-05-20 | 3.D-5 | 1 | No critical equipment (confirmed by DPQE) | cooper.wang@garmin.com
1089 | 961 | BlueNet Gateway | Marine | GMLA1 | Complete | 2021-09-23 | 2021-09-30
1090 | 961 | BlueNet Gateway | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 2.C-2 | 1 | Critical fixture can be used. | allen.chu@garmin.com
1091 | 961 | BlueNet Gateway | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 2.D-5 | 0 | 12.30% scratch caused by the fixture. NPI adds rubber to protect DUT. Texture parts will be verified at the PR phase. (FFP parts without texture) | wendy.ni@garmin.com
1092 | 961 | BlueNet Gateway | Marine | GMLA3 | Complete | 2023-04-06 | 2023-04-06 | 3.C-2 | 0 | Class A TM00362 not released: 40591, 41011, 41012. | wendy.ni@garmin.com
1093 | 961 | BlueNet Gateway | Marine | GMLA3 | Complete | 2023-04-06 | 2023-04-06 | 3.D-5 | 1 | Screw nut fixture scratch has been solved. (refer switch PRissue ID 8894) | wendy.ni@garmin.com
1094 | 1020 | NEO 2T Taiwan Production | Fitness | GMLA1 | Incomplete
1095 | 1020 | NEO 2T Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1096 | 1020 | NEO 2T Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1097 | 1020 | NEO 2T Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1098 | 1020 | NEO 2T Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1099 | 1045 | Edge Explore 2 | Fitness | GMLA1 | Complete | 2021-10-29 | 2021-11-04
1100 | 1045 | Edge Explore 2 | Fitness | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 2.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
1101 | 1045 | Edge Explore 2 | Fitness | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 2.D-5 | 1 | No critical process and equipment | chris.kuo@garmin.com
1102 | 1045 | Edge Explore 2 | Fitness | GMLA3 | Complete | 2022-05-03 | 2022-05-04 | 3.C-2 | 1 | fixture ETA meet PR schedule | nixon.pan@garmin.com
1103 | 1045 | Edge Explore 2 | Fitness | GMLA3 | Complete | 2022-05-03 | 2022-05-04 | 3.D-5 | 1 | No critical E/F need | chris.kuo@garmin.com
1104 | 1080 | Serv - 7" | Marine | GMLA1 | Complete | 2022-03-01 | 2022-03-02
1105 | 1080 | Serv - 7" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 2.C-2 | 1 | PRNP fixture not validation. PQE: Focus on verification result by PDO. The fixture is pass. Change it to complete | jasoncy.hsu@garmin.com
1106 | 1080 | Serv - 7" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 2.D-5 | 1 | According to the questionnaire and criteria. There is no quality issue is caused by fixture in FFP build. It should be complete. | jasoncy.hsu@garmin.com
1107 | 1080 | Serv - 7" | Marine | GMLA3 | Complete | 2023-03-13 | 2023-03-13 | 3.C-2 | 1 | (DPQE Confirmed) No critical fixture (Class A) at ASSY | jasoncy.hsu@garmin.com
1108 | 1080 | Serv - 7" | Marine | GMLA3 | Complete | 2023-03-13 | 2023-03-13 | 3.D-5 | 1 | No fixture design issue from PR1 | jasoncy.hsu@garmin.com
1109 | 1090 | Venu 3S | Fitness | GMLA1 | Complete | 2022-07-21 | 2022-08-01
1110 | 1090 | Venu 3S | Fitness | GMLA2 | Complete | 2023-01-31 | 2023-01-30 | 2.C-2 | 0 | No verification result update: 1. 39237 2. 39341 | ernest.fu@garmin.com
1111 | 1090 | Venu 3S | Fitness | GMLA2 | Complete | 2023-01-31 | 2023-01-30 | 2.D-5 | 0 | 1. Membrane attachment fixture : Sealing rubber is too hard. 2. ECG RT/FT fixture can't clip the bezel and rear case tightly. | ernest.fu@garmin.com
1112 | 1090 | Venu 3S | Fitness | GMLA3 | Complete | 2023-05-23 | 2023-05-25 | 3.C-2 | 0 | 39224 ECG治具 無TM0362表單傅偉諦 42725 撈板治具無干涉檢察劉哲嘉 (Confirmed by DPQE) | leoyt.chen@garmin.com
1113 | 1090 | Venu 3S | Fitness | GMLA3 | Complete | 2023-05-23 | 2023-05-25 | 3.D-5 | 0 | 1. BTB disconnect issue detected at RTESN - (-4X) Pre-bending fixture - (-1X) PCB assembly fixture 2. LRA fail issue detected at RTESN - (-4X) Pre-bending fixture - (-1X) PCB assembly fixture - (-4X) LRA adhesive fixture | leoyt.chen@garmin.com
1114 | 1111 | Catalyst KMR - Hub | Automotive | GMLA1 | Complete | 2022-05-18 | 2022-05-30
1115 | 1111 | Catalyst KMR - Hub | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.C-2 | 1 | (Confirmed by DPQE) 1. No new equipment. 2. Fixture V&V is not implement well as attachement. | evelyn.wang@garmin.com
1116 | 1111 | Catalyst KMR - Hub | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.D-5 | 1 | No equipment & fixture issue as PR issue | evelyn.wang@garmin.com
1117 | 1111 | Catalyst KMR - Hub | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.C-2 | 1 | (1)No new equipment (2)Fixture verification result : Many documents are completed after the reminder, such as the attached files. | evelyn.wang@garmin.com
1118 | 1111 | Catalyst KMR - Hub | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.D-5 | 1 | 1. No new equipment 2. No fixture issue at PR build | evelyn.wang@garmin.com
1119 | 1114 | Tire Temp Sensor | Automotive | GMLA1 | Complete | 2022-06-09 | 2022-06-13
1120 | 1114 | Tire Temp Sensor | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1121 | 1114 | Tire Temp Sensor | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1122 | 1114 | Tire Temp Sensor | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1123 | 1114 | Tire Temp Sensor | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1124 | 1115 | Prop Drive Cost Down | Marine | GMLA1 | Complete | 2022-08-10 | 2022-08-11
1125 | 1115 | Prop Drive Cost Down | Marine | GMLA2 | Complete | 2023-05-02 | 2023-05-02 | 2.C-2 | 1 | (DPQE Confirmed) No Class A fixture 012-04250-00 | jasoncy.hsu@garmin.com
1126 | 1115 | Prop Drive Cost Down | Marine | GMLA2 | Complete | 2023-05-02 | 2023-05-02 | 2.D-5 | 1 | No fixture design issue in SMT | jasoncy.hsu@garmin.com
1127 | 1115 | Prop Drive Cost Down | Marine | GMLA3 | Incomplete |  | 2024-04-29 | 3.C-2 | 0
1128 | 1115 | Prop Drive Cost Down | Marine | GMLA3 | Incomplete |  | 2024-04-29 | 3.D-5 | 0
1129 | 1141 | GPSMAP 9500 | Marine | GMLA3 | Incomplete |  | 2024-03-27 | 3.C-2 | 0
1130 | 1141 | GPSMAP 9500 | Marine | GMLA3 | Incomplete |  | 2024-03-27 | 3.D-5 | 0
1131 | 1141 | GPSMAP 9500 | Marine | GMLA1 | Complete | 2023-01-09 | 2023-01-09
1132 | 1141 | GPSMAP 9500 | Marine | GMLA2 | Incomplete |  | 2024-01-10 | 2.C-2 | 0
1133 | 1141 | GPSMAP 9500 | Marine | GMLA2 | Incomplete |  | 2024-01-10 | 2.D-5 | 0
1134 | 1196 | Instinct 3 AMOLED - 45mm | Outdoor | GMLA1 | Incomplete |  | 2023-07-28
1135 | 1196 | Instinct 3 AMOLED - 45mm | Outdoor | GMLA2 | Incomplete |  | 2024-04-22 | 2.C-2 | 0
1136 | 1196 | Instinct 3 AMOLED - 45mm | Outdoor | GMLA2 | Incomplete |  | 2024-04-22 | 2.D-5 | 0
1137 | 1196 | Instinct 3 AMOLED - 45mm | Outdoor | GMLA3 | Incomplete |  | 2024-07-04 | 3.C-2 | 0
1138 | 1196 | Instinct 3 AMOLED - 45mm | Outdoor | GMLA3 | Incomplete |  | 2024-07-04 | 3.D-5 | 0
1139 | 787 | HRM-Pro | Fitness | GMLA1 | Incomplete
1140 | 787 | HRM-Pro | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1141 | 787 | HRM-Pro | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1142 | 787 | HRM-Pro | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1143 | 787 | HRM-Pro | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1144 | 807 | Daimler_VIS20_2020 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1145 | 807 | Daimler_VIS20_2020 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1146 | 807 | Daimler_VIS20_2020 | OEM Auto | GMLA3 | Incomplete |  | 2018-12-25 | 3.C-2 | 0
1147 | 807 | Daimler_VIS20_2020 | OEM Auto | GMLA3 | Incomplete |  | 2018-12-25 | 3.D-5 | 0
1148 | 839 | ECHOMAP 2020 UHD 9" | Marine | GMLA1 | Incomplete |  | 2019-06-24
1149 | 839 | ECHOMAP 2020 UHD 9" | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1150 | 839 | ECHOMAP 2020 UHD 9" | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1151 | 839 | ECHOMAP 2020 UHD 9" | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1152 | 839 | ECHOMAP 2020 UHD 9" | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1153 | 922 | inReach Mini 2 | Outdoor | GMLA1 | Complete | 2021-03-17 | 2021-03-18
1154 | 922 | inReach Mini 2 | Outdoor | GMLA2 | Complete | 2021-06-25 | 2021-06-25 | 2.C-2 | 1 | Fixture/Equipment list is update on FFP | chris.kuo@garmin.com
1155 | 922 | inReach Mini 2 | Outdoor | GMLA2 | Complete | 2021-06-25 | 2021-06-25 | 2.D-5 | 0 | No verification report of Lens pressing fixture. | chris.kuo@garmin.com
1156 | 922 | inReach Mini 2 | Outdoor | GMLA3 | Complete | 2021-10-12 | 2021-10-13 | 3.C-2 | 1 | Fixture ready for PR2 | chris.kuo@garmin.com
1157 | 922 | inReach Mini 2 | Outdoor | GMLA3 | Complete | 2021-10-12 | 2021-10-13 | 3.D-5 | 1 | Check the equipment and fixture from Pilot run build. Need PDO provide the verification report to NPI. | chris.kuo@garmin.com
1158 | 938 | DriveSmart 66 | Automotive | GMLA2 | Complete | 2021-03-19 | 2021-03-24 | 2.C-2 | 1 | all fixtures meet FFP demands. | chiencheng.huang@garmin.com
1159 | 938 | DriveSmart 66 | Automotive | GMLA2 | Complete | 2021-03-19 | 2021-03-24 | 2.D-5 | 1 | Critical equipment/fixture has been verified and Pass. | chiencheng.huang@garmin.com
1160 | 938 | DriveSmart 66 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-28 | 3.C-2 | 1 | all fixtures for PR completed. | chiencheng.huang@garmin.com
1161 | 938 | DriveSmart 66 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-28 | 3.D-5 | 1 | The fixture and eq have been checked before acceptance | jasonch.chen@garmin.com
1162 | 939 | DriveSmart 76 | Automotive | GMLA2 | Complete | 2021-03-31 | 2021-04-02 | 2.C-2 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
1163 | 939 | DriveSmart 76 | Automotive | GMLA2 | Complete | 2021-03-31 | 2021-04-02 | 2.D-5 | 1 | confirmed no issue | nixon.pan@garmin.com
1164 | 939 | DriveSmart 76 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-24 | 3.C-2 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
1165 | 939 | DriveSmart 76 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-24 | 3.D-5 | 1 | ASSY fixture:Done | daniel.lee@garmin.com
1166 | 940 | DriveSmart 86 | Automotive | GMLA2 | Complete | 2021-04-09 | 2021-04-09 | 2.C-2 | 1 | fixtures are ready before FFP | nixon.pan@garmin.com
1167 | 940 | DriveSmart 86 | Automotive | GMLA2 | Complete | 2021-04-09 | 2021-04-09 | 2.D-5 | 1 | verify in FFP | nixon.pan@garmin.com
1168 | 940 | DriveSmart 86 | Automotive | GMLA3 | Complete | 2021-06-23 | 2021-06-23 | 3.C-2 | 1 | Fixture ETA meet PR schedule | nixon.pan@garmin.com
1169 | 940 | DriveSmart 86 | Automotive | GMLA3 | Complete | 2021-06-23 | 2021-06-23 | 3.D-5 | 1 | Confirmed by DPQE | jasoncy.hsu@garmin.com
1170 | 968 | Descent G1 | Outdoor | GMLA1 | Complete | 2021-04-03 | 2021-03-29
1171 | 968 | Descent G1 | Outdoor | GMLA2 | Complete | 2021-06-29 | 2021-06-29 | 2.C-2 | 1 | MPM confirmed | franksl.chen@garmin.com
1172 | 968 | Descent G1 | Outdoor | GMLA2 | Complete | 2021-06-29 | 2021-06-29 | 2.D-5 | 1 | No critical equipment/fixture (confirmed by DPQE) | cooper.wang@garmin.com
1173 | 968 | Descent G1 | Outdoor | GMLA3 | Complete | 2021-10-13 | 2021-10-13 | 3.C-2 | 0 | Confirmed by MPM on 20211012 EE's ATE fixture need to track | franksl.chen@garmin.com
1174 | 968 | Descent G1 | Outdoor | GMLA3 | Complete | 2021-10-13 | 2021-10-13 | 3.D-5 | 1 | (Confirmed by DPQE) No critical equipment/fixture. | aalto.lo@garmin.com
1175 | 975 | GST - Connect 70_ on hold | Marine | GMLA1 | Incomplete
1176 | 975 | GST - Connect 70_ on hold | Marine | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1177 | 975 | GST - Connect 70_ on hold | Marine | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1178 | 975 | GST - Connect 70_ on hold | Marine | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1179 | 975 | GST - Connect 70_ on hold | Marine | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1180 | 996 | Forerunner 255S | Fitness | GMLA1 | Complete | 2021-04-19 | 2021-04-19
1181 | 996 | Forerunner 255S | Fitness | GMLA2 | Complete | 2021-12-22 | 2021-12-22 | 2.C-2 | 1 | Done | alexty.chang@garmin.com
1182 | 996 | Forerunner 255S | Fitness | GMLA2 | Complete | 2021-12-22 | 2021-12-22 | 2.D-5 | 1 | Will provide the information of verification report on PR build | ernest.fu@garmin.com
1183 | 996 | Forerunner 255S | Fitness | GMLA3 | Complete | 2022-03-31 | 2022-03-31 | 3.C-2 | 0 | PCB screwing fixture, Auto chamber fixture, G-sensor fixture, SN tag pressing fixture | maggie.chang@garmin.com
1184 | 996 | Forerunner 255S | Fitness | GMLA3 | Complete | 2022-03-31 | 2022-03-31 | 3.D-5 | 0 | not provide the documents | maggie.chang@garmin.com
1185 | 1038 | LiveScope Plus (LVS34) | Marine | GMLA1 | Complete | 2021-07-29 | 2021-08-03
1186 | 1038 | LiveScope Plus (LVS34) | Marine | GMLA2 | Complete | 2021-11-23 | 2021-11-23 | 2.C-2 | 1 | (DPQE Confirmed) Checked | jasoncy.hsu@garmin.com
1187 | 1038 | LiveScope Plus (LVS34) | Marine | GMLA2 | Complete | 2021-11-23 | 2021-11-23 | 2.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
1188 | 1038 | LiveScope Plus (LVS34) | Marine | GMLA3 | Complete | 2022-01-26 | 2022-02-02 | 3.C-2 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
1189 | 1038 | LiveScope Plus (LVS34) | Marine | GMLA3 | Complete | 2022-01-26 | 2022-02-02 | 3.D-5 | 1 | DPQE Confirmed | jasoncy.hsu@garmin.com
1190 | 1058 | Descent Mk3 Series - Small | Outdoor | GMLA1 | Complete | 2023-02-21 | 2023-02-21
1191 | 1058 | Descent Mk3 Series - Small | Outdoor | GMLA2 | Complete | 2023-08-30 | 2023-08-30 | 2.C-2 | 0 | See attached | cooper.wang@garmin.com
1192 | 1058 | Descent Mk3 Series - Small | Outdoor | GMLA2 | Complete | 2023-08-30 | 2023-08-30 | 2.D-5 | 1 | No quality issue is caused by fixture design | cooper.wang@garmin.com
1193 | 1058 | Descent Mk3 Series - Small | Outdoor | GMLA3 | Incomplete |  | 2023-11-01 | 3.C-2 | 0 | Not all fixtures meet requirements. (see reference) | cooper.wang@garmin.com
1194 | 1058 | Descent Mk3 Series - Small | Outdoor | GMLA3 | Incomplete |  | 2023-11-01 | 3.D-5 | 0
1195 | 1063 | Tread 8" OEM w/ CAN | Automotive | GMLA2 | Complete | 2022-02-23 | 2022-02-23 | 2.C-2 | 1 | Confirmed by DPQE. | wendy.ni@garmin.com
1196 | 1063 | Tread 8" OEM w/ CAN | Automotive | GMLA2 | Complete | 2022-02-23 | 2022-02-23 | 2.D-5 | 1 | There is no new fixture. Fixture of Tread 8" SXS can be used at Tread 8" OEM. | jason.cai@garmin.com
1197 | 1063 | Tread 8" OEM w/ CAN | Automotive | GMLA3 | Complete | 2022-04-26 | 2022-04-26 | 3.C-2 | 1 | All fixtures are the same as SXS. Confirmed by DPQE. | wendy.ni@garmin.com
1198 | 1063 | Tread 8" OEM w/ CAN | Automotive | GMLA3 | Complete | 2022-04-26 | 2022-04-26 | 3.D-5 | 1 | There is no new added fixture. | jason.cai@garmin.com
1199 | 1064 | Flux S/2 Taiwan Production | Fitness | GMLA1 | Incomplete
1200 | 1064 | Flux S/2 Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1201 | 1064 | Flux S/2 Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1202 | 1064 | Flux S/2 Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1203 | 1064 | Flux S/2 Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1204 | 1082 | Tacx Motion Plates | Fitness | GMLA1 | Incomplete
1205 | 1082 | Tacx Motion Plates | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1206 | 1082 | Tacx Motion Plates | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1207 | 1082 | Tacx Motion Plates | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1208 | 1082 | Tacx Motion Plates | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1209 | 1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA1 | Complete | 2022-07-22 | 2022-07-22
1210 | 1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA2 | Complete | 2022-11-07 | 2022-11-07 | 2.C-2 | 1 | Confirmed by DPQE | howard.jen@garmin.com
1211 | 1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA2 | Complete | 2022-11-07 | 2022-11-07 | 2.D-5 | 1 | Do not have issue related to fixture in FFP issue | howard.jen@garmin.com
1212 | 1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA3 | Complete | 2023-02-17 | 2023-02-23 | 3.C-2 | 1 | All fixture has TM0362, and have check the interferance | howard.jen@garmin.com
1213 | 1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA3 | Complete | 2023-02-17 | 2023-02-23 | 3.D-5 | 1 | No related quality issue caused by Fixture(Confirmed by DPQE) | howard.jen@garmin.com
1214 | 1104 | quatix 7 Sapphire | Marine | GMLA1 | Incomplete
1215 | 1104 | quatix 7 Sapphire | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 2.C-2 | 0
1216 | 1104 | quatix 7 Sapphire | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 2.D-5 | 0
1217 | 1104 | quatix 7 Sapphire | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 3.C-2 | 0
1218 | 1104 | quatix 7 Sapphire | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 3.D-5 | 0
1219 | 1106 | Venu Sq 3 | Fitness | GMLA1 | Complete | 2022-07-15 | 2022-07-26
1220 | 1106 | Venu Sq 3 | Fitness | GMLA2 | Incomplete |  | 2023-01-10 | 2.C-2 | 0
1221 | 1106 | Venu Sq 3 | Fitness | GMLA2 | Incomplete |  | 2023-01-10 | 2.D-5 | 0
1222 | 1106 | Venu Sq 3 | Fitness | GMLA3 | Incomplete |  | 2023-03-22 | 3.C-2 | 0
1223 | 1106 | Venu Sq 3 | Fitness | GMLA3 | Incomplete |  | 2023-03-22 | 3.D-5 | 0
1224 | 1109 | Tacx NEO 3M | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1225 | 1109 | Tacx NEO 3M | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1226 | 1109 | Tacx NEO 3M | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1227 | 1109 | Tacx NEO 3M | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1228 | 1109 | Tacx NEO 3M | Fitness | GMLA1 | Incomplete
1229 | 1133 | LFIN20 | OEM Auto | GMLA1 | Incomplete
1230 | 1133 | LFIN20 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1231 | 1133 | LFIN20 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1232 | 1133 | LFIN20 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1233 | 1133 | LFIN20 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1234 | 1165 | BMW MGU22/IDC_C5 | OEM Auto | GMLA3 | Complete | 2023-09-22 | 2023-09-27 | 3.C-2 | 1 | Rename Gauge to "Calibration Fixture" to prevent confusion. 2023-08-21(AM) | weihsiang.chen@garmin.com
1235 | 1165 | BMW MGU22/IDC_C5 | OEM Auto | GMLA3 | Complete | 2023-09-22 | 2023-09-27 | 3.D-5 | 1 | Has reviewed it, no quality issue without fixture design | ray.hu@garmin.com
1236 | 1213 | Approach G82 | Outdoor | GMLA1 | Incomplete
1237 | 1213 | Approach G82 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1238 | 1213 | Approach G82 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1239 | 1213 | Approach G82 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1240 | 1213 | Approach G82 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1241 | 777 | Approach S62 | Outdoor | GMLA1 | Incomplete |  | 2018-12-27
1242 | 777 | Approach S62 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1243 | 777 | Approach S62 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1244 | 777 | Approach S62 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1245 | 777 | Approach S62 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1246 | 789 | BMW MGU MY20 | OEM Auto | GMLA1 | Incomplete
1247 | 789 | BMW MGU MY20 | OEM Auto | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1248 | 789 | BMW MGU MY20 | OEM Auto | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1249 | 789 | BMW MGU MY20 | OEM Auto | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1250 | 789 | BMW MGU MY20 | OEM Auto | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1251 | 795 | Overlander | Automotive | GMLA1 | Incomplete |  | 2018-08-24
1252 | 795 | Overlander | Automotive | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1253 | 795 | Overlander | Automotive | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1254 | 795 | Overlander | Automotive | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1255 | 795 | Overlander | Automotive | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1256 | 1001 | BC50 IR | Automotive | GMLA1 | Incomplete |  | 2020-12-25
1257 | 1001 | BC50 IR | Automotive | GMLA2 | Incomplete |  | 2021-11-11 | 2.C-2 | 0
1258 | 1001 | BC50 IR | Automotive | GMLA2 | Incomplete |  | 2021-11-11 | 2.D-5 | 0
1259 | 1001 | BC50 IR | Automotive | GMLA3 | Incomplete |  | 2022-02-07 | 3.C-2 | 0
1260 | 1001 | BC50 IR | Automotive | GMLA3 | Incomplete |  | 2022-02-07 | 3.D-5 | 0
1261 | 1002 | BC50 & BC50 IR | Automotive | GMLA1 | Complete | 2021-06-09 | 2021-06-22
1262 | 1002 | BC50 & BC50 IR | Automotive | GMLA2 | Complete | 2021-12-03 | 2021-12-03 | 2.C-2 | 1 | Fixture/Equipment list completed | chris.kuo@garmin.com
1263 | 1002 | BC50 & BC50 IR | Automotive | GMLA2 | Complete | 2021-12-03 | 2021-12-03 | 2.D-5 | 1 | No equipement/fixture issue found | chris.kuo@garmin.com
1264 | 1002 | BC50 & BC50 IR | Automotive | GMLA3 | Complete | 2022-03-02 | 2022-03-03 | 3.C-2 | 1 | Fixture list update | chris.kuo@garmin.com
1265 | 1002 | BC50 & BC50 IR | Automotive | GMLA3 | Complete | 2022-03-02 | 2022-03-03 | 3.D-5 | 1 | No critical process | chris.kuo@garmin.com
1266 | 1110 | Catalyst KMR - Camera | Automotive | GMLA1 | Complete | 2022-05-18 | 2022-05-30
1267 | 1110 | Catalyst KMR - Camera | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.C-2 | 0 | (Confirmed by DPQE) 1. No new equipment. 2. Fixture V&V is not implement well as attachement. | evelyn.wang@garmin.com
1268 | 1110 | Catalyst KMR - Camera | Automotive | GMLA2 | Complete | 2023-04-06 | 2023-04-06 | 2.D-5 | 0 | No fool-proof on ATE fixture and caused retry on "V1P2" Failure rate:3.51%(10/285pcs), issue ID=8903 | evelyn.wang@garmin.com
1269 | 1110 | Catalyst KMR - Camera | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.C-2 | 0
1270 | 1110 | Catalyst KMR - Camera | Automotive | GMLA3 | Incomplete |  | 2024-06-05 | 3.D-5 | 0
1271 | 1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA1 | Complete | 2022-08-22 | 2022-08-29
1272 | 1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA2 | Complete | 2023-02-02 | 2023-02-03 | 2.C-2 | 0 | (DPQE Confirmed) There is no verification result (TM0362) for Class A fixture (LNC FPC & PCB screwing fixture) | jasoncy.hsu@garmin.com
1273 | 1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA2 | Complete | 2023-02-02 | 2023-02-03 | 2.D-5 | 1 | No fixture design issue on FFP according to PR issue | jasoncy.hsu@garmin.com
1274 | 1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA3 | Complete | 2023-05-11 | 2023-05-12 | 3.C-2 | 1 | (DPQE Confirmed) No class A fixture | jasoncy.hsu@garmin.com
1275 | 1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA3 | Complete | 2023-05-11 | 2023-05-12 | 3.D-5 | 1 | No issue caused by fixture design | jasoncy.hsu@garmin.com
1276 | 1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA1 | Complete | 2023-01-17 | 2023-01-19
1277 | 1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA2 | Complete | 2023-09-19 | 2023-09-22 | 2.C-2 | 1 | All fixture verification were pass and accept | chris.kuo@garmin.com
1278 | 1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA2 | Complete | 2023-09-19 | 2023-09-22 | 2.D-5 | 1 | No fixture design issue | chris.kuo@garmin.com
1279 | 1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA3 | Incomplete |  | 2023-11-08 | 3.C-2 | 0
1280 | 1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA3 | Incomplete |  | 2023-11-08 | 3.D-5 | 0
1281 | 1146 | vivoactive 5 | Fitness | GMLA1 | Complete | 2023-01-09 | 2023-01-10
1282 | 1146 | vivoactive 5 | Fitness | GMLA2 | Complete | 2023-04-10 | 2023-04-12 | 2.C-2 | 1 | Checked and Updated | ernest.fu@garmin.com
1283 | 1146 | vivoactive 5 | Fitness | GMLA2 | Complete | 2023-04-10 | 2023-04-12 | 2.D-5 | 0 | SMT / ASSY fixture were easy to damage IC due to PCBA design | ernest.fu@garmin.com
1284 | 1146 | vivoactive 5 | Fitness | GMLA3 | Complete | 2023-06-21 | 2023-06-26 | 3.C-2 | 0 | TM0362 & 干涉檢查 is not been provided. | aalto.lo@garmin.com
1285 | 1146 | vivoactive 5 | Fitness | GMLA3 | Complete | 2023-06-21 | 2023-06-26 | 3.D-5 | 0 | Display chipping issue. | aalto.lo@garmin.com
1286 | 1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA1 | Complete | 2023-06-28 | 2023-06-28
1287 | 1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA3 | Incomplete |  | 2024-01-10 | 3.C-2 | 0
1288 | 1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA3 | Incomplete |  | 2024-01-10 | 3.D-5 | 0
1289 | 1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA2 | Incomplete |  | 2023-10-24 | 2.C-2 | 1 | (DPQE Confirmed) Completed. 100% (14/14) | jasoncy.hsu@garmin.com
1290 | 1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA2 | Incomplete |  | 2023-10-24 | 2.D-5 | 1 | No fixture design issue | jasoncy.hsu@garmin.com
1291 | 1182 | Enduro 3 51mm | Outdoor | GMLA1 | Incomplete |  | 2023-05-29
1292 | 1182 | Enduro 3 51mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-08 | 2.C-2 | 0
1293 | 1182 | Enduro 3 51mm | Outdoor | GMLA2 | Incomplete |  | 2024-02-08 | 2.D-5 | 0
1294 | 1182 | Enduro 3 51mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-15 | 3.C-2 | 0
1295 | 1182 | Enduro 3 51mm | Outdoor | GMLA3 | Incomplete |  | 2024-05-15 | 3.D-5 | 0
1296 | 1202 | Forerunner 970 | Fitness | GMLA1 | Incomplete
1297 | 1202 | Forerunner 970 | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1298 | 1202 | Forerunner 970 | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1299 | 1202 | Forerunner 970 | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1300 | 1202 | Forerunner 970 | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1301 | 1204 | vivoactive 6 | Fitness | GMLA1 | Incomplete
1302 | 1204 | vivoactive 6 | Fitness | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1303 | 1204 | vivoactive 6 | Fitness | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1304 | 1204 | vivoactive 6 | Fitness | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1305 | 1204 | vivoactive 6 | Fitness | GMLA3 | Incomplete |  |  | 3.D-5 | 0
1306 | 1206 | Descent G2 | Outdoor | GMLA1 | Incomplete
1307 | 1206 | Descent G2 | Outdoor | GMLA2 | Incomplete |  |  | 2.C-2 | 0
1308 | 1206 | Descent G2 | Outdoor | GMLA2 | Incomplete |  |  | 2.D-5 | 0
1309 | 1206 | Descent G2 | Outdoor | GMLA3 | Incomplete |  |  | 3.C-2 | 0
1310 | 1206 | Descent G2 | Outdoor | GMLA3 | Incomplete |  |  | 3.D-5 | 0

## g2c2_group
actualGMLASubmitDate | Project_Name | Judgement | Pass_rate
22-Oct | 4 | 4 | 100
22-Nov | 10 | 8 | 80
22-Dec | 2 | 1 | 50
23-Jan | 2 | 0 | 0
23-Feb | 4 | 0 | 0
23-Mar | 2 | 0 | 0
23-Apr | 6 | 3 | 50
23-May | 3 | 2 | 67
23-Jun | 6 | 5 | 83
23-Jul | 2 | 1 | 50
23-Aug | 3 | 1 | 33
23-Sep | 2 | 2 | 100

## g3c2_group
actualGMLASubmitDate | Project_Name | Judgement | Pass_rate
22-Oct | 1 | 1 | 100
22-Nov | 4 | 3 | 75
22-Dec | 5 | 0 | 0
23-Jan | 2 | 1 | 50
23-Feb | 6 | 2 | 33
23-Mar | 7 | 5 | 71
23-Apr | 3 | 1 | 33
23-May | 5 | 2 | 40
23-Jun | 3 | 1 | 33
23-Jul | 5 | 5 | 100
23-Aug | 0 | 0
23-Sep | 5 | 5 | 100
23-Oct | 3 | 3 | 100

## g2d5_group
actualGMLASubmitDate | Project_Name | Judgement | Pass_rate
22-Oct | 4 | 2 | 50
22-Nov | 10 | 10 | 100
22-Dec | 2 | 2 | 100
23-Jan | 2 | 1 | 50
23-Feb | 4 | 3 | 75
23-Mar | 2 | 2 | 100
23-Apr | 6 | 4 | 67
23-May | 3 | 3 | 100
23-Jun | 6 | 3 | 50
23-Jul | 2 | 2 | 100
23-Aug | 3 | 3 | 100
23-Sep | 2 | 2 | 100

## g3d5_group
actualGMLASubmitDate | Project_Name | Judgement | Pass_rate
22-Oct | 1 | 1 | 100
22-Nov | 4 | 4 | 100
22-Dec | 5 | 3 | 60
23-Jan | 2 | 2 | 100
23-Feb | 6 | 6 | 100
23-Mar | 7 | 7 | 100
23-Apr | 3 | 3 | 100
23-May | 5 | 3 | 60
23-Jun | 3 | 2 | 67
23-Jul | 5 | 5 | 100
23-Aug | 0 | 0
23-Sep | 5 | 5 | 100
23-Oct | 3 | 3 | 100