## New Production Status Summary
New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24 | New Production Status Summary 2022-05-24
Project Name | Project Id | PM Project Name | PM Project Id | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM
Xero B60i Laser Navigation Binoculars | 1119 | Xero B60i Laser Navigation Binoculars | 13229 | Top Level Design | Outdoor | 2024-03-22 | 2022-04-20 | 2022-05-11 | 2023-03-15 | 2023-03-29 | 2023-04-05 |  |  | 2024-05-03 | 1 | 0
LED Control Module | 1066 | LED Control Module | 13134 | Top Level Design | Marine | 2024-01-08 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  |  |  | 2024-02-19 | 1 | 0
Descent Mk3 Series - Small | 1058 | Descent Mk3 Series | 12994 | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-01-03 | 2022-01-17 | 2022-08-05 |  |  | 2023-11-13 | 1 | 0
Descent Mk3 Series - Large | 1057 | Descent Mk3 Series | 12994 | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-07-08 | 2022-07-22 | 2022-08-05 | 2023-04-07 |  | 2023-11-13 | 1 | 0
IMWW23 | 1084 | IMWW23 | 14434 | Top Level Design | OEM Auto | 2023-09-18 |  |  | 2021-11-05 | 2021-11-19 |  |  |  | 2023-10-30 | 1 | 0
Prop Drive Cost Down | 1115 | Prop Drive Cost Down | 16233 | Detailed Design | Marine | 2023-08-14 | [7 empty] | 2023-09-25 | 1 | 0
Venu 3 | 1089 | Venu 3 | 15520 | Detailed Design | Fitness | 2023-05-29 |  |  | 2022-01-21 | 2022-02-04 | 2022-07-19 |  |  | 2023-07-10 | 1 | 0
Venu 3S | 1090 | Venu 3S | 15519 | Detailed Design | Fitness | 2023-05-29 |  |  | 2021-12-01 | 2021-12-15 | 2022-07-19 |  |  | 2023-07-10 | 1 | 2
Force Kraken Trolling Motor | 978 | Force Kraken Trolling Motor | 12789 | Factory Prototype | Marine | 2023-05-22 | 2019-12-17 | 2020-01-07 | 2022-03-08 | 2022-03-22 | 2022-06-27 | 2022-06-30 | 2023-02-17 | 2023-07-03 | 1 | 0
MARQ Carbon | 904 | MARQ Carbon | 11252 | Detailed Design | Outdoor | 2023-05-22 | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 | 2022-07-27 | 2022-06-30 | 2023-07-03 | 1 | 0
Venu Sq 2 Plus | 1106 | Venu Sq 2 Plus | 15850 | Detailed Design | Fitness | 2023-05-08 | 2021-11-18 | 2021-12-09 | [5 empty] | 2023-06-19 | 1 | 0
GSD28 | 1068 | GSD28 | 15876 | Detailed Design | Marine | 2023-05-01 | 2021-10-07 | 2021-10-28 | 2022-07-20 | 2022-08-03 | 2022-08-22 |  |  | 2023-06-12 | 1 | 0
GPSMAP 9000 - 19" | 1051 | GPSMAP 9000 | 9946 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 - 24" | 1053 | GPSMAP 9000 | 9946 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 -27" | 1054 | GPSMAP 9000 | 9946 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 - 22" | 1052 | GPSMAP 9000 | 9946 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 1 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
BlueNET Gateway | 961 | BlueNET Gateway | 9756 | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-04-21 | 2022-12-28 | 2023-05-15 | 1 | 0
BlueNET Switch | 962 | BlueNET Switch | 9755 | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-05-19 | 2022-12-28 | 2023-05-15 | 1 | 1
Forerunner 965 | 1103 | Forerunner 965 | 16002 | Detailed Design | Fitness | 2023-04-03 |  |  | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-05-15 | 1 | 0
BMW MGU22/IDC | 815 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2023-04-01 |  | 2019-08-30 | 2020-04-10 | 2020-04-24 | 2020-04-24 |  |  | 2023-05-12 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Sandy.Lee
Varia eBike Radar Tail Light (eRTL615) | 1102 | Varia eBike Radar Tail Light (eRTL615) | 15837 | Detailed Design | Fitness | 2023-03-06 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-17 | 1 | 0
Catalyst KMR - Display | 1120 | Catalyst Kart/Moto/Roadster | 15624 | Detailed Design | Automotive | 2023-03-06 | 2021-09-20 | 2021-10-11 | 2022-02-24 | 2022-03-10 | 2022-05-23 |  |  | 2023-04-17 | 1 | 1
Catalyst KMR - Camera | 1110 | Catalyst Kart/Moto/Roadster | 15624 | Detailed Design | Automotive | 2023-03-06 | 2021-12-13 | 2022-01-03 | 2022-02-24 | 2022-03-10 | 2022-05-24 |  |  | 2023-04-17 | 1 | 5
Catalyst KMR - Hub | 1111 | Catalyst Kart/Moto/Roadster | 15624 | Detailed Design | Automotive | 2023-03-06 | 2021-12-13 | 2022-01-03 | 2022-02-24 | 2022-03-10 | 2022-05-24 |  |  | 2023-04-17 | 1 | 2
Tire Temp Sensor | 1114 | Tire Temp Sensor | 11778 | Detailed Design | Automotive | 2023-03-06 | 2021-12-22 | 2022-01-12 | 2022-04-14 | 2022-04-28 | 2022-08-12 |  |  | 2023-04-17 | 1 | 0
Xero L60i Laser Navigator | 1016 | Xero L60i Laser Navigator | 8510 | Detailed Design | Outdoor | 2023-02-13 | 2021-02-25 | 2021-03-18 | 2022-05-16 | 2022-05-30 | 2022-06-10 |  |  | 2023-03-27 | 1 | 0
Enduro 2023 | 1047 | Enduro 2023 | 14704 | Detailed Design | Outdoor | 2023-02-13 | 2021-09-15 | 2021-10-06 | 2022-03-04 | 2022-03-18 | 2021-11-09 |  |  | 2023-03-27 | 1 | 0
Descent S1 Buoy | 1006 | Descent S1 Buoy | 12799 | Detailed Design | Outdoor | 2023-02-13 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 |  |  | 2023-03-27 | 1 | 0
zumo XT2 | 1101 | zumo XT2 | 16069 | Top Level Design | Automotive | 2023-02-06 |  |  | 2022-02-18 | 2022-03-04 | 2022-05-26 |  |  | 2023-03-20 | 1 | 3
Approach Z50 | 949 | Approach Z50 | 12705 | Factory Prototype | Outdoor | 2023-02-06 | 2020-04-13 | 2020-05-04 | 2020-10-28 | 2020-11-11 | 2022-04-29 | 2022-04-06 |  | 2023-03-20 | 1 | 0
Approach S70s | 1036 | Approach S70S | 15419 | Detailed Design | Outdoor | 2023-01-30 | 2021-08-05 | 2021-08-26 | 2021-12-06 | 2021-12-20 | 2022-04-18 |  |  | 2023-03-13 | 1 | 0
Edge 540 840 | 1069 | Edge 540 840 | 14509 | Factory Prototype | Fitness | 2023-01-30 | 2021-03-11 | 2021-04-01 | 2021-04-14 | 2021-04-28 | 2022-02-07 | 2022-06-03 | 2022-09-23 | 2023-03-13 | 1 | 0
Panoptix PS70 - (SSMB) | 833 | Panoptix PS70 - (SSMB) | 10091 | Factory Prototype | Marine | 2023-01-30 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-07-28 | 2022-10-20 | 2023-03-13 | 1 | 0
Foretrex 801/901 | 1078 | Foretrex 801/901 | 14769 | Detailed Design | Outdoor | 2023-01-23 | 2021-10-01 | 2021-10-22 | 2022-01-28 | 2022-02-11 | 2022-05-27 |  |  | 2023-03-06 | 1 | 0
GMR xHD3 Magnetron Open Arrays | 1105 | GMR xHD3 Magnetron Open Arrays | 15804 | Detailed Design | Marine | 2023-01-16 |  |  | 2022-04-13 | 2022-04-27 | 2022-05-10 |  |  | 2023-02-27 | 1 | 0
Forerunner 265 | 1107 | Forerunner 265 | 14529 | Detailed Design | Fitness | 2023-01-02 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-17 |  |  | 2023-02-13 | 1 | 0
LYWW24 | 1113 | LYWW24 | 15976 | Top Level Design | OEM Auto | 2022-12-30 | [7 empty] | 2023-02-10 | 1 | 0
fenix 7X Pro | 1077 | fenix 7X Pro | 16112 | Detailed Design | Outdoor | 2022-12-19 | [7 empty] | 2023-01-30 | 1 | 0
fenix 7S Pro (2022) | 1076 | fenix 7S Pro (2022) | 16108 | Detailed Design | Outdoor | 2022-12-19 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 |  |  | 2023-01-30 | 1 | 0
fenix 7 Pro | 1075 | fenix 7 Pro | 14729 | Detailed Design | Outdoor | 2022-12-19 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-06-17 | 2022-09-08 | 2023-01-30 | 1 | 0
RV Fixed Displays - 10" | 1081 | RV Fixed Displays (7"/10") | 14554 | Detailed Design | Marine | 2022-12-05 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-05-16 | 2022-06-09 |  | 2023-01-16 | 1 | 0
Approach R50 | 1012 | Approach R50 | 10926 | Detailed Design | Outdoor | 2022-11-28 | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 | 2022-02-28 | 2022-06-30 | 2022-06-30 | 2023-01-09 | 1 | 0
Xero C1 Chronograph | 989 | Xero C1 Chronograph | 12253 | Factory Prototype | Outdoor | 2022-11-21 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-25 | 2022-05-25 | 2022-08-16 | 2023-01-02 | 1 | 0
Tread 8" OEM w/ CAN | 1063 | Tread 8" OEM w/ CAN | 15955 | Pilot Run | Automotive | 2022-11-14 | [6 empty] | 2022-03-16 | 2022-12-26 | 1 | 1
Alpha Dog Collar | 856 | Alpha Dog Collar | 7029 | Factory Prototype | Outdoor | 2022-11-08 | 2021-03-15 | 2021-04-05 | 2021-08-09 | 2021-08-23 | 2022-01-10 | 2022-01-25 |  | 2022-12-20 | 1 | 1
RV Fixed Displays - 7" | 1080 | RV Fixed Displays (7"/10") | 14554 | Detailed Design | Marine | 2022-11-07 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-03-21 | 2022-06-08 |  | 2022-12-19 | 1 | 0
vivomove Trend (previously "4") | 1030 | vivomove Trend (previously "4") | 14004 | Factory Prototype | Fitness | 2022-10-31 | 2020-11-13 | 2020-12-04 | 2021-10-01 | 2021-10-15 | 2021-11-03 | 2022-04-18 | 2022-08-05 | 2022-12-12 | 1 | 0
ECHOMAP UHD2 (Touch) 7" | 1059 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2022-11-21 | 1 | 0
ECHOMAP UHD2 (Touch) 6" | 1018 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2021-11-23 | 2022-05-06 |  | 2022-11-21 | 1 | 0
ECHOMAP UHD2 (Touch) 9" | 1041 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2022-11-21 | 1 | 1
TXTW22_Drive+3.0 (Taroko) -12.3 DA | 964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Detailed Design | OEM Auto | 2022-10-03 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 |  | 2022-11-14 | 1 | 0 |  | Wells.Yu Davidsd.Lin | Zack.Lin Colby.Ren Jeff.Lin | Nick.Yen
FUSION - WB675 Hide Away Stereo | 1043 | FUSION - WB675 Hide Away Stereo | 15524 | Factory Prototype | Marine | 2022-09-28 | [7 empty] | 2022-11-09 | 1 | 0
Instinct Hybrid Analog/Digital(Ripley) | 1029 | Instinct Hybrid Analog/Digital | 13084 | Factory Prototype | Outdoor | 2022-09-19 |  |  | 2021-12-01 | 2021-12-15 |  | 2022-01-05 |  | 2022-10-31 | 1 | 0 |  | Anton.Lin | Eric.Chiang Viola.Kao | Robben.Liu Alexty.Chang
eTrex SE | 1044 | eTrex SE | 15843 | Detailed Design | Outdoor | 2022-09-12 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 |  |  | 2022-10-24 | 1 | 0
Dash Cam Live (LTE) | 990 | Dash Cam Live (LTE) | 13009 | Factory Prototype | Automotive | 2022-09-12 | 2020-09-18 | 2020-10-09 | 2020-11-30 | 2020-12-14 | 2021-06-14 | 2022-01-07 | 2022-05-16 | 2022-10-24 | 1 | 3
Alpha 200/200i Plus (i.MX7 Platform) | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | 16195 | Pilot Run | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 1 | 0
Marq (Gen 2) | 972 | Marq (Gen 2) | 13004 | Detailed Design | Outdoor | 2022-08-22 | 2021-03-03 | 2021-03-31 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-10-03 | 1 | 0
GST - MCU 2.0 | 966 | GST - MCU 2.0 | 12155 | Pilot Run | Marine | 2022-08-22 | [7 empty] | 2022-10-03 | 1 | 0
Bounce(Waldo) | 862 | Bounce | 10919 | Pilot Run | Fitness | 2022-08-01 | 2019-09-03 | 2019-09-24 | 2019-10-22 | 2019-11-05 | 2020-04-30 |  | 2022-01-03 | 2022-09-12 | 1 | 0
Venu Sq 2(IMP) | 1023 | Venu Sq 2 | 14949 | Pilot Run | Fitness | 2022-07-18 | [5 empty] | 2021-11-23 |  | 2022-08-29 | 1 | 0
inReach Messenger | 1027 | inReach Messenger | 14539 | Pilot Run | Outdoor | 2022-07-18 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-11-10 | 2022-01-03 | 2022-03-25 | 2022-08-29 | 1 | 0
TXTW22_Drive+3.0 (Taroko)-9 DA | 953 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Detailed Design | OEM Auto | 2022-07-08 |  |  | 2021-05-28 | 2021-06-11 | 2021-06-18 | 2021-09-02 |  | 2022-08-19 | 1 | 0 |  | Davidsd.Lin Wells.Yu | Jeff.Lin Zack.Lin Colby.Ren | Nick.Yen
Tread - XL (10") | 948 | Tread XL - Baja Race Edition | 12983 | Pilot Run | Automotive | 2022-07-04 | 2020-02-11 | 2020-03-03 | 2020-06-29 | 2020-07-13 | 2020-12-11 | 2021-08-11 | 2021-10-01 | 2022-08-15 | 1 | 0
IXWW22 | 985 | IXWW22 | 11792 | Top Level Design | OEM Auto | 2022-07-04 | [6 empty] | 2021-12-28 | 2022-08-15 | 1 | 0
Tacx NEO Bike Plus_Shifter | 986 | Tacx NEO Bike Plus | 13644 | Pilot Run | Fitness | 2022-06-27 | [5 empty] | 2021-12-01 |  | 2022-08-08 | 1 | 0
BMW MGU22_PL1 | 1028 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0 |  |  |  | Mark.Chang
BMW MGU22_G1 | 1079 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0
dezlCam OTR710 & RV 795 | 1033 | dezlCam OTR710 & RV Cam 795 | 15759 | Pilot Run | Automotive | 2022-06-13 | [6 empty] | 2022-03-21 | 2022-07-25 | 1 | 0
DriveSmart76 Synaptics Redesigns | 1098 | DriveSmart Synaptics Redesigns | 16182 | Pilot Run | Automotive | 2022-06-09 | [7 empty] | 2022-07-21 | 1 | 0
RV/Camper 2022 - 8" | 1061 | RV/Camper 2022 | 15969 | Pilot Run | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0
RV/Camper 2022-10" | 1062 | RV/Camper 2022 | 15969 | Pilot Run | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0
RV/Camper 2022 - 7" | 1060 | RV/Camper 2022 | 15969 | Pilot Run | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0
Tread Audio System | 1009 | Tread Audio System | 12874 | Pilot Run | Automotive | 2022-06-06 | 2020-11-24 | 2020-12-15 | 2021-03-17 | 2021-03-31 | 2021-07-19 | 2021-08-23 | 2022-01-14 | 2022-07-18 | 1 | 0
Enduro 2022 | 1072 | Enduro 2022 | 16003 | Pilot Run | Outdoor | 2022-05-30 | [6 empty] | 2022-02-14 | 2022-07-11 | 1 | 0
Edge Explore 2 | 1045 | Edge Explore 2 | 14994 | Product Launch | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0
Tacx NEO Bike Plus | 1100 | Tacx NEO Bike Plus | 13644 | Pilot Run | Fitness | 2022-05-30 |  |  | 2020-04-22 | 2020-05-06 |  |  | 2022-03-28 | 2022-07-11 | 1 | 0
LiveScope XR | 1017 | LiveScope XR - New Transducer | 15024 | Product Launch | Marine | 2022-05-23 | 2021-02-26 | 2021-03-19 | 2021-07-16 | 2021-07-30 | 2021-08-11 | 2021-08-19 |  | 2022-07-04 | 1 | 1
Delta Simple | 969 | Delta SE | 13020 | Pilot Run | Outdoor | 2022-05-16 | 2020-08-21 | 2020-09-11 | 2020-12-28 | 2021-01-11 | 2021-07-01 | 2021-07-30 | 2022-03-09 | 2022-06-27 | 1 | 0
dezl OTR Series 2022 - 8" | 1056 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 1 | 0
dezl OTR Series 2022 - 6" | 1074 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-12-20 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 1 | 0
dezl OTR Series 2022-10" | 1055 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 1 | 0
dezl OTR Series 2022 - 7" | 1073 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 1 | 0
HRM-Pro Plus | 1022 | HRM-Pro Plus | 14484 | Pilot Run | Fitness | 2022-05-09 | [7 empty] | 2022-06-20 | 1 | 0
DriveSmart66 Synaptics Redesigns | 1097 | DriveSmart Synaptics Redesigns | 16182 | Pilot Run | Automotive | 2022-05-06 | [7 empty] | 2022-06-17 | 1 | 0
BC50 & BC50 IR | 1002 | BC50 and BC50 IR | 13939 | Product Launch | Automotive | 2022-04-25 | 2020-09-15 | 2020-10-06 | 2020-12-22 | 2021-01-05 | 2021-08-02 | 2021-09-08 | 2021-12-09 | 2022-06-06 | 1 | 0
Xero G1(s) SatCom Scouting Camera | 826 | Xero G1(s) SatCom Scouting Camera | 7011 | Pilot Run | Outdoor | 2022-04-18 |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  | 2022-05-30 | 1 | 0 |  | Derek.Cheng | Frankie.Lee | Ken.Kuo
GHC 50 | 1037 | GHC 50 | 14939 | Pilot Run | Marine | 2022-04-18 | [7 empty] | 2022-05-30 | 1 | 0
Forerunner 255 | 1032 | Forerunner 255 and 255 Music | 13179 | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-23 | 2021-12-29 | 2022-05-30 | 1 | 0
Forerunner 255S | 996 | Forerunner 255 and 255 Music | 13179 | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-22 | 2021-12-28 | 2022-05-30 | 1 | 0
Forerunner 955 and 955 Solar | 967 | Forerunner 955 and 955 Solar | 12875 | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-05-30 | 1 | 1
Edge 1040 | 936 | Edge 1040 | 11262 | Product Launch | Fitness | 2022-04-18 | 2020-01-23 | 2020-02-13 | 2020-10-20 | 2020-11-03 | 2021-08-13 | 2021-04-28 | 2021-12-29 | 2022-05-30 | 1 | 0
2022 vivofit jr. 3 SKUs | 1095 | 2022 vivofit jr. 3 SKUs | 15907 | Pilot Run | Fitness | 2022-04-11 |  |  |  |  | 2021-09-13 |  |  | 2022-05-23 | 1 | 0
ECHOMAP UHD2 (Keyed) 5" | 987 | ECHOMAP UHD2 (Keyed) | 13094 | Product Launch | Marine | 2022-04-06 | 2020-06-29 | 2020-07-20 | 2021-01-19 | 2021-02-02 | 2021-03-02 |  | 2022-01-14 | 2022-05-18 | 1 | 0
ECHOMAP UHD2 (Keyed) 7" | 988 | ECHOMAP UHD2 (Keyed) | 13094 | Product Launch | Marine | 2022-04-06 |  |  |  |  | 2021-03-02 |  | 2022-01-14 | 2022-05-18 | 1 | 0
Tacx Vortex 2M | 1070 | Tacx Vortex 2M | 13589 | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1
vivosmart 5 (Franklin) | 1034 | vivosmart 5 (Franklin) | 14064 | Production | Fitness | 2022-03-07 | 2020-11-06 | 2020-11-27 | 2021-02-05 | 2021-02-19 | 2021-01-26 | 2021-08-31 | 2021-11-05 | 2022-04-18 | 1 | 0
Dezl Headset | 1015 | Dezl Headset | 13139 | Product Launch | Automotive | 2022-03-07 | [7 empty] | 2022-04-18 | 1 | 0
BMW MGU22-RSE | 895 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-03-07 |  | 2019-10-31 | 2020-05-15 | 2020-05-29 | 2020-05-29 |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang | Sandy.Lee
Panoptix LiveScope HD (LVS34HD Transducer) | 1038 | Panoptix LiveScope HD (LVS34HD Transducer) | 15822 | Production | Marine | 2022-03-01 | 2021-03-01 | 2021-03-22 | 2021-07-16 | 2021-07-30 | 2021-08-09 | 2021-08-12 | 2021-12-10 | 2022-04-12 | 0 | 0
quatix 7 Sapphire | 1104 | quatix 7 Sapphire | 16114 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0
quatix 7 | 1085 | quatix 7 | 15801 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0
Varia Radar Camera (RCT715) | 955 | Varia Radar Camera (RCT715) | 12714 | Production | Fitness | 2022-02-14 | 2020-03-24 | 2020-04-14 | 2020-12-01 | 2020-12-15 | 2021-04-28 | 2021-04-15 | 2021-10-29 | 2022-03-28 | 1 | 0
D2 Echo (EPIX) | 1040 | D2 Echo (EPIX) | 13079 | Production | Outdoor | 2022-01-17 | [7 empty] | 2022-02-28 | 0 | 0
Descent G1 | 968 | Descent G1 | 12995 | Production | Outdoor | 2022-01-03 | 2020-07-24 | 2020-08-14 |  |  | 2020-12-14 |  |  | 2022-02-14 | 0 | 0
vivomove "Lite" | 979 | vivomove Sport (previously "Lite") | 12989 | Production | Fitness | 2021-11-08 | [7 empty] | 2021-12-20 | 1 | 0
"Austin" | 983 | "Austin" | 13684 | Production | Outdoor | 2021-11-01 | 2020-03-05 | 2020-03-26 | 2020-08-31 | 2020-09-14 | 2020-09-15 |  |  | 2021-12-13 | 1 | 0
Venu 2 Plus | 879 | Venu 2 Plus | 12514 | Production | Fitness | 2021-10-18 | 2020-01-01 | 2020-01-22 | 2020-02-07 | 2020-02-21 | 2020-06-05 |  |  | 2021-11-29 | 1 | 0
fenix 7X | 960 | fenix 7X | 13934 | Production | Outdoor | 2021-10-04 | 2020-04-17 | 2020-04-02 | 2022-10-07 | 2022-10-21 |  | 2020-11-06 | 2021-02-15 | 2021-11-15 | 0 | 0
fenix 7S | 959 | fenix 7S | 13824 | Production | Outdoor | 2021-10-04 | [7 empty] | 2021-11-15 | 1 | 0
One Battery Bike Project | 909 | One Battery Bike Project | 12851 | Production | Fitness | 2021-09-06 | 2019-12-10 | 2019-12-31 | 2020-04-02 | 2020-04-16 | 2020-06-25 |  |  | 2021-10-18 | 1 | 0
NEO 2T Taiwan Production | 1021 | NEO 2T Taiwan Production | 15329 | Production | Fitness | 2021-06-22 | [7 empty] | 2021-08-03 | 1 | 0
Battery Charger | 998 | Battery Charger | 14544 | Production | Outdoor | 2021-04-26 | [7 empty] | 2021-06-07 | 1 | 0
Venu H(Asia ISO13485 Certification) | 1008 | Asia ISO13485 Certification | 13949 | Production | Fitness | 2021-04-12 | [7 empty] | 2021-05-24 | 1 | 0
Venu 2 | 903 | Venu 2 | 13028 | Production | Fitness | 2021-03-15 | [7 empty] | 2021-04-26 | 1 | 0
Venu 2S | 868 | Venu 2S | 11026 | Production | Fitness | 2021-03-02 | [7 empty] | 2021-04-13 | 1 | 0
Enduro 2020 | 898 | Enduro 2020 | 12690 | Production | Outdoor | 2021-01-11 | [7 empty] | 2021-02-22 | 1 | 0
Lumen | 860 | Lumen | 11752 | Production | Fitness | 2020-11-30 | 2019-07-01 | 2019-07-22 | 2019-11-21 | 2019-12-05 |  |  |  | 2021-01-11 | 0 | 0
Descent T1 Transmitter | 867 | Descent T1 Transmitter | 10190 | Production | Outdoor | 2020-11-02 | 2018-02-07 | 2018-02-28 | 2018-07-11 | 2018-07-25 | 2018-08-31 |  |  | 2020-12-14 | 1 | 0
GPSMAP 64xr/sxr | 900 | GPSMAP 64xr/sxr | 12526 | Production | Outdoor | 2020-08-26 | [7 empty] | 2020-10-07 | 1 | 0
Forerunner 745 | 872 | Forerunner 745 | 12183 | Production | Fitness | 2020-07-13 | 2019-03-05 | 2019-03-26 | 2019-08-27 | 2019-09-10 | 2019-10-28 |  |  | 2020-08-24 | 1 | 0
Descent Mk2 | 835 | Descent Mk2 | 9800 | Production | Outdoor | 2020-06-22 | 2019-07-24 | 2019-08-14 | 2019-09-30 | 2019-10-14 | 2020-01-10 |  |  | 2020-08-03 | 1 | 0
Alpha 200i | 848 | Alpha 200i | 7053 | Production | Outdoor | 2020-05-25 | 2018-09-10 | 2018-10-01 | 2019-02-05 | 2019-02-19 | 2019-05-13 |  |  | 2020-07-06 | 1 | 0
Instinct Solar | 853 | Instinct Solar | 11132 | Production | Outdoor | 2020-05-18 | 2019-03-05 | 2019-03-26 | 2019-08-02 | 2019-08-16 | 2019-08-23 |  |  | 2020-06-29 | 1 | 0
fenix 6S Solar (2020) | 892 | fenix 6S Solar (2020) | 12689 | Production | Outdoor | 2020-05-11 | 2019-07-05 | 2019-07-26 | 2019-08-02 | 2019-08-16 |  |  |  | 2020-06-22 | 1 | 0
Edge 1030 Plus | 864 | Edge 1030 Plus | 12254 | Production | Fitness | 2020-05-04 | 2019-08-08 | 2019-08-29 | 2019-09-05 | 2019-09-19 | 2019-11-19 |  |  | 2020-06-15 | 1 | 0
quatix 6 | 889 | quatix 6 | 10410 | Production | Marine | 2020-03-02 | [7 empty] | 2020-04-13 | 0 | 0
Garmin Swim 2 | 811 | Garmin Swim 2 | 7091 | Production | Fitness | 2019-09-23 | 2018-10-08 | 2018-10-29 |  |  | 2019-01-25 |  |  | 2019-11-04 | 0 | 0
GPSMAP 86x | 873 | GPSMAP 86x | 11147 | Production | Marine | 2019-09-09 |  |  |  |  | 2019-02-11 |  |  | 2019-10-21 | 1 | 0
GPSMAP 9000_Black Box | 1122 | GPSMAP 9000 | 9946 | Detailed Design | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
EPIX PRO (Gen 2) 51mm | 1094 | EPIX PRO (Gen 2) 51mm | 16218 | Detailed Design | Outdoor | [9 empty] | 0 | 0
EPIX PRO (Gen 2) 47mm | 1093 | EPIX PRO (Gen 2) 47mm | 16217 | Detailed Design | Outdoor | [9 empty] | 0 | 0
GPSMAP 66sr/66i Plus (i.MX7 Platform) | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | 16211 | Pilot Run | Outdoor | [9 empty] | 0 | 0
Approach S70 | 1088 | Approach S70 | 16176 | Detailed Design | Outdoor | [9 empty] | 0 | 0
GPSMAP 68 | 1091 | GPSMAP 68 | 16137 | New Product Concept | Outdoor | [9 empty] | 0 | 0
LIIN22 | 1108 | LIIN22 | 16129 | Top Level Design | OEM Auto | [9 empty] | 0 | 0
quatix 7x Solar | 1086 | quatix 7x Solar | 16113 | Production | Marine | [9 empty] | 0 | 0
Instinct 2X Solar | 1112 | Instinct 2X Solar | 16020 | Detailed Design | Outdoor | [9 empty] | 0 | 0
Lily 2 | 1123 | Lily 2 | 15993 | Top Level Design | Fitness | [9 empty] | 0 | 0
LWIN21 | 1035 | LWIN21 | 15814 | Product Launch | OEM Auto | [9 empty] | 0 | 0
Tacx NEO 3M | 1109 | Tacx NEO 3M | 15808 | Detailed Design | Fitness | [9 empty] | 0 | 0
EPIX PRO (Gen 2) 42mm | 1092 | EPIX PRO (Gen 2) 42mm | 15803 | Detailed Design | Outdoor | [9 empty] | 0 | 0
Descent X1i | 1121 | Descent X1i | 15469 | Top Level Design | Outdoor | [9 empty] | 0 | 0
Tacx Motion Plates | 1082 | Tacx Motion Plates | 14854 | Production | Fitness | [9 empty] | 1 | 1
Tactix 7 | 1087 | Tactix 7 | 14754 | Production | Outdoor | [9 empty] | 0 | 0
Alpha 200 | 1007 | Alpha 200 | 14639 | Production | Outdoor | [9 empty] | 1 | 0
Forerunner 265s | 1118 | Forerunner 265 | 14529 | Detailed Design | Fitness | [9 empty] | 0 | 0
Approach S42 | 1083 | Approach S42 | 13814 | Production | Outdoor | [9 empty] | 0 | 0
Product - Flight Stream Redesign | 977 | Product - Flight Stream Redesign | 13634 | Derivative Product Concept | Aviation | [9 empty] | 0 | 0
Product - G3X/G500TXi Hybrid | 1050 | Product - G3X/G500TXi Hybrid | 12717 | Product Development Plan | Aviation | [9 empty] | 0 | 0
LYAF20 | 877 | LYAF20 | 12599 | Pilot Run | OEM Auto | [9 empty] | 0 | 0
LFIN20 | 876 | LFIN20 | 12554 | Production | OEM Auto | [9 empty] | 1 | 0
Product - GDU77XW | 1048 | Product - GDU77XW | 12510 | Product Development Plan | Aviation | [9 empty] | 0 | 0
Product - GDU147XW | 1049 | Product - GDU147XW | 12509 | Product Development Plan | Aviation | [9 empty] | 0 | 0
Product - 1.3\" GTR/GNC | 984 | Product - 1.3\" GTR/GNC | 12164 | Development | Aviation | [9 empty] | 0 | 0
eTrex Solar | 1065 | eTrex Solar | 10901 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Willycw.Wu Viola.Kao | Tina.Yang Franksl.Chen
Pet Tracker | 944 | Pet Tracker | 10666 | Cancelled | Outdoor | [9 empty] | 0 | 0
DGCN20 | 785 | DGCN20 | 10620 | Product Launch | OEM Auto | [9 empty] | 1 | 0
LXTW19 - SCR | 1067 | LXTW19 | 10140 | Production | OEM Auto | [9 empty] | 0 | 0