## GMLAL Status Summary- 2022 New
Category | Project Name | Phase Name | Description of Task (PM System) | (G1) Mechanical Design Review Date/ (G2) Factory prototype design review Date/ (G3) Pilot Run Built Complete Date (From PM System) | GMLA Phase | Build Close Meeting Target Date ---GMLA Start--- (Default) | Build Close Meeting Actual Date ---GMLA Start--- (MPM Maintain) | Build Close Meeting Actual Date ---GMLA Start--- (FOR "P Column" Reference) | DPQE | GMLA Risk Level (PQE Maintain) | Score (PQE Maintain) | GMLA Result Complete (PQE Maintain) | GMLA Monthly Report Complete (PQE Maintain) | GMLA Result in PRWeb | *GMLA Complete Target Date (Close meeting + 8 Working Days) | Actual GMLA Complete Date (PQE Maintain) | PQE Note | MPM | Delivery Target Date (GMLA Complete Date + 5 Working Days) | Actual Delivery Date To Design Team Date | MPM Note | Receive Feedback From Design Team (Y/N) |  | Product development Score (%) | Product validation Score (%) | Process development Score (%) | Process validation Score (%) | Supply chain/ Supply of parts Score (%) | Others Score (%)
Marine | Fusion - Apollo Amplifiers 6 / 8 channel (Tune Free Amplifiers) | Detailed Design | Mechanical Design Review | 2020-11-09 | GMLA1 | 2020-10-19 | 2019-07-31 | 2019-07-31 | Jason Hsu | B | 86.27% | Y |  | N | 2019-08-12 | 2020-09-07 | 和Tune Free Amplifiers 1 / 4 channel共用G1 | Audon Peng | 2020-09-14 | 2020-09-08 |  | N |  | 92% | 50% | 100% | 75% | 100% | 100%
Aviation | Aera 760 | Detailed Design | Working Prototype Built | unknown | GMLA1 | #VALUE! | 2019-08-13 | 2019-08-13 | Abner Tsai | A | 96.83% | Y | Y | N | 2019-08-23 | 2020-02-03 |  | no MPM | 2020-02-10 | No need | No need to deliver, due to PQE report delay. |  |  | 92% | 100% | 100% | 92% | 100% | 100%
OEM Auto | PGWW20 | Detailed Design | Mechanical Design Review | 2019-09-09 | GMLA1 | 2019-08-19 |  | 2019-08-19 | Arthur Yu |  |  | - |  | N | 2019-08-29 |  | No GMLA at this phase | Nick Yen | 1900-01-05
Outdoor | GPSMAP 65/65s | Detailed Design | Working Prototype Built | 2020-02-19 | GMLA1 | 2020-01-29 | 2019-12-10 | 2019-12-10 | Ernest Fu | - | - | - | - | N | 2019-12-20 | - | 2020/4/27: DFM meeting 2019/12/10 Over due no need to provide GMLA | Frank Chen | #VALUE!
Outdoor | GPSMAP 66sr | Factory Prototye | Final Factory Prototype Built | 2020-01-17 | GMLA2 | 2019-12-27 | 2019-12-13 | 2019-12-13 | Chris Kuo | B | 89.22% | Y | Y | N | 2019-12-25 | 2019-12-25 |  | No MPM | 2020-01-01 | no need | PQE update report status 2020-WK20 |  |  | 89% | 87% | 100% | 80% | 94% | -
Outdoor | Alpha 200i | Factory Prototye | Final Factory Prototype Built | 2020-01-10 | GMLA2 | 2019-12-20 |  | 2019-12-20 | Chris Kuo | A | 91.18% | Y |  | N | 2020-01-01 | 2020-03-27 | [7 empty] | 89% | 87% | 100% | 87% | 94% | -
Marine | MSC-10 [Marine Satellite Compass] | Detailed Design | Working Prototype Built | 2020-05-29 | GMLA1 | 2020-05-08 | 2019-12-23 | 2019-12-23 | Abner Tsai | - | - | - | - | N | 2020-01-02 |  | over due, no need to provide GMLA at this phase. | Ken Kuo | 1900-01-05
Outdoor | fenix 6 Solar (2020) | Factory Prototye | Final Factory Prototype Built | 2020-01-10 | GMLA2 | 2019-12-20 | 2019-12-26 | 2019-12-26 | Abner Tsai | A | 91.87% | Y | Y | N | 2020-01-07 | 2020-01-03 |  | Robben Liu | 2020-01-10 | 2020-01-06 |  | N |  | 100% | 94% | 88% | 85% | 100% | 100%
Fitness | Edge 130 Plus | Factory Prototye | Final Factory Prototype Built | 2020-01-13 | GMLA2 | 2019-12-23 | 2020-01-06 | 2020-01-06 | Abner Tsai | A->B | 91.11% | Y | Y | N | 2020-01-16 | 2020-02-21 |  | Alex | 2020-02-28 | 9/7 已詢問NPI提供後續對策 | No need to deliver, due to PQE report delay. |  |  | 94% | 100% | 100% | 77% | 100% | 100%
Outdoor | fenix 6S Solar (2020) | Factory Prototye | Final Factory Prototype Built | 2020-01-10 | GMLA2 | 2019-12-20 | 2020-01-08 | 2020-01-08 | Abner Tsai | A->B | 92.25% | Y | Y | N | 2020-01-20 | 2020-01-16 |  | Will Ma | 2020-01-23 | 2020-01-22 |  |  |  | 83% | 94% | 96% | 89% | 100% | 100%
Automotive | Tread | Detailed Design | Working Prototype Built | 2020-03-13 | GMLA1 | 2020-02-21 | 2020-01-16 | 2020-01-16 | Abner Tsai | A | 90.48% | Y | Y | N | 2020-01-28 | 2020-02-21 | Abner checked the close meeting date to be 2020/1/16 | CC | 2020-02-28 | 2020-03-06 | After discuss with PQE, waiting for strain gauge and deliver on 3/6 |  |  | 100% | 67% | 100% | 75% | 100% | 100%
Automotive | 2020 RV Series - 7"Displays | Pilot Run | Pilot Run Units Built | 2020-03-16 | GMLA3 | 2020-03-09 | 2020-01-16 | 2020-01-16 | Jason Hsu | A->B | 93.65% | Y | Y | N | 2020-01-28 | 2020-02-12 |  | Jason Lee | 2020-02-19 | 2020-02-13 |  | N |  | 100% | 81% | 94% | 94% | 100% | 100%
Fitness | Venu 2S | Detailed Design | Working Prototype Built | 2020-06-23 | GMLA1 | 2020-06-02 | 2020-01-20 | 2020-01-20 | Ernest Fu | B | 85% | Y | Y | N | 2020-01-30 | 2020-04-29 |  | Alex | 2020-05-06 | 2020-05-05 |  |  |  | 75% | 67% | 100% | 75% | 100% | 100%
Marine | FUSION - ERX400 | Pilot Run | Pilot Run Units Built | 2020-01-31 | GMLA3 | 2020-01-24 | 2020-01-21 | 2020-01-21 | Chris Kuo | B->C | 78.99% | Y | Y | N | 2020-01-31 | 2020-02-06 |  | Ken Kuo | 2020-02-13 | 2020-02-12 |  | Y |  | 80% | 90% | 82% | 67% | 80% | 100%
Fitness | Varia Radar Tail Light (RTL515) | Factory Prototye | Final Factory Prototype Built | 2020-01-15 | GMLA2 | 2019-12-25 | 2020-01-22 | 2020-01-22 | Abner Tsai | B->C | 82.11% | Y | Y | N | 2020-02-03 | 2020-03-17 |  | no MPM | 2020-03-24 | 9/7 已詢問NPI提供後續對策 | No need to deliver, due to PQE report delay. |  |  | 78% | 57% | 100% | 75% | 100% | 100%
Automotive | zumo XT | Pilot Run | Pilot Run Units Built | 2020-01-23 | GMLA3 | 2020-01-16 | 2020-01-24 | 2020-01-24 | Jason Hsu | B->C | 89.86% | Y | Y | N | 2020-02-05 | 2020-02-10 |  | CC | 2020-02-17 | 2020-02-11 | since PQE sent to MPM on 2/11 | N |  | 100% | 100% | 97% | 83% | 60% | 100%
Outdoor | Montana 7xx | Factory Prototye | Final Factory Prototype Built | 2019-12-17 | GMLA2 | 2019-11-26 | 2020-01-27 | 2020-01-27 | Abner Tsai | A->B | 92.59% | Y | Y | N | 2020-02-06 | 2020-02-04 |  | Sherry | 2020-02-11 | 2020-02-11 |  | N |  | 100% | 86% | 88% | 92% | 100% | 100%
Fitness | Edge 1030 Plus | Factory Prototye | Final Factory Prototype Built | 2020-01-29 | GMLA2 | 2020-01-08 | 2020-02-06 | 2020-02-06 | Abner Tsai | B->C | 87.41% | Y | Y | N | 2020-02-18 | 2020-02-07 |  | Frank Chen | 2020-02-14 | 2020-02-07 |  | Y |  | 78% | 95% | 71% | 90% | 100% | 100%
Automotive | Catalyst | Factory Prototye | Final Factory Prototype Built | 2020-02-24 | GMLA2 | 2020-02-03 | 2020-02-06 | 2020-02-06 | Chris Kuo | A->B | 93.94% | Y | Y | N | 2020-02-18 | 2020-02-28 |  | No MPM (Sandy) | 2020-03-06 | 2020-03-05 |  |  |  | 94% | 81% | 100% | 93% | 100% | 100%
Marine | 2020 RV Series - 8"Displays | Pilot Run | Pilot Run Units Built | 2020-03-16 | GMLA3 | 2020-03-09 | 2020-02-06 | 2020-02-06 | Jason Hsu | A->B | 90.7% | Y | Y | N | 2020-02-18 | 2020-03-04 | RV 8"工程文件 / 資料皆上傳到Dezl800的PRWeb，故GMLA參考Dezl 800 | Jason Lee | 2020-03-11 | 2020-03-09 |  | N |  | 93% | 100% | 87% | 82% | 100% | 100%
Marine | 2020 RV Series - 10" Displays | Pilot Run | Pilot Run Units Built | 2020-03-16 | GMLA3 | 2020-03-09 | 2020-02-06 | 2020-02-06 | Jason Hsu | A->B | 92.86% | Y | Y | N | 2020-02-18 | 2020-03-04 | RV 10"工程文件 / 資料皆上傳到Dezl1000的PRWeb，故GMLA參考Dezl 1000 | Jason Lee | 2020-03-11 | 2020-03-09 |  | N |  | 93% | 100% | 94% | 82% | 100% | 100%
Marine | FUSION - WB670 Hide Away Stereo | Factory Prototye | Final Factory Prototype Built | 2020-02-14 | GMLA2 | 2020-01-24 | 2020-02-07 | 2020-02-07 | Chris Kuo | A | 92.06% | Y | Y | N | 2020-02-19 | 2020-02-17 |  | Ken Kuo | 2020-02-24 | 2020-02-24 |  |  |  | 83% | 90% | 92% | 92% | 100% | 100%
Outdoor | Enduro 2020 | Factory Prototye | Final Factory Prototype Built | 2020-02-04 | GMLA2 | 2020-01-14 | 2020-02-07 | 2020-02-07 | Abner Tsai | B->C | 74.81% | Y | Y | N | 2020-02-19 | 2020-09-04 |  | Chiencheng Huang | 2020-09-11 | 2020-09-11 | Has delivered to Olathe | Y |  | 100% | 71% | 63% | 60% | 100% | 100%
Automotive | dezl OTR/LGV 800 | Pilot Run | Pilot Run Units Built | 2020-02-14 | GMLA3 | 2020-02-07 | 2020-02-07 | 2020-02-07 | Jason Hsu | A->B | 90.7% | Y | Y | N | 2020-02-19 | 2020-02-27 |  | Audon Peng | 2020-03-05 | 2020-03-03 |  | N |  | 93% | 100% | 87% | 82% | 100% | 100%
Automotive | dezl OTR/LGV 700 | Pilot Run | Pilot Run Units Built | 2020-02-14 | GMLA3 | 2020-02-07 | 2020-02-07 | 2020-02-07 | Jason Hsu | A->B | 96.12% | Y | Y | N | 2020-02-19 | 2020-02-25 |  | Audon Peng | 2020-03-03 | 2020-03-02 |  | N |  | 100% | 95% | 95% | 94% | 100% | 100%
Automotive | dezl OTR/LGV 1000 | Pilot Run | Pilot Run Units Built | 2020-02-28 | GMLA3 | 2020-02-21 | 2020-02-07 | 2020-02-07 | Jason Hsu | A->B | 92.86% | Y | Y | N | 2020-02-19 | 2020-03-03 |  | Audon Peng | 2020-03-10 | 2020-03-09 |  | N |  | 93% | 100% | 94% | 82% | 100% | 100%
Marine | 2020 RV Series - Dock | Pilot Run | Pilot Run Units Built | 2020-03-16 | GMLA3 | 2020-03-09 | 2020-02-07 | 2020-02-07 | Jason Hsu | A->B | 92.06% | Y | Y | N | 2020-02-19 | 2020-02-18 |  | Jason Lee | 2020-02-25 | 2020-02-21 |  | Y |  | 100% | 95% | 89% | 85% | 100% | 100%
Outdoor | Descent Mk2 | Pilot Run | Pilot Run Units Built | 2020-03-19 | GMLA3 | 2020-03-12 | 2020-02-13 | 2020-02-13 | Abner Tsai | C | 61.59% | Y | Y | N | 2020-02-25 | 2020-03-06 | Abner checked the close meeting date to be 2020/2/13 | Frank Chen | 2020-03-13 | 2020-03-13 |  |  |  | 53% | 43% | 77% | 55% | 60% | 100%
Marine | Fantom 254 / 256 | Factory Prototye | Final Factory Prototype Built | 2020-02-19 | GMLA2 | 2020-01-29 | 2020-02-18 | 2020-02-18 | Chris Kuo | A->B | 94.81% | Y | Y | N | 2020-02-28 | 2020-03-03 |  | Audon Peng | 2020-03-10 | 2020-03-04 |  | N |  | 94% | 86% | 100% | 94% | 100% | 100%
Outdoor | Descent Mk2s | Detailed Design | Working Prototype Built | 2020-06-12 | GMLA1 | 2020-05-22 | 2020-02-18 | 2020-02-18 | Abner Tsai | A | 95.24% | Y | Y | N | 2020-02-28 | 2020-02-27 | Abner checked the close meeting data to be 2020/2/18 | Frank Chen | 2020-03-05 | 2020-03-03 |  | Y |  | 92% | 100% | 100% | 92% | 95% | 100%
Outdoor | Approach R10 | Detailed Design | Working Prototype Built | 2020-02-18 | GMLA1 | 2020-01-28 | 2020-02-18 | 2020-02-18 | Abner Tsai | B | 88.89% | Y | Y | N | 2020-02-28 | 2020-03-02 | Abner checked the close meeting data to be 2020/2/18 | Robben Liu | 2020-03-09 | 2020-03-03 |  | N |  | 75% | 67% | 100% | 100% | 95% | 100%
Fitness | Lily(Lumen) | Detailed Design | Working Prototype Built | 2020-02-21 | GMLA1 | 2020-01-31 | 2020-02-19 | 2020-02-19 | Ernest Fu | B | 80.95% | Y | Y | N | 2020-03-02 | 2020-03-05 | Abner checked the close meeting date to be 2020/2/19 | Sherry | 2020-03-12 | 2020-03-16 | Additional confirmation cause delayed |  |  | 50% | 89% | 100% | 92% | 81% | 100%
Fitness | Bounce | Detailed Design | Working Prototype Built | 2020-04-28 | GMLA1 | 2020-04-07 | 2020-02-25 | 2020-02-25 | Abner Tsai | B | 80.95% | Y | Y | N | 2020-03-06 | 2020-03-02 | Kid Tracker LTE Smartwatch | Frank Chen | 2020-03-09 | 2020-03-05 |  | Y |  | 75% | 100% | 0% | 50% | 100% | 100%
Outdoor | fenix 6 Solar (2020) | Pilot Run | Pilot Run Units Built | 2020-04-17 | GMLA3 | 2020-04-10 | 2020-02-27 | 2020-02-27 | Abner Tsai | B->C | 84.78% | Y | Y | N | 2020-03-10 | 2020-03-10 | Abner checked the close meeting date to be 2020/2/27. | Robben Liu | 2020-03-17 | 2020-03-12 |  | N |  | 100% | 81% | 74% | 90% | 80% | 100%
Outdoor | fenix 6S Solar (2020) | Pilot Run | Pilot Run Units Built | 2020-04-17 | GMLA3 | 2020-04-10 | 2020-02-28 | 2020-02-28 | Abner Tsai | B->C | 77.54% | Y | Y | N | 2020-03-11 | 2020-03-12 |  | Will Ma | 2020-03-19 | 2020-03-18 |  |  |  | 80% | 86% | 69% | 76% | 80% | 100%
Fitness | Varia Radar-Only (RVR315) | Pilot Run | Pilot Run Units Built | 2020-03-04 | GMLA3 | 2020-02-26 | 2020-03-03 | 2020-03-03 | Abner Tsai | B->C | 83.72% | Y | Y | N | 2020-03-13 | 2020-03-06 |  | Sherry | 2020-03-13 | 2020-03-16 | Additional confirmation cause delayed |  |  | 80% | 81% | 88% | 74% | 100% | 100%
Fitness | Varia Radar Tail Light (RTL515) | Pilot Run | Pilot Run Units Built | 2020-03-11 | GMLA3 | 2020-03-04 | 2020-03-09 | 2020-03-09 | Abner Tsai | A->B | 94.31% | Y | Y | N | 2020-03-19 | 2020-03-17 | Jason help to update build close meeting actual date due to no MPM | no MPM | 2020-03-24 | 2020-03-24 |  |  |  | 100% | 100% | 100% | 82% | 93% | 100%
Marine | GT36/GT56 UHD Transducers | Detailed Design | Working Prototype Built | 2020-04-03 | GMLA1 | 2020-03-13 | No MPM | 2020-03-13 | Abner Tsai | - | - | - | - | N | 2020-03-25 |  | over due, no need to provide GMLA at this phase. | Ken Kuo | 1900-01-05
Outdoor | Alpha 200i | Pilot Run | Pilot Run Units Built | 2020-03-27 | GMLA3 | 2020-03-20 | 2020-03-19 | 2020-03-19 | Chris Kuo | A->B | 90.58% | Y | y | N | 2020-03-31 | 2020-03-26 |  | Will Ma | 2020-04-02 | 2020-04-01 |  |  |  | 73% | 86% | 95% | 93% | 93% | 100%
Fitness | vivofit jr. 3 | Detailed Design | Working Prototype Built | 2020-03-24 | GMLA1 | 2020-03-03 | 2020-03-20 | 2020-03-20 | Abner Tsai | B | 85.71% | Y | Y | N | 2020-04-01 | 2020-03-30 |  | Abbie Chang | 2020-04-06 | 2020-04-06 |  |  |  | 75% | 67% | 100% | 75% | 100% | 100%
Marine | Telematics (Garmin) | Pilot Run | Pilot Run Units Built | 2020-03-23 | GMLA3 | 2020-03-16 | 2020-03-20 | 2020-03-20 | Ernest Fu | B->C | 77.54% | Y | Y | N | 2020-04-01 | 2020-03-30 |  | Ken Kuo | 2020-04-06 | 2020-04-06 |  |  |  | 100% | 71% | 72% | 83% | 53% | 100%
Fitness | Forerunner 745 | Factory Prototye | Final Factory Prototype Built | 2020-03-25 | GMLA2 | 2020-03-04 | 2020-03-25 | 2020-03-25 | Abner Tsai | C | 65.93% | Y | Y | N | 2020-04-06 | 2020-03-04 |  | Alex | 2020-03-11 | 2020-03-16 | PQE issue report before meeting |  |  | 91.67% | 91.67% | 91.67% | 91.67% | 91.67% | 100%
Marine | FUSION - WB670 Hide Away Stereo | Pilot Run | Pilot Run Units Built | 2020-04-02 | GMLA3 | 2020-03-26 | 2020-03-26 | 2020-03-26 | Chris Kuo | A->B | 92.75% | Y | Y | N | 2020-04-07 | 2020-03-31 |  | Ken Kuo | 2020-04-07 | 2020-04-06 |  | Y |  | 100% | 71% | 97% | 95% | 93% | 100%
Automotive | Garmin PowerSwitch | Detailed Design | Working Prototype Built | 2020-04-09 | GMLA1 | 2020-03-19 | 2020-03-27 | 2020-03-27 | Ernest Fu | B | 88.89% | Y | Y | N | 2020-04-08 | 2020-04-06 |  | Lori Tsai | 2020-04-13 | 2020-04-08 |  | Y |  | 67% | 100% | 100% | 100% | 100% | 50%
Fitness | Rally RS/ RK200/100 | Pilot Run | Pilot Run Units Built | 2020-05-01 | GMLA3 | 2020-04-24 | 2020-03-30 | 2020-03-30 | Chris Kuo | B->C | 81.75% | Y | Y | N | 2020-04-09 | 2020-04-16 |  | Audon Peng | 2020-04-23 | 2020-04-23 |  | N |  | 73% | 71% | 92% | 82% | 73% | 100%
Automotive | Dash Cam Mini 2 | Detailed Design | Working Prototype Built | 2020-06-17 | GMLA1 | 2020-05-27 | 2020-03-30 | 2020-03-30 | Ernest Fu | A | 90% | Y | Y | N | 2020-04-09 | 2020-06-24 |  | Lori Tsai | 2020-07-01 | 2020-07-01 |  |  |  | 75% | 100% | 100% | 75% | 100% | 100%
Fitness | Edge 130 Plus | Pilot Run | Pilot Run Units Built | 2020-03-06 | GMLA3 | 2020-02-28 | 2020-04-08 | 2020-04-08 | Ernest Fu | A->B | 96.21% | y | y | N | 2020-04-20 | 2020-04-13 | need to check close meeting date (set the tentative date to be 2020/4/15) | Alex | 2020-04-20 | no need | PQE delay and after MP. |  |  | 93% | 100% | 92% | 97% | 100% | 100%
Fitness | Edge 1030 Plus | Pilot Run | Pilot Run Units Built | 2020-04-17 | GMLA3 | 2020-04-10 | 2020-04-08 | 2020-04-08 | Ernest Fu | B->C | 79.84% | Y | Y | N | 2020-04-20 | 2020-04-17 |  | Frank Chen | 2020-04-24 | 2020-04-23 |  |  |  | 93% | 71% | 82% | 82% | 60% | 100%
Fitness | Venu 2 | Detailed Design | Working Prototype Built | 2020-06-23 | GMLA1 | 2020-06-02 | 2020-04-15 | 2020-04-15 | Cooper Wang | A | 92.06% | Y | Y | N | 2020-04-27 | 2020-04-23 |  | Alex | 2020-04-30 | 2020-04-23 |  |  |  | 94% | 67% | 75% | 79% | 100% | 100%
Outdoor | GPSMAP 65/65s | Factory Prototye | Final Factory Prototype Built | 2020-05-13 | GMLA2 | 2020-04-22 | 2020-04-17 | 2020-04-17 | Ernest Fu | A->B | 92.59% | Y | Y | N | 2020-04-29 | 2020-05-21 | 2020/04/17 finished FP close meeting 2020/04/27 移轉 2020/05/20 異動MPM | Abbie Chang | 2020-05-28 | 2020-05-26 |  |  |  | 100% | 71% | 100% | 92% | 100% | 100%
Marine | GPS 24xd (Dual frequency, 19x replacement) | Factory Prototye | Final Factory Prototype Built | 2020-04-29 | GMLA2 | 2020-04-08 | 2020-04-17 | 2020-04-17 | Chris Kuo | B | 88.15% | Y | Y | N | 2020-04-29 | 2020-04-30 | FFP 4/13 | No MPM | 2020-05-07 | 2020-05-07 |  |  |  | 100% | 57% | 100% | 85% | 100% | 100%
Outdoor | Descent T1 Transmitter | Pilot Run | Pilot Run Units Built | 2020-05-07 | GMLA3 | 2020-04-30 | 2020-04-20 | 2020-04-20 | Ernest Fu | B->C | 78.52% | Y | Y | N | 2020-04-30 | 2020-04-28 | PR3 close meeting date is 2020/04/20 | Frank Chen | 2020-05-05 | 2020-05-05 |  |  |  | 100% | 95% | 64% | 79% | 60% | 100%
Outdoor | Xero X1i Crossbow Scope | Factory Prototye | Final Factory Prototype Built | 2020-04-10 | GMLA2 | 2020-03-20 | 2020-04-22 | 2020-04-22 | Chris Kuo | B->C | 71.85% | Y | Y | N | 2020-05-04 | 2020-03-16 | FFP cancelled/FP只Run一次 3/13開會即當作FFP Meeting。 | Chiencheng Huang | 2020-03-23 | 2020-03-18 |  |  |  | 50% | 48% | 58% | 83% | 100% | 100%
Outdoor | Instinct Solar | Pilot Run | Pilot Run Units Built | 2020-05-01 | GMLA3 | 2020-04-24 | 2020-04-23 | 2020-04-23 | Abner Tsai | B->C | 84.78% | Y | Y | N | 2020-05-05 | 2020-04-29 |  | Chiencheng Huang | 2020-05-06 | 2020-05-05 |  |  |  | 73% | 81% | 85% | 90% | 80% | 100%
Outdoor | Montana 7xx | Pilot Run | Pilot Run Units Built | 2020-04-24 | GMLA3 | 2020-04-17 | 2020-04-28 | 2020-04-28 | Abner Tsai | B->C | 71.01% | Y | Y | N | 2020-05-08 | 2020-05-13 |  | Sherry | 2020-05-20 | 2020-05-20 |  |  |  | 60% | 43% | 77% | 83% | 60% | 100%
Fitness | Venu Sq (Entry-level smartwatch) | Factory Prototye | Final Factory Prototype Built | 2020-04-30 | GMLA2 | 2020-04-09 | 2020-04-30 | 2020-04-30 | Ernest Fu | B->C | 87.41% | Y | Y | N | 2020-05-12 | 2020-05-11 |  | Will Ma | 2020-05-18 | 2020-05-18 |  |  |  | 100% | 57% | 100% | 85% | 94% | 100%
Automotive | Dash Cam 47 / 57 / 67W | Detailed Design | Working Prototype Built | 2020-06-19 | GMLA1 | 2020-05-29 | 2020-04-30 | 2020-04-30 | Jason Hsu | A | 92.06% | Y | Y | N | 2020-05-12 | 2020-06-23 |  | Robben Liu | 2020-06-30 | No need | Did not assign PQE for GMLA 1 review but 6/22 assigned | N |  | 92% | 100% | 100% | 75% | 95% | 100%
Automotive | Catalyst | Pilot Run | Pilot Run Units Built | 2020-05-08 | GMLA3 | 2020-05-01 | No MPM | 2020-05-01 | Jason Hsu | B->C | 78.86% | Y | Y | N | 2020-05-13 | 2020-05-11 | 5/11: PR close meeting on 5/7 is postponed by NPI because build is already done for 1 month. | No MPM | 2020-05-18 | 2020-05-15 |  |  |  | 80% | 52% | 75% | 97% | 80% | 100%
Marine | Striker Cast | Pilot Run | Pilot Run Units Built | 2020-05-25 | GMLA3 | 2020-05-18 | 2020-05-05 | 2020-05-05 | Abner Tsai | B->C | 78.99% | Y | Y | N | 2020-05-15 | 2020-05-12 | FFP5.5還未驗證完 | Ken Kuo | 2020-05-19 | 2020-05-15 |  |  |  | 80% | 71% | 85% | 81% | 60% | 100%
OEM Auto | LYAF20 | Pilot Run | Pilot Run Build Complete | 2020-05-15 | GMLA3 | 2020-05-08 | No MPM | 2020-05-08 | Cherry Tsai | - | - | - | N | N | 2020-05-20 |  | overdue | No MPM | 1900-01-05
Outdoor | GPSMAP 66sr | Pilot Run | Pilot Run Units Built | 2020-05-21 | GMLA3 | 2020-05-14 | 2020-05-08 | 2020-05-08 | Chris Kuo | B->C | 89.86% | Y | Y | N | 2020-05-20 | 2020-05-18 |  | Sherry | 2020-05-25 | 2020-05-25 |  |  |  | 87% | 71% | 97% | 93% | 87% | 100%
Fitness | Index S2 | Pilot Run | Pilot Run Build Complete | 2020-05-28 | GMLA3 | 2020-05-21 | No MPM | 2020-05-21 | Abner Tsai |  |  | - | N | N | 2020-06-02 |  | This is ODM product, so no need to do GMLA. | no MPM | 1900-01-05
Fitness | Lily(Lumen) | Factory Prototye | Final Factory Prototype Built | 2020-06-16 | GMLA2 | 2020-05-26 | 2020-05-26 | 2020-05-26 | Ernest Fu | B->C | 88.89% | Y | Y | N | 2020-06-05 | 2020-06-04 |  | Sherry | 2020-06-11 | 2020-06-11 |  |  |  | 83% | 81% | 100% | 83% | 100% | 100%
Automotive | Garmin PowerSwitch | Factory Prototye | Final Factory Prototype Built | 2020-06-26 | GMLA2 | 2020-06-05 | 2020-06-10 | 2020-06-10 | Ernest Fu | B->C | 89.63% | Y | Y | N | 2020-06-22 | 2020-06-15 |  | Lori Tsai | 2020-06-22 | 2020-06-22 |  |  |  | 83% | 86% | 88% | 90% | 100% | 100%
Marine | Malibu Display | Detailed Design | Working Prototype Built | 2020-06-24 | GMLA1 | 2020-06-03 | 2020-06-16 | 2020-06-16 | Jason Hsu | B | 84.13% | Y | Y | N | 2020-06-26 | 2020-07-09 | GMLA1已過期，需要再後補. 7/9: updated | Ken Kuo | 2020-07-16 | No need | PQE issue report too late and passed design review date. |  |  | 42% | 100% | 100% | 75% | 100% | 100%
Outdoor | GPSMAP 65/65s | Pilot Run | Pilot Run Units Built | 2020-06-24 | GMLA3 | 2020-06-17 | 2020-06-17 | 2020-06-17 | Ernest Fu | B->C | 86.67% | Y | Y | N | 2020-06-29 | 2020-07-01 | Dragon Boat Festival | Abbie Chang | 2020-07-08 | 2020-07-06 |  |  |  | 100% | 95% | 75% | 95% | 60% | 100%
Marine | GPS 24xd (Dual frequency, 19x replacement) | Pilot Run | Pilot Run Units Built | 2020-06-06 | GMLA3 | 2020-05-30 | 2020-06-18 | 2020-06-18 | Chris Kuo | A->B | 94.2% | Y | Y | N | 2020-06-30 | 2020-06-18 | 5/11: PR hasn't been started yet | no MPM | 2020-06-25 | 2020-06-28 | 連假 |  |  | 80% | 86% | 97% | 98% | 100% | 100%
Outdoor | Xero X1i Crossbow Scope | Pilot Run | Pilot Run Units Built | 2020-07-10 | GMLA3 | 2020-07-03 | 2020-06-20 | 2020-06-20 | Chris Kuo | B->C | 70.27% | Y | Y | N | 2020-07-01 | 2020-07-10 | Since there will be PR2 build, the timing of PR#1 and GMLA#3 did not align with MPM. | Chiencheng Huang | 2020-07-17 | 2020-07-17 |  |  |  | 73% | 71% | 92% | 54% | 60% | 83%
Fitness | Forerunner 745 | Pilot Run | Pilot Run Units Built | 2020-06-16 | GMLA3 | 2020-06-09 | 2020-06-20 | 2020-06-20 | Abner Tsai | C | 67.39% | Y | Y | N | 2020-07-01 | 2020-06-15 |  | Alex | 2020-06-22 | 2020-06-22 |  | Y |  | 53% | 52% | 82% | 57% | 80% | 100%
Marine | Fantom 254 / 256 | Pilot Run | Pilot Run Units Built | 2020-06-11 | GMLA3 | 2020-06-04 | 2020-06-19 | 2020-06-19 | Chris Kuo | A->B | 92.03% | Y | Y | N | 2020-07-01 | 2020-06-30 |  | Audon Peng | 2020-07-07 | 2020-07-07 |  |  |  | 93% | 86% | 97% | 86% | 100% | 100%
Fitness | Venu Sq (Entry-level smartwatch) | Pilot Run | Pilot Run Units Built | 2020-07-10 | GMLA3 | 2020-07-03 | 2020-06-24 | 2020-06-24 | Ernest Fu | B->C | 84.44% | Y | Y | N | 2020-07-06 | 2020-07-03 |  | Will Ma | 2020-07-10 | 2020-07-08 |  |  |  | 80% | 100% | 72% | 95% | 60% | 100%
Outdoor | Approach S12 | Detailed Design | Working Prototype Built | 2020-07-17 | GMLA1 | 2020-06-26 | 2020-06-29 | 2020-06-29 | Ernest Fu | A | 93.65% | Y | Y | N | 2020-07-09 | 2020-07-03 |  | Sherry | 2020-07-10 | 2020-07-10 |  |  |  | 92% | 100% | 100% | 100% | 86% | 100%
Fitness | vivofit jr. 3 | Factory Prototye | Final Factory Prototype Built | 2020-07-14 | GMLA2 | 2020-06-23 | 2020-06-30 | 2020-06-30 | Ernest Fu | B->C | 88.89% | Y | Y | N | 2020-07-10 | 2020-07-09 |  | Abbie Chang | 2020-07-16 | 2020-07-10 |  | N |  | 94% | 57% | 96% | 92% | 100% | 100%
Automotive | Tread - Overland Edition | Detailed Design | Working Prototype Built | 2020-10-16 | GMLA1 | 2020-09-25 | 2020-07-08 | 2020-07-08 | Jason Hsu | B | 82.54% | Y | Y | N | 2020-07-20 | 2020-07-16 |  | Lori Tsai | 2020-07-23 | 2020-07-28 | System outage issue |  |  | 92% | 100% | 0% | 42% | 100% | 100%
Marine | FUSION - Signature Series V3 | Pilot Run | Pilot Run Build Complete | 2020-07-17 | GMLA3 | 2020-07-10 |  | 2020-07-10 | Jason Hsu |  |  | - |  | N | 2020-07-22 |  |  |  | 1900-01-05
Fitness | Varia Core (One Battery Bike) | Detailed Design | Working Prototype Built | 2020-08-04 | GMLA1 | 2020-07-14 | 2020-07-16 | 2020-07-16 | Ernest Fu | A | 95% | Y | Y | N | 2020-07-28 | 2020-07-21 |  | Nixon Pan | 2020-07-28 | 2020-07-27 |  |  |  | 100% | 100% | 100% | 100% | 86% | 100%
Outdoor | Approach R10 | Factory Prototye | Final Factory Prototype Built | 2020-10-16 | GMLA2 | 2020-09-25 | 2020-07-17 | 2020-07-17 | Chris Kuo | B->C | 88.15% | Y | Y | N | 2020-07-29 | 2020-07-27 |  | Robben Liu | 2020-08-03 | 2020-07-29 |  | N |  | 94% | 67% | 100% | 90% | 83% | 100%
Fitness | Mercury | Detailed Design | Working Prototype Built | 2020-08-10 | GMLA1 | 2020-07-20 | No MPM | 2020-07-20 | Ernest Fu |  |  | - | - | N | 2020-07-30 |  |  | No MPM | 1900-01-05
Marine | GPSmap 7x3/9x3/12x3 | Factory Prototye | Final Factory Prototype Built | 2020-07-21 | GMLA2 | 2020-06-30 | 2020-07-22 | 2020-07-22 | Jason Hsu | B->C | 79.26% | Y | Y | N | 2020-08-03 | 2020-07-29 |  | Audon Peng | 2020-08-05 | 2020-08-05 |  | Y |  | 67% | 57% | 96% | 81% | 83% | 100%
Outdoor | Descent Mk2s | Factory Prototye | Final Factory Prototype Built | 2020-09-10 | GMLA2 | 2020-08-20 | 2020-07-30 | 2020-07-30 | Abner Tsai / Ernest Fu | A-> B | 93.33% | Y | Y | N | 2020-08-11 | 2020-08-10 |  | Frank Chen | 2020-08-17 | 2020-08-13 |  |  |  | 100% | 86% | 96% | 90% | 100% | 100%
Fitness | Rally XC200/100 | Detailed Design | Working Prototype Built | 2020-07-31 | GMLA1 | 2020-07-10 | 2020-07-31 | 2020-07-31 | Abner Tsai |  |  | - | - | N | 2020-08-12 |  | After BOM compare, the GMLA can refer to Rally Rx series | Audon Peng | 1900-01-05
Outdoor | Approach G12 | Detailed Design | Working Prototype Built | 2020-08-10 | GMLA1 | 2020-07-20 | 2020-08-05 | 2020-08-05 | Chris Kuo | A | 98.04% | Y | Y | N | 2020-08-17 | 2020-08-12 |  | Sherry Shih | 2020-08-19 | 2020-08-20 |  |  |  | 100% | 100% | 100% | 100% | 92% | 100%
Automotive | Tread | Factory Prototye | Final Factory Prototype Built | 2020-08-07 | GMLA2 | 2020-07-17 | 2020-08-06 | 2020-08-06 | Jason Hsu | B->C | 85.19% | Y | Y | N | 2020-08-18 | 2020-08-06 | GMLA 2已詢問MPM新的FFP close meeting 日期，預計延到7/30，實際日期為8/6 | CC | 2020-08-13 | 2020-08-06 |  | Y |  | 94% | 57% | 88% | 85% | 100% | 100%
Fitness | Forerunner 55 | Detailed Design | Working Prototype Built | 2020-08-21 | GMLA1 | 2020-07-31 | 2020-08-06 | 2020-08-06 | Ernest Fu | B | 80.39% | Y | Y | N | 2020-08-18 | 2020-08-17 |  | Alex | 2020-08-24 | 2020-08-31 |  |  |  | 75% | 50% | 100% | 92% | 75% | 100%
Automotive | Garmin PowerSwitch | Pilot Run | Pilot Run Units Built | 2020-08-14 | GMLA3 | 2020-08-07 | 2020-08-11 | 2020-08-11 | Ernest Fu | B->C | 88.15% | Y | Y | N | 2020-08-21 | 2020-08-19 |  | Lori Tsai | 2020-08-26 | 2020-08-26 |  |  |  | 100% | 86% | 90% | 92% | 50% | 100%
Marine | GT36/GT56 UHD Transducers | Factory Prototye | Final Factory Prototype Built | 2020-08-24 | GMLA2 | 2020-08-03 | 2020-08-12 | 2020-08-12 | Jason Hsu | B->C | 87.3% | Y | Y | N | 2020-08-24 | 2020-08-19 |  | Ken Kuo | 2020-08-26 | 2020-08-26 |  |  |  | 50% | 83% | 88% | 98% | 100% | 100%
Marine | FUSION - RA60 | Detailed Design | Working Prototype Built | 2020-08-14 | GMLA1 | 2020-07-24 | 2020-08-17 | 2020-08-17 | Jason Hsu | A | 92.16% | Y | Y | N | 2020-08-27 | 2020-08-25 |  | Ken Kuo | 2020-09-01 | 2020-08-31 |  |  |  | 92% | 100% | 100% | 75% | 100% | 100%
Fitness | vivofit jr. 3 | Pilot Run | Pilot Run Units Built | 2020-09-01 | GMLA3 | 2020-08-25 | 2020-08-20 | 2020-08-20 | Ernest Fu | B->C | 83.7% | Y | Y | N | 2020-09-01 | 2020-08-28 |  | Abbie Chang | 2020-09-04 | 2020-09-07 |  |  |  | 100% | 71% | 85% | 90% | 50% | 100%
Fitness | Rally XC200/100 | Factory Prototye | Final Factory Prototype Built | 2020-09-15 | GMLA2 | 2020-08-25 | 2020-08-20 | 2020-08-20 | Abner Tsai |  |  | - | - | N | 2020-09-01 |  | After BOM compare, the GMLA can refer to Rally Rx series | Audon Peng | 1900-01-05
Automotive | DriveSmart 86 | Detailed Design | Working Prototype Built | 2020-10-02 | GMLA1 | 2020-09-11 | 2020-08-21 | 2020-08-21 | Jason Hsu | B | 82.35% | Y | Y | N | 2020-09-02 | 2020-08-28 |  | Nixon Pan | 2020-09-04 | 2020-09-02 |  |  |  | 75% | 50% | 100% | 75% | 100% | 100%
Automotive | Drive 56 | Detailed Design | Working Prototype Built | 2020-09-25 | GMLA1 | 2020-09-04 | 2020-08-21 | 2020-08-21 | Abner Tsai | B | 86.27% | Y | Y | N | 2020-09-02 | 2020-08-28 |  | Chiencheng Huang | 2020-09-04 | 2020-09-07 |  |  |  | 75% | 100% | 100% | 92% | 75% | 100%
Fitness | Lily(Lumen) | Pilot Run | Pilot Run Units Built | 2020-09-29 | GMLA3 | 2020-09-22 | 2020-08-28 | 2020-08-28 | Ernest Fu | B->C | 77.78% | Y | Y | N | 2020-09-09 | 2020-09-07 |  | Sherry | 2020-09-14 | 2020-09-14 |  |  |  | 60% | 71% | 77% | 93% | 50% | 100%
Marine | Fusion - Apollo Amplifiers 1 / 4 channel (Tune Free Amplifiers) | Detailed Design | Working Prototype Built | 2020-11-09 | GMLA1 | 2020-10-19 | 2020-08-28 | 2020-08-28 | Jason Hsu | B | 86.27% | Y | Y | N | 2020-09-09 | 2020-09-07 | 8/28 update: DFM meeting CH 1/4預計8/28，CH 6/8待確認 | Audon Peng | 2020-09-14 | 2020-09-08 |  |  |  | 92% | 50% | 100% | 75% | 100% | 100%
Outdoor | Xero A1i PRO Bow Sight | Detailed Design | Working Prototype Built | 2020-09-28 | GMLA1 | 2020-09-07 | 2020-09-03 | 2020-09-03 | Chris Kuo | A | 92.16% | Y | Y | N | 2020-09-15 | 2020-09-11 | 此機種是Bowsight的衍生機種。 | Lori Tsai | 2020-09-18 | 2020-09-17 |  |  |  | 92% | 50% | 100% | 100% | 100% | 100%
Fitness | Rally XC200/100 | Pilot Run | Pilot Run Units Built | 2020-10-14 | GMLA3 | 2020-10-07 | 2020-09-04 | 2020-09-04 | Abner Tsai |  |  | - | - | N | 2020-09-16 |  | After BOM compare, the GMLA can refer to Rally Rx series | Audon Peng | 1900-01-05
Automotive | DriveSmart 76 | Detailed Design | Working Prototype Built | 2020-10-02 | GMLA1 | 2020-09-11 | 2020-09-07 | 2020-09-07 | Jason Hsu | A | 92.16% | Y | Y | N | 2020-09-17 | 2020-09-14 |  | Nixon Pan | 2020-09-21 | 2020-09-16 |  |  |  | 92% | 50% | 100% | 100% | 100% | 100%
Automotive | DriveSmart 66 | Detailed Design | Working Prototype Built | 2020-09-25 | GMLA1 | 2020-09-04 | 2020-09-07 | 2020-09-07 | Abner Tsai | A | 90.2% | Y | Y | N | 2020-09-17 | 2020-09-16 |  | Chiencheng Huang | 2020-09-23 | 2020-09-21 |  |  |  | 92% | 100% | 100% | 67% | 100% | 100%
Fitness | Venu 2 Plus | Detailed Design | Working Prototype Built | 2020-09-30 | GMLA1 | 2020-09-09 | 2020-09-11 | 2020-09-11 | Cooper Wang | B | 86.72% | Y | Y | N | 2020-09-23 | 2020-09-21 |  | Alex | 2020-09-28 | 2020-09-28 |  |  |  | 92% | 100% | 100% | 50% | 100% | 100%
Fitness | Forerunner 945 LTE | Factory Prototye | Final Factory Prototype Built | 2020-09-29 | GMLA2 | 2020-09-08 | 2020-09-11 | 2020-09-11 | Abner Tsai | B->C | 89.68% | Y | Y | N | 2020-09-23 | 2020-09-22 |  | Alex | 2020-09-29 | 2020-09-28 |  |  |  | 83% | 83% | 88% | 92% | 100% | 100%
Automotive | Dash Cam 47 / 57 / 67W | Factory Prototye | Final Factory Prototype Built | 2020-10-13 | GMLA2 | 2020-09-22 | 2020-09-16 | 2020-09-16 | Jason Hsu | B->C | 86.51% | Y | Y | N | 2020-09-28 | 2020-09-25 |  | Robben Liu | 2020-10-02 | 2020-09-29 |  |  |  | 83% | 67% | 88% | 90% | 100% | 100%
Marine | Surround View Camera System | Detailed Design | Working Prototype Built | 2020-11-02 | GMLA1 | 2020-10-12 | 2020-09-18 | 2020-09-18 | Jason Hsu | A | 92.16% | Y | Y | N | 2020-09-30 | 2020-09-28 |  | Ken Kuo | 2020-10-05 | 2020-10-05 |  |  |  | 92% | 100% | 100% | 75% | 100% | 100%
Automotive | Dash Cam Mini 2 | Factory Prototye | Final Factory Prototype Built | 2020-09-29 | GMLA2 | 2020-09-08 | 2020-09-18 | 2020-09-18 | Ernest Fu | B->C | 83.33% | Y | Y | N | 2020-09-30 | 2020-09-28 |  | Lori Tsai | 2020-10-05 | 2020-10-05 |  |  |  | 94% | 50% | 88% | 83% | 100% | 100%
Marine | GT36/GT56 UHD Transducers | Pilot Run | Pilot Run Units Built | 2020-10-08 | GMLA3 | 2020-10-01 | 2020-09-22 | 2020-09-22 | Jason Hsu | B | 86.67% | Y | Y | N | 2020-10-02 | 2020-10-05 | 因中秋連假，和MPM確認Target Date延後至10/5。 | Ken Kuo | 2020-10-12 | 2020-10-12 |  |  |  | 100% | 86% | 62% | 90% | 75% | 100%
Marine | FUSION - AP-DA214 (Zone Amplifier) | Detailed Design | Working Prototype Built | 2020-10-01 | GMLA1 | 2020-09-10 | 2020-09-23 | 2020-09-23 | Jason Hsu | B | 76.47% | Y | Y | N | 2020-10-05 | 2020-10-01 |  | Lori Tsai | 2020-10-08 | 2020-10-06 |  |  |  | 50% | 100% | 0% | 75% | 100% | 100%
Fitness | Venu 2 | Factory Prototye | Final Factory Prototype Built | 2020-10-06 | GMLA2 | 2020-09-15 | 2020-09-25 | 2020-09-25 | Cooper Wang | B->C | 71.43% | Y | Y | N | 2020-10-07 | 2020-10-08 | 因中秋連假，和MPM確認Target Date由10/5延後至10/8。 | Alex | 2020-10-15 | 2020-10-15 |  |  |  | 92% | 67% | 100% | 92% | 100% | 100%
Fitness | Varia Core (One Battery Bike) | Factory Prototye | Final Factory Prototype Built | 2020-10-20 | GMLA2 | 2020-09-29 | 2020-09-25 | 2020-09-25 | Jason Hsu | B->C | 81.75% | Y | Y | N | 2020-10-07 | 2020-10-07 | 因中秋連假，和MPM確認Target Date延後至10/7。 | Nixon Pan | 2020-10-14 | 2020-10-12 |  |  |  | 94% | 67% | 75% | 79% | 100% | 100%
Outdoor | fenix 7S | Detailed Design | Working Prototype Built | 2020-10-07 | GMLA1 | 2020-09-16 | 2020-09-26 | 2020-09-26 | Abner Tsai | B | 86.27% | Y | Y | N | 2020-10-07 | 2020-10-07 | 因中秋連假，和MPM確認Target Date由10/5延後至10/8。 Cooper代發 | Abbie Chang | 2020-10-14 | 2020-10-08 |  |  |  | 75% | 100% | 100% | 75% | 100% | 100%
Outdoor | fenix 7 | Detailed Design | Working Prototype Built | 2020-10-12 | GMLA1 | 2020-09-21 | 2020-09-29 | 2020-09-29 | Abner Tsai | A | 94.12% | Y | Y | N | 2020-10-09 | 2020-10-08 | Cooper代發 | Nixon Pan | 2020-10-15 | 2020-10-08 | Close meeting completed by 9/11, but need to wait for DFM meeting. |  |  | 75% | 100% | 100% | 67% | 100% | 100%
Outdoor | fenix 7X | Detailed Design | Working Prototype Built | 2020-10-14 | GMLA1 | 2020-09-23 | 2020-10-02 | 2020-10-02 | Abner Tsai | B | 88.24% | Y | Y | N | 2020-10-14 | 2020-10-08 | Cooper代發 | Will Ma | 2020-10-15 | 2020-10-12 |  | N |  | 94% | 94% | 58% | 50% | 100% | 100%
Automotive | Tread - SXS Edition | Detailed Design | Working Prototype Built | 2020-10-16 | GMLA1 | 2020-09-25 | 2020-10-05 | 2020-10-05 | Abner Tsai | A | 92.16% | Y | Y | N | 2020-10-15 | 2020-10-14 | Cooper代發/原為Tread 8" | Lori Tsai | 2020-10-21 | 2020-10-26 |  |  |  | 100% | 100% | 100% | 67% | 100% | 100%
Marine | Lithium Battery (Ice Fishing) | Detailed Design | Mechanical Design Review | 2020-11-04 | GMLA1 | 2020-10-14 |  | 2020-10-14 | Jason Hsu |  |  | - |  | N | 2020-10-26 |  | No G1 for this project. |  | 1900-01-05
Marine | GPSmap 7x3/9x3/12x3 | Pilot Run | Pilot Run Units Built | 2020-10-12 | GMLA3 | 2020-10-05 | 2020-10-14 | 2020-10-14 | Jason Hsu | B->C | 81.48% | Y | Y | N | 2020-10-26 | 2020-10-08 |  | Audon Peng | 2020-10-15 | 2020-10-15 |  | N |  | 100% | 86% | 62% | 90% | 75% | 100%
Outdoor | Instinct 2 | Detailed Design | Working Prototype Built | 2020-11-20 | GMLA1 | 2020-10-30 | 2020-10-15 | 2020-10-15 | Abner Tsai | A | 90.2% | Y | Y | N | 2020-10-27 | 2020-10-26 |  | Robben Liu | 2020-11-02 | 2020-10-29 |  |  |  | 92% | 100% | 100% | 67% | 100% | 100%
Fitness | Venu 2S | Factory Prototye | Final Factory Prototype Built | 2020-10-13 | GMLA2 | 2020-09-22 | 2020-10-21 | 2020-10-21 | Ernest Fu | A | 97.62% | Y | Y | N | 2020-11-02 | 2020-10-30 |  | Alex | 2020-11-06 | 2020-11-04 |  |  |  | 92% | 100% | 100% | 94% | 100% | 100%
Automotive | Tread XL - Overland Edition | Detailed Design | Working Prototype Built | 2020-10-16 | GMLA1 | 2020-09-25 | 2020-10-21 | 2020-10-21 | Abner Tsai | A | 94.12% | Y | Y | N | 2020-11-02 | 2020-10-30 | Cooper代發/ 原為Overlander 10" | Audon Peng | 2020-11-06 | 2020-11-02 |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Outdoor | Instinct 2S | Detailed Design | Working Prototype Built | 2020-11-20 | GMLA1 | 2020-10-30 | 2020-10-21 | 2020-10-21 | Abner Tsai | B | 80.39% | Y | Y | N | 2020-11-02 | 2020-10-30 | Cooper代發 | Frank Chen | 2020-11-06 | 2020-11-02 |  |  |  | 67% | 100% | 100% | 50% | 100% | 100%
Automotive | Tread XL - Baja Race Edition | Detailed Design | Working Prototype Built | 2020-11-20 | GMLA1 | 2020-10-30 | 2020-10-21 | 2020-10-21 | Abner Tsai | A | 94.12% | Y | Y | N | 2020-11-02 | 2020-10-30 | 原Baja (Off Road 2021) Please refer Overlander 10" | Audon Peng | 2020-11-06 | 2020-11-02 |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Outdoor | Alpha 10 | Pilot Run | Pilot Run Units Built | 2020-11-05 | GMLA3 | 2020-10-29 | 2020-10-21 | 2020-10-21 | Chris Kuo | A | 96.3% | Y | Y | N | 2020-11-02 | 2020-10-29 | 由於PR2太多軟體重工，與MPM討論將GMLA3將用PR3來評估 | Robben Liu | 2020-11-05 | 2020-10-30 |  |  |  | 100% | 86% | 100% | 95% | 100% | 100%
Fitness | vivomove Sport (previously "Lite") | Detailed Design | Mechanical Design Review | 2020-10-27 | GMLA1 | 2020-10-06 | 2020-10-23 | 2020-10-23 | Ernest Fu | G | 87.5% | Y | Y | N | 2020-11-04 | 2020-11-02 |  | Sherry Shih | 2020-11-09 | 2020-11-03 |  | N |  | 75% | 100% | 100% | 75% | 100% | 100%
Outdoor | Approach S12 | Factory Prototye | Final Factory Prototype Built | 2020-11-06 | GMLA2 | 2020-10-16 | 2020-10-29 | 2020-10-29 | Abner Tsai | A->B | 93.65% | Y | Y | N | 2020-11-10 | 2020-11-09 |  | Sherry | 2020-11-16 | 2020-11-13 |  | Y |  | 100% | 67% | 100% | 96% | 100% | 100%
Marine | MSC-10 [Marine Satellite Compass] | Factory Prototye | Final Factory Prototype Built | 2020-11-04 | GMLA2 | 2020-10-14 | 2020-11-04 | 2020-11-04 | Abner Tsai | B->C | 88.89% | Y | Y | N | 2020-11-16 | 2020-11-05 |  | Ken Kuo | 2020-11-12 | 2020-11-10 |  |  |  | 67% | 83% | 83% | 98% | 100% | 100%
Marine | Malibu Display | Factory Prototye | Final Factory Prototype Built | 2020-12-10 | GMLA2 | 2020-11-19 | 2020-11-04 | 2020-11-04 | Jason Hsu | A | 96.03% | Y | Y | N | 2020-11-16 | 2020-11-13 |  | Ken Kuo | 2020-11-20 | 2020-11-19 |  |  |  | 100% | 94% | 100% | 92% | 100% | 100%
Outdoor | EPIX (Gen 2) (原"Austin) | Detailed Design | Working Prototype Built | 2020-12-10 | GMLA1 | 2020-11-19 | 2020-11-19 | 2020-11-19 | Abner Tsai | B | 88.24% | Y | Y | N | 2020-12-01 | 2020-11-30 | 原"Austin" | Nixon Pan | 2020-12-07 | 2020-12-02 |  |  |  | 100% | 100% | 0% | 75% | 100% | 100%
Automotive | Tread | Pilot Run | Pilot Run Units Built | 2020-12-04 | GMLA3 | 2020-11-27 | 2020-11-25 | 2020-11-25 | Jason Hsu | B->C | 85.19% | Y | Y | N | 2020-12-07 | 2020-12-01 |  | CC | 2020-12-08 | 2020-12-03 |  | N |  | 80% | 71% | 92% | 88% | 75% | 100%
OEM Auto | IXWW22 | Detailed Design | Mechanical Design Review | 2020-12-16 | GMLA1 | 2020-11-25 |  | 2020-11-25 | Cherry Tsai |  |  | - |  | N | 2020-12-07 |  |  | Nick Yen | 1900-01-05
Outdoor | Enduro 2020 | Pilot Run | Pilot Run Units Built | 2020-12-18 | GMLA3 | 2020-12-11 | 2020-11-26 | 2020-11-26 | Abner Tsai | B->C | 88.89% | Y | Y | N | 2020-12-08 | 2020-12-01 |  | Chiencheng Huang | 2020-12-08 | 2020-12-08 |  | N |  | 80% | 71% | 97% | 95% | 75% | 100%
Outdoor | Xero G1(s) SatCom Scouting Camera | Factory Prototye | Final Factory Prototype Built | 2021-02-24 | GMLA2 | 2021-02-03 | 2020-11-30 | 2020-11-30 | Chris Kuo | B->C | 88.1% | Y | Y | N | 2020-12-10 | 2020-12-07 |  | CC | 2020-12-14 | 2020-12-13 |  | N |  | 83% | 44% | 100% | 96% | 100% | 100%
Outdoor | Alpha 200 | Detailed Design | Working Prototype Built | 2020-12-16 | GMLA1 | 2020-11-25 |  | 2020-11-25 | Chris Kuo | A | 100% | Y | Y | N | 2020-12-14 | 2020-12-14 |  | Will Ma | 2020-12-21 | 2020-12-15 |  | N |  | 100% | 100% | 100% | 100% | 100% | 100%
Fitness | Varia Radar Camera (RCT715) | Detailed Design | Working Prototype Built | 2020-12-15 | GMLA1 | 2020-11-24 | 2020-12-04 | 2020-12-04 | Chris Kuo | A | 96.08% | Y | Y | N | 2020-12-16 | 2020-12-11 |  | Sherry Shih | 2020-12-18 | 2020-12-18 |  |  |  | 92% | 100% | 100% | 92% | 100% | 100%
Automotive | Dash Cam Mini 2 | Pilot Run | Pilot Run Build Complete | 2020-12-18 | GMLA3 | 2020-12-11 | 2020-12-09 | 2020-12-09 | Ernest Fu | B->C | 82.98% | Y | N | Y | 2020-12-21 | 2020-12-18 |  | Lori Tsai | 2020-12-28 | 2020-12-28 |  | N |  | 56% | 86% | 92% | 90% | 60% | 100%
OEM Auto | PGWW20 | Factory Prototye | Factory Prototype Design Review | 2020-12-31 | GMLA2 | 2020-12-10 |  | 2020-12-10 | Arthur Yu |  |  | - |  | N | 2020-12-22 |  | No GMLA at this phase | Nick Yen | 1900-01-05
Outdoor | Descent Mk2s | Pilot Run | Pilot Run Build Complete | 2020-12-29 | GMLA3 | 2020-12-22 | 2020-12-10 | 2020-12-10 | Abner Tsai | B->C | 82.98% | Y | N | Y | 2020-12-22 | 2020-12-22 |  | Frank Chen | 2020-12-29 | 2020-12-29 |  | Y |  | 83% | 71% | 90% | 82% | 73% | 100%
Automotive | Dash Cam 47 / 57 / 67W | Pilot Run | Pilot Run Build Complete | 2020-12-18 | GMLA3 | 2020-12-11 | 2020-12-14 | 2020-12-14 | Jason Hsu | B->C | 84.4% | Y | N | Y | 2020-12-24 | 2020-12-24 | 12/24 submit. 12/25 return. 12/28 re-submit | Robben Liu | 2020-12-31 | 2020-12-31 |  | N |  | 72% | 86% | 100% | 87% | 40% | 100%
Fitness | Forerunner 945 LTE | Pilot Run | Pilot Run Build Complete | 2020-12-04 | GMLA3 | 2020-11-27 | 2020-12-16 | 2020-12-16 | Abner Tsai | B->C | 80.85% | Y | N | Y | 2020-12-28 | 2020-12-28 |  | Alex | 2021-01-04 | 2021-01-04 |  |  |  | 67% | 81% | 79% | 92% | 60% | 100%
Fitness | Venu 2 | Pilot Run | Pilot Run Build Complete | 2020-12-22 | GMLA3 | 2020-12-15 | 2020-12-18 | 2020-12-18 | Cooper Wang | A->B | 94.33% | Y | N | Y | 2020-12-30 | 2020-12-30 |  | Alex | 2021-01-06 | 2021-01-06 |  |  |  | 100% | 100% | 100% | 87% | 80% | 100%
OEM Auto | BMW MGU22-RSE | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 | 2020-12-18 | 2020-12-18 | Valentina | C | 68.52% | Y |  | Y | 2020-12-30 | 2021-02-06 |  | Sandy Lee | [5 empty] | 71% | 81% | 58% | 73% | 67% | 58%
OEM Auto | BMW MGU22/IDC | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 | 2020-12-18 | 2020-12-18 | James Huang/ Allen Chen | B->C | 81.48% | Y |  | Y | 2020-12-30 | 2021-01-27 |  | Jason Lee | 2021-02-03 | no need |  |  |  | 71% | 90% | 92% | 98% | 54% | 67%
Outdoor | Approach G12 | Factory Prototye | Factory Prototype Design Review | 2021-01-04 | GMLA2 | 2020-12-14 | 2020-12-21 | 2020-12-21 | Chris Kuo | B->C | 94.81% | Y | N | Y | 2020-12-31 | 2020-12-25 |  | Sherry Shih | 2021-01-01 | 2020-12-31 |  |  |  | 100% | 78% | 100% | 94% | 100% | 100%
Outdoor | fenix 7S | Factory Prototye | Factory Prototype Design Review | 2020-12-29 | GMLA2 | 2020-12-08 | 2020-12-23 | 2020-12-23 | Abner Tsai | B->C | 87.41% | Y | N | Y | 2021-01-04 | 2020-12-28 |  | Abbie Chang | 2021-01-04 | 2020-12-29 |  | N |  | 86% | 78% | 100% | 81% | 93% | 100%
Outdoor | Approach S12 | Pilot Run | Pilot Run Build Complete | 2020-12-08 | GMLA3 | 2020-12-01 | 2020-12-23 | 2020-12-23 | Ernest Fu | B->C | 80.14% | Y | N | Y | 2021-01-04 | 2021-01-04 |  | Sherry | 2021-01-11 | 2021-01-11 |  |  |  | 61% | 81% | 85% | 90% | 53% | 100%
Outdoor | Approach R10 | Pilot Run | Pilot Run Build Complete | 2020-12-18 | GMLA3 | 2020-12-11 | 2020-12-24 | 2020-12-24 | Chris Kuo | B->C | 84.4% | Y | N | Y | 2021-01-05 | 2021-01-04 |  | Robben Liu | 2021-01-11 | 2021-01-11 |  | N |  | 83% | 95% | 95% | 85% | 33% | 100%
Outdoor | fenix 7 | Factory Prototye | Factory Prototype Design Review | 2021-01-05 | GMLA2 | 2020-12-15 | 2020-12-29 | 2020-12-29 | Abner Tsai | A->B | 91.11% | Y | N | Y | 2021-01-08 | 2021-01-08 |  | Nixon Pan | 2021-01-15 | 2021-01-13 |  |  |  | 95% | 78% | 100% | 85% | 100% | 100%
Outdoor | fenix 7X | Factory Prototye | Factory Prototype Design Review | 2021-02-15 | GMLA2 | 2021-01-25 | 2020-12-30 | 2020-12-30 | Ernest Fu | B->C | 88.89% | Y | N | Y | 2021-01-11 | 2021-01-15 |  | Will Ma | 2021-01-22 | 2021-01-15 |  | N |  | 95% | 67% | 100% | 85% | 93% | 100%
Outdoor | Xero A1i PRO Bow Sight | Factory Prototye | Factory Prototype Design Review | 2021-03-30 | GMLA2 | 2021-03-09 | 2021-01-01 | 2021-01-01 | Chris Kuo | A->B | 92.59% | Y | N | Y | 2021-01-13 | 2021-01-11 |  | Lori Tsai | 2021-01-18 | 2021-01-18 |  |  |  | 86% | 78% | 100% | 96% | 93% | 100%
Automotive | Dash Cam Live (LTE) | Detailed Design | Mechanical Design Review | 2020-12-14 | GMLA1 | 2020-11-23 | 2021-01-06 | 2021-01-06 | Chris Kuo | A | 93.33% | Y | N | Y | 2021-01-18 | 2021-01-18 |  | Lori Tsai | 2021-01-25 | 2021-01-25 |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Marine | WDU Cost down (EmpirBus Low cost web server solution) | Detailed Design | Mechanical Design Review | 2021-02-03 | GMLA1 | 2021-01-13 |  | 2021-01-13 | Jason Hsu |  |  | - |  | N | 2021-01-25 |  | No G1 for this project. | Audon Peng | 1900-01-05
Fitness | Venu 2S | Pilot Run | Pilot Run Build Complete | 2020-11-30 | GMLA3 | 2020-11-23 | 2021-01-15 | 2021-01-15 | Ernest Fu | A->B | 91.49% | Y | N | Y | 2021-01-27 | 2021-01-27 |  | Alex | 2021-02-03 | 2021-02-02 |  |  |  | 100% | 100% | 92% | 92% | 60% | 100%
Marine | ECHOMAP UHD2 (Keyed) 5" | Detailed Design | Mechanical Design Review | 2021-02-02 | GMLA1 | 2021-01-12 | 2021-01-15 | 2021-01-15 | Jason Hsu | B | 86.67% | Y | N | Y | 2021-01-27 | 2021-01-27 |  | Ken Kuo | 2021-02-03 | 2021-02-01 |  |  |  | 75% | 100% | 100% | 75% | 100% | 100%
Marine | MSC-10 [Marine Satellite Compass] | Pilot Run | Pilot Run Build Complete | 2021-01-11 | GMLA3 | 2021-01-04 | 2021-01-20 | 2021-01-20 | Jason Hsu | A->B | 92.2% | Y | Y | Y | 2021-02-01 | 2021-02-01 |  | Ken Kuo | 2021-02-08 | 2021-02-06 |  |  |  | 100% | 71% | 100% | 90% | 100% | 89%
Fitness | Forerunner 55 | Factory Prototye | Factory Prototype Design Review | 2021-01-18 | GMLA2 | 2020-12-28 | 2021-01-21 | 2021-01-21 | Ernest Fu | B->C | 88.89% | Y | N | Y | 2021-02-02 | 2021-02-02 |  | Alex | 2021-02-09 | 2021-02-08 |  |  |  | 86% | 78% | 100% | 85% | 93% | 100%
Marine | Malibu Display | Pilot Run | Pilot Run Build Complete | 2021-01-18 | GMLA3 | 2021-01-11 | 2021-01-22 | 2021-01-22 | Jason Hsu | A | 90.78% | Y | N | Y | 2021-02-03 | 2021-02-03 |  | Ken Kuo | 2021-02-10 | 2021-02-06 |  |  |  | 94% | 100% | 97% | 90% | 53% | 100%
Marine | ECHOMAP UHD2 (Keyed) 7" | Detailed Design | Mechanical Design Review | 2021-02-02 | GMLA1 | 2021-01-12 | 2021-01-22 | 2021-01-22 | Jason Hsu | B | 86.67% | Y |  | Y | 2021-02-03 | 2021-02-01 |  | Chiencheng Huang | 2021-02-08 | 2021-02-04 |  |  |  | 75% | 100% | 100% | 75% | 100% | 100%
OEM Auto | DGCN20 | Pilot Run | Pilot Run Build Complete | 2021-01-11 | GMLA3 | 2021-01-04 | 2021-01-26 | 2021-01-26 | Arthur Yu | A->B | 95.83% | Y |  | Y | 2021-02-05 | 2021-02-23 |  | Nick Yen | 2021-03-02 | 2021-03-02 |  |  |  | 100% | 96% | 95% | 95% | 100% | 92%
Marine | FUSION - RA60 | Factory Prototye | Factory Prototype Design Review | 2021-02-09 | GMLA2 | 2021-01-19 | 2021-01-28 | 2021-01-28 | Jason Hsu | A->B | 92.59% | Y | N | Y | 2021-02-09 | 2021-02-06 |  | Ken Kuo | 2021-02-12 | 2021-02-08 |  |  |  | 100% | 94% | 96% | 90% | 80% | 100%
Fitness | Edge 1040 | Detailed Design | Mechanical Design Review | 2020-11-03 | GMLA1 | 2020-10-13 | 2021-02-05 | 2021-02-05 | Chris Kuo | A | 93.33% | Y | N | Y | 2021-02-24 | 2021-02-19 |  | Jack Chen | 2021-02-26 | 2021-02-19 |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Marine | Fusion - Apollo Amplifiers 1 / 4 channel (Tune Free Amplifiers) | Factory Prototye | Factory Prototype Design Review | 2021-05-06 | GMLA2 | 2021-04-15 | 2021-02-08 | 2021-02-08 | Jason Hsu | A | 93.33% | Y | N | Y | 2021-02-25 | 2021-02-08 | 從G2開始1/4和6/8分開兩個專案在PRWeb做GMLA評估，因為兩個專案生產有時間差。(1/4的較早) | Audon Peng | 2021-02-15 | 2021-02-08 |  | N |  | 100% | 94% | 100% | 83% | 100% | 100%
Fitness | Varia Core (One Battery Bike) | Pilot Run | Pilot Run Build Complete | 2021-01-29 | GMLA3 | 2021-01-22 | 2021-02-05 | 2021-02-05 | Jason Hsu | B->C | 81.56% | Y | N | Y | 2021-03-03 | 2021-03-03 |  | Nixon Pan | 2021-03-10 | 2021-03-05 |  |  |  | 78% | 90% | 72% | 85% | 80% | 100%
Marine | GPSMAP 79 Series | Detailed Design | Mechanical Design Review | 2021-01-14 | GMLA1 | 2020-12-24 | 2021-02-19 | 2021-02-19 | Jason Hsu | A | 93.33% | Y |  | Y | 2021-03-03 | 2021-03-03 |  | Jason Lee | 2021-03-10 | 2021-03-09 |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Outdoor | Approach Z20 (Approach Z50) | Detailed Design | Mechanical Design Review | 2020-11-11 | GMLA1 | 2020-10-21 | 2021-02-22 | 2021-02-22 | Chris Kuo | A | 97.78% | Y | N | Y | 2021-03-04 | 2021-03-03 |  | Robben Liu | 2021-03-10 | 2021-03-05 |  |  |  | 100% | 100% | 100% | 92% | 100% | 100%
Outdoor | Approach G12 | Pilot Run | Pilot Run Build Complete | 2021-02-04 | GMLA3 | 2021-01-28 | 2021-02-22 | 2021-02-22 | Chris Kuo | A | 98.58% | Y | N | Y | 2021-03-04 | 2021-03-04 |  | Sherry Shih | 2021-03-11 | 2021-03-10 |  |  |  | 100% | 100% | 100% | 95% | 100% | 100%
OEM Auto | PGWW20 | Pilot Run | Pilot Run Build Complete | 2021-03-02 | GMLA3 | 2021-02-23 |  | 2021-02-23 | Jack Yang |  |  | - |  | N | 2021-03-05 |  |  | Nick Yen | 1900-01-05
Outdoor | Descent S1 Buoy | Detailed Design | Mechanical Design Review | 2020-11-17 | GMLA1 | 2020-10-27 | 2021-02-26 | 2021-02-26 | Chris Kuo | A | 93.33% | Y | N | Y | 2021-03-10 | 2021-03-04 | [Chris] No FRM178 and WP build yet, change the date to 3/26 | Frank Chen | 2021-03-11 | 2021-03-04 |  | Y |  | 100% | 100% | 100% | 75% | 100% | 100%
Automotive | CamperVan | Pilot Run | Pilot Run Build Complete | 2021-02-09 | GMLA3 | 2021-02-02 | 2021-03-02 | 2021-03-02 |  |  |  | - |  | N | 2021-03-12 | - | This project uses existing Drive Smart 65 hardware and only with change of software. Hence, no need to have GMLA for this project. (confirmed with MPM) | Chiencheng Huang | #VALUE!
Fitness | Venu 2 Plus | Factory Prototye | Factory Prototype Design Review | 2021-03-18 | GMLA2 | 2021-02-25 | 2021-03-05 | 2021-03-05 | Cooper Wang | B->C | 85.19% | Y | N | Y | 2021-03-17 | 2021-03-17 |  | Alex | 2021-03-24 | 2021-03-24 |  |  |  | 76% | 83% | 83% | 83% | 100% | 100%
Marine | WDU Cost down (EmpirBus Low cost web server solution) | Factory Prototye | Factory Prototype Design Review | 2021-04-27 | GMLA2 | 2021-04-06 | 2021-03-08 | 2021-03-08 | Jason Hsu | A | 93.33% | Y |  | Y | 2021-03-18 | 2021-03-18 |  | Audon Peng | 2021-03-25 | 2021-03-25 |  |  |  | 71% | 100% | 88% | 100% | 100% | 100%
Outdoor | inReach Mini 2 | Detailed Design | Mechanical Design Review | 2021-03-16 | GMLA1 | 2021-02-23 | 2021-03-08 | 2021-03-08 | Chris Kuo | A | 100% | Y | N | Y | 2021-03-18 | 2021-03-17 |  | Robben Liu | 2021-03-24 | 2021-03-17 |  | n |  | 100% | 100% | 100% | 100% | 100% | 100%
OEM Auto | LWIN21 | Detailed Design | Mechanical Design Review | 2021-03-30 | GMLA1 | 2021-03-09 |  | 2021-03-09 | Ray Hu |  |  | - |  | N | 2021-03-19 |  | This is deriative project from LFIN, so no need to do GMLA analysis. | Not assigned | 1900-01-05
Fitness | Mercury | Pilot Run | Pilot Run Units Built | 2021-03-19 | GMLA3 | 2021-03-12 | No MPM | 2021-03-12 | Ernest Fu |  |  | - | - | N | 2021-03-24 |  |  | No MPM | 1900-01-05
Automotive | DriveSmart 66 | Factory Prototye | Factory Prototype Design Review | 2021-04-01 | GMLA2 | 2021-03-11 | 2021-03-12 | 2021-03-12 | Wendy Ni | A->B | 91.11% | Y | N | Y | 2021-03-24 | 2021-03-19 |  | Chiencheng Huang | 2021-03-26 | 2021-03-24 |  |  |  | 86% | 78% | 100% | 96% | 80% | 100%
Outdoor | EPIX (Gen 2) (原"Austin) | Factory Prototye | Factory Prototype Design Review | 2021-04-09 | GMLA2 | 2021-03-19 | 2021-03-17 | 2021-03-17 | Cooper Wang | Y | 84.44% | Y |  | Y | 2021-03-29 | 2021-03-29 | 原"Austin" | Nixon Pan | 2021-04-05 | 2021-04-05 |  |  |  | 100% | 83% | 88% | 69% | 100% | 100%
Outdoor | Descent G1 | Detailed Design | Mechanical Design Review | 2021-03-05 | GMLA1 | 2021-02-12 | 2021-03-17 | 2021-03-17 | Cooper Wang | G | 93.33% | Y | N | Y | 2021-03-29 | 2021-03-29 |  | Frank Chen | 2021-04-05 | 2021-04-05 |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Automotive | Drive 56 | Factory Prototye | Factory Prototype Design Review | 2021-04-01 | GMLA2 | 2021-03-11 | 2021-03-18 | 2021-03-18 | Wendy Ni |  |  | - | N | N | 2021-03-30 |  | 3/19 got information of project cancelled. | Chiencheng Huang | 1900-01-05
Fitness | NEO 2T Taiwan Production | Pilot Run | Pilot Run Build Complete | 2021-04-09 | GMLA3 | 2021-04-02 | 2021-03-19 | 2021-03-19 | Wendy Ni | R | 51.06% | Y |  | Y | 2021-03-31 | 2021-03-31 | MP product tranfered from Netherlands. | Lori Tsai | 2021-04-07 | 2021-04-07 |  |  |  | 33% | 86% | 38% | 69% | 40% | 0%
Automotive | DriveSmart 76 | Factory Prototye | Factory Prototype Design Review | 2021-03-12 | GMLA2 | 2021-02-19 | 2021-03-19 | 2021-03-19 | Jason Hsu | R | 91.11% | Y | N | Y | 2021-03-31 | 2021-03-31 |  | Nixon Pan | 2021-04-07 | 2021-04-07 |  |  |  | 86% | 67% | 100% | 94% | 100% | 100%
OEM Auto | LWIN21 | Factory Prototye | Factory Prototype Design Review | 2021-04-12 | GMLA2 | 2021-03-22 |  | 2021-03-22 | Ray Hu |  |  | - |  | N | 2021-04-01 |  | This is deriative project from LFIN, so no need to do GMLA analysis. | Not assigned | 1900-01-05
Marine | FUSION - RA60 | Pilot Run | Pilot Run Build Complete | 2021-03-19 | GMLA3 | 2021-03-12 | 2021-03-26 | 2021-03-26 | Jason Hsu | Y | 82.98% | Y | N | Y | 2021-04-07 | 2021-04-07 |  | Ken Kuo | 2021-04-14 | 2021-04-14 |  |  |  | 67% | 100% | 92% | 77% | 60% | 100%
Marine | Fusion - Apollo Amplifiers 6 / 8 channel (Tune Free Amplifiers) | Pilot Run | Pilot Run Build Complete | 2021-06-11 | GMLA3 | 2021-06-04 | 2021-06-22 | 2021-06-22 | Jason Hsu | Y | 85.11% | Y |  | Y | 2021-07-02 | 2021-06-23 | 從G2開始1/4和6/8分開兩個專案在PRWeb做GMLA評估，因為兩個專案生產有時間差。(1/4的較早 | Audon Peng | 2021-06-30 | 2021-07-12 |  |  |  | 86% | 88% | 100% | 77% | 60% | 100%
Fitness | Forerunner 955 and 955 Solar | Detailed Design | Mechanical Design Review | 2020-10-26 | GMLA1 | 2020-10-05 | 2021-03-29 | 2021-03-29 | Ernest Fu | G | 100% | Y | Y | Y | 2021-04-08 | 2021-04-07 |  | Alex chang | 2021-04-14 | 2021-04-15 |  |  |  | 100% | 100% | 92% | 100% | 100% | 100%
Automotive | DriveSmart 86 | Factory Prototye | Factory Prototype Design Review | 2021-04-01 | GMLA2 | 2021-03-11 | 2021-03-26 | 2021-03-26 | Jason Hsu | R | 91.11% | Y | N | Y | 2021-04-09 | 2021-04-09 | 4/2 & 4/5放假，due date往後延2天 | Nixon Pan | 2021-04-16 | 2021-04-13 |  |  |  | 86% | 83% | 100% | 88% | 100% | 100%
OEM Auto | LYWW20 | Pilot Run | Pilot Run Build Complete | 2021-02-25 | GMLA3 | 2021-02-18 | 2021-03-29 | 2021-03-29 | Cherry Tsai | Y | 91.07% | Y |  | Y | 2021-04-12 | 2021-04-09 |  | Nick Yen | 2021-04-16 | 2021-04-15 |  |  |  | 100% | 100% | 92% | 69% | 100% | 100%
Marine | FUSION - AP-DA214 (Zone Amplifier) | Factory Prototye | Factory Prototype Design Review | 2021-04-14 | GMLA2 | 2021-04-09 | 2021-04-01 | 2021-04-01 | Jason Hsu | Y | 86.67% | Y | N | Y | 2021-04-13 | 2021-04-13 |  | Lori Tsai | 2021-04-20 | 2021-04-20 |  |  |  | 100% | 67% | 100% | 75% | 100% | 100%
Fitness | Forerunner 55 | Pilot Run | Pilot Run Build Complete | 2021-02-24 | GMLA3 | 2021-02-17 | 2021-04-01 | 2021-04-01 | Ernest Fu | Y | 70.21% | Y | N | Y | 2021-04-13 | 2021-04-12 |  | Alex | 2021-04-19 | 2021-04-19 |  |  |  | 67% | 86% | 77% | 62% | 40% | 100%
Outdoor | fenix 7S | Pilot Run | Pilot Run Build Complete | 2021-03-12 | GMLA3 | 2021-03-30 | 2021-03-30 | 2021-03-30 | Cooper Wang | R | 76.6% | Y | N | Y | 2021-04-13 | 2021-04-13 | GMLA系統上因為日期計算問題，將close meeting date微調成4/1 (實際為3/30) | Frank Chen | 2021-04-20 | 2021-04-16 |  |  |  | 100% | 100% | 92% | 69% | 100% | 100%
Fitness | Forerunner 255 Small | Detailed Design | Mechanical Design Review | 2021-02-15 | GMLA1 | 2021-01-25 | 2021-04-07 | 2021-04-07 | Ernest Fu | G | 86.67% | Y |  | Y | 2021-04-19 | 2021-04-19 |  | Alex chang | 2021-04-26 | 2021-04-26 |  |  |  | 75% | 100% | 100% | 75% | 100% | 100%
Fitness | Forerunner 255 | Detailed Design | Mechanical Design Review | 2021-02-15 | GMLA1 | 2021-01-25 | 2021-04-07 | 2021-04-07 | Ernest Fu | G | 83.33% | Y |  | Y | 2021-04-19 | 2021-04-18 |  | Robben Liu | 2021-04-23 | 2021-04-21 |  |  |  | 75% | 100% | 100% | 75% | 100% | -
Marine | Fusion - Apollo Amplifiers 1 / 4 channel (Tune Free Amplifiers) | Pilot Run | Pilot Run Build Complete | 2021-06-10 | GMLA3 | 2021-06-03 | 2021-04-13 | 2021-04-13 | Jason Hsu | R | 78.72% | Y | N | Y | 2021-04-23 | 2021-04-26 | 從G2開始1/4和6/8分開兩個專案在PRWeb做GMLA評估，因為兩個專案生產有時間差。(1/4的較早 | Audon Peng | 2021-05-04 | 2021-05-04 |  |  |  | 50% | 86% | 85% | 85% | 60% | 100%
Marine | Lithium Battery (Ice Fishing) | Factory Prototye | Factory Prototype Design Review | 2021-05-06 | GMLA2 | 2021-04-15 |  | 2021-04-15 | Jason Hsu |  |  | - |  | N | 2021-04-27 |  | No G2 for this project. |  | 1900-01-05
Outdoor | Delta SE | Detailed Design | Mechanical Design Review | 2021-01-11 | GMLA1 | 2020-12-21 | 2021-04-19 | 2021-04-19 | Chris Kuo | G | 86.67% | y |  | y | 2021-04-29 | 2021-04-22 | No FRM178 build yet (先按照PR Web設定新的close meeting date，but MPM告知應該要3月初才會開CLOSE MEETING) 4/19招開DFM | Sherry Shih | 2021-04-29 | 2021-04-26 |  |  |  | 100% | 50% | 100% | 75% | 100% | 100%
Outdoor | Alpha 200 | Factory Prototye | Factory Prototype Design Review | 2021-04-23 | GMLA2 | 2021-04-19 |  | 2021-04-19 | Chris Kuo |  |  | - | N | N | 2021-04-29 |  | Same with Alpha 200i (iridium or not) | Will Ma | 1900-01-05
Fitness | vivomove Sport (previously "Lite") | Factory Prototye | Factory Prototype Design Review | 2021-05-11 | GMLA2 | 2021-04-20 | 2021-04-21 | 2021-04-21 | Ernest Fu | R | 60% | Y | N | Y | 2021-05-03 | 2021-05-03 |  | Sherry Shih | 2021-05-10 | 2021-05-10 |  |  |  | 71% | 17% | 75% | 56% | 60% | 100%
Outdoor | fenix 7 | Pilot Run | Pilot Run Build Complete | 2021-04-08 | GMLA3 | 2021-04-01 | 2021-04-23 | 2021-04-23 | Cooper Wang | R | 70.21% | Y | N | Y | 2021-05-05 | 2021-05-05 |  | Nixon Pan | 2021-05-12 | 2021-05-12 |  |  |  | 33% | 86% | 77% | 69% | 60% | 100%
Outdoor | Instinct 2 | Factory Prototye | Factory Prototype Design Review | 2021-04-30 | GMLA2 | 2021-04-16 | 2021-04-29 | 2021-04-29 | Cooper Wang | Y | 88.89% | Y | N | Y | 2021-05-11 | 2021-05-11 |  | Robben Liu | 2021-05-18 | 2021-05-18 |  |  |  | 86% | 100% | 100% | 81% | 80% | 100%
Automotive | Drive 56 | Pilot Run | Pilot Run Build Complete | 2021-05-06 | GMLA3 | 2021-04-29 |  | 2021-04-29 | Wendy Ni |  |  | - | N | N | 2021-05-11 | - |  | Chiencheng Huang | #VALUE!
Outdoor | Instinct 2S | Factory Prototye | Factory Prototype Design Review | 2021-04-30 | GMLA2 | 2021-04-16 | 2021-04-30 | 2021-04-30 | Cooper Wang | Y | 91.11% | Y | N | Y | 2021-05-12 | 2021-05-12 |  | Frank Chen | 2021-05-19 | 2021-05-19 |  |  |  | 86% | 83% | 100% | 88% | 100% | 100%
Marine | Fusion - Apollo Amplifiers 6 / 8 channel (Tune Free Amplifiers) | Factory Prototye | Factory Prototype Design Review | 2021-05-07 | GMLA2 | 2021-04-16 | 2021-05-03 | 2021-05-03 | Jason Hsu | R | 84.44% | Y |  | Y | 2021-05-13 | 2021-05-13 | 從G2開始1/4和6/8分開兩個專案在PRWeb做GMLA評估，因為兩個專案生產有時間差。(1/4的較早 | Audon Peng | 2021-05-20 | 2021-05-20 |  |  |  | 100% | 67% | 100% | 75% | 80% | 100%
Automotive | dezl watch | Factory Prototye | Factory Prototype Design Review | 2021-07-09 | GMLA2 | 2021-06-18 | 2021-05-04 | 2021-05-04 | Wendy Ni | Y | 88.64% | Y |  | Y | 2021-05-14 | 2021-05-14 |  | Robben Liu | 2021-05-21 | 2021-05-14 |  |  |  | 86% | 83% | 100% | 88% | 83% | 100%
Fitness | Bounce | Factory Prototye | Factory Prototype Design Review | 2021-04-27 | GMLA2 | 2021-04-06 | 2021-05-05 | 2021-05-05 | Ernest Fu | Y | 84.44% | Y | N | Y | 2021-05-17 | 2021-05-06 | Will have another FP build due to big change of APP development (new schedule will be informed by 2021/3/9) | Frank Chen | 2021-05-13 | 2021-05-12 |  |  |  | 71% | 83% | 100% | 75% | 100% | 100%
OEM Auto | WGCN21 | Pilot Run | Pilot Run Build Complete | 2021-05-17 | GMLA3 | 2021-05-10 |  | 2021-05-10 |  |  |  | - |  | N | 2021-05-20 |  | This is a software project for Venu 2/ Venu 2S, so no GMLA for this project. |  | 1900-01-05
Outdoor | fenix 7X | Pilot Run | Pilot Run Build Complete | 2021-04-20 | GMLA3 | 2021-04-13 | 2021-05-10 | 2021-05-10 | Cooper Wang | R | 78.72% | y | N | y | 2021-05-20 | 2021-05-20 |  | Sherry Shih | 2021-05-27 | 2021-05-27 |  |  |  | 71% | 50% | 92% | 85% | 80% | 100%
Fitness | vivosmart 5 (Franklin) | Detailed Design | Mechanical Design Review | 2021-02-19 | GMLA1 | 2021-01-29 | 2021-05-12 | 2021-05-12 | Ernest Fu | G | 75% | Y |  | Y | 2021-05-24 | 2021-05-17 |  | Nixon Pan | 2021-05-24 | 2021-05-20 |  |  |  | 75% | 50% | 100% | 75% | 100% | -
Marine | Surround View Camera System | Factory Prototye | Factory Prototype Design Review | 2021-07-01 | GMLA2 | 2021-06-10 | 2021-05-13 | 2021-05-13 | Jason Hsu | R | 79.55% | Y | N | Y | 2021-05-25 | 2021-05-25 |  | Ken Kuo | 2021-06-01 | 2021-05-31 |  |  |  | 71% | 100% | 63% | 75% | 100% | 100%
Marine | Marine Sensor Gateway (GSI-10) | Pilot Run | Pilot Run Build Complete | 2021-05-07 | GMLA3 | 2021-04-30 | 2021-05-14 | 2021-05-14 | Chris Kuo |  |  | - | N | N | 2021-05-26 |  | Same with GPSMAP black box |  | 1900-01-05
Outdoor | Alpha 200 | Pilot Run | Pilot Run Build Complete | 2021-05-25 | GMLA3 | 2021-05-18 |  | 2021-05-18 | Chris Kuo |  |  | - | N | N | 2021-05-28 |  | Same with Alpha 200i (iridium or not) | Will Ma | 1900-01-05
Marine | GC 300 (PTZ) Camera | Detailed Design | Mechanical Design Review | 2021-06-09 | GMLA1 | 2021-05-19 |  | 2021-05-19 | Jason Hsu |  |  | - | N | N | 2021-05-31 |  | Confirmed with MPM that no need to to do GMLA for this product |  | 1900-01-05
Automotive | Dezl Headset | Detailed Design | Mechanical Design Review | 2021-02-01 | GMLA1 | 2021-01-11 | 2021-05-19 | 2021-05-19 | Wendy Ni | G | 91.67% | Y |  | Y | 2021-05-31 | 2021-05-25 | G1應該會在5月開始 | Lori Tsai | 2021-06-01 | 2021-05-28 |  |  |  | 75% | 100% | 100% | 100% | 100% | -
OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | Detailed Design | Mechanical Design Review | 2020-12-28 | GMLA1 | 2020-12-07 | 2021-05-21 | 2021-05-21 | Ray Hu | G | 88.24% | Y |  | Y | 2021-06-02 | 2021-06-01 |  | Nick Yen | 2021-06-08 | 2021-06-02 |  |  |  | 75% | 67% | 100% | 100% | 100% | 100%
Marine | FUSION - AP-DA214 (Zone Amplifier) | Pilot Run | Pilot Run Build Complete | 2021-05-14 | GMLA3 | 2021-05-07 | 2021-05-25 | 2021-05-25 | Jason Hsu | Y | 91.49% | Y | N | Y | 2021-06-04 | 2021-06-01 |  | Lori Tsai | 2021-06-08 | 2021-06-02 |  |  |  | 100% | 88% | 100% | 77% | 100% | 100%
Marine | Lithium Battery (Ice Fishing) | Pilot Run | Pilot Run Build Complete | 2021-07-02 | GMLA3 | 2021-06-25 |  | 2021-06-25 | Jason Hsu |  |  | - |  | N | 2021-07-07 |  | No G3 for this project. |  | 1900-01-05
Automotive | BC50 and BC50 IR | Detailed Design | Mechanical Design Review | 2021-01-05 | GMLA1 | 2020-12-15 | 2021-06-10 | 2021-06-10 | Chris Kuo | G | 91.67% | Y | N | Y | 2021-06-22 | 2021-06-15 | The close meeting is for WP2. | Chienchen Huang | 2021-06-22 |  |  |  |  | 100% | 33% | 75% | 69% | 83% | 100%
Fitness | Bounce | Pilot Run | Pilot Run Build Complete | 2021-04-30 | GMLA3 | 2021-04-23 | 2021-07-01 | 2021-07-01 | Ernest Fu | Y | 82.98% | Y | N | Y | 2021-07-13 | 2021-07-12 | Kid Tracker LTE Smartwatch | Frank Chen | 2021-07-19 | 2021-07-19 |  |  |  | 57% | 100% | 100% | 77% | 60% | 100%
Marine | WDU Cost down (EmpirBus Low cost web server solution) | Pilot Run | Pilot Run Build Complete | 2021-06-02 | GMLA3 | 2021-05-26 | 2021-06-04 | 2021-06-04 | Jason Hsu | Y | 87.23% | Y |  | Y | 2021-06-16 | 2021-06-16 |  | Audon Peng | 2021-06-23 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | -
Marine | GPSMAP 79 Series | Factory Prototye | Factory Prototype Design Review | 2021-06-15 | GMLA2 | 2021-05-25 | 2021-06-04 | 2021-06-04 | Jason Hsu | R | 84.09% | Y |  | Y | 2021-06-16 | 2021-06-16 |  | Leo Chen | 2021-06-23 |  |  |  |  | 71% | 88% | 100% | 85% | 80% | 100%
Automotive | DriveSmart 66 | Pilot Run | Pilot Run Build Complete | 2021-05-06 | GMLA3 | 2021-04-29 | 2021-06-16 | 2021-06-16 | Wendy Ni | R | 82.98% | Y | N | Y | 2021-06-28 | 2021-06-22 |  | Chiencheng Huang | 2021-06-29 |  |  |  |  | 86% | 63% | 100% | 85% | 60% | 100%
Outdoor | Xero A1i PRO Bow Sight | Pilot Run | Pilot Run Build Complete | 2021-06-21 | GMLA3 | 2021-06-14 | 2021-07-05 | 2021-07-05 | Chris Kuo | Y | 89.36% | Y | N | Y | 2021-07-15 | 2021-07-15 |  | Lori Tsai | 2021-07-22 | 2021-07-22 |  |  |  | 100% | 88% | 92% | 92% | 60% | 100%
Outdoor | inReach Mini 2 | Factory Prototye | Factory Prototype Design Review | 2021-07-08 | GMLA2 | 2021-06-17 | 2021-06-16 | 2021-06-16 | Chris Kuo | R | 81.82% | Y | N | Y | 2021-06-28 | 2021-06-25 |  | Robben Liu | 2021-07-02 |  |  |  |  | 100% | 67% | 88% | 75% | 83% | 100%
Marine | Surround View Camera System | Pilot Run | Pilot Run Build Complete | 2021-08-06 | GMLA3 | 2021-07-30 | 2021-08-20 | 2021-08-20 | Jason Hsu | R | 76.6% | Y | N | Y | 2021-09-01 | 2021-09-01 |  | Ken Kuo | 2021-09-08 |  |  |  |  | 57% | 88% | 92% | 69% | 60% | 100%
Marine | GMR Fantom 18x/24x | Factory Prototye | Factory Prototype Design Review | 2021-06-09 | GMLA2 | 2021-05-19 | 2021-06-10 | 2021-06-10 | Jason Hsu | R | 72.73% | Y | N | Y | 2021-06-22 | 2021-06-22 |  | Audon Peng | 2021-06-29 |  |  |  |  | 86% | 63% | 100% | 69% | 80% | 100%
OEM Auto | LWIN21 | Pilot Run | Pilot Run Build Complete | 2021-06-21 | GMLA3 | 2021-06-14 |  | 2021-06-14 | Ray Hu |  |  | - |  | N | 2021-06-24 |  | This is deriative project from LFIN, so no need to do GMLA analysis. | Not assigned | 1900-01-05
Automotive | DriveSmart 76 | Pilot Run | Pilot Run Build Complete | 2021-04-16 | GMLA3 | 2021-04-09 | 2021-06-14 | 2021-06-14 | Wendy Ni | R | 78.72% | Y | N | Y | 2021-06-24 | 2021-06-22 |  | Nixon Pan | 2021-06-29 | 2021-07-01 |  |  |  | 86% | 63% | 100% | 77% | 40% | 100%
Outdoor | inReach Messenger | Detailed Design | Mechanical Design Review | 2021-08-27 | GMLA1 | 2021-08-06 | 2021-08-23 | 2021-08-23 | Chris Kuo | G | 83.33% | Y |  | Y | 2021-09-02 | 2021-09-02 |  | Not assigned yet | 2021-09-09 |  |  |  |  | 100% | 50% | 100% | 75% | 100% | 0%
Marine | GC 300 (PTZ) Camera | Pilot Run | Pilot Run Build Complete | 2021-08-31 | GMLA3 | 2021-08-24 |  | 2021-08-24 | Jason Hsu |  |  | - | N | N | 2021-09-03 |  | Confirmed with MPM that no need to to do GMLA for this product |  | 1900-01-05
Automotive | Tread Audio System | Detailed Design | Mechanical Design Review | 2021-04-14 | GMLA1 | 2021-03-24 | 2021-06-17 | 2021-06-17 | Wendy Ni | G | 100% | Y |  | Y | 2021-06-29 | 2021-06-21 |  | Ken Kuo/ Tim Wu | 2021-06-28 |  |  |  |  | 71% | 83% | 88% | 81% | 100% | 100%
Outdoor | Descent G1 | Factory Prototye | Factory Prototype Design Review | 2021-05-28 | GMLA2 | 2021-05-07 | 2021-06-17 | 2021-06-17 | Cooper Wang | R | 93.18% | Y | N | Y | 2021-06-29 | 2021-06-29 |  | Frank Chen | 2021-07-06 |  |  |  |  | 100% | 83% | 100% | 88% | 100% | 100%
Automotive | DriveSmart 86 | Pilot Run | Pilot Run Build Complete | 2021-05-06 | GMLA3 | 2021-04-29 | 2021-06-11 | 2021-06-11 | Jason Hsu | R | 80.85% | Y | N | Y | 2021-06-23 | 2021-06-23 |  | Nixon Pan | 2021-06-30 | 2021-06-30 |  |  |  | 100% | 100% | 100% | 100% | 100% | -
Automotive | Tread XL - Baja Race Edition | Factory Prototye | Factory Prototype Design Review | 2021-06-18 | GMLA2 | 2021-05-28 | 2021-08-26 | 2021-08-26 | Jason Hsu | R | 86.36% | Y |  | Y | 2021-09-07 | 2021-09-07 | PRWeb name: Tread - XL (10") | Leo Chen | 2021-09-14 | 2021-09-09 |  |  |  | 100% | 67% | 88% | 81% | 100% | 100%
Outdoor | Instinct 2 | Pilot Run | Pilot Run Build Complete | 2021-06-28 | GMLA3 | 2021-06-21 | 2021-07-06 | 2021-07-06 | Cooper Wang | R | 80.85% | Y | N | Y | 2021-07-16 | 2021-07-15 |  | Robben Liu | 2021-07-22 | 2021-07-22 |  |  |  | 86% | 88% | 77% | 77% | 80% | 100%
Automotive | Tread XL - Overland Edition | Factory Prototye | Factory Prototype Design Review | 2021-08-13 | GMLA2 | 2021-07-23 | 2021-08-26 | 2021-08-26 | Jason Hsu | R | 86.36% | Y | N | Y | 2021-09-07 | 2021-09-07 | PRWeb name: Tread - XL (10") | Leo Chen | 2021-09-14 | 2021-09-09 |  |  |  | 100% | 67% | 88% | 81% | 100% | 100%
Fitness | Tacx NEO Bike Plus | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | 2021-07-09 | 2021-07-09 | Chris Kuo | G | 75% | Y |  | Y | 2021-07-21 | 2021-07-19 |  | Frank Chen | 2021-07-26 | ? |  |  |  | 50% | 100% | 100% | 75% | 100% | 0%
Outdoor | Instinct 2S | Pilot Run | Pilot Run Build Complete | 2021-07-05 | GMLA3 | 2021-06-28 | 2021-07-14 | 2021-07-14 | Cooper Wang | R | 76.6% | Y | N | Y | 2021-07-26 | 2021-07-26 |  | Frank Chen | 2021-08-02 |  |  |  |  | 86% | 63% | 77% | 77% | 80% | 100%
Automotive | Tread - Overland Edition | Factory Prototye | Factory Prototype Design Review | 2021-07-02 | GMLA2 | 2021-06-11 | 2021-07-14 | 2021-07-14 | Wendy Ni | R | 81.82% | Y | N | Y | 2021-07-26 | 2021-07-26 | PRWeb name: Tread 8" | Lori Tsai | 2021-08-02 |  |  |  |  | 86% | 50% | 88% | 88% | 83% | 100%
Automotive | Tread - SXS Edition | Factory Prototye | Factory Prototype Design Review | 2021-07-02 | GMLA2 | 2021-06-11 | 2021-07-14 | 2021-07-14 | Wendy Ni | R | 81.82% | Y | N | Y | 2021-07-26 | 2021-07-26 | 原為Tread 8" (PRWeb name: Tread 8" ) | Lori Tsai | 2021-08-02 |  |  |  |  | 86% | 50% | 88% | 88% | 83% | 100%
Marine | GPSMAP 79 Series | Pilot Run | Pilot Run Build Complete | 2021-07-23 | GMLA3 | 2021-07-16 | 2021-08-27 | 2021-08-27 | Jason Hsu | R | 80.85% | Y |  | Y | 2021-09-08 | 2021-09-08 |  | Leo Chen | 2021-09-15 | 2021-09-10 |  |  |  | 71% | 75% | 92% | 77% | 80% | 100%
Fitness | Varia Radar Camera (RCT715) | Factory Prototye | Factory Prototype Design Review | 2021-09-15 | GMLA2 | 2021-08-25 | 2021-08-30 | 2021-08-30 | Chris Kuo | Y | 86.36% | Y | N | Y | 2021-09-09 | 2021-09-09 |  | Sherry Shih | 2021-09-16 | 2021-09-16 |  |  |  | 86% | 83% | 100% | 81% | 83% | 100%
Fitness | Venu 2 Plus | Pilot Run | Pilot Run Build Complete | 2021-05-11 | GMLA3 | 2021-05-04 | 2021-07-19 | 2021-07-19 | Cooper Wang | Y | 89.36% | Y | N | Y | 2021-07-29 | 2021-07-29 |  | Alex | 2021-08-05 |  |  |  |  | 86% | 88% | 100% | 85% | 80% | 100%
Marine | LiveScope Plus (LVS34) | Detailed Design | Mechanical Design Review | 2021-07-21 | GMLA1 | 2021-06-30 | 2021-07-22 | 2021-07-22 | Jason Hsu | G | 91.67% | Y |  | Y | 2021-08-03 | 2021-07-29 | Original name: Panoptix LiveScope HD (LVS34HD Transducer) | Ryan Li | 2021-08-05 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Marine | GMR Fantom 18x/24x | Pilot Run | Pilot Run Build Complete | 2021-07-22 | GMLA3 | 2021-07-15 | 2021-09-03 | 2021-09-03 | Jason Hsu | Y | 89.36% | Y | N | Y | 2021-09-15 | 2021-09-14 |  | Jack Chen | 2021-09-21 | 2021-09-17 |  |  |  | 100% | 88% | 92% | 85% | 80% | 100%
Marine | LiveScope XR (LVS62) | Detailed Design | Mechanical Design Review | 2021-08-04 | GMLA1 | 2021-07-14 | 2021-07-23 | 2021-07-23 | Jason Hsu | G | 100% | Y |  | Y | 2021-08-04 | 2021-07-29 | Original name: LiveScope XR - New Transducer | Ryan Li | 2021-08-05 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100%
Marine | ECHOMAP UHD2 (Keyed) 5" | Factory Prototye | Factory Prototype Design Review | 2021-09-10 | GMLA2 | 2021-08-20 | 2021-09-08 | 2021-09-08 | Jason Hsu | Y | 90.91% | Y | N | Y | 2021-09-22 | 2021-09-22 |  | Ken Kuo | 2021-09-29 |  |  |  |  | 100% | 83% | 100% | 81% | 100% | 100%
Marine | GC 300 (PTZ) Camera | Factory Prototye | Factory Prototype Design Review | 2021-08-25 | GMLA2 | 2021-08-04 |  | 2021-08-04 | Jason Hsu |  |  | - | N | N | 2021-08-16 |  | Confirmed with MPM that no need to to do GMLA for this product |  | 1900-01-05
Marine | ECHOMAP UHD2 (Keyed) 7" | Factory Prototye | Factory Prototype Design Review | 2021-09-10 | GMLA2 | 2021-08-20 | 2021-09-10 | 2021-09-10 | Jason Hsu | Y | 88.64% | Y |  | Y | 2021-09-22 | 2021-09-22 |  | Ken Kuo | 2021-09-29 |  |  |  |  | 100% | 83% | 88% | 81% | 100% | 100%
Fitness | vivomove Sport (previously "Lite") | Pilot Run | Pilot Run Build Complete | 2021-08-09 | GMLA3 | 2021-08-02 | 2021-09-11 | 2021-09-11 | Ernest Fu | R | 70.21% | Y | Y | Y | 2021-09-23 | 2021-09-23 | 9/27 modify | Sherry Shih | 2021-09-30 |  |  |  |  | 57% | 88% | 77% | 69% | 40% | 100%
Marine | BlueNET Gateway | Detailed Design | Mechanical Design Review | 2021-08-25 | GMLA1 | 2021-08-04 | 2021-09-20 | 2021-09-20 | Chris Kuo | G | 91.67% | Y | N | Y | 2021-09-30 | 2021-09-23 |  | Chiencheng Huang/ Tim Wu | 2021-09-30 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | 0%
Marine | BlueNET Switch | Detailed Design | Mechanical Design Review | 2021-10-15 | GMLA1 | 2021-09-24 | 2021-09-20 | 2021-09-20 | Chris Kuo | G | 91.67% | Y | N | Y | 2021-09-30 | 2021-09-23 |  | Chiencheng Huang | 2021-09-30 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | 0%
Outdoor | Xero G1(s) SatCom Scouting Camera | Pilot Run | Pilot Run Build Complete | 2021-08-13 | GMLA3 | 2021-08-06 | 2021-09-21 | 2021-09-21 | Chris Kuo | R | 78.72% | Y | N | Y | 2021-10-01 | 2021-08-12 |  | CC | 2021-08-19 |  |  |  |  | 86% | 63% | 100% | 69% | 60% | 100%
OEM Auto | BMW MGU22-RSE | Pilot Run | Pilot Run Build Complete | 2021-04-21 | GMLA3 | 2021-04-14 | 2021-09-24 | 2021-09-24 | Ray Hu | Y | 91.07% | Y |  | Y | 2021-10-06 | 2021-10-19 |  | Sandy Lee | 2021-10-26 |  |  |  |  | 50% | 100% | 100% | 92% | 88% | 100%
Outdoor | EPIX (Gen 2) (原"Austin) | Pilot Run | Pilot Run Build Complete | 2021-09-07 | GMLA3 | 2021-08-31 | 2021-09-24 | 2021-09-24 | Cooper Wang | R | 91.49% | Y |  | Y | 2021-10-06 | 2021-10-01 | 原"Austin" | Nixon Pan | 2021-10-08 |  |  |  |  | 86% | 100% | 100% | 92% | 60% | 100%
Outdoor | Descent G1 | Pilot Run | Pilot Run Build Complete | 2021-09-17 | GMLA3 | 2021-09-10 | 2021-10-01 | 2021-10-01 | Cooper Wang | R | 78.72% | Y | N | Y | 2021-10-13 | 2021-10-13 |  | Frank Chen | 2021-10-20 |  |  |  |  | 57% | 75% | 85% | 92% | 60% | 100%
Outdoor | inReach Mini 2 | Pilot Run | Pilot Run Build Complete | 2021-09-15 | GMLA3 | 2021-09-08 | 2021-10-01 | 2021-10-01 | Chris Kuo | R | 82.98% | Y | N | Y | 2021-10-13 | 2021-10-12 |  | Robben Liu | 2021-10-19 |  |  |  |  | 71% | 75% | 100% | 92% | 40% | 100%
OEM Auto | BMW MGU22_PL1 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | James Huang/ Allen Chen/ Valentina |  |  | N |  | N | #NUM! |  | Project in Poland |  | 1900-01-05
Automotive | dezl watch | Pilot Run | Pilot Run Build Complete | 2021-09-30 | GMLA3 | 2021-09-23 | 2021-10-08 | 2021-10-08 | Wendy Ni | Y | 85.11% | Y |  | Y | 2021-10-20 | 2021-10-20 |  | Robben Liu | 2021-10-27 |  |  |  |  | 86% | 88% | 100% | 77% | 60% | 100%
OEM Auto | BMW MGU22_PL1 | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | James Huang/ Allen Chen/ Valentina |  |  | N |  | N | #NUM! |  | Project in Poland |  | 1900-01-05
OEM Auto | BMW MGU22_PL1 | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | James Huang/ Allen Chen/ Valentina |  |  | N |  | N | #NUM! |  | Project in Poland |  | 1900-01-05
OEM Auto | TXTW22_Drive+3.0 (Taroko)-12.3 DA | Detailed Design | Mechanical Design Review | 2020-12-28 | GMLA1 | 2020-12-07 | 2021-10-14 | 2021-10-14 | Ray Hu | G | 100% | Y |  | Y | 2021-10-26 | 2021-10-22 |  | Nick Yen | 2021-10-29 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100%
Fitness | Venu Sq 2 | Detailed Design | Mechanical Design Review |  | GMLA1 | 2021-10-14 | 2021-10-14 | 2021-10-14 | Aalto Lo | G | 97.67% | Y |  | N | 2021-10-26 | 2021-10-26 |  | Jack Chen | 2021-11-02 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | -
Automotive | Tread - Overland Edition | Pilot Run | Pilot Run Build Complete | 2021-08-19 | GMLA3 | 2021-08-12 | 2021-10-22 | 2021-10-22 | Wendy Ni | R | 74.47% | Y | N | N | 2021-11-03 | 2021-10-29 |  | Leo Chen | 2021-11-05 |  |  |  |  | 57% | 63% | 92% | 77% | 60% | 100%
Automotive | Dezl Headset | Factory Prototye | Factory Prototype Design Review | 2021-11-09 | GMLA2 | 2021-10-19 | 2021-11-10 | 2021-11-10 | Wendy Ni | R | 84.09% | Y |  | N | 2021-11-22 | 2021-11-18 |  | Lori Tsai | 2021-11-25 |  |  |  |  | 100% | 50% | 100% | 81% | 83% | 100%
Fitness | vivosmart 5 (Franklin) | Factory Prototye | Factory Prototype Design Review | 2021-10-20 | GMLA2 | 2021-09-29 | 2021-10-08 | 2021-10-08 | Ernest Fu | R | 84.09% | Y |  | Y | 2021-10-20 | 2021-10-18 |  | Nixon Pan | 2021-10-25 |  |  |  |  | 100% | 67% | 75% | 81% | 100% | 100%
Automotive | dezlCam OTR710 & RV 795 | Detailed Design | Mechanical Design Review | 2021-07-29 | GMLA1 | 2021-07-23 | 2021-10-08 | 2021-10-08 | Wendy Ni | G | 91.67% | Y |  | Y | 2021-10-20 | 2021-10-08 |  | Tim Wu | 2021-10-15 | 2021-10-13 |  |  |  | 100% | 100% | 100% | 75% | 100% | 0%
Fitness | vivomove Trend (previously "4") | Detailed Design | Mechanical Design Review | 2021-10-15 | GMLA1 | 2021-09-24 | 2021-10-12 | 2021-10-12 | Ernest Fu | G | 83.33% | Y |  | Y | 2021-10-22 | 2021-10-22 |  | Sherry Shih | 2021-10-29 |  |  |  |  | 75% | 100% | 100% | 75% | 100% | -
Marine | GST - Connect 70 | Pilot Run | Pilot Run Build Complete | On hold | GMLA3 | #VALUE! |  | #VALUE! | Jason Hsu |  |  | N | N | N | #VALUE! |  | Project cancelled | Audon Peng | 1900-01-05
Marine | quatix 7 | Factory Prototye | Factory Prototype Design Review | 2021-12-02 | GMLA2 | 2021-11-11 |  | 2021-11-11 | Jason Hsu |  |  | N |  | N | 2021-11-23 |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Outdoor | Alpha Dog Collar | Detailed Design | Working Prototype Built | 2021-07-30 | GMLA1 | 2021-07-09 | 2021-10-12 | 2021-10-12 | Chris Kuo | A | 92.59% | Y | Y | N | 2021-10-22 | 2020-01-21 |  | Robben Liu | 2020-01-28 | 2020-01-28 | Design delay |  |  | 75% | 100% | 100% | 89% | 100% | -
Automotive | Tread - SXS Edition | Pilot Run | Pilot Run Build Complete | 2021-09-16 | GMLA3 | 2021-09-09 | 2021-10-22 | 2021-10-22 | Wendy Ni | R | 74.47% | Y | N | N | 2021-11-03 | 2021-10-29 | 原為Tread 8" | Lori Tsai | 2021-11-05 |  |  |  |  | 57% | 63% | 92% | 77% | 60% | 100%
Marine | LiveScope Plus (LVS34) | Factory Prototye | Factory Prototype Design Review | 2021-11-25 | GMLA2 | 2021-11-04 | 2021-11-11 | 2021-11-11 | Jason Hsu | Y | 86.36% | Y |  | N | 2021-11-23 | 2021-11-23 | Original name: Panoptix LiveScope HD (LVS34HD Transducer) | Ryan Li | 2021-11-30 |  |  |  |  | 100% | 83% | 75% | 81% | 100% | 100%
Automotive | dezl OTR Series 2022- 6" | Detailed Design | Mechanical Design Review | 2021-09-14 | GMLA1 | 2021-08-24 | 2021-10-25 | 2021-10-25 | Wendy Ni | G | 100% | Y |  | N | 2021-11-04 | 2021-11-01 | DFM meeting is estimate to be around 10/E~11/B. | Stephanie Yang | 2021-11-08 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | -
Automotive | dezl OTR Series 2022- 7" | Detailed Design | Mechanical Design Review | 2021-09-14 | GMLA1 | 2021-08-24 | 2021-10-25 | 2021-10-25 | Wendy Ni | G | 100% | Y |  | N | 2021-11-04 | 2021-11-02 | DFM meeting is estimate to be around 10/E~11/B. | Stephanie Yang | 2021-11-09 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | -
Automotive | dezl OTR Series 2022- 10" | Detailed Design | Mechanical Design Review | 2021-11-04 | GMLA1 | 2021-10-14 | 2021-11-17 | 2021-11-17 | Wendy Ni | G | 91.67% | Y |  | N | 2021-11-29 | 2021-11-17 | DFM meeting is estimate to be around 10/E~11/B. | Stephanie Yang | 2021-11-24 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | -
Outdoor | Approach R50 | Detailed Design | Mechanical Design Review | 2021-07-12 | GMLA1 | 2021-06-21 | 2021-12-06 | 2021-12-06 | Chris Kuo | G | 91.67% | Y | N | Y | 2021-12-16 | 2021-12-07 |  | Nixon Pan | 2021-12-14 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | 0%
Automotive | dezl OTR Series 2022- 8" | Detailed Design | Mechanical Design Review | 2021-09-14 | GMLA1 | 2021-08-24 | 2021-11-17 | 2021-11-17 | Wendy Ni | G | 91.67% | Y |  | N | 2021-11-29 | 2021-11-17 | DFM meeting is estimate to be around 10/E~11/B. | Stephanie Yang | 2021-11-24 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | -
Outdoor | Delta SE | Factory Prototye | Factory Prototype Design Review | 2021-11-30 | GMLA2 | 2021-11-09 | 2021-11-22 | 2021-11-22 | Chris Kuo | R | 90.91% | Y |  | N | 2021-12-02 | 2021-12-02 |  | Sherry Shih | 2021-12-09 |  |  |  |  | 86% | 67% | 100% | 94% | 100% | 100%
Automotive | Tread Audio System | Factory Prototye | Factory Prototype Design Review | 2021-12-22 | GMLA2 | 2021-12-01 | 2021-12-24 | 2021-12-24 | Wendy Ni | Y | 88.64% | Y |  | N | 2022-01-05 | 2022-01-05 |  | Ken Kuo/ Tim Wu | 2022-01-12 |  |  |  |  | 100% | 83% | 88% | 81% | 100% | 100%
Marine | GHC 50 | Factory Prototye | Factory Prototype Design Review | 2021-11-19 | GMLA2 | 2021-10-29 |  | 2021-10-29 | Jason Hsu |  |  | N |  | N | 2021-11-10 |  |  | Ken Kuo | 1900-01-05
Outdoor | Instinct Crossover | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | 2021-10-29 | 2021-10-29 | Aalto Lo | G | 75% | Y |  | N | 2021-11-10 | 2021-11-08 |  | Anson Lu | 2021-11-15 |  |  |  |  | 75% | 100% | 100% | 50% | 100% | -
Marine | quatix 7 | Pilot Run | Pilot Run Build Complete | 2022-01-07 | GMLA3 | 2021-12-31 |  | 2021-12-31 | Jason Hsu |  |  | N |  | N | 2022-01-12 |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Automotive | BC50 and BC50 IR | Factory Prototye | Factory Prototype Design Review | 2021-11-22 | GMLA2 | 2021-11-01 | 2021-11-23 | 2021-11-23 | Chris Kuo | Y | 88.64% | Y | N | N | 2021-12-03 | 2021-12-03 |  | Leo Chen | 2021-12-10 |  |  |  |  | 86% | 67% | 100% | 88% | 100% | 100%
Marine | GPSMAP 9000 - 22" | Detailed Design | Mechanical Design Review | 2022-03-30 | GMLA1 | 2022-03-09 | 2021-11-25 | 2021-11-25 | Jason Hsu | G | 75% | Y |  | N | 2021-12-07 | 2021-12-07 |  | Nick Yen | 2021-12-14 |  |  |  |  | 50% | 100% | 100% | 75% | 100%
Marine | ECHOMAP UHD2 (Touch) 6" | Detailed Design | Mechanical Design Review | 2021-12-03 | GMLA1 | 2021-11-12 | 2021-12-01 | 2021-12-01 | Jason Hsu | G | 91.67% | Y |  | N | 2021-12-13 | 2021-12-13 |  | Lori Tsai/ Stephanie Yang | 2021-12-20 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Marine | ECHOMAP UHD2 (Touch) 6" | Factory Prototye | Factory Prototype Design Review | 2022-06-21 | GMLA2 | 2022-05-31 |  | 2022-05-31 | Jason Hsu |  |  | N |  | N | 2022-06-10 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Fitness | Forerunner 955 and 955 Solar | Factory Prototye | Factory Prototype Design Review | 2021-11-04 | GMLA2 | 2021-10-14 | 2021-11-05 | 2021-11-05 | Ernest Fu | R | 79.55% | Y |  | N | 2021-11-17 | 2021-11-15 |  | Alex chang | 2021-11-22 |  |  |  |  | 86% | 67% | 75% | 81% | 83% | 100%
Fitness | Edge 1040 | Factory Prototye | Factory Prototype Design Review | 2021-11-15 | GMLA2 | 2021-10-25 | 2021-11-05 | 2021-11-05 | Chris Kuo | R | 79.55% | Y | N | N | 2021-11-17 | 2021-11-16 |  | Jack Chen | 2021-11-23 |  |  |  |  | 100% | 50% | 88% | 69% | 100% | 100%
Automotive | Tread XL - Overland Edition | Pilot Run | Pilot Run Build Complete | 2021-10-21 | GMLA3 | 2021-10-14 | 2021-11-05 | 2021-11-05 | Jason Hsu | R | 82.98% | Y | N | N | 2021-11-17 | 2021-11-17 | 原為Overlander 10" | Leo Chen | 2021-11-24 |  |  |  |  | 86% | 75% | 92% | 77% | 80% | 100%
Marine | ECHOMAP UHD2 (Touch) 6" | Pilot Run | Pilot Run Build Complete | 2022-08-15 | GMLA3 | 2022-08-08 |  | 2022-08-08 | Jason Hsu |  |  | N |  |  | 2022-08-18 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Marine | FUSION - WB675 Hide Away Stereo | Factory Prototye | Factory Prototype Design Review | 2021-12-08 | GMLA2 | 2021-11-17 |  | 2021-11-17 | Jason Hsu |  |  | N |  | N | 2021-11-29 |  |  | Not assigned yet | 1900-01-05
OEM Auto | IMWW23 | Detailed Design | Mechanical Design Review | 2021-11-24 | GMLA1 | 2021-11-03 | 2021-12-02 | 2021-12-02 | Cherry Tsai | G | 92.86% | Y |  | N | 2021-12-14 | 2021-12-14 |  | Nick Yen | 2021-12-21 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Marine | LiveScope XR (LVS62) | Factory Prototye | Factory Prototype Design Review | 2021-12-08 | GMLA2 | 2021-11-17 | 2021-12-03 | 2021-12-03 | Jason Hsu | R | 79.55% | Y |  | Y | 2021-12-15 | 2021-12-06 | Original name: LiveScope XR - New Transducer | Ryan Li | 2021-12-13 |  |  |  |  | 86% | 67% | 75% | 75% | 100% | 100%
Fitness | Varia Radar Camera (RCT715) | Pilot Run | Pilot Run Build Complete | 2021-11-26 | GMLA3 | 2021-11-19 | 2021-12-08 | 2021-12-08 | Chris Kuo | R | 85.11% | Y | N | N | 2021-12-20 | 2021-12-20 |  | Sherry Shih | 2021-12-27 |  |  |  |  | 86% | 75% | 100% | 85% | 60% | 100%
OEM Auto | IXWW22 | Factory Prototye | Factory Prototype Design Review | 2021-12-22 | GMLA2 | 2021-12-01 | 2021-12-08 | 2021-12-08 | Cherry Tsai | Y | 96.43% | y |  | N | 2021-12-20 | 2021-12-20 |  | Nick Yen | 2021-12-27 |  |  |  |  | 100% | 88% | 100% | 100% | 100% | 100%
Fitness | Forerunner 255 | Factory Prototye | Factory Prototype Design Review | 2021-12-03 | GMLA2 | 2021-11-12 | 2021-12-10 | 2021-12-10 | Ernest Fu | R | 88.64% | Y |  | N | 2021-12-22 | 2021-12-21 |  | Robben Liu | 2021-12-28 |  |  |  |  | 86% | 83% | 88% | 88% | 100% | 100%
Automotive | RV/Camper 2022 - 10" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-24 | 2022-01-24 | Wendy Ni |  |  | N/A |  | N | 2022-02-03 | no need | PCB & 機構件同dezl 1010, 與MPM確認不須GMLA | Not assigned yet | #VALUE!
Outdoor | Xero C1 Chronograph | Detailed Design | Mechanical Design Review | 2021-07-29 | GMLA1 | 2021-07-08 | 2022-01-05 | 2022-01-05 | Chris Kuo | G | 91.67% | Y |  | N | 2022-01-17 | 2022-01-13 |  | Leo Chen | 2022-01-20 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | -
Fitness | Forerunner 255 Small | Factory Prototye | Factory Prototype Design Review | 2021-12-03 | GMLA2 | 2021-11-12 | 2021-12-10 | 2021-12-10 | Ernest Fu | R | 90.91% | Y |  | N | 2021-12-22 | 2021-12-22 |  | Alex chang | 2021-12-29 |  |  |  |  | 100% | 83% | 88% | 88% | 100% | 100%
Marine | Panoptix PS70 - (SSMB) | Detailed Design | Mechanical Design Review | 2021-12-09 | GMLA1 | 2021-11-18 | 2021-12-13 | 2021-12-13 | Jason Hsu | G | 91.67% | Y |  | N | 2021-12-23 | 2021-12-23 |  | Tim Wu | 2021-12-30 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Outdoor | eTrex SE | Detailed Design | Mechanical Design Review | 2021-12-20 | GMLA1 | 2021-11-29 | 2021-12-13 | 2021-12-13 | Chris Kuo | G | 91.67% | Y |  | N | 2021-12-23 | 2021-12-21 |  | Not assigned yet | 2021-12-28 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | -
Automotive | dezl OTR Series 2022- 6" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-14 | 2022-01-14 | Wendy Ni | Y | 93.18% | Y |  | N | 2022-01-26 | 2022-01-26 |  | Stephanie Yang | 2022-02-02 |  |  |  |  | 100% | 83% | 100% | 88% | 100% | 100%
Fitness | vivosmart 5 (Franklin) | Pilot Run | Pilot Run Build Complete | 2021-12-01 | GMLA3 | 2021-11-24 | 2021-12-15 | 2021-12-15 | Ernest Fu | R | 76.6% | Y |  | N | 2021-12-27 | 2021-12-27 | FP/ PR schedule are not confirmed yet (2021/7/1) | Nixon Pan | 2022-01-03 |  |  |  |  | 71% | 63% | 100% | 69% | 60% | 100%
Fitness | Tacx Motion Plates | Factory Prototye | Factory Prototype Design Review | 2022-01-06 | GMLA2 | 2021-12-16 |  | 2021-12-16 | Chris Kuo |  |  | N |  | N | 2021-12-28 |  | Not TW build | Not assigned yet | 1900-01-05
Fitness | Edge Explore 2 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | 2021-10-25 | 2021-10-25 | Chris Kuo | G | 83.33% | Y |  | N | 2021-11-04 | 2021-10-29 |  | Not assigned yet | 2021-11-05 |  |  |  |  | 75% | 100% | 100% | 75% | 100% | -
Marine | GHC 50 | Pilot Run | Pilot Run Build Complete | 2022-01-12 | GMLA3 | 2022-01-05 |  | 2022-01-05 | Jason Hsu |  |  | N |  | N | 2022-01-17 |  |  | Ken Kuo | 1900-01-05
Fitness | Tacx Motion Plates | Pilot Run | Pilot Run Build Complete | 2022-01-17 | GMLA3 | 2022-01-10 |  | 2022-01-10 | Chris Kuo |  |  | N/A |  | N | 2022-01-20 |  | Not TW build | Not assigned yet | 1900-01-05
Fitness | Garmin Powered Mount | Factory Prototye | Factory Prototype Design Review | 2022-01-31 | GMLA2 | 2022-01-10 |  | 2022-01-10 | Chris Kuo |  |  | N/A |  | N | 2022-01-20 |  |  | Not assigned yet | 1900-01-05
Automotive | dezl OTR Series 2022- 7" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-14 | 2022-01-14 | Wendy Ni | R | 90.91% | Y |  | N | 2022-01-26 | 2022-01-26 |  | Stephanie Yang | 2022-02-02 |  |  |  |  | 100% | 67% | 100% | 88% | 100% | 100%
Automotive | dezlCam OTR710 & RV Cam 795 | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-17 | 2022-01-17 | Wendy Ni | R | 86.36% | Y |  | N | 2022-01-27 | 2022-01-27 |  | Tim Wu | 2022-02-03 |  |  |  |  | 100% | 67% | 100% | 81% | 83% | 100%
Automotive | dezl OTR Series 2022- 8" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-17 | 2022-01-17 | Wendy Ni | R | 90.91% | Y |  | N | 2022-01-27 | 2022-01-27 | The target date has been confirmed with MPM. | Stephanie Yang | 2022-02-03 |  |  |  |  | 100% | 67% | 100% | 88% | 100% | 100%
Automotive | RV/Camper 2022 - 7" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 |  | 2022-01-14 | Wendy Ni |  |  | N/A |  | N | 2022-01-26 | no need | PCB & 機構件同DS76, 與MPM確認不須GMLA | Not assigned yet | #VALUE!
Automotive | RV/Camper 2022 - 8" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 |  | 2022-01-14 | Wendy Ni |  |  | N/A |  | N | 2022-01-26 | no need | PCB & 機構件同DS86, 與MPM確認不須GMLA | Not assigned yet | #VALUE!
Marine | LiveScope Plus (LVS34) | Pilot Run | Pilot Run Build Complete | 2021-12-31 | GMLA3 | 2021-12-24 | 2022-01-21 | 2022-01-21 | Jason Hsu | Y | 89.36% | Y |  | N | 2022-02-07 | 2022-01-26 | Target date postponed to 2022/2/7 due to lunar new year. Original name: Panoptix LiveScope HD (LVS34HD Transducer) | Ryan Li | 2022-02-02 |  |  |  |  | 86% | 88% | 92% | 92% | 80% | 100%
Fitness | Tacx NEO Bike Plus | Factory Prototye | Factory Prototype Design Review | 2022-01-05 | GMLA2 | 2021-12-15 | 2022-01-20 | 2022-01-20 | Chris Kuo | R | 88.64% | Y |  | N | 2022-02-08 | 2022-02-07 |  | Frank Chen | 2022-02-14 |  |  |  |  | 86% | 83% | 100% | 88% | 83% | 100%
Automotive | Dezl Headset | Pilot Run | Pilot Run Build Complete | 2022-01-03 | GMLA3 | 2021-12-27 | 2022-01-27 | 2022-01-27 | Wendy Ni | R | 63.83% | Y |  | N | 2022-02-08 | 2022-02-08 |  | Lori Tsai | 2022-02-15 |  |  |  |  | 29% | 75% | 100% | 54% | 20% | 100%
Outdoor | Marq (Gen 2) | Detailed Design | Mechanical Design Review | 2021-08-30 | GMLA1 | 2021-08-09 | 2022-01-19 | 2022-01-19 | Cooper Wang | G | 91.67% | Y |  | N | 2022-02-10 | 2022-02-10 | Target date postponed to 2022/2/10 due to lunar new year. | Sherry Shih | 2022-02-17 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | 100%
Outdoor | Foretrex 801/901 | Detailed Design | Mechanical Design Review | 2022-03-03 | GMLA1 | 2022-02-10 | TBD | TBD | Chris Kuo |  |  | N |  | N | #VALUE! |  |  | Not assigned yet | 1900-01-05
Marine | quatix Wake | Factory Prototye | Factory Prototype Design Review | 2022-05-23 | GMLA2 | 2022-05-02 |  | 2022-05-02 | Jason Hsu |  |  | N |  | N | 2022-05-12 |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Marine | FUSION - WB675 Hide Away Stereo | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Fitness | Tacx Vortex 2M | Factory Prototye | Factory Prototype Design Review | 2022-02-28 | GMLA2 | 2022-02-07 |  | 2022-02-07 | Chris Kuo |  |  | N/A |  | N | 2022-02-17 |  | This project has been canclled. | No MPM | 1900-01-05
Automotive | Tread 8" OEM | Factory Prototye | Factory Prototype Design Review |  | GMLA2 |  | 2022-02-11 | 2022-02-11 | Wendy Ni | R | 90.91% | Y |  | Y | 2022-02-23 | 2022-02-23 |  | Lori Tsai | [5 empty] | 100% | 67% | 88% | 94% | 100% | 100%
Fitness | Edge 1040 | Pilot Run | Pilot Run Build Complete | 2022-01-19 | GMLA3 | 2022-01-12 | 2022-02-15 | 2022-02-15 | Chris Kuo | R | 80.85% | Y | N | Y | 2022-02-25 | 2022-02-25 |  | Jack Chen | 2022-03-04 |  |  |  |  | 80.7% | 63% | 100% | 85% | 60% | 100%
Outdoor | Approach S70S | Detailed Design | Mechanical Design Review | 2022-03-09 | GMLA1 | 2022-02-16 | TBD | TBD | Cooper Wang |  |  | N |  | N | #VALUE! |  |  | Not assigned yet | 1900-01-05
Marine | GHC 50 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Ken Kuo | 1900-01-05
Marine | RV Fixed Displays- 7" | Detailed Design | Mechanical Design Review | 2022-02-18 | GMLA1 | 2022-01-28 | 2022-02-18 | 2022-02-18 | Jason Hsu | G | 91.67% | Y |  | Y | 2022-03-02 | 2022-03-01 |  | Tim Wu | 2022-03-08 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | -
Outdoor | Delta SE | Pilot Run | Pilot Run Build Complete | 2022-03-17 | GMLA3 | 2022-03-10 | 2022-04-13 | 2022-04-13 | Chris Kuo | Y | 91.49% | Y |  | Y | 2022-04-25 | 2022-04-21 |  | Robben Liu | 2022-04-28 |  |  |  |  | 100% | 88% | 100% | 92% | 60% | 100%
Marine | RV Fixed Displays- 10" | Detailed Design | Mechanical Design Review | 2022-02-18 | GMLA1 | 2022-01-28 | 2022-02-18 | 2022-02-18 | Jason Hsu | G | 91.67% | Y |  | Y | 2022-03-02 | 2022-03-01 |  | Tim Wu | 2022-03-08 |  |  |  |  | 75% | 100% | 100% | 100% | 100% | -
Automotive | dezl OTR Series 2022- 10" | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-01-24 | 2022-01-24 | Wendy Ni | R | 90.91% | Y |  | N | 2022-02-09 | 2022-02-09 | Target date postponed to 2022/2/9 due to lunar new year. | Stephanie Yang | 2022-02-16 |  |  |  |  | 100% | 67% | 100% | 88% | 100% | 100%
Marine | FUSION - WB675 Hide Away Stereo | Pilot Run | Pilot Run Build Complete | 2022-01-26 | GMLA3 | 2022-01-19 |  | 2022-01-19 | Jason Hsu |  |  | N/A |  | N | 2022-01-31 |  |  | Not assigned yet | 1900-01-05
Automotive | BC50 and BC50 IR | Pilot Run | Pilot Run Build Complete | 2022-01-04 | GMLA3 | 2021-12-28 | 2022-02-21 | 2022-02-21 | Chris Kuo | R | 85.11% | Y | N | Y | 2022-03-03 | 2022-03-03 |  | Leo Chen | 2022-03-10 |  |  |  |  | 86% | 75% | 100% | 85% | 60% | 100%
Marine | GST - Connect 70 | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Jason Hsu |  |  | N | N | N | #NUM! |  | Project cancelled | Audon Peng | 1900-01-05
Marine | GST - Connect 70 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Jason Hsu |  |  | N | N | N | #NUM! |  | Project cancelled | Audon Peng | 1900-01-05
Outdoor | inReach Messenger | Factory Prototye | Factory Prototype Design Review | 2022-03-08 | GMLA2 | 2022-02-15 | 2022-02-21 | 2022-02-21 | Chris Kuo | R | 79.55% | Y |  | Y | 2022-03-03 | 2022-03-03 |  | Nixon Pan | 2022-03-10 |  |  |  |  | 80.71% | 67% | 75% | 81% | 100% | 100%
Marine | ECHOMAP UHD2 (Keyed) 7" | Pilot Run | Pilot Run Build Complete | 2021-11-17 | GMLA3 | 2021-11-10 | 2022-02-21 | 2022-02-21 | Jason Hsu | R | 91.49% | Y |  | Y | 2022-03-03 | 2022-03-03 |  | Ken Kuo | 2022-03-10 |  |  |  |  | 86% | 88% | 100% | 85% | 100% | 100%
Marine | ECHOMAP UHD2 (Keyed) 5" | Pilot Run | Pilot Run Build Complete | 2021-11-17 | GMLA3 | 2021-11-10 | 2022-02-21 | 2022-02-21 | Jason Hsu | R | 89.36% | Y | N | Y | 2022-03-03 | 2022-03-03 |  | Ken Kuo | 2022-03-10 |  |  |  |  | 86% | 75% | 100% | 85% | 100% | 100%
Fitness | Edge Explore 2 | Factory Prototye | Factory Prototype Design Review | 2022-02-25 | GMLA2 | 2022-02-04 | 2022-02-21 | 2022-02-21 | Chris Kuo | R | 90.91% | Y |  | Y | 2022-03-03 | 2022-03-03 |  | Jack Chen | 2022-03-10 |  |  |  |  | 86% | 83% | 100% | 88% | 100% | 100%
Automotive | RV/Camper 2022 - 10" | Pilot Run | Pilot Run Build Complete | 2022-03-01 | GMLA3 | 2022-02-22 |  | 2022-02-22 | Not assigned yet |  |  | N/A |  | N | 2022-03-04 |  | PCB & 機構件同dezl 1010, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Automotive | RV/Camper 2022 - 7" | Pilot Run | Pilot Run Build Complete | 2022-03-01 | GMLA3 | 2022-02-22 |  | 2022-02-22 | Not assigned yet |  |  | N/A |  | N | 2022-03-04 |  | PCB & 機構件同DS76, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Automotive | Tread XL - Baja Race Edition | Pilot Run | Pilot Run Build Complete | 2021-12-27 | GMLA3 | 2021-12-20 | 2021-11-05 | 2021-11-05 | Jason Hsu | R | 82.98% | Y |  | N | 2021-11-17 | 2021-11-17 | 原Baja (Off Road 2021) Please refer Overlander 10" | Leo Chen | 2021-11-24 |  |  |  |  | 86% | 75% | 92% | 77% | 80% | 100%
OEM Auto | WGCN21 | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 |  |  |  | - |  | N | #NUM! |  | This is a software project for Venu 2/ Venu 2S, so no GMLA for this project. |  | 1900-01-05
OEM Auto | WGCN21 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 |  |  |  | - |  | N | #NUM! |  | This is a software project for Venu 2/ Venu 2S, so no GMLA for this project. |  | 1900-01-05
Automotive | RV/Camper 2022 - 8" | Pilot Run | Pilot Run Build Complete | 2022-03-01 | GMLA3 | 2022-02-22 |  | 2022-02-22 | Not assigned yet |  |  | N/A |  | N | 2022-03-04 |  | PCB & 機構件同DS86, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Automotive | Dash Cam Live (LTE) | Pilot Run | Pilot Run Build Complete | 2022-07-13 | GMLA3 | 2022-07-06 |  | 2022-07-06 | Chris Kuo |  |  | N | N | N | 2022-07-18 |  |  | Lori Tsai | 1900-01-05
Marine | GPSMAP 9000 - 24" | Detailed Design | Mechanical Design Review | 2022-05-04 | GMLA1 | 2022-04-13 | 2022-02-23 | 2022-02-23 | Jason Hsu | G | 83.33% | Y |  | Y | 2022-03-07 | 2022-03-07 |  | Nick Yen/ Stephanie Yang | 2022-03-14 |  |  |  |  | 75% | 100% | 100% | 75% | 100% | -
Fitness | Forerunner 955 and 955 Solar | Pilot Run | Pilot Run Build Complete | 2022-02-02 | GMLA3 | 2022-01-26 | 2022-02-25 | 2022-02-25 | Ernest Fu | R | 82.98% | Y |  | Y | 2022-03-09 | 2022-03-09 |  | Alex chang | 2022-03-16 |  |  |  |  | 86% | 75% | 85% | 85% | 80% | 100%
OEM Auto | IXWW22 | Pilot Run | Pilot Run Build Complete | 2022-01-12 | GMLA3 | 2022-01-05 | 2022-03-07 | 2022-03-07 | Simon Ko | Y | 84.75% | Y |  | Y | 2022-03-17 | 2022-03-18 |  | Nick Yen | 2022-03-25 |  |  |  |  | 71% | 100% | 85% | 69% | 100% | 88%
Automotive | Tread Audio System | Pilot Run | Pilot Run Build Complete | 2022-01-27 | GMLA3 | 2022-01-20 | 2022-03-02 | 2022-03-02 | Wendy Ni | R | 91.49% | Y |  | Y | 2022-03-18 | 2022-03-11 |  | Ken Kuo/ Tim Wu | 2022-03-18 |  |  |  |  | 83% | 86% | 100% | 92% | 80% | 100%
Fitness | Mercury | Factory Prototye | Final Factory Prototype Built | unknown | GMLA2 | #VALUE! | No MPM | #VALUE! | Ernest Fu |  |  | - | - | N | #VALUE! |  | Need to check the FFP close meeting time | No MPM | 1900-01-05
OEM Auto | IXJP24 | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 |  |  |  | - |  | N | #NUM! |  |  |  | 1900-01-05
OEM Auto | IXJP24 | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 |  |  |  | - |  | N | #NUM! |  |  |  | 1900-01-05
OEM Auto | IXJP24 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 |  |  |  | - |  | N | #NUM! |  |  |  | 1900-01-05
OEM Auto | Honda MLFA | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Arthur Yu |  |  | - |  | N | #NUM! |  | Deriative project from MKSA |  | 1900-01-05
OEM Auto | Honda MLFA | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Arthur Yu |  |  | - |  | N | #NUM! |  | Deriative project from MKSA |  | 1900-01-05
OEM Auto | Honda MLFA | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Arthur Yu |  |  | - |  | N | #NUM! |  | Deriative project from MKSA |  | 1900-01-05
OEM Auto | TXTW22_Drive+3.0 (Taroko)-12.3 DA | Factory Prototye | Factory Prototype Design Review | 2022-01-21 | GMLA2 | 2021-12-31 | 2022-05-23 | 2022-05-23 | Simon Ko |  |  | N |  | N | 2022-06-02 |  |  | Nick Yen | 1900-01-05
Outdoor | inReach Messenger | Pilot Run | Pilot Run Build Complete | 2022-04-14 | GMLA3 | 2022-04-07 | 2022-05-05 | 2022-05-05 | Chris Kuo |  |  | N |  | N | 2022-05-17 |  |  | Neo Lin | 1900-01-05
Marine | GMR Fantom 18x/24x | Detailed Design | Mechanical Design Review | 2021-01-06 | GMLA1 | 2020-12-16 | No WP request | No WP request | Jason Hsu |  |  | - | N | N | #VALUE! |  |  | Audon Peng | 1900-01-05
Fitness | Garmin Powered Mount | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Chris Kuo |  |  | - |  | N | #NUM! |  |  |  | 1900-01-05
Fitness | Edge 140 | Factory Prototye | Factory Prototype Design Review | 2020-02-14 | GMLA2 | 2020-01-24 | project cancelled | project cancelled | Abner Tsai |  |  | - | N | N | #VALUE! |  |  | No MPM | 1900-01-05
Fitness | Edge 140 | Pilot Run | Pilot Run Build Complete | 2020-04-24 | GMLA3 | 2020-04-17 | project cancelled | project cancelled | Abner Tsai |  |  | - | N | N | #VALUE! |  |  | No MPM | 1900-01-05
Automotive | Digital Switch | Detailed Design | Mechanical Design Review | cancelled | GMLA1 | #VALUE! | No MPM | #VALUE! | Abner Tsai |  |  | - | N | N | #VALUE! |  | Project cancelled | No MPM | 1900-01-05
Automotive | Digital Switch | Factory Prototye | Factory Prototype Design Review | cancelled | GMLA2 | #VALUE! | No MPM | #VALUE! | Abner Tsai |  |  | - | N | N | #VALUE! |  | Project cancelled | No MPM | 1900-01-05
Automotive | Digital Switch | Pilot Run | Pilot Run Build Complete | cancelled | GMLA3 | #VALUE! | No MPM | #VALUE! | Abner Tsai |  |  | - | N | N | #VALUE! |  | Project cancelled | No MPM | 1900-01-05
Automotive | dezl watch | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | no need | no need | Wendy Ni |  |  | - |  | N | #VALUE! |  | No WP for this project, so there is no G1. | Robben Liu | 1900-01-05
Automotive | CamperVan | Detailed Design | Mechanical Design Review | Not applicable. | GMLA1 | #VALUE! |  | #VALUE! |  |  |  | - |  | N | #VALUE! |  | This project uses existing Drive Smart 65 hardware. |  | 1900-01-05
Automotive | CamperVan | Factory Prototye | Factory Prototype Design Review | Not applicable. | GMLA2 | #VALUE! |  | #VALUE! |  |  |  | - |  | N | #VALUE! |  | As CamperVan is based on the DS 65 hardware, we do not plan to have this review. |  | 1900-01-05
Aviation | Aera 760 | Factory Prototye | Final Factory Prototype Built | unknown | GMLA2 | #VALUE! |  | #VALUE! | Abner Tsai | - | - | - | - | N | #VALUE! | - | No need to to do GMLA for aviation product | no MPM | #VALUE!
Aviation | Aera 760 | Pilot Run | Pilot Run Units Built | unknown | GMLA3 | #VALUE! |  | #VALUE! | Abner Tsai | - | - | - | - | N | #VALUE! | - | No need to to do GMLA for aviation product | no MPM | #VALUE!
Outdoor | Marq (Gen 2) | Factory Prototye | Factory Prototype Design Review | 2022-08-02 | GMLA2 | 2022-07-12 |  | 2022-07-12 | Cooper Wang |  |  | N |  | N | 2022-07-22 |  |  | Not assigned yet | 1900-01-05
Fitness | vivomove Trend | Factory Prototye | Factory Prototype Design Review | 2022-06-17 | GMLA2 | 2022-05-27 |  | 2022-05-27 | Aalto Lo |  |  | N |  | N | 2022-06-08 |  |  | Sherry Shih | 1900-01-05
Outdoor | Xero L60i Laser Navigator | Detailed Design | Mechanical Design Review | 2021-12-08 | GMLA1 | 2021-11-17 | Net yet | Net yet | Chris Kuo |  |  | N |  | N | #VALUE! |  |  | Lori Tsai | 1900-01-05
Marine | quatix Wake | Pilot Run | Pilot Run Build Complete | 2022-06-13 | GMLA3 | 2022-06-06 |  | 2022-06-06 | Jason Hsu |  |  | N |  | N | 2022-06-16 |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Outdoor | Pet Tracker | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 |  |  |  | N | N | N | #NUM! |  |  |  | 1900-01-05
Outdoor | Pet Tracker | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 |  |  |  | N | N | N | #NUM! |  |  |  | 1900-01-05
Outdoor | Pet Tracker | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 |  |  |  | N | N | N | #NUM! |  |  |  | 1900-01-05
Marine | GPSMAP 9000 - 19" | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | 2022-04-27 | 2022-04-27 | Jason Hsu |  |  | N |  | N | 2022-05-09 |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | Factory Prototye | Factory Prototype Design Review | 2022-01-21 | GMLA2 | 2021-12-31 | 2022-03-08 | 2022-03-08 | Simon Ko | Y | 81.48% | Y |  | Y | 2022-03-18 | 2022-03-20 |  | Nick Yen | 2022-03-25 |  |  |  |  | 86% | 100% | 88% | 75% | 88% | 63%
Marine | quatix 7 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Outdoor | Enduro 2023 | Detailed Design | Mechanical Design Review | 2022-03-18 | GMLA1 | 2022-02-25 |  | 2022-02-25 | Cooper Wang |  |  | N/A |  | N | 2022-03-09 |  | A derivative of the Fenix 7X | Not assigned yet | 1900-01-05
Marine | ECHOMAP UHD2 (Touch) 7" | Detailed Design | Mechanical Design Review | 2021-12-03 | GMLA1 | 2021-11-12 | 2021-12-01 | 2021-12-01 | Jason Hsu | G | 91.67% | Y |  |  | 2021-12-13 | 2021-12-13 |  | Lori Tsai/ Stephanie Yang | 2021-12-20 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Marine | quatix Wake | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  | Deriative project from Fenix7 | Not assigned yet | 1900-01-05
Marine | ECHOMAP UHD2 (Touch) 7" | Factory Prototye | Factory Prototype Design Review | 2022-06-21 | GMLA2 | 2022-05-31 |  | 2022-05-31 | Jason Hsu |  |  | N |  | N | 2022-06-10 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Marine | GPSMAP 9000 - 27" | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 | 2022-04-27 | 2022-04-27 | Jason Hsu |  |  | N |  | N | 2022-05-09 |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Automotive | RV/Camper 2022 - 10" | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Not assigned yet |  |  | N |  | N | #NUM! |  | PCB & 機構件同dezl 1010, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Outdoor | Approach Z50 | Factory Prototye | Factory Prototype Design Review | 2022-09-28 | GMLA2 | 2022-09-07 | 2022-07-29 | 2022-07-29 | Chris Kuo |  |  | N | N | N | 2022-08-10 |  |  | Robben Liu | 1900-01-05
Outdoor | Descent S1 Buoy | Factory Prototye | Factory Prototype Design Review | 2022-02-04 | GMLA2 | 2022-01-14 | 2022-06-30 | 2022-06-30 | Chris Kuo |  |  | N | N | N | 2022-07-12 |  |  | Frank Chen | 1900-01-05
Automotive | RV/Camper 2022 - 7" | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Not assigned yet |  |  | N |  | N | #NUM! |  | PCB & 機構件同DS76, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Outdoor | Approach R50 | Factory Prototye | Factory Prototype Design Review | 2022-09-01 | GMLA2 | 2022-08-11 |  | 2022-08-11 | Chris Kuo |  |  | N | N | N | 2022-08-23 |  |  | Nixon Pan | 1900-01-05
OEM Auto | TXTW22_Drive+3.0 (Taroko)-12.3 DA | Pilot Run | Pilot Run Build Complete | 2022-05-06 | GMLA3 | 2022-04-29 | 2022-05-23 | 2022-05-23 | Simon Ko |  |  | N |  | N | 2022-06-02 |  |  | Sandy Lee | 1900-01-05
Automotive | RV/Camper 2022 - 8" | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Not assigned yet |  |  | N |  | N | #NUM! |  | PCB & 機構件同DS86, 與MPM確認不須GMLA | Not assigned yet | 1900-01-05
Fitness | Forerunner 255 | Pilot Run | Pilot Run Build Complete | 2022-01-31 | GMLA3 | 2022-01-24 | 2022-03-21 | 2022-03-21 | Ernest Fu | R | 87.23% | Y |  | Y | 2022-03-31 | 2022-03-30 |  | Robben Liu | 2022-04-06 |  |  |  |  | 100% | 88% | 92% | 77% | 80% | 100%
Fitness | Tacx Motion Plates | Detailed Design | Mechanical Design Review | 2021-05-26 | GMLA1 | 2021-05-05 |  | 2021-05-05 | Chris Kuo |  |  | N |  | N | 2021-05-17 |  | Not TW build | Not assigned yet | 1900-01-05
Fitness | Forerunner 255 Small | Pilot Run | Pilot Run Build Complete | 2022-01-31 | GMLA3 | 2022-01-24 | 2022-03-21 | 2022-03-21 | Ernest Fu | R | 78.72% | Y |  | Y | 2022-03-31 | 2022-03-31 |  | Alex chang | 2022-04-07 |  |  |  |  | 100% | 63% | 85% | 69% | 80% | 100%
Fitness | Garmin Powered Mount | Pilot Run | Pilot Run Build Complete | 2022-03-07 | GMLA3 | 2022-02-28 |  | 2022-02-28 | Chris Kuo |  |  | N/A |  | N | 2022-03-10 |  |  |  | 1900-01-05
Marine | MARQ Carbon (Gen 2) | Detailed Design | Mechanical Design Review | 2021-09-06 | GMLA1 | 2021-08-16 | TBD | TBD | Aalto Lo |  |  | N |  | N | #VALUE! |  |  | Nixon Pan | 1900-01-05
Outdoor | Instinct Crossover | Factory Prototye | Factory Prototype Design Review | 2022-02-25 | GMLA2 | 2022-02-04 | 2022-05-30 | 2022-05-30 | Aalto Lo |  |  | N |  | N | 2022-06-09 |  |  | Robben Liu | 1900-01-05
Marine | LiveScope XR (LVS62) | Pilot Run | Pilot Run Build Complete | 2022-03-16 | GMLA3 | 2022-03-09 | 2022-03-28 | 2022-03-28 | Jason Hsu | R | 80.85% | Y |  | Y | 2022-04-07 | 2022-04-07 | Original name: LiveScope XR - New Transducer | Ryan Li | 2022-04-14 |  |  |  |  | 86% | 63% | 100% | 69% | 80% | 100%
Automotive | dezlCam OTR710 & RV Cam 795 | Pilot Run | Pilot Run Build Complete | 2022-03-16 | GMLA3 | 2022-03-09 | 2022-04-25 | 2022-04-25 | Wendy Ni |  |  | N |  | N | 2022-05-05 |  |  | Not assigned yet | 1900-01-05
Fitness | Tacx Vortex 2M | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Chris Kuo |  |  | N |  | N | #NUM! |  | This project has been canclled. | No MPM | 1900-01-05
OEM Auto | BMW MGU22/IDC | Pilot Run | Pilot Run Build Complete | 2021-04-21 | GMLA3 | 2021-04-14 | 2022-05-31 | 2022-05-31 | Allen Chen/ Ray Hu |  |  | N |  | N | 2022-06-10 |  |  | Jason Lee | 1900-01-05
OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | Pilot Run | Pilot Run Build Complete | 2022-05-06 | GMLA3 | 2022-04-29 | 2022-05-30 | 2022-05-30 | Ray Hu |  |  | N |  | N | 2022-06-09 |  |  | Sandy Lee | 1900-01-05
Automotive | dezl OTR Series 2022- 10" | Pilot Run | Pilot Run Build Complete | 2022-03-15 | GMLA3 | 2022-03-08 | TBD | 2022-03-30 | Wendy Ni | Y | 93.62% | Y |  | Y | 2022-04-11 | 2022-04-11 |  | Stephanie Yang | 2022-04-18 |  |  |  |  | 71% | 100% | 100% | 92% | 100% | 100%
Outdoor | Alpha Dog Collar | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Chris Kuo |  |  | N | N | N | #NUM! |  |  | Robben Liu | 1900-01-05
Fitness | Edge Explore 2 | Pilot Run | Pilot Run Build Complete | 2022-04-11 | GMLA3 | 2022-04-04 | 2022-04-22 | 2022-04-22 | Chris Kuo | R | 82.98% | Y |  | Y | 2022-05-04 | 2022-05-03 |  | Nixon Pan | 2022-05-10
Fitness | Edge 540 840 | Detailed Design | Mechanical Design Review | 2021-04-28 | GMLA1 | 2021-04-07 |  | 2021-04-07 | Chris Kuo |  |  | - |  | N | 2021-04-19 |  | No this project on PRWeb | Not assigned yet | 1900-01-05
Marine | ECHOMAP UHD2 (Touch) 7" | Pilot Run | Pilot Run Build Complete | 2022-08-15 | GMLA3 | 2022-08-08 |  | 2022-08-08 | Jason Hsu |  |  | N |  | N | 2022-08-18 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Marine | ECHOMAP UHD2 (Touch) 9" | Detailed Design | Mechanical Design Review | 2021-11-12 | GMLA1 | 2021-10-22 | 2021-12-01 | 2021-12-01 | Jason Hsu | G | 91.67% | Y |  | N | 2021-12-13 | 2021-12-13 |  | Lori Tsai/ Stephanie Yang | 2021-12-20 |  |  |  |  | 100% | 100% | 100% | 75% | 100% | 100%
Marine | ECHOMAP UHD2 (Touch) 9" | Factory Prototye | Factory Prototype Design Review | 2022-06-21 | GMLA2 | 2022-05-31 |  | 2022-05-31 | Jason Hsu |  |  | N |  | N | 2022-06-10 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Marine | ECHOMAP UHD2 (Touch) 9" | Pilot Run | Pilot Run Build Complete | 2022-08-15 | GMLA3 | 2022-08-08 |  | 2022-08-08 | Jason Hsu |  |  | N |  | N | 2022-08-18 |  |  | Lori Tsai/ Stephanie Yang | 1900-01-05
Fitness | Venu Sq 2 | Pilot Run | Pilot Run Build Complete | 2022-04-20 | GMLA3 | 2022-04-13 | TBD | TBD | Aalto Lo |  |  | N |  | N | #VALUE! |  |  | Jack Chen | 1900-01-05
Outdoor | Xero L60i Laser Navigator | Factory Prototye | Factory Prototype Design Review | 2022-05-05 | GMLA2 | 2022-04-14 | 2022-05-20 | 2022-05-20 | Chris Kuo |  |  | N |  | N | 2022-06-01 |  |  | Not assigned yet | 1900-01-05
Outdoor | Instinct Crossover | Pilot Run | Pilot Run Build Complete | 2022-04-22 | GMLA3 | 2022-04-15 | TBD | TBD | Aalto Lo |  |  | N |  | N | #VALUE! |  |  | Anson Lu | 1900-01-05
Fitness | Edge 540 840 | Factory Prototye | Factory Prototype Design Review | 2022-09-05 | GMLA2 | 2022-08-15 |  | 2022-08-15 | Chris Kuo |  |  | N |  | N | 2022-08-25 |  |  | Not assigned yet | 1900-01-05
Automotive | dezl OTR Series 2022- 8" | Pilot Run | Pilot Run Build Complete | 2022-03-15 | GMLA3 | 2022-03-08 | TBD | 2022-03-30 | Wendy Ni | R | 87.23% | Y |  | Y | 2022-04-11 | 2022-04-11 |  | Stephanie Yang | 2022-04-18 |  |  |  |  | 71% | 75% | 100% | 92% | 80% | 100%
Fitness | Venu Sq 2 | Factory Prototye | Factory Prototype Design Review | 2022-04-19 | GMLA2 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Aalto Lo | R | 88.64% | Y |  | Y | 2022-04-11 | 2022-04-08 |  | Jack Chen | 2022-04-15 |  |  |  | 100 | 100% | 83% | 88% | 81% | 100% | 100%
Fitness | vivomove Trend | Pilot Run | Pilot Run Build Complete | 2022-08-26 | GMLA3 | 2022-08-19 |  | 2022-08-19 | Aalto Lo |  |  | N |  | N | 2022-08-31 |  |  | Sherry Shih | 1900-01-05
Outdoor | Approach R50 | Pilot Run | Pilot Run Build Complete | TBD | GMLA3 | #VALUE! |  | #VALUE! | Chris Kuo |  |  | N | N | N | #VALUE! |  |  | Nixon Pan | 1900-01-05
Marine | RV Fixed Displays- 7" | Factory Prototye | Factory Prototype Design Review | 2022-10-11 | GMLA2 | 2022-09-20 |  | 2022-09-20 | Jason Hsu |  |  | N |  | N | 2022-09-30 |  |  | Not assigned yet | 1900-01-05
Marine | RV Fixed Displays- 10" | Factory Prototye | Factory Prototype Design Review | 2022-10-11 | GMLA2 | 2022-09-20 |  | 2022-09-20 | Jason Hsu |  |  | N |  | N | 2022-09-30 |  |  | Not assigned yet | 1900-01-05
Outdoor | Descent S1 Buoy | Pilot Run | Pilot Run Build Complete | 2022-03-11 | GMLA3 | 2022-03-04 | TBD | TBD | Chris Kuo |  |  | N | N | N | #VALUE! |  |  | Frank Chen | 1900-01-05
Outdoor | Xero C1 Chronograph | Factory Prototye | Factory Prototype Design Review | 2022-07-28 | GMLA2 | 2022-07-07 |  | 2022-07-07 | Chris Kuo |  |  | N |  | N | 2022-07-19 |  |  | Leo Chen | 1900-01-05
Outdoor | eTrex SE | Factory Prototye | Factory Prototype Design Review | 2022-06-10 | GMLA2 | 2022-05-20 |  | 2022-05-20 | Chris Kuo |  |  | N |  | N | 2022-06-01 |  |  | Not assigned yet | 1900-01-05
Outdoor | Approach Z50 | Pilot Run | Pilot Run Build Complete | 2022-11-24 | GMLA3 | 2022-11-17 |  | 2022-11-17 | Chris Kuo |  |  | N | N | N | 2022-11-29 |  |  | Robben Liu | 1900-01-05
Marine | BlueNET Gateway | Factory Prototye | Factory Prototype Design Review | 2022-06-29 | GMLA2 | 2022-06-08 |  | 2022-06-08 | Chris Kuo |  |  | N | N | N | 2022-06-20 |  |  | Chiencheng Huang/ Tim Wu | 1900-01-05
Marine | BlueNET Switch | Factory Prototye | Factory Prototype Design Review | 2022-06-29 | GMLA2 | 2022-06-08 |  | 2022-06-08 | Chris Kuo |  |  | N | N | N | 2022-06-20 |  |  | Chiencheng Huang/ Tim Wu | 1900-01-05
Marine | GPSMAP 9000 - 22" | Factory Prototye | Factory Prototype Design Review | 2022-11-28 | GMLA2 | 2022-11-07 | 2022-07-08 | 2022-07-08 | Jason Hsu |  |  | N |  | N | 2022-07-20 |  |  | Nick Yen | 1900-01-05
OEM Auto | IMWW23 | Factory Prototye | Factory Prototype Design Review | 2022-07-19 | GMLA2 | 2022-06-28 |  | 2022-06-28 | Cherry Tsai |  |  | N |  | N | 2022-07-08 |  |  | Not assigned yet | 1900-01-05
Outdoor | Marq (Gen 2) | Pilot Run | Pilot Run Build Complete | 2022-06-27 | GMLA3 | 2022-06-20 |  | 2022-06-20 | Cooper Wang |  |  | N |  | N | 2022-06-30 |  |  | Not assigned yet | 1900-01-05
Fitness | Edge 540 840 | Pilot Run | Pilot Run Build Complete | 2022-07-11 | GMLA3 | 2022-07-04 |  | 2022-07-04 | Chris Kuo |  |  | N |  | N | 2022-07-14 |  |  | Not assigned yet | 1900-01-05
Outdoor | Xero C1 Chronograph | Pilot Run | Pilot Run Build Complete | 2022-07-12 | GMLA3 | 2022-07-05 |  | 2022-07-05 | Chris Kuo |  |  | N |  | N | 2022-07-15 |  |  | Leo Chen | 1900-01-05
Marine | RV Fixed Displays- 7" | Pilot Run | Pilot Run Build Complete | 2022-12-02 | GMLA3 | 2022-11-25 |  | 2022-11-25 | Jason Hsu |  |  | N |  | N | 2022-12-07 |  |  | Not assigned yet | 1900-01-05
Marine | RV Fixed Displays- 10" | Pilot Run | Pilot Run Build Complete | 2022-12-02 | GMLA3 | 2022-11-25 |  | 2022-11-25 | Jason Hsu |  |  | N |  | N | 2022-12-07 |  |  | Not assigned yet | 1900-01-05
Outdoor | Xero L60i Laser Navigator | Pilot Run | Pilot Run Build Complete | 2022-07-21 | GMLA3 | 2022-07-14 |  | 2022-07-14 | Chris Kuo |  |  | N |  | N | 2022-07-26 |  |  | Not assigned yet | 1900-01-05
Outdoor | eTrex SE | Pilot Run | Pilot Run Build Complete | 2022-07-28 | GMLA3 | 2022-07-21 |  | 2022-07-21 | Chris Kuo |  |  | N |  | N | 2022-08-02 |  |  | Not assigned yet | 1900-01-05
OEM Auto | IMWW23 | Pilot Run | Pilot Run Build Complete | 2023-02-17 | GMLA3 | 2023-02-10 |  | 2023-02-10 | Cherry Tsai |  |  | N |  | N | 2023-02-22 |  |  | Not assigned yet | 1900-01-05
Marine | MARQ Carbon (Gen 2) | Factory Prototye | Factory Prototype Design Review | 2022-08-02 | GMLA2 | 2022-07-12 |  | 2022-07-12 | Aalto Lo |  |  | N |  | N | 2022-07-22 |  |  | Nixon Pan | 1900-01-05
Marine | BlueNET Gateway | Pilot Run | Pilot Run Build Complete | 2022-08-12 | GMLA3 | 2022-08-05 |  | 2022-08-05 | Chris Kuo |  |  | N | N | N | 2022-08-17 |  |  | Chiencheng Huang/ Tim Wu | 1900-01-05
Marine | BlueNET Switch | Pilot Run | Pilot Run Build Complete | 2022-08-12 | GMLA3 | 2022-08-05 |  | 2022-08-05 | Chris Kuo |  |  | N | N | N | 2022-08-17 |  |  | Chiencheng Huang/ Tim Wu | 1900-01-05
Marine | GPSMAP 9000 - 22" | Pilot Run | Pilot Run Build Complete | 2023-01-27 | GMLA3 | 2023-01-20 |  | 2023-01-20 | Jason Hsu |  |  | N |  | N | 2023-02-01 |  |  | Nick Yen | 1900-01-05
Outdoor | Approach S70S | Factory Prototye | Factory Prototype Design Review | 2022-10-13 | GMLA2 | 2022-09-22 |  | 2022-09-22 | Cooper Wang |  |  | N |  | N | 2022-10-04 |  |  | Not assigned yet | 1900-01-05
Marine | MARQ Carbon (Gen 2) | Pilot Run | Pilot Run Build Complete | 2022-07-29 | GMLA3 | 2022-07-22 |  | 2022-07-22 | Aalto Lo |  |  | N |  | N | 2022-08-03 |  |  | Nixon Pan | 1900-01-05
Outdoor | Foretrex 801/901 | Factory Prototye | Factory Prototype Design Review | 2022-10-13 | GMLA2 | 2022-09-22 |  | 2022-09-22 | Chris Kuo |  |  | N |  | N | 2022-10-04 |  |  | Not assigned yet | 1900-01-05
Outdoor | Foretrex 801/901 | Pilot Run | Pilot Run Build Complete | 2022-12-02 | GMLA3 | 2022-11-25 |  | 2022-11-25 | Chris Kuo |  |  | N |  | N | 2022-12-07 |  |  | Not assigned yet | 1900-01-05
Outdoor | Approach S70S | Pilot Run | Pilot Run Build Complete | 2022-12-05 | GMLA3 | 2022-11-28 |  | 2022-11-28 | Cooper Wang |  |  | N |  | N | 2022-12-08 |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7 Pro | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7 Pro | Factory Prototye | Factory Prototype Design Review | 2022-08-23 | GMLA2 | 2022-08-02 |  | 2022-08-02 | Cooper Wang |  |  | N |  | N | 2022-08-12 |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7 Pro | Pilot Run | Pilot Run Build Complete | 2022-10-18 | GMLA3 | 2022-10-11 |  | 2022-10-11 | Cooper Wang |  |  | N |  | N | 2022-10-21 |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7S Pro | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7S Pro | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7S Pro | Pilot Run | Pilot Run Build Complete | 2022-10-18 | GMLA3 | 2022-10-11 |  | 2022-10-11 | Cooper Wang |  |  | N |  | N | 2022-10-21 |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7X Pro | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7X Pro | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | fenix 7X Pro | Pilot Run | Pilot Run Build Complete | 2022-10-18 | GMLA3 | 2022-10-11 |  | 2022-10-11 | Cooper Wang |  |  | N |  | N | 2022-10-21 |  |  | Not assigned yet | 1900-01-05
Automotive | Dash Cam Live (LTE) | Factory Prototye | Factory Prototype Design Review | 2022-01-07 | GMLA2 | 2021-12-17 | 2022-04-14 | 2022-04-14 | Chris Kuo | R | 81.82% | Y | N | Y | 2022-04-26 | 2022-04-26 |  | Lori Tsai | 2022-05-03 |  |  |  |  | 71.43% | 50% | 100% | 81% | 100% | 100%
Outdoor | Enduro 2023 | Factory Prototye | Factory Prototype Design Review | 2022-10-04 | GMLA2 | 2022-09-13 |  | 2022-09-13 | Cooper Wang |  |  | N |  | N | 2022-09-23 |  | A derivative of the Fenix 7X | Not assigned yet | 1900-01-05
Outdoor | Enduro 2023 | Pilot Run | Pilot Run Build Complete | 2022-11-24 | GMLA3 | 2022-11-17 |  | 2022-11-17 | Cooper Wang |  |  | N |  | N | 2022-11-29 |  | A derivative of the Fenix 7X | Not assigned yet | 1900-01-05
Outdoor | eTrex Solar | Detailed Design | Mechanical Design Review | 2022-04-21 | GMLA1 | 2022-03-31 | TBD | TBD | Chris Kuo |  |  | N |  | N | #VALUE! |  |  | Not assigned yet | 1900-01-05
Outdoor | eTrex Solar | Factory Prototye | Factory Prototype Design Review | 2023-01-09 | GMLA2 | 2022-12-19 |  | 2022-12-19 | Chris Kuo |  |  | N |  | N | 2022-12-29 |  |  | Not assigned yet | 1900-01-05
Outdoor | eTrex Solar | Pilot Run | Pilot Run Build Complete | 2023-01-20 | GMLA3 | 2023-01-13 |  | 2023-01-13 | Chris Kuo |  |  | N |  | N | 2023-01-25 |  |  | Not assigned yet | 1900-01-05
Outdoor | Approach S70 | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Jack Chen | 1900-01-05
Outdoor | Approach S70 | Factory Prototye | Factory Prototype Design Review | 2022-10-13 | GMLA2 | 2022-09-22 |  | 2022-09-22 | Cooper Wang |  |  | N |  | N | 2022-10-04 |  |  | Jack Chen | 1900-01-05
Outdoor | Approach S70 | Pilot Run | Pilot Run Build Complete | 2022-12-05 | GMLA3 | 2022-11-28 |  | 2022-11-28 | Cooper Wang |  |  | N |  | N | 2022-12-08 |  |  | Jack Chen | 1900-01-05
Outdoor | Alpha Dog Collar | Factory Prototye | Factory Prototype Design Review | 2022-05-13 | GMLA2 | 2022-04-22 | 2022-06-30 | 2022-06-30 | Chris Kuo |  |  | N | N | N | 2022-07-12 |  |  | Robben Liu | 1900-01-05
Marine | GPSMAP 9000 - 27" | Factory Prototye | Factory Prototype Design Review | 2022-06-02 | GMLA2 | 2022-05-12 | 2022-07-22 | 2022-07-22 | Jason Hsu |  |  | N |  | N | 2022-08-03 |  |  | Tim Wu | 1900-01-05
Marine | Panoptix PS70 - (SSMB) | Pilot Run | Pilot Run Build Complete | 2022-07-15 | GMLA3 | 2022-07-08 |  | 2022-07-08 | Jason Hsu |  |  | N |  | N | 2022-07-20 |  |  | Tim Wu | 1900-01-05
Fitness | Venu 3 | Detailed Design | Mechanical Design Review | 2021-12-22 | GMLA1 | 2021-12-01 | Net yet | Net yet | Ernest Fu/ Aalto Lo |  |  | N |  | N | #VALUE! |  |  | Alex chang | 1900-01-05
Fitness | Venu 3 | Factory Prototye | Factory Prototype Design Review | 2023-01-10 | GMLA2 | 2022-12-20 |  | 2022-12-20 | Ernest Fu/ Aalto Lo |  |  | N |  | N | 2022-12-30 |  |  | Alex chang | 1900-01-05
Fitness | Venu 3 | Pilot Run | Pilot Run Build Complete | 2023-03-20 | GMLA3 | 2023-03-13 |  | 2023-03-13 | Ernest Fu/ Aalto Lo |  |  | N |  | N | 2023-03-23 |  |  | Alex chang | 1900-01-05
Fitness | Venu 3S | Detailed Design | Mechanical Design Review | 2021-12-22 | GMLA1 | 2021-12-01 | Net yet | Net yet | Ernest Fu |  |  | N |  | N | #VALUE! |  |  | Alex chang | 1900-01-05
Fitness | Venu 3S | Factory Prototye | Factory Prototype Design Review | 2023-01-10 | GMLA2 | 2022-12-20 |  | 2022-12-20 | Ernest Fu |  |  | N |  | N | 2022-12-30 |  |  | Alex chang | 1900-01-05
Fitness | Venu 3S | Pilot Run | Pilot Run Build Complete | 2023-03-20 | GMLA3 | 2023-03-13 |  | 2023-03-13 | Ernest Fu |  |  | N |  | N | 2023-03-23 |  |  | Alex chang | 1900-01-05
Automotive | dezl OTR Series 2022- 6" | Pilot Run | Pilot Run Build Complete | 2022-03-15 | GMLA3 | 2022-03-08 | TBD | 2022-04-07 | Wendy Ni | Y | 78.72% | Y |  | Y | 2022-04-19 | 2022-04-11 |  | Stephanie Yang | 2022-04-18 |  |  |  |  | 43% | 88% | 92% | 77% | 80% | 100%
Marine | GPSMAP 9000 - 19" | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Marine | GPSMAP 9000 - 19" | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Fitness | Tacx NEO Bike Plus | Pilot Run | Pilot Run Build Complete | 2022-03-21 | GMLA3 | 2022-03-14 | TBD | TBD | Chris Kuo |  |  | N |  | N | #VALUE! |  |  | Frank Chen | 1900-01-05
Marine | GPSMAP 9000 - 24" | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Marine | GPSMAP 9000 - 24" | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Fitness | Tacx Vortex 2M | Pilot Run | Pilot Run Build Complete | 2022-03-22 | GMLA3 | 2022-03-15 |  | 2022-03-15 | Chris Kuo |  |  | N/A |  | N | 2022-03-25 |  | This project has been canclled. | No MPM | 1900-01-05
Marine | GPSMAP 9000 - 27" | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Marine | GPSMAP 9000 - 27" | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Jason Hsu |  |  | N |  | N | #NUM! |  |  | Nick Yen/ Stephanie Yang | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 42mm | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 42mm | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 42mm | Pilot Run | Pilot Run Build Complete | 2022-11-15 | GMLA3 | 2022-11-08 |  | 2022-11-08 | Cooper Wang |  |  | N |  | N | 2022-11-18 |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 47mm | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 47mm | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 47mm | Pilot Run | Pilot Run Build Complete | 2022-11-16 | GMLA3 | 2022-11-09 |  | 2022-11-09 | Cooper Wang |  |  | N |  | N | 2022-11-21 |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 51mm | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 51mm | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | EPIX PRO (Gen 2) 51mm | Pilot Run | Pilot Run Build Complete |  | GMLA3 | -7 |  | -7 | Cooper Wang |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Outdoor | Instinct 2X Solar | Detailed Design | Mechanical Design Review | 2022-07-05 | GMLA1 | 2022-06-14 |  | 2022-06-14 | Cooper Wang |  |  | N |  | N | 2022-06-24 |  |  |  | 1900-01-05
Outdoor | Instinct 2X Solar | Factory Prototye | Factory Prototype Design Review | 2022-12-19 | GMLA2 | 2022-11-28 |  | 2022-11-28 | Cooper Wang |  |  | N |  | N | 2022-12-08 |  |  |  | 1900-01-05
Outdoor | Instinct 2X Solar | Pilot Run | Pilot Run Build Complete | 2023-01-24 | GMLA3 | 2023-01-17 |  | 2023-01-17 | Cooper Wang |  |  | N |  | N | 2023-01-27 |  |  |  | 1900-01-05
Fitness | Venu Sq 2 Plus | Detailed Design | Mechanical Design Review |  | GMLA1 | -21 |  | -21 | Ernest Fu |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Fitness | Venu Sq 2 Plus | Factory Prototye | Factory Prototype Design Review |  | GMLA2 | -21 |  | -21 | Ernest Fu |  |  | N |  | N | #NUM! |  |  | Not assigned yet | 1900-01-05
Fitness | Venu Sq 2 Plus | Pilot Run | Pilot Run Build Complete | 2023-03-03 | GMLA3 | 2023-02-24 |  | 2023-02-24 | Ernest Fu |  |  | N |  | N | 2023-03-08 |  |  | Not assigned yet | 1900-01-05
Outdoor | Descent Mk3s | Detailed Design | Mechanical Design Review | 2022-01-17 | GMLA1 | 2021-12-27 | 2022-05-31 | 2022-05-31 | Cooper Wang |  |  | N |  | N | 2022-06-10 |  |  | Leo Chen | 1900-01-05
Outdoor | Descent Mk3s | Factory Prototye | Factory Prototype Design Review | 2023-01-23 | GMLA2 | 2023-01-02 |  | 2023-01-02 | Cooper Wang |  |  | N |  | N | 2023-01-12 |  |  | Leo Chen | 1900-01-05
Outdoor | Descent Mk3s | Pilot Run | Pilot Run Build Complete | 2023-03-10 | GMLA3 | 2023-03-03 |  | 2023-03-03 | Cooper Wang |  |  | N |  | N | 2023-03-15 |  |  | Leo Chen | 1900-01-05
Outdoor | Descent Mk3 | Detailed Design | Mechanical Design Review | 2022-01-25 | GMLA1 | 2022-01-04 | TBD | TBD | Cooper Wang |  |  | N |  | N | #VALUE! |  |  | Leo Chen | 1900-01-05
Outdoor | Descent Mk3 | Factory Prototye | Factory Prototype Design Review | 2023-01-23 | GMLA2 | 2023-01-02 |  | 2023-01-02 | Cooper Wang |  |  | N |  | N | 2023-01-12 |  |  | Leo Chen | 1900-01-05
Outdoor | Descent Mk3 | Pilot Run | Pilot Run Build Complete | 2023-03-10 | GMLA3 | 2023-03-03 |  | 2023-03-03 | Cooper Wang |  |  | N |  | N | 2023-03-15 |  |  | Leo Chen | 1900-01-05
Fitness | Forerunner 265 | Detailed Design | Mechanical Design Review | 2022-03-08 | GMLA1 | 2022-02-15 | TBD | TBD | Ernest Fu |  |  | N |  |  | #VALUE! |  |  | Not assigned yet | 1900-01-05
Fitness | Forerunner 265 | Factory Prototye | Factory Prototype Design Review | 2022-11-14 | GMLA2 | 2022-10-24 |  | 2022-10-24 | Ernest Fu |  |  | N |  |  | 2022-11-03 |  |  | Not assigned yet | 1900-01-05
Fitness | Forerunner 265 | Pilot Run | Pilot Run Build Complete | 2023-01-18 | GMLA3 | 2023-01-11 |  | 2023-01-11 | Ernest Fu |  |  | N |  |  | 2023-01-23 |  |  | Not assigned yet | 1900-01-05
Fitness | Forerunner 965 | Detailed Design | Mechanical Design Review | 2022-02-01 | GMLA1 | 2022-01-11 |  | 2022-01-11 | Ernest Fu |  |  | N |  |  | 2022-01-21 |  |  | Not assigned yet | 1900-01-05
Fitness | Forerunner 965 | Factory Prototye | Factory Prototype Design Review | 2022-12-08 | GMLA2 | 2022-11-17 |  | 2022-11-17 | Ernest Fu |  |  | N |  |  | 2022-11-29 |  |  | Not assigned yet | 1900-01-05
Fitness | Forerunner 965 | Pilot Run | Pilot Run Build Complete | 2023-02-16 | GMLA3 | 2023-02-09 |  | 2023-02-09 | Ernest Fu |  |  | N |  |  | 2023-02-21 |  |  | Not assigned yet | 1900-01-05
Fitness | Tacx NEO 3M | Detailed Design | Mechanical Design Review | TBC | GMLA1 | #VALUE! |  | #VALUE! | Chris Kuo |  |  | N |  |  | #VALUE! |  |  | Not assigned yet | 1900-01-05
Fitness | Tacx NEO 3M | Factory Prototye | Factory Prototype Design Review | 2023-03-01 | GMLA2 | 2023-02-08 |  | 2023-02-08 | Chris Kuo |  |  | N |  |  | 2023-02-20 |  |  | Not assigned yet | 1900-01-05
Fitness | Tacx NEO 3M | Pilot Run | Pilot Run Build Complete | 2023-04-19 | GMLA3 | 2023-04-12 |  | 2023-04-12 | Chris Kuo |  |  | N |  |  | 2023-04-24 |  |  | Not assigned yet | 1900-01-05
Automotive | Tread 8" OEM | Detailed Design | Mechanical Design Review |  | GMLA1 |  |  | 0 | Wendy Ni |  |  | N |  |  | 1900-01-10 |  | This product starts from FFP | Lori Tsai
Automotive | dezl OTR Series 2022- 7" | Pilot Run | Pilot Run Build Complete | 2022-03-15 | GMLA3 | 2022-03-08 | TBD | 2022-04-07 | Wendy Ni | Y | 80.85% | Y |  | Y | 2022-04-19 | 2022-04-11 |  | Stephanie Yang | 2022-04-18 |  |  |  |  | 43% | 88% | 92% | 85% | 80% | 100%
Automotive | Tread 8" OEM | Pilot Run | Pilot Run Build Complete |  | GMLA3 |  | 2022-04-14 | 2022-04-14 | Wendy Ni | R | 78.72% | N/A |  | Y | 2022-04-26 | 2022-04-26 |  | Lori Tsai | [5 empty] | 71% | 75% | 92% | 85% | 40% | 100%
Outdoor | Approach Z50 | Detailed Design | Mechanical Design Review | 2020-11-11 | GMLA1 |  |  |  | Chris Kuo | [8 empty] | Robben Liu/ Donna Chiu
Outdoor | Approach Z50 | Factory Prototye | Factory Prototype Design Review | 2022-08-23 | GMLA2 |  |  |  | Chris Kuo | [8 empty] | Robben Liu/ Donna Chiu
Outdoor | Approach Z50 | Pilot Run | Pilot Run Build Complete | 2022-10-28 | GMLA3 |  |  |  | Chris Kuo | [8 empty] | Robben Liu/ Donna Chiu
Marine | BlueNET Switch | Detailed Design | Mechanical Design Review | 2022-01-04 | GMLA1 |  |  |  | Chris Kuo | [8 empty] | Tim Wu
Marine | BlueNET Switch | Factory Prototye | Factory Prototype Design Review | 2022-12-15 | GMLA2 |  |  |  | Chris Kuo | [8 empty] | Tim Wu
Marine | BlueNET Switch | Pilot Run | Pilot Run Build Complete | 2023-02-03 | GMLA3 |  |  |  | Chris Kuo | [8 empty] | Tim Wu
Marine | Force Kraken Trolling Motor | Detailed Design | Mechanical Design Review | 2022-02-22 | GMLA1 | 2022-02-01 | 2022-03-05 | 2022-03-05 | Jason Hsu |  |  | N/A |  | N/A | 2022-03-16 |  | No WP and will have FP1 directly, so remove GMLA1 report. | Tim Wu
Marine | Force Kraken Trolling Motor | Factory Prototye | Factory Prototype Design Review | 2023-02-09 | GMLA2 | 2023-01-19 | 2022-09-01 | 2022-09-01 | Jason Hsu | [5 empty] | 2022-09-13 |  |  | Tim Wu
Marine | Force Kraken Trolling Motor | Pilot Run | Pilot Run Build Complete | 2023-03-24 | GMLA3 | 2023-03-17 |  | 2023-03-17 | Jason Hsu | [5 empty] | 2023-03-29 |  |  | Tim Wu
Marine | LED Control Module | Detailed Design | Mechanical Design Review | 2023-02-28 | GMLA1 |  |  |  | Jason Hsu | [8 empty] | TBD
Marine | LED Control Module | Factory Prototye | Factory Prototype Design Review | 2023-10-02 | GMLA2 |  |  |  | Jason Hsu | [8 empty] | TBD
Marine | LED Control Module | Pilot Run | Pilot Run Build Complete | 2023-11-07 | GMLA3 |  |  |  | Jason Hsu | [8 empty] | TBD
Marine | GMR xHD3 Magnetron Open Arrays | Detailed Design | Mechanical Design Review | 2022-04-27 | GMLA1 |  | 2022-04-18 | 2022-04-18 | Jason Hsu | G | 91.67% | Y |  | Y | 2022-04-28 | 2022-04-28 |  | Stephanie Yang | [5 empty] | 75% | 100% | 100% | 100% | 100%
Marine | GMR xHD3 Magnetron Open Arrays | Factory Prototye | Factory Prototype Design Review | 2022-09-29 | GMLA2 |  | 2022-04-18 |  | Jason Hsu | [8 empty] | Stephanie Yang
Marine | GMR xHD3 Magnetron Open Arrays | Pilot Run | Pilot Run Build Complete | 2022-11-29 | GMLA3 |  | 2022-04-18 |  | Jason Hsu | [8 empty] | Stephanie Yang
Outdoor | Xero B60i Laser Navigation Binoculars | Detailed Design | Mechanical Design Review | 2023-03-29 | GMLA1 |  |  |  | Chris Kuo | [8 empty] | TBD
Outdoor | Xero B60i Laser Navigation Binoculars | Factory Prototye | Factory Prototype Design Review | 2023-10-26 | GMLA2 |  |  |  | Chris Kuo | [8 empty] | TBD
Outdoor | Xero B60i Laser Navigation Binoculars | Pilot Run | Pilot Run Build Complete | 2024-01-18 | GMLA3 |  |  |  | Chris Kuo | [8 empty] | TBD
| RV Fixed Displays (7"/10") | [7 empty] | Jason Hsu
| ECHOMAP UHD2 (Keyed) | [7 empty] | Jason Hsu
| ECHOMAP UHD2 (Touch) | [7 empty] | Jason Hsu
| TXTW22_Drive+3.0 (Taroko) | [7 empty] | Ray Hu/Simon Ko
| dezl OTR Series 2022 | [7 empty] | Wendy Ni
| GPSMAP 9000 | [7 empty] | Jason Hsu
| zumo XT2 | [7 empty] | Wendy Ni
| Tire Temp Sensor | [7 empty] | Wendy Ni
| Catalyst Kart/Moto/Roadster | [7 empty] | Aalto Lo
Formulas:
TBD = IF(OR([No MPM]="no MPM", [No MPM]=""), G397,[No MPM])
Note on G1: Yang, Jessica: G1: Mechanical Design Review -21 G2: Factory prototype design review -21 G3: Pilot Run Built Complete -7
Note on H1: Yang, Jessica: Close Meeting在2020/12/7 (含)以後的，會在PRWeb GMLA System直接評估GMLA結果。
Note on K11: Yang, Jessica: *GMLA result: Down grad to “B” Down grade when amount of failed * marked item is larger than 2. Down grade when any ** marked item fails
Note on P16: Yang, Jessica: Wait for FFP2 close meeting: 2020/1/21
Note on P18: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: FFP2 close meeting 12/20 回覆: 延至12/26
Note on P19: Yang, Jessica: wait for FFP2 close meeting
Note on H23: Yang, Jessica: FP3 Assembly: 2020/1/13~1/22
Note on B66: Yang, Jessica: ECHOMAP PLUS A7
Note on B75: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on B77: Yang, Jessica: family name: eRVR315
Note on B107: Yang, Jessica: family name: eRVR315
Note on B111: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on H114: Tsai, Abner: wp2 close meeting
Note on B116: Yang, Jessica: PRWeb: Tread XL (10")
Note on B118: Yang, Jessica: PRWeb: Tread XL (10")
Note on B123: Yang, Jessica: ECHOMAP PLUS A7
Note on B124: Yang, Jessica: PM System: EPIX - 47MM (Gen 2)
Note on B152: Yang, Jessica: ECHOMAP PLUS A7
Note on B158: Yang, Jessica: family name: eRVR315
Note on H158: Pan, Nixon: Per OLA request PR built delay to 12/30 due to resolve some FP open issues for layout minor changes.
Note on B167: Yang, Jessica: family name: mini2
Note on B171: Yang, Jessica: family name: EPIX 2 PM System: EPIX - 47MM (Gen 2)
Note on B186: Yang, Jessica: FR255 Basic: 非音樂版 FR 255 & FR255S: 兩份GMLA
Note on B197: Yang, Jessica: Instinct 2 - DEZL
Note on E210: Yang, Jessica: prototype design review date (the mechanical design review date is blank in PM system)
Note on B221: Yang, Jessica: Family: Messenger
Note on B226: Yang, Jessica: PRWeb: Tread XL (10")
Note on B228: Yang, Jessica: PRWeb: Tread XL (10")
Note on B231: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on B232: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on B247: Yang, Jessica: PM System: EPIX - 47MM (Gen 2)
Note on B251: Yang, Jessica: Family name: INSTINCT 2 - DEZL
Note on B256: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on B263: Yang, Jessica: Family name:ALPHA T20
Note on B264: Yang, Jessica: PRWeb: Tread - SXS (8")
Note on B266: Yang, Jessica: family name: DEZL OTRLGV610
Note on B267: Yang, Jessica: family name: DEZL OTRLG710
Note on B268: Yang, Jessica: Family name: DEZL OTRLGV1010
Note on B270: Yang, Jessica: Family name: DEZL OTRLGV810
Note on B274: Yang, Jessica: PM System: Instinct Crossover
Note on B277: Yang, Jessica: Family name: GPSMAP 9X22
Note on B282: Yang, Jessica: PRWeb: Tread XL (10")
Note on B286: Yang, Jessica: Product Launch Family Name:PANOPTIX LIVE SCOPE XR
Note on B319: Yang, Jessica: Family Name: RV 7 FD2
Note on B321: Yang, Jessica: Family Name: RV 10 FD2
Note on B327: Yang, Jessica: Family name: Messenger
Note on B333: Yang, Jessica: PRWeb: Tread XL (10")
Note on B338: Yang, Jessica: Famili name: GPSMAP 9X19
Note on B390: Yang, Jessica: PM System: Instinct Crossover
Note on B406: Yang, Jessica: PM System: Instinct Crossover
Note on B526: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: 資料串聯用，不要刪除阿~~
Note on B527: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: 資料串聯用，不要刪除RR
Note on B528: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: 資料串聯用，不要刪除RR
Note on B529: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: 資料串聯用，不要刪除~~
Note on B530: [對話串註解] 您的 Excel 版本可讓您讀取此對話串註解; 但若以較新的 Excel 版本開啟此檔案，將會移除對它進行的所有編輯。深入了解: https://go.microsoft.com/fwlink/?linkid=870924。 註解: 資料串聯用，不要刪除~~