## New Production Status Summary
New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20 | New Production Status Summary 2023-03-20
Project Name | Project Id | PM Project Name | PM Project Id | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM | DPQE
Rally 110/210 Family | 1135 | Rally 110/210 Family | 16349 | Detailed Design | Fitness | 2025-01-06 | 2022-12-20 | 2023-01-10 | [5 empty] | 2025-02-17 | 1 | 0 |  | Stephen.Shen | John.Chiu | Neo.Lin | Chris.Kuo
Force Kayak Propulsion System | 1134 | Force Kayak Propulsion System | 10617 | Top Level Design | Marine | 2024-11-11 | 2023-01-13 | 2023-04-17 | 2023-07-06 | 2023-07-20 | 2023-07-31 |  |  | 2024-12-23 | 1 | 0 |  | Steve.Chiang | Allen.Chu Jimmy.Kuo | Lori.Tsai | Jasoncy.Hsu
GPSMAP 68 | 1091 | GPSMAP 68 | 16137 | Top Level Design | Outdoor | 2024-10-07 | 2022-12-20 | 2023-01-10 | 2023-08-16 | 2023-08-30 | 2024-01-04 |  |  | 2024-11-18 | 1 | 0 |  | Ruby.Huang | Viola.Kao Joel.Wu | Nixon.Pan | Howard.Jen
Engine Cut-Off System (ECOS/MOB) | 1180 | Engine Cut-Off System (ECOS/MOB) | 16198 | Top Level Design | Marine | 2024-09-30 | 2023-01-02 | 2023-01-23 | 2023-10-18 | 2023-11-01 | 2023-11-17 |  |  | 2024-11-11 | 1 | 0 |  | Bowman.Lai | Darren.Chen Charlotte.Chen | Nick.Yen
Xero B60i Laser Navigation Binoculars | 1119 | Xero B60i Laser Navigation Binoculars | 13229 | Detailed Design | Outdoor | 2024-09-16 | 2022-03-17 | 2022-04-07 | 2023-09-07 | 2023-09-21 | 2023-09-28 |  |  | 2024-10-28 | 1 | 0 |  | Alex.Pu | Jason.Cai | Donna.Chiu | Chris.Kuo
TGWW25 | 1138 | TGWW25 | 16227 | Top Level Design | OEM Auto | 2024-08-31 | [5 empty] | 2023-09-07 | 2024-06-28 | 2024-10-11 | 1 | 0 |  | Davidsd.Lin | Jim.Shen Colby.Ren Jeff.Lin | Jason.Fan | Ray.Hu Simon.Ko
Varia Headlight Camera | 1152 | Varia Headlight Camera | 16183 | Top Level Design | Fitness | 2024-08-19 | [7 empty] | 2024-09-30 | 1 | 0 |  | Stephen.Shen | Amberif.Wang | Tina.Yang | Chris.Kuo
LYWW24 | 1113 | LYWW24 | 15976 | Top Level Design | OEM Auto | 2024-08-05 | 2022-05-20 | 2022-06-10 |  |  |  | 2022-09-23 | 2023-10-24 | 2024-09-16 | 1 | 0 |  | Davidsd.Lin Erichw.Wang | Jim.Shen Colby.Ren | Nick.Yen Jason.Fan | Simon.Ko
Tread 10" OEM - Kawasaki CAN | 1142 | Tread 10" OEM - Kawasaki CAN | 16584 | Pilot Run | Automotive | 2024-05-27 | [5 empty] | 2023-04-07 |  | 2024-07-08 | 1 | 2 |  | Steve.Chiang | Jason.Cai | Neo.Lin
Approach G20 | 1168 | Approach G20 | 15619 | Top Level Design | Outdoor | 2024-05-20 | 2023-01-11 | 2023-02-01 | 2023-05-17 | 2023-05-31 | 2023-09-01 |  |  | 2024-07-01 | 1 | 0 |  | Ruby.Huang | Viola.Kao Daniel.Tsai | Erinsa.Lu | Chris.Kuo
Flush Mount Stainless Steel Camera | 1151 | Flush Mount Stainless Steel Camera | 16300 | Detailed Design | Marine | 2024-05-13 | 2022-11-02 | 2022-11-23 |  |  | 2023-09-22 | 2023-10-06 | 2024-02-14 | 2024-06-24 | 1 | 0 |  | Bowman.Lai | Isaac.Wang | Tim.Wu | Evelyn.Wang
Edge 1050 | 1137 | Edge 1050 | 16197 | Detailed Design | Fitness | 2024-05-13 | [7 empty] | 2024-06-24 | 1 | 0 |  | Stephen.Shen | JulieJJ.Lin Viola.Kao | Ryan.Li | Wendy.Ni
EPIX (Gen 3) 51mm | 1174 | EPIX (Gen 3) 51mm | 16801 | Top Level Design | Outdoor | 2024-05-06 | 2022-12-20 | 2023-01-10 | 2023-03-31 | 2023-04-14 | 2023-05-22 |  |  | 2024-06-17 | 1 | 0 |  | Shawn.Huang | Viola.Kao Eason.Chen | Leol.Chen | Howard.Jen
dezl headset (2nd Gen) | 1132 | dezl headset (2nd Gen) | 16249 | Detailed Design | Automotive | 2024-05-06 | 2022-08-11 | 2022-09-01 | [5 empty] | 2024-06-17 | 1 | 0 |  | Shawn.Yu | Chloe.Lin2 | Allyson.Kuo | Wendy.Ni
BMW MGU22/IDC_C5 | 1165 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2024-05-02 | [7 empty] | 2024-06-13 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Jasper.Huang Sandy.Lee Joseph.Yen Mark.Chang | Tiffany2.Chen Ray.Hu Cherry.Tsai
2024 Value Dash Cams(Mini3) | 1158 | 2024 Value Dash Cams | 16544 | Top Level Design | Automotive | 2024-03-18 | 2023-01-13 | 2023-02-03 | 2023-03-24 | 2023-04-07 | 2023-07-17 |  |  | 2024-04-29 | 1 | 0 |  | Stephen.Shen | Frankie.Lee Amberif.Wang Jasonch.Chen | Jason.Fan | Wendy.Ni
Prop Drive Cost Down | 1115 | Prop Drive Cost Down | 16233 | Factory Prototype | Marine | 2024-02-12 | 2022-02-14 | 2022-03-07 | 2022-07-08 | 2022-07-22 | 2023-01-05 |  |  | 2024-03-25 | 1 | 0 |  | Iris.Wu | John.Chiu | Nick.Yen | Jasoncy.Hsu
LED Control Module | 1066 | LED Control Module | 13134 | Detailed Design | Marine | 2024-01-08 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  |  |  | 2024-02-19 | 1 | 0 |  | Iris.Wu | Frankie.Lee Darren.Chen | Robben.Liu | Evelyn.Wang
Product - GDU147XW | 1049 | Product - GDU147XW | 12509 | Product Development Plan | Aviation | 2024-01-03 | [7 empty] | 2024-02-14 | 1 | 5 |  | Stephen.Shen | Edward.Tu Jimmy.Kuo | Donna.Chiu Sandy.Lee | Evelyn.Wang
Large Format TXi | 1167 | Large Format TXi | 16136 | Derivative Product Concept | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  |  |  | Donna.Chiu | Evelyn.Wang
Large Format TXi | 1155 | Large Format TXi | 16136 | Derivative Product Concept | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  |  |  | Donna.Chiu | Evelyn.Wang
Product - GDU77XW | 1048 | Product - GDU77XW | 12510 | Product Development Plan | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  |  |  | Donna.Chiu Sandy.Lee | Evelyn.Wang
Forerunner 165 and 165 Music | 1145 | Forerunner 165 and 165 Music | 16437 | Detailed Design | Fitness | 2023-12-29 | 2022-07-25 | 2022-08-15 | 2022-11-04 | 2022-11-18 | 2022-11-23 |  |  | 2024-02-09 | 1 | 0 |  | PeiRu.Tsai | Viola.Kao Johnny.Ko | Erinsa.Lu | Cooper.Wang
Approach R50 | 1012 | Approach R50 | 10926 | Detailed Design | Outdoor | 2023-12-25 | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 | 2022-02-28 |  |  | 2024-02-05 | 1 | 0 |  | Roger.Chan Steve.Chiang | Chloe.Lin2 Johnny.Liu | Allyson.Kuo | Chris.Kuo
GPSMAP 9500 | 1141 | GPSMAP 9500 | 16616 | Detailed Design | Marine | 2023-11-27 |  |  | 2023-01-13 | 2023-01-27 | 2023-02-03 |  |  | 2024-01-08 | 1 | 0 |  | Bowman.Lai | Allen.Chu Ruby.Chang | Nick.Yen | Jasoncy.Hsu
Lily 2 | 1123 | Lily 2 | 15993 | Factory Prototype | Fitness | 2023-10-30 | [5 empty] | 2023-03-07 |  | 2023-12-11 | 1 | 0 |  | Shawn.Huang | Steve.Lee Viola.Kao George.Chang | Tina.Yang Alexty.Chang | Ernest.Fu
ECHOMAP Ultra 2 - 12" | 1147 | ECHOMAP Ultra 2 | 16483 | Detailed Design | Marine | 2023-10-23 |  |  | 2023-03-09 | 2023-03-23 | 2023-03-24 |  |  | 2023-12-04 | 1 | 0 |  | Derek.Cheng | Darren.Chen Isaac.Wang | Donna.Chiu | Jasoncy.Hsu
ECHOMAP Ultra 2 - 10" | 1178 | ECHOMAP Ultra 2 | 16483 | Detailed Design | Marine | 2023-10-23 |  |  | 2023-03-09 | 2023-03-23 | 2023-03-24 |  |  | 2023-12-04 | 1 | 0 |  | Derek.Cheng | Darren.Chen Isaac.Wang | Donna.Chiu | Jasoncy.Hsu
Xero L60i Laser Navigator | 1016 | Xero L60i Laser Navigator | 8510 | Detailed Design | Outdoor | 2023-10-16 | 2021-02-25 | 2021-03-18 | 2022-10-28 | 2022-11-11 | 2022-11-25 |  |  | 2023-11-27 | 1 | 3 |  | Alex.Pu | Jason.Cai Jasonch.Chen | Lori.Tsai | Chris.Kuo
Descent Mk3 Series - Small | 1058 | Descent Mk3 Series | 16205 | Detailed Design | Outdoor | 2023-10-09 | 2021-08-13 | 2021-09-03 | 2022-07-14 | 2022-07-28 | 2022-08-26 | 2023-04-14 | 2023-07-03 | 2023-11-20 | 1 | 2 |  | Daniel.Mao | Viola.Kao Eric.Chiang | Franksl.Chen | Cooper.Wang
Tread 8" OEM w/ CAN | 1063 | Tread 8" OEM w/ CAN | 15955 | Pilot Run | Automotive | 2023-10-02 | [6 empty] | 2022-03-16 | 2023-11-13 | 1 | 0 |  | Derek.Cheng | Johnny.Liu Jason.Cai | Lori.Tsai | Wendy.Ni
Descent Mk3 Series - Large | 1057 | Descent Mk3 Series | 12994 | Factory Prototype | Outdoor | 2023-09-25 | 2021-08-13 | 2021-09-03 | 2022-07-20 | 2022-08-03 | 2022-08-26 | 2023-04-19 |  | 2023-11-06 | 1 | 3 |  | Shawn.Huang | Maggie.Chang Viola.Kao | Leol.Chen | Cooper.Wang
BMW Motorrad Nav VI Production Support | 1140 | BMW Motorrad Nav VI Production Support | 10170 | Pilot Run | OEM Auto | 2023-09-25 | [5 empty] | 2022-10-19 | 2023-04-21 | 2023-11-06 | 1 | 1 |  | Alex.Pu | Frankie.Lee | Nick.Yen
Alpha LTE | 1139 | Alpha LTE | 16095 | Detailed Design | Outdoor | 2023-09-18 | 2022-04-28 | 2022-05-19 | [5 empty] | 2023-10-30 | 1 | 0 |  | Dannyhp.Cheng | Lulu.Lee | Tina.Yang | Ernest.Fu
IMWW23 | 1084 | IMWW23 | 14434 | Top Level Design | OEM Auto | 2023-09-18 |  |  | 2021-11-05 | 2021-11-19 |  | 2022-11-24 | 2023-05-10 | 2023-10-30 | 1 | 0 |  | Shawn.Yu Davidsd.Lin Erichw.Wang | Jim.Shen Colby.Ren | Jason.Fan Nick.Yen | Simon.Ko Cherry.Tsai
GSD28 | 1068 | GSD28 | 15876 | Factory Prototype | Marine | 2023-09-11 | 2021-10-07 | 2021-10-28 | 2022-11-25 | 2022-12-09 | 2022-12-21 |  | 2023-07-04 | 2023-10-23 | 1 | 0 |  | Bowman.Lai | Edward.Tu Charlotte.Chen | Donna.Chiu | Jasoncy.Hsu
eTrex Solar | 1065 | eTrex Solar | 10901 | Factory Prototype | Outdoor | 2023-09-11 | 2021-10-14 | 2021-11-04 | 2022-12-07 | 2022-12-21 | 2023-02-06 | 2023-02-13 |  | 2023-10-23 | 1 | 0 |  | Steve.Chiang | Viola.Kao Willycw.Wu | Tina.Yang Franksl.Chen | Chris.Kuo
HRM-Fit | 1160 | HRM-Fit | 16053 | Detailed Design | Fitness | 2023-09-04 | 2022-09-22 | 2022-10-13 | 2023-04-04 | 2023-04-18 | 2022-12-19 |  |  | 2023-10-16 | 1 | 0 |  | Iris.Wu | Johnny.Liu Frankie.Lee | Erinsa.Lu | Chris.Kuo
MARQ Carbon | 904 | MARQ Carbon | 11252 | Factory Prototype | Outdoor | 2023-09-04 | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 | 2022-12-23 | 2023-04-19 | 2023-10-16 | 1 | 5 |  | Shawn.Huang | Pattie.Lan Viola.Kao Peter.Lo | Nixon.Pan | Cooper.Wang
TXTW22_Drive+3.0 (Taroko) -12.3 DA | 964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Product Launch | OEM Auto | 2023-09-04 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 | 2023-04-03 | 2023-10-16 | 1 | 0 |  | Davidsd.Lin Erichw.Wang Wells.Yu Davidsd.Lin | Jim.Shen Colby.Ren Jeff.Lin Zack.Lin Colby.Ren Jeff.Lin | Nick.Yen Jason.Fan Nick.Yen | Ray.Hu Simon.Ko Ray.Hu Simon.Ko
Connect 50 transition to Taiwan Manufacturing | 1127 | Connect 50 transition to Taiwan Manufacturing | 16347 | Pilot Run | Marine | 2023-08-21 | [7 empty] | 2023-10-02 | 1 | 0 |  | Derek.Cheng | Charlotte.Chen
DC-2023 Premium Dash Cameras | 1130 | DC-2023 Premium Dash Cameras | 16199 | Factory Prototype | Automotive | 2023-08-14 | 2022-07-15 | 2022-08-05 | 2023-01-19 | 2023-02-02 | 2023-02-03 | 2023-03-24 | 2023-05-29 | 2023-09-25 | 1 | 1 |  | Stephen.Shen | Chloe.Lin2 | Donna.Chiu Sandy.Lee | Wendy.Ni
GPSMAP 9000 - 19" | 1051 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-08-07 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-18 | 1 | 1 |  | Roger.Chan Derek.Cheng | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 - 24" | 1053 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-08-07 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-18 | 1 | 2 |  | Roger.Chan Derek.Cheng | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 -27" | 1054 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-08-07 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-18 | 1 | 1 |  | Roger.Chan Derek.Cheng | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 - 22" | 1052 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-08-07 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-09-18 | 1 | 1 |  | Roger.Chan Derek.Cheng | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
vivoactive 5 | 1146 | vivoactive 5 | 16388 | Factory Prototype | Fitness | 2023-07-31 |  |  | 2022-09-09 | 2022-09-23 | 2022-09-02 |  |  | 2023-09-11 | 1 | 0 |  | Anton.Lin Vincent.Yeh | Viola.Kao Willycw.Wu | Jackhl.Chen
Descent S1 Buoy | 1006 | Descent S1 Buoy | 12799 | Factory Prototype | Outdoor | 2023-07-31 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 | 2022-08-15 | 2022-11-14 | 2023-09-11 | 1 | 0 |  | Daniel.Mao | Viola.Kao Daniel.Tsai | Franksl.Chen | Aalto.Lo
Catalyst KMR - Hub | 1111 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-24 | 2019-07-24 | 2019-08-14 | 2022-02-10 | 2022-02-24 | 2022-06-27 |  |  | 2023-09-04 | 1 | 1 |  | Frankie.Lee Stephen.Shen Steve.Chiang | Frankie.Lee Steve.Chiang | Allyson.Kuo Sandy.Lee | Evelyn.Wang
Catalyst KMR - Camera | 1110 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-24 | 2019-07-24 | 2019-08-14 | 2022-02-10 | 2022-02-24 | 2022-06-27 |  |  | 2023-09-04 | 1 | 2 |  | Frankie.Lee Stephen.Shen Steve.Chiang | Frankie.Lee Steve.Chiang | Allyson.Kuo Sandy.Lee | Evelyn.Wang
TWIN23 | 1144 | TWIN23 | 16503 | Detailed Design | OEM Auto | 2023-07-17 | [7 empty] | 2023-08-28 | 1 | 0 |  | Davidsd.Lin Shawn.Yu | Colby.Ren Jeff.Lin Jim.Shen |  | Ray.Hu Simon.Ko
Catalyst KMR - Display | 1120 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-07-10 | 2021-09-20 | 2021-10-11 | 2022-02-04 | 2022-02-18 | 2022-06-27 |  |  | 2023-08-21 | 1 | 2 |  | Frankie.Lee Stephen.Shen Steve.Chiang | Frankie.Lee Steve.Chiang | Allyson.Kuo Sandy.Lee | Evelyn.Wang
Serv - 7" | 1080 | Serv (7"/10") | 14554 | Pilot Run | Marine | 2023-07-10 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-08-03 | 2022-08-26 | 2022-12-20 | 2023-08-21 | 1 | 0 |  | Bowman.Lai | Allen.Chu John.Chiu Ruby.Chang | Tim.Wu | Jasoncy.Hsu
Serv - 10" | 1081 | Serv (7"/10") | 14554 | Pilot Run | Marine | 2023-07-10 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-07-20 | 2022-08-26 | 2022-12-20 | 2023-08-21 | 1 | 1 |  | Bowman.Lai | Allen.Chu John.Chiu Ruby.Chang | Tim.Wu | Jasoncy.Hsu
Force Kraken Trolling Motor | 978 | Force Kraken Trolling Motor | 12789 | Factory Prototype | Marine | 2023-07-10 | 2019-12-17 | 2020-01-07 | 2022-02-08 | 2022-02-22 | 2022-07-18 | 2022-08-15 | 2023-04-11 | 2023-08-21 | 1 | 4 |  | Iris.Wu | John.Chiu Allen.Chu Daniel.Lee Jimmy.Kuo | Tim.Wu | Jasoncy.Hsu
Product - G3X/G500TXi Hybrid | 1050 | Product - G3X/G500TXi Hybrid | 12717 | Product Development Plan | Aviation | 2023-07-01 | [7 empty] | 2023-08-11 | 1 | 0
BlueNet Gateway | 961 | BlueNet Gateway | 9756 | Pilot Run | Marine | 2023-06-26 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-04-21 | 2023-02-01 | 2023-08-07 | 1 | 0 |  | Stephen.Shen | Allen.Chu | Tim.Wu | Wendy.Ni
BlueNet Switch | 962 | BlueNet Switch | 9755 | Pilot Run | Marine | 2023-06-26 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-05-19 | 2023-02-01 | 2023-08-07 | 1 | 0 |  | Stephen.Shen | Chloe.Lin2 | Tim.Wu | Wendy.Ni
Xero C1 Chronograph | 989 | Xero C1 Chronograph | 12253 | Factory Prototype | Outdoor | 2023-06-26 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-24 | 2023-01-04 | 2023-03-31 | 2023-08-07 | 1 | 0 |  | PeiRu.Tsai | Viola.Kao Kuo.Kuo | Leol.Chen | Chris.Kuo
GT15M Thru-Hull Flush | 1129 | GT15M Thru-Hull Flush | 16387 | Factory Prototype | Marine | 2023-06-19 | 2022-08-26 | 2022-06-08 | 2022-11-03 | 2022-11-17 | 2022-12-23 |  |  | 2023-07-31 | 1 | 0 |  | Iris.Wu Joannajh.Huang | Edward.Tu Jimmy.Kuo | Leol.Chen | Evelyn.Wang
GMR xHD3 Domes (18/24xHD replacement) | 1126 | GMR xHD3 Domes (18/24xHD replacement) | 16246 | Factory Prototype | Marine | 2023-05-29 | 2022-04-01 | 2022-04-22 | 2022-08-30 | 2022-09-13 | 2022-10-04 | 2022-10-21 | 2023-03-02 | 2023-07-10 | 1 | 0 |  | Alex.Pu | Darren.Chen Isaac.Wang | Nick.Yen Jason.Fan | Jasoncy.Hsu
Venu 3 | 1089 | Venu 3 | 15520 | Pilot Run | Fitness | 2023-05-29 | 2021-09-09 | 2021-09-30 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-08-03 | 2023-03-15 | 2023-07-10 | 1 | 1 |  | Shawn.Huang | Steve.Lee Viola.Kao George.Chang | Tina.Yang Alexty.Chang | Cooper.Wang
Venu 3S | 1090 | Venu 3S | 15519 | Pilot Run | Fitness | 2023-05-29 | 2021-09-09 | 2021-09-30 | 2021-12-08 | 2021-12-22 | 2022-04-26 |  |  | 2023-07-10 | 1 | 1 |  | Shawn.Huang | Steve.Lee Viola.Kao Roger.Huang | Jackhl.Chen Alexty.Chang | Ernest.Fu
Panoptix PS70 - (SSMB) | 833 | Panoptix PS70 - (SSMB) | 10091 | Pilot Run | Marine | 2023-05-29 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-09-05 | 2023-03-07 | 2023-07-10 | 1 | 0 |  | Derek.Cheng | Jimmy.Kuo | Tim.Wu | Evelyn.Wang
GMR xHD3 Magnetron Open Arrays | 1105 | GMR xHD3 Magnetron Open Arrays | 15804 | Pilot Run | Marine | 2023-05-02 |  |  | 2022-05-06 | 2022-05-20 | 2022-08-03 |  |  | 2023-06-13 | 1 | 0 |  | Bowman.Lai | Isaac.Wang | Allyson.Kuo | Jasoncy.Hsu
fenix 7 Pro | 1075 | fenix 7 Pro | 14729 | Pilot Run | Outdoor | 2023-04-24 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-23 | 2022-12-30 | 2023-06-05 | 1 | 3 |  | Ruby.Huang | Viola.Kao Robert.Pan Stansy.Wang | Nixon.Pan | Ernest.Fu
Montana 7xx Parts Shortage Redesign | 1153 | Montana 7xx Parts Shortage Redesign | 15279 | Pilot Run | Outdoor | 2023-04-17 | [7 empty] | 2023-05-29 | 1 | 1 |  | Dannyhp.Cheng | Joel.Wu |  | Chris.Kuo
Alpha Dog Collar | 856 | Alpha Dog Collar | 7029 | Pilot Run | Outdoor | 2023-04-10 | 2021-03-15 | 2021-04-05 | 2021-08-09 | 2021-08-23 | 2022-01-10 | 2022-01-25 | 2022-11-23 | 2023-05-22 | 1 | 0 |  | Dannyhp.Cheng | Eason.Chen | Robben.Liu | Chris.Kuo
Approach S70 | 1088 | Approach S70 - 47mm | 16176 | Pilot Run | Outdoor | 2023-04-10 | 2021-08-05 | 2021-08-26 | 2022-03-15 | 2022-03-29 | 2022-07-22 | 2022-09-07 |  | 2023-05-22 | 1 | 0 |  | Ruby.Huang Andyjs.Chen | Viola.Kao Daniel.Tsai | Jackhl.Chen Erinsa.Lu | Cooper.Wang
Approach S70s | 1036 | Approach S70 - 42mm | 15419 | Pilot Run | Outdoor | 2023-04-10 | 2021-08-05 | 2021-08-26 | 2022-03-15 | 2022-03-29 | 2022-07-22 | 2022-09-07 |  | 2023-05-22 | 1 | 2 |  | Vincent.Yeh Dannyhp.Cheng | Viola.Kao Kuo.Kuo | Jackhl.Chen | Cooper.Wang
BMW MGU22/IDC | 815 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2023-04-01 |  | 2019-08-30 | 2020-04-10 | 2020-04-24 | 2020-04-24 |  |  | 2023-05-12 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | Jasper.Huang James.Chou Jasper.Huang James.Chou | Jasper.Huang Sandy.Lee Joseph.Yen Mark.Chang Sandy.Lee | Tiffany2.Chen Ray.Hu Cherry.Tsai Cherry.Tsai Tiffany2.Chen Allen.Chen Ray.Hu Ramzi.Jundi Melanie.Bruns Marina.Keller Martin.Overzier Andy.Kocon Ramzi.Jundi Melanie.Bruns Marina.Keller Martin.Overzier Andy.Kocon
fenix 7X Pro | 1077 | fenix 7X Pro | 16112 | Detailed Design | Outdoor | 2023-03-27 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-28 |  | 2023-05-08 | 1 | 1 |  | Shawn.Huang | Viola.Kao Roger.Huang Stansy.Wang | Jackhl.Chen | Ernest.Fu
fenix 7S Pro (2022) | 1076 | fenix 7S Pro (2022) | 16108 | Pilot Run | Outdoor | 2023-03-27 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-26 | 2022-12-30 | 2023-05-08 | 1 | 1 |  | Dannyhp.Cheng | Viola.Kao Robert.Pan Stansy.Wang | Franksl.Chen | Cooper.Wang
Foretrex 801/901 | 1078 | Foretrex 801/901 | 14769 | Product Launch | Outdoor | 2023-03-20 | 2021-10-01 | 2021-10-22 | 2022-03-11 | 2022-03-25 | 2022-07-22 | 2022-09-23 |  | 2023-05-01 | 1 | 0 |  | PeiRu.Tsai | Amyry.Chen Viola.Kao | Neo.Lin | Ernest.Fu
EPIX PRO (Gen 2) 47mm | 1093 | EPIX PRO (Gen 2) 47mm | 16217 | Detailed Design | Outdoor | 2023-03-13 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 |  |  | 2023-04-24 | 1 | 3 |  | Ruby.Huang | Viola.Kao Stansy.Wang Robert.Pan | Neo.Lin | Cooper.Wang
zumo XT2 | 1101 | zumo XT2 | 16069 | Product Launch | Automotive | 2023-03-13 | 2021-09-15 | 2021-10-06 | 2022-03-08 | 2022-03-22 | 2022-04-14 |  | 2022-12-01 | 2023-04-24 | 1 | 0 |  | Derek.Cheng | Frankie.Lee | Nick.Yen | Wendy.Ni
EPIX PRO (Gen 2) 51mm | 1094 | EPIX PRO (Gen 2) 51mm | 16218 | Detailed Design | Outdoor | 2023-03-06 | [5 empty] | 2022-08-31 | 2022-12-14 | 2023-04-17 | 1 | 0 |  | PeiRu.Tsai | Viola.Kao Roger.Huang Stansy.Wang | Robben.Liu | Cooper.Wang
Varia eBike Radar Tail Light (eRTL615) | 1102 | Varia eBike Radar Tail Light (eRTL615) | 15837 | Product Launch | Fitness | 2023-03-06 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-17 | 1 | 0 |  | PeiRu.Tsai | Lulu.Lee | Ryan.Li | Chris.Kuo
Instinct 2X Solar | 1112 | Instinct 2X Solar | 16020 | Product Launch | Outdoor | 2023-03-01 | 2022-02-04 | 2022-02-25 | 2022-07-29 | 2022-08-12 | 2022-04-01 | 2022-11-28 | 2022-12-09 | 2023-04-12 | 1 | 3 |  | Daniel.Mao Andyjs.Chen | Viola.Kao Eason.Chen Arthur.Wang | Lori.Tsai | Aalto.Lo
EPIX PRO (Gen 2) 42mm | 1092 | EPIX PRO (Gen 2) 42mm | 15803 | Product Launch | Outdoor | 2023-03-01 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 | 2022-09-01 | 2022-11-28 | 2023-04-12 | 1 | 2 |  | Daniel.Mao | Robert.Pan Stansy.Wang Viola.Kao | Franksl.Chen | Aalto.Lo
Edge 540 840 | 1069 | Edge 540 840 | 14509 | Product Launch | Fitness | 2023-02-13 | 2021-03-11 | 2021-04-01 | 2021-04-14 | 2021-04-28 | 2022-02-07 | 2022-06-03 | 2022-10-14 | 2023-03-27 | 1 | 0 |  | Andyjs.Chen | Viola.Kao George.Chang Pattie.Lan | Leol.Chen | Chris.Kuo
eTrex SE | 1044 | eTrex SE | 15843 | Production | Outdoor | 2023-02-06 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 | 2022-05-23 |  | 2023-03-20 | 1 | 0 |  | Andyjs.Chen | Viola.Kao Lulu.Lee Eason.Chen | Neo.Lin Franksl.Chen | Chris.Kuo
Forerunner 965 | 1103 | Forerunner 965 | 16002 | Product Launch | Fitness | 2023-01-09 | 2021-12-17 | 2022-01-07 | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-02-20 | 1 | 1 |  | Anton.Lin | Viola.Kao Johnny.Ko Daniel.Tsai | Erinsa.Lu Alexty.Chang | Aalto.Lo
Forerunner 265s | 1118 | Forerunner 265 | 14529 | Production | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 0 |  | Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan | Ernest.Fu
Forerunner 265 | 1107 | Forerunner 265 | 14529 | Production | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 0 |  | Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan | Ernest.Fu
ECHOMAP UHD2 (Touch) 7" | 1059 | ECHOMAP UHD2 (Touch) | 13095 | Production | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  | 2022-10-07 | 2023-01-30 | 1 | 0 |  | Alex.Pu Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan | Jasoncy.Hsu
ECHOMAP UHD2 (Touch) 9" | 1041 | ECHOMAP UHD2 (Touch) | 13095 | Production | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  | 2022-10-07 | 2023-01-30 | 1 | 0 |  | Alex.Pu Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan | Jasoncy.Hsu
ECHOMAP UHD2 (Touch) 6" | 1018 | ECHOMAP UHD2 (Touch) | 13095 | Production | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2021-11-23 | 2022-05-06 | 2022-10-07 | 2023-01-30 | 1 | 0 |  | Alex.Pu Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan | Jasoncy.Hsu
Dash Cam Live (LTE) | 990 | Dash Cam Live (LTE) | 13009 | Production | Automotive | 2022-11-21 | 2020-09-18 | 2020-10-09 | 2020-11-30 | 2020-12-14 | 2021-06-14 | 2022-01-07 | 2022-07-28 | 2023-01-02 | 0 | 0 |  | Stephen.Shen | Jasonch.Chen | Lori.Tsai | Chris.Kuo
vivomove Trend (previously "4") | 1030 | vivomove Trend (previously "4") | 14004 | Production | Fitness | 2022-11-14 | 2020-11-13 | 2020-12-04 | 2021-10-01 | 2021-10-15 | 2021-11-03 | 2022-04-18 | 2022-08-05 | 2022-12-26 | 1 | 0 |  | Andyjs.Chen | Viola.Kao Joel.Wu | Leol.Chen | Aalto.Lo
Bounce(Waldo) | 862 | Bounce | 10919 | Production | Fitness | 2022-10-24 | 2019-09-03 | 2019-09-24 | 2019-10-22 | 2019-11-05 | 2020-04-30 |  | 2022-01-03 | 2022-12-05 | 1 | 0 |  | Shawn.Huang | Viola.Kao Calvinyt.Hsu | Franksl.Chen | Ernest.Fu
LIIN22 | 1108 | LIIN22 | 16129 | Product Launch | OEM Auto | 2022-10-11 | [7 empty] | 2022-11-22 | 1 | 0 |  | Shawn.Yu | Jim.Shen Shawn.Yu Colby.Ren |  | Ray.Hu Simon.Ko
Instinct Hybrid Analog/Digital(Ripley) | 1029 | Instinct Hybrid Analog/Digital | 13084 | Production | Outdoor | 2022-10-11 |  |  | 2021-12-01 | 2021-12-15 |  | 2022-01-05 |  | 2022-11-22 | 1 | 1 |  | Anton.Lin Anton.Lin | Viola.Kao Eric.Chiang Eric.Chiang Viola.Kao | Alexty.Chang Robben.Liu Robben.Liu Alexty.Chang | Aalto.Lo Aalto.Lo
Marq (Gen 2) | 972 | Marq (Gen 2) | 13004 | Production | Outdoor | 2022-10-10 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-11-21 | 0 | 0 |  | Shawn.Huang | Viola.Kao Arthur.Wang | Neo.Lin Alexty.Chang | Cooper.Wang
GST - MCU 2.0 | 966 | GST - MCU 2.0 | 12155 | Production | Marine | 2022-09-19 | [7 empty] | 2022-10-31 | 1 | 0 |  | Iris.Wu | Chloe.Lin2 |  | Jasoncy.Hsu
Alpha 200/200i Plus (i.MX7 Platform) | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | 16195 | Pilot Run | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 0 | 0 |  | Daniel.Mao Dannyhp.Cheng | JulieJJ.Lin
TXTW22_Drive+3.0 (Taroko)-9 DA | 953 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Product Launch | OEM Auto | 2022-08-24 |  |  | 2021-05-28 | 2021-06-11 | 2021-06-18 | 2021-09-02 |  | 2022-10-05 | 1 | 0 |  | Davidsd.Lin Erichw.Wang Davidsd.Lin Wells.Yu | Jim.Shen Colby.Ren Jeff.Lin Jeff.Lin Zack.Lin Colby.Ren | Nick.Yen Jason.Fan Nick.Yen | Ray.Hu Simon.Ko Simon.Ko Ray.Hu
Venu Sq 2(IMP) | 1023 | Venu Sq 2 | 14949 | Production | Fitness | 2022-08-01 | 2021-04-29 | 2021-03-10 |  |  |  | 2021-11-23 |  | 2022-09-12 | 1 | 0 |  | Anton.Lin | Leo.Chiu Viola.Kao | Jackhl.Chen | Aalto.Lo
BMW MGU22_PL1 | 1028 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Jasper.Huang Sandy.Lee Joseph.Yen Mark.Chang Mark.Chang | Tiffany2.Chen Ray.Hu Cherry.Tsai
BMW MGU22_G1 | 1079 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Jasper.Huang Sandy.Lee Joseph.Yen Mark.Chang | Tiffany2.Chen Ray.Hu Cherry.Tsai
Edge Explore 2 | 1045 | Edge Explore 2 | 14994 | Production | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0 |  | Anton.Lin Dannyhp.Cheng | Viola.Kao Arthur.Wang | Nixon.Pan Jackhl.Chen | Chris.Kuo
Forerunner 955 and 955 Solar | 967 | Forerunner 955 and 955 Solar | 12875 | Production | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-05-30 | 0 | 0 |  | Anton.Lin | Viola.Kao Eric.Chiang | Alexty.Chang | Ernest.Fu
2022 vivofit jr. 3 SKUs | 1095 | 2022 vivofit jr. 3 SKUs | 15907 | Production | Fitness | 2022-04-11 |  |  |  |  | 2021-09-13 |  |  | 2022-05-23 | 0 | 0 |  |  | Steve.Lee Viola.Kao Eason.Chen |  | Ernest.Fu
Tacx Vortex 2M | 1070 | Tacx Vortex 2M | 13589 | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1 |  |  | Claudia.vanRhoon | bianca | Marijn
Tactix 7 | 1087 | Tactix 7 | 14754 | Production | Outdoor | 2022-03-07 | [7 empty] | 2022-04-18 | 0 | 0 |  |  | Leo.Chiu Viola.Kao |  | Cooper.Wang
BMW MGU22-RSE | 895 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-03-07 |  | 2019-10-31 | 2020-05-15 | 2020-05-29 | 2020-05-29 |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | Jasper.Huang James.Chou Jasper.Huang | Jasper.Huang Sandy.Lee Joseph.Yen Mark.Chang Sandy.Lee | Tiffany2.Chen Ray.Hu Cherry.Tsai Cherry.Tsai Allen.Chen Ray.Hu Tiffany2.Chen
D2 Echo (EPIX) | 1040 | D2 Echo (EPIX) | 13079 | Production | Outdoor | 2022-01-17 | [7 empty] | 2022-02-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao |  | Cooper.Wang
vivomove "Lite" | 979 | vivomove Sport (previously "Lite") | 12989 | Production | Fitness | 2021-11-08 | [7 empty] | 2021-12-20 | 1 | 0 |  | Herry.Lan | Viola.Kao Joel.Wu | Sherry.Shih | Ernest.Fu
"Austin" | 983 | "Austin" | 13684 | Production | Outdoor | 2021-11-01 | 2020-03-05 | 2020-03-26 | 2020-08-31 | 2020-09-14 | 2020-09-15 |  |  | 2021-12-13 | 1 | 0 |  | Aaron.Lin | Leo.Chiu Viola.Kao | Nixon.Pan | Cooper.Wang
Venu 2 Plus | 879 | Venu 2 Plus | 12514 | Production | Fitness | 2021-10-18 | 2020-01-01 | 2020-01-22 | 2020-02-07 | 2020-02-21 | 2020-06-05 |  |  | 2021-11-29 | 1 | 0 |  | Anton.Lin | Steve.Lee Viola.Kao | Alexty.Chang | Cooper.Wang
fenix 7S | 959 | fenix 7S | 13824 | Production | Outdoor | 2021-10-04 | [7 empty] | 2021-11-15 | 1 | 0 |  |  | Viola.Kao Stansy.Wang | Franksl.Chen | Cooper.Wang
Battery Charger | 998 | Battery Charger | 14544 | Production | Outdoor | 2021-04-26 | [7 empty] | 2021-06-07 | 1 | 0 |  | Dannyhp.Cheng Emma.Lin | Viola.Kao |  | Chris.Kuo
Xero G2i SatCom Scouting Camera | 826 | Xero G2i SatCom Scouting Camera | 7011 | Cancelled | Outdoor |  |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  |  | 0 | 0 |  | Derek.Cheng Derek.Cheng | Frankie.Lee Frankie.Lee | Nixon.Pan Ken.Kuo Ken.Kuo | Chris.Kuo Chris.Kuo
EPIX (Gen 3) 47mm | 1173 | EPIX (Gen 3) 47mm | 16802 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Viola.Kao Eason.Chen | Erinsa.Lu | Howard.Jen
DEZL 2024 - 8" | 1170 | DEZL 2024 | 16718 | Product Development Plan | Automotive | [9 empty] | 0 | 0 |  | Iris.Wu |  | Allyson.Kuo Lori.Tsai | Wendy.Ni
DEZL 2024 - 10" | 1171 | DEZL 2024 | 16718 | Product Development Plan | Automotive | [9 empty] | 0 | 0 |  | Iris.Wu |  | Allyson.Kuo Lori.Tsai | Wendy.Ni
GT17M-THF | 1162 | GT17M-THF | 16706 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Joannajh.Huang
LWIN23 | 1177 | LWIN23 | 16704 | Top Level Design | OEM Auto | [9 empty] | 0 | 0 |  | Roger.Chan Davidsd.Lin | Jim.Shen Colby.Ren |  | Simon.Ko
PGWW23 | 1136 | PGWW23 | 16590 | Product Development Plan | OEM Auto | [9 empty] | 0 | 0 |  | Roger.Chan Davidsd.Lin | Jim.Shen Colby.Ren | Nick.Yen | Arthur.Yu Ray.Hu Simon.Ko
GPSMAP 16X3 Chartplotters | 1156 | GPSMAP 16X3 Chartplotters | 16588 | Detailed Design | Marine | [9 empty] | 0 | 0 |  | Bowman.Lai | Star.Shao Charlotte.Chen | Robben.Liu
2024 Value Dash Cams(DC48) | 1159 | 2024 Value Dash Cams | 16544 | Top Level Design | Automotive |  | 2023-01-13 | 2023-02-03 | 2023-03-24 | 2023-04-07 |  |  |  |  | 0 | 0 |  | Stephen.Shen | Frankie.Lee Amberif.Wang Jasonch.Chen | Jason.Fan | Wendy.Ni
Motorcycle Radar 2023 | 1150 | Motorcycle Radar 2023 | 16539 | Top Level Design | Automotive | [9 empty] | 0 | 0 |  | Iris.Wu | Frankie.Lee | Nick.Yen | Wendy.Ni
fenix 8 Series | 1176 | fenix 8 Series | 16514 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Dannyhp.Cheng Andyjs.Chen | Viola.Kao Eason.Chen | Neo.Lin Robben.Liu Franksl.Chen | Howard.Jen
Descent T2 Transceiver | 1157 | Descent T2 Transceiver | 16456 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Vincent.Yeh Dannyhp.Cheng | Eric.Chiang Viola.Kao | Robben.Liu | Ernest.Fu
Fusion - RA800 | 1149 | Fusion - RA800 | 16411 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng | Ruby.Chang
Tacx Climbing Accessory | 1169 | Tacx Climbing Accessory | 16345 | Top Level Design | Fitness | [9 empty] | 0 | 0 |  |  | Claudia.vanRhoon
Instinct 3 Series | 1175 | Instinct 3 Series | 16298 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  | Andyjs.Chen | Viola.Kao Willycw.Wu | Tina.Yang Jackhl.Chen
Tacx FLUX 3M | 1148 | Tacx FLUX 3M | 16250 | Top Level Design | Fitness | [9 empty] | 0 | 0 |  |  |  |  | Jasoncy.Hsu
Lily Athlete | 1163 | Lily Athlete | 16248 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Vincent.Yeh Dannyhp.Cheng | Kuo.Kuo Viola.Kao | Franksl.Chen | Evelyn.Wang
EPIX (Gen 3) 43mm | 1172 | EPIX (Gen 3) 43mm | 16244 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Shawn.Huang PeiRu.Tsai | Viola.Kao Eason.Chen | Nixon.Pan | Aalto.Lo
inReach Messenger 2 | 1164 | inReach Messenger 2 | 16216 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Ruby.Huang | Johnny.Ko Viola.Kao | Franksl.Chen | Evelyn.Wang
eTrex Touch Gen 2 | 1161 | eTrex Touch Gen 2 | 16215 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  | Alex.Pu | JulieJJ.Lin Viola.Kao |  | Chris.Kuo
GPSMAP 66sr/66i Plus (i.MX7 Platform) | 1116 | GPSMAP 67/67i (i.MX7 Platform) | 16211 | Production | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao | Willycw.Wu
Tacx NEO 3M | 1109 | Tacx NEO 3M | 15808 | Factory Prototype | Fitness | [9 empty] | 0 | 0 |  |  | Claudia.vanRhoon Robin.deGroot |  | Chris.Kuo
Descent X1i | 1121 | Descent X1i | 15469 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Viola.Kao Joel.Wu | Tim.Wu | Chris.Kuo
Tacx Motion Plates | 1082 | Tacx Motion Plates | 14854 | Production | Fitness | [9 empty] | 1 | 0 |  |  | Claudia.vanRhoon | bianca | Marijn
Enduro 2023 | 1047 | Enduro 2023 | 14704 | Detailed Design | Outdoor |  | 2021-09-15 | 2021-10-06 | 2022-08-30 | 2022-09-13 | 2021-11-09 |  |  |  | 0 | 0 |  | Dannyhp.Cheng | Viola.Kao Stansy.Wang | Neo.Lin | Cooper.Wang
Tacx Sports bottle | 1128 | Tacx Sports bottle | 14164 | Pilot Run | Fitness | [9 empty] | 0 | 0 |  |  | Johnny.Liu Claudia.vanRhoon
Product - Flight Stream Redesign | 977 | Product - Flight Stream Redesign | 13634 | Derivative Product Concept | Aviation | [9 empty] | 0 | 0 |  | Stephen.Shen | Edward.Tu Jimmy.Kuo
Product - 1.3\" GTR/GNC | 984 | Product - 1.3\" GTR/GNC | 12164 | Development | Aviation | [9 empty] | 0 | 0 |  | Steve.Chiang |  | Allyson.Kuo | Evelyn.Wang