## New Production Status Summary
New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20 | New Production Status Summary 2023-11-20
Project Name | Project Id | PM Project Name | PM Project Id | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM | DPQE
Fusion - 80 Series Marine Stereos | 1209 | Fusion - 80 Series Marine Stereos | 16753 | Top Level Design | Marine | 2025-09-30 |  |  |  |  | 2024-11-08 |  |  | 2025-11-11 | 1 | 0 |  | Steve.Chiang | Star.Shao Simonyc.Chen | Jackhl.Chen | Jasoncy.Hsu
Approach Z84 | 1220 | Approach Z84 | 16673 | Top Level Design | Outdoor | 2025-09-15 | [7 empty] | 2025-10-27 | 1 | 0 |  | Alex.Pu | Amber.Wang Johnny.Liu | Nick.Yen | Ernest.Fu
Garmin Fixed Mount VHF with AIS | 1184 | Garmin Fixed Mount VHF with AIS | 16743 | Detailed Design | Marine | 2025-06-19 | [7 empty] | 2025-07-31 | 1 | 0 |  | Derek.Cheng | Star.Shao Ruby.Chang | Alexty.Chang Nick.Yen | Evelyn.Wang
Aviation Headset - | 1192 | Aviation Headset - | 16319 | Detailed Design | Automotive | 2025-04-21 | 2023-06-30 | 2023-07-21 | 2023-11-23 | 2023-12-07 | 2024-05-01 | 2024-08-16 | 2024-11-22 | 2025-06-02 | 1 | 1 |  | Alex.Pu | Jasonch.Chen Johnny.Liu Bettyyz.Wang | Nixon.Pan | Evelyn.Wang
Xero G2i Scouting Camera | 1181 | Xero G2i Scouting Camera | 16543 | Top Level Design | Outdoor | 2025-04-01 | 2023-02-28 | 2023-03-21 |  |  |  | 2023-10-06 | 2023-11-24 | 2025-05-13 | 1 | 0 |  | Derek.Cheng | Frankie.Lee Johnny.Liu | Nixon.Pan | Chris.Kuo
Force Kayak Propulsion System | 1134 | Force Kayak Propulsion System | 10617 | Detailed Design | Marine | 2025-03-31 | 2022-05-05 | 2022-05-26 | 2023-12-26 | 2024-01-09 | 2024-01-29 |  |  | 2025-05-12 | 1 | 0 |  | Steve.Chiang | Jimmy.Kuo Allen.Chu Ruby.Chang Simonyc.Chen | Lori.Tsai | Jasoncy.Hsu
HRM6-200 (Basic) | 1187 | HRM-200 | 16555 | Detailed Design | Fitness | 2025-03-10 | [7 empty] | 2025-04-21 | 1 | 0 |  | Iris.Wu | John.Chiu Johnny.Liu | Erinsa.Lu | Ernest.Fu
Instinct Y | 1199 | Instinct Y | 16597 | Detailed Design | Outdoor | 2025-02-24 | [7 empty] | 2025-04-07 | 1 | 0 |  | Andy.Chuang | JeffPY.Liao Leo.Chiu | Jackhl.Chen | Leoyt.Chen
fenix 8 Connected 47mm | 1217 | fenix 8 Connected 47mm | 17284 | Detailed Design | Outdoor | 2025-01-20 | 2023-08-04 | 2023-08-25 | 2023-12-05 | 2023-12-19 | 2024-01-03 |  |  | 2025-03-03 | 1 | 0 |  | PeiRu.Tsai | Amyry.Chen | Franksl.Chen | Aalto.Lo
DEZL Sideview | 1191 | DEZL Sideview | 16808 | Detailed Design | Automotive | 2025-01-13 | 2023-08-02 | 2023-08-23 |  |  | 2024-02-21 |  |  | 2025-02-24 | 1 | 0 |  | Stephen.Shen | Jasonch.Chen Johnny.Liu | Robben.Liu | Ernest.Fu
Fusion - RA800 | 1149 | Fusion - RA800 | 16411 | Detailed Design | Marine | 2025-01-13 | 2023-04-21 | 2023-05-12 |  |  | 2024-06-28 |  |  | 2025-02-24 | 1 | 0 |  | Derek.Cheng | Ruby.Chang | Lori.Tsai Lori.Tsai Lori.Tsai Lori.Tsai | Jasoncy.Hsu
Rally 110/210 Family | 1135 | Rally 110/210 Family | 16349 | Detailed Design | Fitness | 2025-01-06 | 2022-12-20 | 2023-01-10 | [5 empty] | 2025-02-17 | 1 | 6 |  | Stephen.Shen | John.Chiu Johnny.Liu | Neo.Lin | Chris.Kuo
Engine Cut-Off System (ECOS/MOB) | 1180 | Engine Cut-Off System (ECOS/MOB) | 16198 | Detailed Design | Marine | 2024-12-16 | 2023-01-30 | 2023-02-20 | 2023-12-22 | 2024-01-05 | 2024-01-26 |  |  | 2025-01-27 | 1 | 0 |  | Bowman.Lai | Charlotte.Chen Star.Shao Ruby.Chang | Nick.Yen | Jasoncy.Hsu
HRM6-600 (Adv.) | 1186 | HRM-600 | 16005 | Detailed Design | Fitness | 2024-12-16 | [7 empty] | 2025-01-27 | 1 | 0 |  | Iris.Wu | John.Chiu Johnny.Liu | Erinsa.Lu | Ernest.Fu
GPSMAP H1/H1i | 1091 | GPSMAP 68 | 16137 | Detailed Design | Outdoor | 2024-10-07 | 2022-12-20 | 2023-01-10 | 2023-08-16 | 2023-08-30 | 2024-01-04 | 2024-04-05 | 2024-07-05 | 2024-11-18 | 1 | 0 |  | Ruby.Huang | Joel.Wu JeffPY.Liao | Nixon.Pan | Cooper.Wang
Varia Headlight Camera | 1152 | Varia Headlight Camera | 16183 | Detailed Design | Fitness | 2024-09-30 | 2023-03-22 | 2023-04-12 | [5 empty] | 2024-11-11 | 1 | 0 |  | Stephen.Shen | Amberif.Wang Johnny.Liu Bettyyz.Wang | Leol.Chen | Chris.Kuo
Instinct 3 Solar - 50mm | 1194 | Instinct 3 Solar - 50mm | 17269 | Detailed Design | Outdoor | 2024-09-16 | 2023-04-20 | 2023-05-11 | 2023-08-01 | 2023-08-15 | 2023-08-21 |  |  | 2024-10-28 | 1 | 0 |  | Daniel.Mao | Willycw.Wu JeffPY.Liao | Erinsa.Lu | Aalto.Lo
Xero B60i Laser Navigation Binoculars | 1119 | Xero B60i Laser Navigation Binoculars | 13229 | Detailed Design | Outdoor | 2024-09-16 | 2023-12-01 | 2024-03-27 | 2024-08-14 | 2024-08-28 | 2024-09-10 |  |  | 2024-10-28 | 1 | 0 |  | Alex.Pu | Jason.Cai Johnny.Liu | Donna.Chiu | Chris.Kuo
eTrex Touch | 1161 | eTrex Touch | 16215 | Detailed Design | Outdoor | 2024-09-09 | [7 empty] | 2024-10-21 | 1 | 0 |  | Alex.Pu | JulieJJ.Lin JeffPY.Liao | Neo.Lin | Chris.Kuo
TGWW25 | 1138 | TGWW25 | 16227 | Top Level Design | OEM Auto | 2024-08-31 | 2023-01-23 | 2023-02-13 |  |  |  | 2024-01-11 | 2024-02-22 | 2024-10-11 | 1 | 0 |  | Davidsd.Lin | Colby.Ren Jim.Shen Howard.Huang | Jason.Fan | Simon.Ko WeiHsiang.Chen
Tread 6" plus optional handlebar controller | 1189 | Tread 6" plus optional handlebar controller | 16866 | Detailed Design | Automotive | 2024-08-26 |  | 2023-09-05 | 2024-01-15 | 2024-01-29 | 2023-12-08 |  |  | 2024-10-07 | 1 | 0 |  | Derek.Cheng | Chloe.Lin2 Johnny.Liu Bettyyz.Wang | Nick.Yen | Chris.Kuo
Enduro 3 47mm | 1176 | Enduro 3 47mm | 16514 | Detailed Design | Outdoor | 2024-08-26 | 2023-04-14 | 2023-05-05 | 2023-08-04 | 2023-08-18 | 2023-08-14 |  |  | 2024-10-07 | 1 | 0 |  | Dannyhp.Cheng | Amyry.Chen JeffPY.Liao | Franksl.Chen | Leoyt.Chen
Instinct 3 Solar - 45mm | 1175 | Instinct 3 Solar | 16298 | Detailed Design | Outdoor | 2024-08-26 | 2023-04-20 | 2023-05-11 | 2023-07-25 | 2023-08-08 | 2023-08-14 |  |  | 2024-10-07 | 1 | 0 |  | Andyjs.Chen | JeffPY.Liao Willycw.Wu | Jackhl.Chen | Aalto.Lo
Lily 2 Active | 1163 | Lily Athlete | 16248 | Detailed Design | Fitness | 2024-08-12 | [7 empty] | 2024-09-23 | 1 | 0 |  | Dannyhp.Cheng Vincent.Yeh | Kuo.Kuo | Franksl.Chen | Ernest.Fu
Blaze | 1190 | Equine Wellness System | 16140 | Detailed Design | Fitness | 2024-08-07 | [7 empty] | 2024-09-18 | 1 | 0 |  | Andyjs.Chen | Lulu.Lee | Jackhl.Chen | Ernest.Fu
Instinct 3 AMOLED - 45mm | 1196 | Instinct 3 AMOLED | 17074 | Detailed Design | Outdoor | 2024-08-05 | 2023-04-20 | 2023-05-11 | 2023-07-25 | 2023-08-08 | 2023-08-14 |  |  | 2024-09-16 | 1 | 0 |  | Andyjs.Chen | JeffPY.Liao Willycw.Wu | Jackhl.Chen | Aalto.Lo
LYWW24 | 1113 | LYWW24 | 15976 | Top Level Design | OEM Auto | 2024-08-05 | 2022-05-20 | 2022-06-10 |  |  |  | 2022-09-23 | 2023-10-24 | 2024-09-16 | 1 | 0 |  | Davidsd.Lin Erichw.Wang | Colby.Ren Jim.Shen | Jason.Fan Donna.Chiu | Simon.Ko
Prop Drive Cost Down | 1115 | Prop Drive Cost Down | 16233 | Factory Prototype | Marine | 2024-07-15 | 2022-02-14 | 2022-03-07 | 2022-09-16 | 2022-09-30 | 2023-01-05 |  |  | 2024-08-26 | 1 | 0 |  | Iris.Wu | Jimmy.Kuo | Nick.Yen | Jasoncy.Hsu
inReach Messenger 2 | 1164 | inReach Messenger 2 | 16216 | Detailed Design | Outdoor | 2024-07-15 | [7 empty] | 2024-08-26 | 1 | 0 |  | Ruby.Huang Vincent.Yeh | Daniel.Tsai | Franksl.Chen | Evelyn.Wang
Catalyst KMR - Hub | 1111 | Catalyst Kart/Moto/Roadster | 15624 | Cancelled | Automotive | 2024-07-15 | 2019-07-24 | 2019-08-14 | 2022-02-10 | 2022-02-24 | 2022-06-27 |  |  | 2024-08-26 | 1 | 0 |  | Steve.Chiang Stephen.Shen Frankie.Lee | Frankie.Lee Steve.Chiang Johnny.Liu | Allyson.Kuo Jackhl.Chen | Evelyn.Wang
Catalyst KMR - Display | 1120 | Catalyst Kart/Moto/Roadster | 15624 | Cancelled | Automotive | 2024-07-15 | 2021-09-20 | 2021-10-11 | 2022-02-04 | 2022-02-18 | 2022-06-27 |  |  | 2024-08-26 | 1 | 3 |  | Steve.Chiang Stephen.Shen Frankie.Lee | Frankie.Lee Steve.Chiang Johnny.Liu | Allyson.Kuo Jackhl.Chen | Evelyn.Wang
Catalyst KMR - Camera | 1110 | Catalyst Kart/Moto/Roadster | 15624 | Cancelled | Automotive | 2024-07-15 | 2019-07-24 | 2019-08-14 | 2022-06-10 | 2022-06-24 | 2022-06-27 |  |  | 2024-08-26 | 1 | 0 |  | Steve.Chiang Stephen.Shen Frankie.Lee | Frankie.Lee Steve.Chiang Johnny.Liu | Allyson.Kuo Jackhl.Chen | Evelyn.Wang
fenix 8 47mm | 1173 | fenix 8 47mm | 16802 | Detailed Design | Outdoor | 2024-07-08 | 2022-11-11 | 2022-12-02 | 2023-06-21 | 2023-07-05 | 2023-08-25 |  |  | 2024-08-19 | 1 | 0 |  | Dannyhp.Cheng | Amyry.Chen JeffPY.Liao | Erinsa.Lu | Aalto.Lo
2024 Value Dash Cams(DC48) | 1159 | 2024 Value Dash Cams | 16544 | Factory Prototype | Automotive | 2024-07-02 | 2023-01-13 | 2023-02-03 | 2023-03-24 | 2023-04-07 |  | 2023-11-29 | 2024-03-20 | 2024-08-13 | 1 | 0 |  | Iris.Wu Stephen.Shen | Amberif.Wang Bettyyz.Wang Frankie.Lee Jasonch.Chen Johnny.Liu | Jason.Fan | Chris.Kuo
2024 Value Dash Cams(Mini3) | 1158 | 2024 Value Dash Cams | 16544 | Factory Prototype | Automotive | 2024-07-02 | 2023-01-13 | 2023-02-03 | 2023-03-24 | 2023-04-07 | 2023-07-17 | 2023-08-25 | 2024-03-22 | 2024-08-13 | 1 | 2 |  | Iris.Wu Stephen.Shen | Amberif.Wang Bettyyz.Wang Frankie.Lee Jasonch.Chen Johnny.Liu | Jason.Fan | Chris.Kuo
Instinct SE (45 mm) | 1198 | Instinct SE (45 mm) | 17268 | Detailed Design | Outdoor | 2024-07-01 | [7 empty] | 2024-08-12 | 1 | 0 |  | Andyjs.Chen | JeffPY.Liao Kuo.Kuo | Tina.Yang Robben.Liu | Aalto.Lo
Instinct SE (40 mm) | 1197 | Instinct SE (40 mm) | 17075 | Detailed Design | Outdoor | 2024-07-01 | [7 empty] | 2024-08-12 | 1 | 0 |  | Ruby.Huang | Kuo.Kuo JeffPY.Liao | Tina.Yang Leol.Chen | Leoyt.Chen
fenix 8 43mm | 1172 | fenix 8 43mm | 16244 | Detailed Design | Outdoor | 2024-06-24 | 2023-01-30 | 2023-02-20 | 2023-11-07 | 2023-11-21 | 2023-07-10 | 2023-12-15 | 2024-03-22 | 2024-08-05 | 1 | 12 |  | Janet.Sun | Eason.Chen | Nixon.Pan | Leoyt.Chen
LED Control Module | 1066 | LED Control Module | 13134 | Factory Prototype | Marine | 2024-06-18 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  | 2023-10-02 |  | 2024-07-30 | 1 | 0 |  | Iris.Wu | Frankie.Lee Darren.Chen | Robben.Liu | Evelyn.Wang
Enduro 3 51mm | 1182 | Enduro 3 51mm | 17001 | Detailed Design | Outdoor | 2024-06-17 | 2022-11-11 | 2022-12-02 | 2023-05-24 | 2023-06-07 | 2023-06-23 |  |  | 2024-07-29 | 1 | 0 |  | Shawn.Huang | Robert.Pan | Neo.Lin | Aalto.Lo
Approach G20 | 1168 | Approach G20 | 15619 | Detailed Design | Outdoor | 2024-06-17 | 2023-02-21 | 2023-03-17 | 2023-06-05 | 2023-06-19 | 2023-09-29 |  |  | 2024-07-29 | 1 | 0 |  | Ruby.Huang | Daniel.Tsai JeffPY.Liao | Erinsa.Lu | Chris.Kuo
Descent X1i | 1121 | Descent X1i | 15469 | Detailed Design | Outdoor | 2024-06-17 | 2022-05-26 | 2022-06-16 | 2022-11-25 | 2022-12-09 |  | 2023-12-06 | 2024-03-21 | 2024-07-29 | 1 | 0 |  | PeiRu.Tsai | Joel.Wu JeffPY.Liao | Tim.Wu | Jasoncy.Hsu
fenix 8 51mm | 1174 | fenix 8 51mm | 16801 | Detailed Design | Outdoor | 2024-06-13 | 2023-04-10 | 2023-05-01 | 2023-05-23 | 2023-06-06 | 2023-06-28 |  |  | 2024-07-25 | 1 | 0 |  | Shawn.Huang | Eason.Chen JeffPY.Liao | Leol.Chen | Aalto.Lo
dezl headset (2nd Gen) | 1132 | dezl headset (2nd Gen) | 16249 | Factory Prototype | Automotive | 2024-06-11 | 2022-08-11 | 2022-09-01 |  |  | 2023-06-02 |  |  | 2024-07-23 | 1 | 0 |  | Howard.Huang | Chloe.Lin2 Jason.Cai Bettyyz.Wang Johnny.Liu | Lori.Tsai | Evelyn.Wang
DEZL 2024 - OTR725 | 1183 | DEZL 2024 | 16718 | Detailed Design | Automotive | 2024-06-10 |  |  |  |  | 2023-08-25 |  |  | 2024-07-22 | 1 | 1 |  | Iris.Wu Stephen.Shen Bowman.Lai | Johnny.Liu Frankie.Lee Chloe.Lin2 Jason.Cai Amberif.Wang Bettyyz.Wang | Lori.Tsai | Ernest.Fu
DEZL 2024 - OTR820/1020 | 1170 | DEZL 2024 | 16718 | Detailed Design | Automotive | 2024-06-10 |  |  |  |  | 2023-08-25 |  |  | 2024-07-22 | 1 | 0 |  | Iris.Wu Stephen.Shen Bowman.Lai | Johnny.Liu Frankie.Lee Chloe.Lin2 Jason.Cai Amberif.Wang Bettyyz.Wang | Lori.Tsai | Ernest.Fu
DEZL 2024 - OTR620/720 | 1171 | DEZL 2024 | 16718 | Detailed Design | Automotive | 2024-06-10 |  |  | 2023-05-08 | 2023-05-22 | 2023-09-15 |  |  | 2024-07-22 | 1 | 1 |  | Iris.Wu Stephen.Shen Bowman.Lai | Johnny.Liu Frankie.Lee Chloe.Lin2 Jason.Cai Amberif.Wang Bettyyz.Wang | Lori.Tsai | Ernest.Fu
Motorcycle Radar 2023 | 1150 | Motorcycle Radar 2023 | 16539 | Detailed Design | Automotive | 2024-06-10 | 2023-02-16 | 2023-03-09 | 2023-09-15 | 2023-09-29 | 2023-11-10 |  |  | 2024-07-22 | 1 | 0 |  | Alex.Pu | Frankie.Lee Johnny.Liu | Nick.Yen | Aalto.Lo
Enduro 3 XT (Pando) | 1047 | Enduro 3 Sport (Pando) | 14704 | Detailed Design | Outdoor | 2024-06-10 | 2021-09-15 | 2021-10-06 | 2022-08-30 | 2022-09-13 | 2021-11-09 |  |  | 2024-07-22 | 1 | 5 |  | Dannyhp.Cheng | Roger.Huang | Neo.Lin | Cooper.Wang
GT17M-THF | 1162 | GT17M-THF | 16706 | Detailed Design | Marine | 2024-05-27 | 2023-03-30 | 2023-04-20 |  |  | 2023-05-04 | 2023-12-29 | 2024-03-15 | 2024-07-08 | 1 | 0 |  | Iris.Wu | Allen.Chu | Jason.Fan | Jasoncy.Hsu
Tread 10" OEM - Kawasaki CAN | 1142 | Tread 10" OEM - Kawasaki CAN | 16584 | Pilot Run | Automotive | 2024-05-27 | [5 empty] | 2023-05-16 |  | 2024-07-08 | 1 | 0 |  | Steve.Chiang | Jason.Cai Johnny.Liu | Neo.Lin
GC 255 and GC 245 | 1151 | GC 255 and GC 245 | 16300 | Factory Prototype | Marine | 2024-05-27 | 2022-11-02 | 2022-11-23 |  |  | 2023-10-30 | 2023-11-08 | 2024-02-28 | 2024-07-08 | 1 | 3 |  | Bowman.Lai | Isaac.Wang | Tim.Wu | Evelyn.Wang
Edge 1050 | 1137 | Edge 1050 | 16197 | Factory Prototype | Fitness | 2024-05-13 | [7 empty] | 2024-06-24 | 1 | 2 |  | Stephen.Shen | JeffPY.Liao Anderson.Chen | Ryan.Li | Leoyt.Chen
BMW MGU22/IDC_C5 | 1165 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2024-05-02 | [6 empty] | 2023-08-22 | 2024-06-13 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou Howard.Huang Colby.Ren | Sandy.Lee Ryan.Li | Tiffany2.Chen Cherry.Tsai Ray.Hu
DC-2023 Premium Dash Cameras | 1130 | DC-2023 Premium Dash Cameras | 16199 | Pilot Run | Automotive | 2024-04-29 | 2022-07-15 | 2022-08-05 | 2023-01-19 | 2023-02-02 | 2023-02-03 | 2023-04-06 | 2023-09-14 | 2024-06-10 | 1 | 1 |  | Stephen.Shen | Chloe.Lin2 Johnny.Liu | Donna.Chiu Sandy.Lee | Chris.Kuo
GPSMAP 9500 | 1141 | GPSMAP 9500 | 16616 | Factory Prototype | Marine | 2024-04-22 |  |  | 2023-04-17 | 2023-05-01 | 2023-05-08 |  |  | 2024-06-03 | 1 | 0 |  | Bowman.Lai | Ruby.Chang Allen.Chu | Nick.Yen | Jasoncy.Hsu
Approach R50 | 1012 | Approach R50 | 10926 | Factory Prototype | Outdoor | 2024-04-22 | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 | 2023-03-09 |  | 2024-01-19 | 2024-06-03 | 1 | 1 |  | Steve.Chiang Roger.Chan | Johnny.Liu Chloe.Lin2 Bettyyz.Wang | Nixon.Pan | Chris.Kuo
Drive 53 w/ Type-C | 1219 | Drive 53 w/ Type-C | 17037 | Pilot Run | Automotive | 2024-03-11 | [7 empty] | 2024-04-22 | 1 | 0 |  | Iris.Wu | Jason.Cai Johnny.Liu
Serv - 7" | 1080 | Serv (7"/10") | 14554 | Product Launch | Marine | 2024-03-11 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-08-03 | 2022-08-26 | 2022-12-20 | 2024-04-22 | 1 | 0 |  | Bowman.Lai | John.Chiu Allen.Chu Ruby.Chang | Tim.Wu | Jasoncy.Hsu
Serv - 10" | 1081 | Serv (7"/10") | 14554 | Product Launch | Marine | 2024-03-11 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-07-20 | 2022-08-26 | 2022-12-20 | 2024-04-22 | 1 | 0 |  | Bowman.Lai | John.Chiu Allen.Chu Ruby.Chang | Tim.Wu | Jasoncy.Hsu
Descent S1 Buoy | 1006 | Descent S1 Buoy | 12799 | Factory Prototype | Outdoor | 2024-03-11 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 | 2022-08-15 | 2023-06-23 | 2024-04-22 | 1 | 0 |  | Daniel.Mao | Daniel.Tsai JeffPY.Liao | Franksl.Chen | Aalto.Lo
Xero L60i Laser Navigator | 1016 | Xero L60i Laser Navigator | 8510 | Factory Prototype | Outdoor | 2024-02-26 | 2021-02-25 | 2021-03-18 | 2021-11-24 | 2021-12-08 | 2022-12-02 |  |  | 2024-04-08 | 1 | 7 |  | Alex.Pu | Jason.Cai Jasonch.Chen Johnny.Liu | Lori.Tsai | Chris.Kuo
GPSMAP 16X3 Chartplotters | 1156 | GPSMAP 16X3 Chartplotters | 16588 | Factory Prototype | Marine | 2024-02-05 | 2023-02-02 | 2023-02-23 | 2023-05-25 | 2023-06-08 | 2023-06-19 |  |  | 2024-03-18 | 1 | 0 |  | Bowman.Lai | Star.Shao Charlotte.Chen | Robben.Liu | Jasoncy.Hsu
Panoptix PS70 - (SSMB) | 833 | Panoptix PS70 - (SSMB) | 10091 | Pilot Run | Marine | 2024-01-22 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-09-05 | 2023-03-07 | 2024-03-04 | 1 | 0 |  | Derek.Cheng | Jimmy.Kuo Darren.Chen | Tim.Wu | Evelyn.Wang
Product - GDU147XW | 1049 | Product - GDU147XW | 12509 | Product Development Plan | Aviation | 2024-01-03 | [7 empty] | 2024-02-14 | 1 | 0 |  | Stephen.Shen | Jimmy.Kuo Edward.Tu | Sandy.Lee Donna.Chiu | Evelyn.Wang
Forerunner 165 and 165 Music | 1145 | Forerunner 165 and 165 Music | 16437 | Pilot Run | Fitness | 2024-01-02 | 2022-07-25 | 2022-08-15 | 2022-11-04 | 2022-11-18 | 2022-11-23 |  |  | 2024-02-13 | 1 | 0 |  | PeiRu.Tsai | JulieJJ.Lin JeffPY.Liao | Erinsa.Lu | Cooper.Wang
Large Format TXi | 1155 | Large Format TXi | 16136 | Derivative Product Concept | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  |  |  | Donna.Chiu | Evelyn.Wang
Product - G3X/G500TXi Hybrid | 1050 | Product - G3X/G500TXi Hybrid | 12717 | Product Development Plan | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  | Kent.Liu
Product - GDU77XW | 1048 | Product - GDU77XW | 12510 | Product Development Plan | Aviation | 2024-01-01 | [7 empty] | 2024-02-12 | 1 | 0 |  |  |  | Sandy.Lee Donna.Chiu | Evelyn.Wang
BMW Motorrad Nav VI Production Support | 1140 | BMW Motorrad Nav VI Production Support | 10170 | Pilot Run | OEM Auto | 2023-12-08 | [5 empty] | 2022-10-19 | 2023-04-21 | 2024-01-19 | 1 | 0 |  | Shawn.Yu | Frankie.Lee | Nick.Yen
ECHOMAP Ultra 2 - 12" | 1147 | ECHOMAP Ultra 2 | 16483 | Pilot Run | Marine | 2023-11-22 |  |  | 2023-03-24 | 2023-04-07 | 2023-04-13 | 2023-05-17 | 2023-08-15 | 2024-01-03 | 1 | 0 |  | Derek.Cheng | Isaac.Wang Darren.Chen | Donna.Chiu | Jasoncy.Hsu
ECHOMAP Ultra 2 - 10" | 1178 | ECHOMAP Ultra 2 | 16483 | Pilot Run | Marine | 2023-11-22 |  |  | 2023-03-24 | 2023-04-07 | 2023-04-13 | 2023-05-17 | 2023-08-15 | 2024-01-03 | 1 | 1 |  | Derek.Cheng | Isaac.Wang Darren.Chen | Donna.Chiu | Jasoncy.Hsu
Lily 2 | 1123 | Lily 2 | 15993 | Product Launch | Fitness | 2023-11-20 |  |  | 2022-12-21 | 2023-01-04 |  | 2023-03-07 | 2023-08-15 | 2024-01-01 | 1 | 1 |  | Shawn.Huang | George.Chang Steve.Lee JeffPY.Liao | Tina.Yang Jackhl.Chen | Ernest.Fu
Tread 8" OEM w/ CAN | 1063 | Tread 8" OEM w/ CAN | 15955 | Cancelled | Automotive | 2023-11-13 | [6 empty] | 2022-03-16 | 2023-12-25 | 1 | 1 |  | Derek.Cheng | Jason.Cai Johnny.Liu | Lori.Tsai | Evelyn.Wang
Product - 1.3\" GTR/GNC | 984 | Product - 1.3\" GTR/GNC | 12164 | Development | Aviation | 2023-11-07 | [7 empty] | 2023-12-19 | 1 | 0 |  | Steve.Chiang |  | Allyson.Kuo Donna.Chiu | Evelyn.Wang
HRM-Fit | 1160 | HRM-Fit | 16053 | Product Launch | Fitness | 2023-11-06 | 2022-09-22 | 2022-10-13 | 2023-04-04 | 2023-04-18 | 2022-12-19 |  |  | 2023-12-18 | 1 | 1 |  | Iris.Wu | Johnny.Liu Amberif.Wang Bettyyz.Wang | Erinsa.Lu | Chris.Kuo
Descent Mk3 Series - Small | 1058 | Descent Mk3 Series | 16205 | Pilot Run | Outdoor | 2023-10-30 | 2021-08-13 | 2021-09-03 | 2022-07-14 | 2022-07-28 | 2022-08-26 | 2023-04-28 | 2023-09-18 | 2023-12-11 | 1 | 0 |  | Daniel.Mao | JeffPY.Liao Joel.Wu | Franksl.Chen | Cooper.Wang
PGWW23 | 1136 | PGWW23 | 16590 | Production | OEM Auto | 2023-10-23 | 2023-04-18 | 2023-05-09 |  |  | 2023-05-10 |  |  | 2023-12-04 | 1 | 0 |  | Kevin.Liu3 Roger.Chan Tom.Tang Davidsd.Lin | Colby.Ren Jim.Shen | Nick.Yen | Ray.Hu Simon.Ko
Descent Mk3 Series - Large | 1057 | Descent Mk3 Series | 12994 | Product Launch | Outdoor | 2023-10-23 | 2021-08-13 | 2021-09-03 | 2022-07-20 | 2022-08-03 | 2022-09-07 | 2023-06-27 | 2023-08-16 | 2023-12-04 | 1 | 1 |  | Shawn.Huang Janet.Sun | Maggie.Chang JeffPY.Liao | Leol.Chen | Cooper.Wang
eTrex Solar | 1065 | eTrex Solar | 10901 | Production | Outdoor | 2023-10-16 | 2021-10-14 | 2021-11-04 | 2022-12-07 | 2022-12-21 | 2023-02-06 | 2023-02-13 | 2023-08-01 | 2023-11-27 | 1 | 0 |  | Steve.Chiang | Willycw.Wu JeffPY.Liao | Tina.Yang Neo.Lin | Chris.Kuo
Descent T2 Transceiver | 1157 | Descent T2 Transceiver | 16456 | Product Launch | Outdoor | 2023-10-02 | [6 empty] | 2023-08-02 | 2023-11-13 | 1 | 0 |  | Dannyhp.Cheng Vincent.Yeh | Eric.Chiang JeffPY.Liao | Robben.Liu | Ernest.Fu
Alpha LTE | 1139 | Alpha LTE | 16095 | Pilot Run | Outdoor | 2023-10-02 | 2022-04-28 | 2022-05-19 | 2023-02-08 | 2023-02-22 |  | 2023-03-31 | 2023-07-13 | 2023-11-13 | 1 | 0 |  | Dannyhp.Cheng | Lulu.Lee |  | Ernest.Fu
IMWW23 | 1084 | IMWW23 | 14434 | Production | OEM Auto | 2023-10-02 |  |  | 2021-11-26 | 2021-12-10 |  | 2022-11-24 | 2023-06-01 | 2023-11-13 | 1 | 0 |  | Davidsd.Lin Shawn.Yu Erichw.Wang | Colby.Ren Jim.Shen | Nick.Yen Jason.Fan | Simon.Ko Cherry.Tsai
GSD28 | 1068 | GSD28 | 15876 | Production | Marine | 2023-09-25 | 2021-10-07 | 2021-10-28 | 2022-11-25 | 2022-12-09 | 2022-12-21 |  | 2023-07-14 | 2023-11-06 | 1 | 0 |  | Bowman.Lai | Charlotte.Chen Edward.Tu | Donna.Chiu | Jasoncy.Hsu
MARQ Carbon | 904 | MARQ Carbon | 11252 | Production | Outdoor | 2023-09-04 | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 | 2022-12-23 | 2023-04-19 | 2023-10-16 | 1 | 0 |  | Shawn.Huang Andy.Chuang Ruby.Huang | Viola.Kao Peter.Lo Pattie.Lan JeffPY.Liao | Nixon.Pan | Aalto.Lo
TXTW22_Drive+3.0 (Taroko) -12.3 DA | 964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Product Launch | OEM Auto | 2023-09-04 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 | 2023-04-03 | 2023-10-16 | 1 | 0 |  | Davidsd.Lin Erichw.Wang | Colby.Ren Jim.Shen | Nick.Yen Jason.Fan | Ray.Hu Simon.Ko
Xero C1 Chronograph | 989 | Xero C1 Chronograph | 12253 | Pilot Run | Outdoor | 2023-08-28 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-24 | 2023-01-04 | 2023-05-12 | 2023-10-09 | 0 | 0 |  | PeiRu.Tsai | Kuo.Kuo JeffPY.Liao | Leol.Chen | Chris.Kuo
GPSMAP 9000 - 19" | 1051 | GPSMAP 9000 | 9946 | Production | Marine | 2023-08-21 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-10-02 | 1 | 0 |  | Derek.Cheng Roger.Chan | Jimmy.Kuo John.Chiu Jasonch.Chen Charlotte.Chen Allen.Chu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 - 24" | 1053 | GPSMAP 9000 | 9946 | Production | Marine | 2023-08-21 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-10-02 | 1 | 0 |  | Derek.Cheng Roger.Chan | Jimmy.Kuo John.Chiu Jasonch.Chen Charlotte.Chen Allen.Chu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 -27" | 1054 | GPSMAP 9000 | 9946 | Production | Marine | 2023-08-21 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-10-02 | 1 | 0 |  | Derek.Cheng Roger.Chan | Jimmy.Kuo John.Chiu Jasonch.Chen Charlotte.Chen Allen.Chu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
GPSMAP 9000 - 22" | 1052 | GPSMAP 9000 | 9946 | Production | Marine | 2023-08-21 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-10-02 | 1 | 0 |  | Derek.Cheng Roger.Chan | Jimmy.Kuo John.Chiu Jasonch.Chen Charlotte.Chen Allen.Chu | Nick.Yen | Jasoncy.Hsu Evelyn.Wang
Connect 50 transition to Taiwan Manufacturing | 1127 | Connect 50 transition to Taiwan Manufacturing | 16347 | Pilot Run | Marine | 2023-08-21 | [7 empty] | 2023-10-02 | 1 | 0 |  | Derek.Cheng | Charlotte.Chen
BlueNet Gateway | 961 | BlueNet Gateway | 9756 | Production | Marine | 2023-08-14 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-04-21 | 2023-02-01 | 2023-09-25 | 1 | 0 |  | Stephen.Shen | Allen.Chu | Tim.Wu | Jasoncy.Hsu
BlueNet Switch | 962 | BlueNet Switch | 9755 | Production | Marine | 2023-08-14 | 2021-03-17 | 2021-04-07 | 2021-12-21 | 2022-01-04 | 2022-02-17 | 2022-05-19 | 2023-02-01 | 2023-09-25 | 1 | 0 |  | Stephen.Shen | Chloe.Lin2 | Tim.Wu | Jasoncy.Hsu
GMR xHD3 Domes (18/24xHD replacement) | 1126 | GMR xHD3 Domes (18/24xHD replacement) | 16246 | Production | Marine | 2023-08-07 | 2022-04-01 | 2022-04-22 | 2022-08-30 | 2022-09-13 | 2022-10-04 | 2022-10-21 | 2023-03-02 | 2023-09-18 | 1 | 0 |  | Alex.Pu | Isaac.Wang Darren.Chen | Jason.Fan Nick.Yen | Jasoncy.Hsu
TWIN23 | 1144 | TWIN23 | 16503 | Detailed Design | OEM Auto | 2023-07-17 | [7 empty] | 2023-08-28 | 0 | 0 |  | Davidsd.Lin Shawn.Yu | Jim.Shen Colby.Ren |  | Simon.Ko Ray.Hu
Force Kraken Trolling Motor | 978 | Force Kraken Trolling Motor | 12789 | Production | Marine | 2023-07-17 | 2019-12-17 | 2020-01-07 | 2022-02-08 | 2022-02-22 | 2022-07-18 | 2022-08-15 | 2023-05-02 | 2023-08-28 | 0 | 0 |  | Iris.Wu | Daniel.Lee Jimmy.Kuo Allen.Chu John.Chiu | Tim.Wu | Jasoncy.Hsu
Venu 3 | 1089 | Venu 3 | 15520 | Production | Fitness | 2023-07-03 | 2021-09-09 | 2021-09-30 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-08-03 | 2023-03-15 | 2023-08-14 | 1 | 0 |  | Shawn.Huang Andyjs.Chen | George.Chang Steve.Lee JeffPY.Liao | Alexty.Chang Tina.Yang | Leoyt.Chen
Venu 3S | 1090 | Venu 3S | 15519 | Production | Fitness | 2023-07-03 | 2021-09-09 | 2021-09-30 | 2021-12-08 | 2021-12-22 | 2022-04-26 |  |  | 2023-08-14 | 1 | 0 |  | Shawn.Huang | Roger.Huang Steve.Lee JeffPY.Liao | Alexty.Chang Jackhl.Chen | Leoyt.Chen
GMR xHD3 Magnetron Open Arrays | 1105 | GMR xHD3 Magnetron Open Arrays | 15804 | Production | Marine | 2023-05-02 |  |  | 2022-05-06 | 2022-05-20 | 2022-08-03 |  |  | 2023-06-13 | 1 | 0 |  | Bowman.Lai | Isaac.Wang | Allyson.Kuo Lori.Tsai | Jasoncy.Hsu
Approach S70 | 1088 | Approach S70 - 47mm | 16176 | Production | Outdoor | 2023-04-24 | 2021-08-05 | 2021-08-26 | 2022-03-15 | 2022-03-29 | 2022-07-22 | 2022-09-07 |  | 2023-06-05 | 1 | 0 |  | Andyjs.Chen Ruby.Huang | Daniel.Tsai Viola.Kao | Jackhl.Chen Erinsa.Lu | Cooper.Wang
fenix 7X Pro | 1077 | fenix 7X Pro | 16112 | Production | Outdoor | 2023-04-24 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-28 |  | 2023-06-05 | 1 | 0 |  | Shawn.Huang | Stansy.Wang Roger.Huang Viola.Kao | Jackhl.Chen | Ernest.Fu
fenix 7S Pro (2022) | 1076 | fenix 7S Pro (2022) | 16108 | Production | Outdoor | 2023-04-24 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-26 | 2022-12-30 | 2023-06-05 | 1 | 0 |  | Dannyhp.Cheng | Stansy.Wang Viola.Kao Robert.Pan | Franksl.Chen | Cooper.Wang
fenix 7 Pro | 1075 | fenix 7 Pro | 14729 | Production | Outdoor | 2023-04-24 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-09-23 | 2022-12-30 | 2023-06-05 | 0 | 0 |  | Ruby.Huang | Stansy.Wang Robert.Pan Viola.Kao | Nixon.Pan | Ernest.Fu
Montana 7xx Parts Shortage Redesign | 1153 | Montana 7xx Parts Shortage Redesign | 15279 | Production | Outdoor | 2023-04-17 | [7 empty] | 2023-05-29 | 0 | 0 |  | Dannyhp.Cheng | Joel.Wu |  | Chris.Kuo
EPIX PRO (Gen 2) 47mm | 1093 | EPIX PRO (Gen 2) 47mm | 16217 | Production | Outdoor | 2023-04-13 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 |  |  | 2023-05-25 | 0 | 0 |  | Ruby.Huang | Robert.Pan Stansy.Wang Viola.Kao | Neo.Lin | Cooper.Wang
EPIX PRO (Gen 2) 42mm | 1092 | EPIX PRO (Gen 2) 42mm | 15803 | Production | Outdoor | 2023-04-13 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 | 2022-09-01 | 2022-11-28 | 2023-05-25 | 1 | 0 |  | Daniel.Mao | Stansy.Wang Viola.Kao Robert.Pan | Franksl.Chen | Aalto.Lo
BMW MGU22/IDC | 815 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2023-04-01 |  | 2019-08-30 | 2020-04-10 | 2020-04-24 | 2020-04-24 |  |  | 2023-05-12 | 0 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou Howard.Huang Colby.Ren | Sandy.Lee Ryan.Li | Tiffany2.Chen Cherry.Tsai Ray.Hu
Foretrex 801/901 | 1078 | Foretrex 801/901 | 14769 | Production | Outdoor | 2023-03-24 | 2021-10-01 | 2021-10-22 | 2022-03-11 | 2022-03-25 | 2022-07-22 | 2022-09-23 |  | 2023-05-05 | 1 | 0 |  | PeiRu.Tsai | Amyry.Chen Viola.Kao | Neo.Lin | Ernest.Fu
Varia eBike Radar Tail Light (eRTL615) | 1102 | Varia eBike Radar Tail Light (eRTL615) | 15837 | Production | Fitness | 2023-03-13 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-24 | 1 | 0 |  | PeiRu.Tsai | Lulu.Lee | Ryan.Li | Chris.Kuo
Instinct 2X Solar | 1112 | Instinct 2X Solar | 16020 | Production | Outdoor | 2023-03-01 | 2022-02-04 | 2022-02-25 | 2022-07-29 | 2022-08-12 | 2022-04-01 | 2022-11-28 | 2022-12-09 | 2023-04-12 | 1 | 0 |  | Andyjs.Chen Daniel.Mao | Viola.Kao Arthur.Wang Eason.Chen | Lori.Tsai | Aalto.Lo
eTrex SE | 1044 | eTrex SE | 15843 | Production | Outdoor | 2023-02-06 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 | 2022-05-23 |  | 2023-03-20 | 0 | 0 |  | Andyjs.Chen | Viola.Kao Eason.Chen Lulu.Lee | Franksl.Chen Neo.Lin | Chris.Kuo
Forerunner 965 | 1103 | Forerunner 965 | 16002 | Production | Fitness | 2023-01-09 | 2021-12-17 | 2022-01-07 | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-02-20 | 1 | 0 |  | Anton.Lin | Daniel.Tsai JeffPY.Liao | Alexty.Chang Erinsa.Lu | Aalto.Lo
Forerunner 265s | 1118 | Forerunner 265 | 14529 | Production | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 0 | 0 |  | Andyjs.Chen | Amyry.Chen JeffPY.Liao | Nixon.Pan | Ernest.Fu
Forerunner 265 | 1107 | Forerunner 265 | 14529 | Production | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 0 | 0 |  | Andyjs.Chen | Amyry.Chen JeffPY.Liao | Nixon.Pan | Ernest.Fu
Marq (Gen 2) | 972 | Marq (Gen 2) | 13004 | Production | Outdoor | 2022-10-10 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-11-21 | 1 | 0 |  | Shawn.Huang | Arthur.Wang JeffPY.Liao | Alexty.Chang Neo.Lin | Cooper.Wang
Alpha 200/200i Plus (i.MX7 Platform) | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | 16195 | Production | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 1 | 0 |  | Dannyhp.Cheng Daniel.Mao | JulieJJ.Lin
BMW MGU22_PL1 | 1028 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou Howard.Huang Colby.Ren | Sandy.Lee Ryan.Li | Tiffany2.Chen Cherry.Tsai Ray.Hu
BMW MGU22_G1 | 1079 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 0 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou Howard.Huang Colby.Ren | Sandy.Lee Ryan.Li | Tiffany2.Chen Cherry.Tsai Ray.Hu
Edge Explore 2 | 1045 | Edge Explore 2 | 14994 | Production | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0 |  | Dannyhp.Cheng Anton.Lin | Arthur.Wang Viola.Kao | Jackhl.Chen Nixon.Pan | Chris.Kuo
Forerunner 955 and 955 Solar | 967 | Forerunner 955 and 955 Solar | 12875 | Production | Fitness | 2022-04-25 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-06-06 | 0 | 0 |  | Anton.Lin | Eric.Chiang Viola.Kao | Alexty.Chang | Ernest.Fu
Tacx Vortex 2M | 1070 | Tacx Vortex 2M | 13589 | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1 |  |  | Claudia.vanRhoon | bianca | Marijn
BMW MGU22-RSE | 895 | BMW MGU22 | 10718 | Detailed Design | OEM Auto | 2022-03-07 |  | 2019-10-31 | 2020-05-15 | 2020-05-29 | 2020-05-29 |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou Howard.Huang Colby.Ren | Sandy.Lee Ryan.Li | Tiffany2.Chen Cherry.Tsai Ray.Hu
Xero G1 SatCom Scouting Camera | 826 | Xero G2i SatCom Scouting Camera | 7011 | Cancelled | Outdoor |  |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  |  | 1 | 0 |  | Derek.Cheng | Frankie.Lee | Ken.Kuo Nixon.Pan | Chris.Kuo
LWIN24 | 1221 | LWIN24 | 17343 | Top Level Design | OEM Auto | [9 empty] | 0 | 0 |  | Davidsd.Lin Shawn.Yu | Tom.Hsiao Colby.Ren |  | Simon.Ko
Force Pro (Anchor Lock & Sonar Relaunch) | 1222 | Force Pro (Anchor Lock & Sonar Relaunch) | 17285 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Steve.Chiang | Edward.Tu Jimmy.Kuo Simonyc.Chen | Tim.Wu | Jasoncy.Hsu
LXMY24 | 1193 | LXMY24 | 17227 | Top Level Design | OEM Auto | [9 empty] | 0 | 0 |  |  | Jim.Shen Tom.Hsiao Colby.Ren |  | Simon.Ko
Instinct 3 OLED - 50mm | 1195 | Instinct 3 OLED - 50mm | 17178 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao | JeffPY.Liao Willycw.Wu | Erinsa.Lu | Aalto.Lo
GPSMAP 9000xsv-13" | 1223 | GPSMAP 9000xsv | 17079 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng |  | Nick.Yen
GPSMAP 9000xsv-17" | 1224 | GPSMAP 9000xsv | 17079 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng |  | Nick.Yen
GPSMAP 9000xsv-10" | 1216 | GPSMAP 9000xsv | 17079 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng |  | Nick.Yen
Descent G2 | 1206 | Descent G2 | 17064 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Andy.Chuang | Leo.Chiu | Tim.Wu | Yali.Xu
Approach S50 | 1203 | Approach S50 | 17029 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao |  | Jason.Fan | Cooper.Wang
Edge MTB | 1208 | Edge MTB | 16987 | Product Development Plan | Fitness | [9 empty] | 0 | 0 |  | Andyjs.Chen | Lulu.Lee | Franksl.Chen | Cooper.Wang
fenix 8 Connected 51mm | 1218 | fenix 8 Connected 51mm | 16935 | Top Level Design | Outdoor | [9 empty] | 0 | 0 |  | Andyjs.Chen | Eason.Chen | Franksl.Chen Nixon.Pan | Aalto.Lo
Montana 710/710i/760i | 1215 | Montana 710/710i/760i | 16908 | Pilot Run | Outdoor | [9 empty] | 0 | 0 |  | Dannyhp.Cheng | Leo.Chiu
Forerunner 270 - 42mm | 1214 | Forerunner 270 - 42/47MM | 16810 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Andy.Chuang Shawn.Huang | Lulu.Lee George.Chang | Neo.Lin | Leoyt.Chen
Forerunner 270 - 47mm | 1201 | Forerunner 270 | 16810 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Andy.Chuang Shawn.Huang | Lulu.Lee George.Chang | Neo.Lin | Leoyt.Chen
Forerunner 970 | 1202 | Forerunner 970 | 16809 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Janet.Sun Shawn.Huang | Steve.Lee George.Chang | Leol.Chen Neo.Lin | Aalto.Lo
LiDAR Lite v5 | 1212 | LiDAR Lite v5 | 16791 | Top Level Design | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao | Chloe.Lin2 Johnny.Liu | Robben.Liu | Ernest.Fu
Approach G82 | 1213 | Approach G82 | 16736 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Andy.Chuang | JeffPY.Liao Leo.Chiu | Robben.Liu | Cooper.Wang
LWIN23 | 1177 | LWIN23 | 16704 | Cancelled | OEM Auto | [9 empty] | 0 | 0 |  | Roger.Chan Davidsd.Lin | Jim.Shen Colby.Ren |  | Simon.Ko
Enduro XT | 1207 | Enduro XT | 16536 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  | Andyjs.Chen | Pattie.Lan
Panoptix PS22-IF Transducer and Ice Fishing Bundles | 1210 | Panoptix PS22-IF Transducer and Ice Fishing Bundles | 16501 | Factory Prototype | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng | Allen.Chu |  | Jasoncy.Hsu
Venu X1 | 1211 | Venu X1 | 16384 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Vincent.Yeh | Pattie.Lan | Leol.Chen | Chris.Kuo
Tacx Climbing Accessory | 1169 | Tacx Climbing Accessory | 16345 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  |  | Claudia.vanRhoon
Tacx FLUX 3M | 1148 | Tacx FLUX 3M | 16250 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  |  |  | Jackhl.Chen | Jasoncy.Hsu
vivoactive 6 | 1204 | vivoactive 6 | 16236 | Product Development Plan | Fitness | [9 empty] | 0 | 0 |  | Dannyhp.Cheng | JeffPY.Liao Daniel.Tsai | Sandy.Lee | Jack.Cheng
Dive Light with Sonar | 1205 | Dive Light with Sonar | 16230 | New Product Concept | Outdoor | [9 empty] | 0 | 0 |  | Janet.Sun |  |  | Aalto.Lo
GPSMAP 66sr/66i Plus (i.MX7 Platform) | 1116 | GPSMAP 67/67i (i.MX7 Platform) | 16211 | Production | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao | Willycw.Wu
Venu 4 (41mm, 45mm) | 1200 | Venu 4 (41mm, 45mm) | 16119 | Product Development Plan | Fitness | [9 empty] | 0 | 0 |  | Janet.Sun PeiRu.Tsai | Anderson.Chen JeffPY.Liao | Jackhl.Chen Jason.Fan | Leoyt.Chen
Tacx NEO 3M | 1109 | Tacx NEO 3M | 15808 | Product Launch | Fitness | [9 empty] | 0 | 0 |  |  | Robin.deGroot Claudia.vanRhoon
Tacx Motion Plates | 1082 | Tacx Motion Plates | 14854 | Production | Fitness | [9 empty] | 1 | 0 |  |  | Claudia.vanRhoon | bianca | Marijn
Tacx Sports bottle | 1128 | Tacx Sports bottle | 14164 | Pilot Run | Fitness | [9 empty] | 0 | 0 |  |  | Johnny.Liu Claudia.vanRhoon
Equine Dynamics System | 1185 | Equine Dynamics System | 10702 | Cancelled | Outdoor | [9 empty] | 0 | 0 |  |  | Johnny.Liu |  | Chris.Kuo