## New Production Status Summary
New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11 | New Production Status Summary 2022-08-11
Project Name | Project Id | PM Project Name | PM Project Id | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM
LYWW24 | 1113 | LYWW24 | 15976 | Top Level Design | OEM Auto | 2024-08-05 | 2022-05-20 | 2022-06-10 | [5 empty] | 2024-09-16 | 1 | 0 |  | Davidsd.Lin Erichw.Wang | Jim.Shen Colby.Ren | Nick.Yen Jason.Fan
Xero B60i Laser Navigation Binoculars | 1119 | Xero B60i Laser Navigation Binoculars | 13229 | Detailed Design | Outdoor | 2024-03-22 | 2022-04-20 | 2022-05-11 | 2023-03-15 | 2023-03-29 | 2023-04-05 |  |  | 2024-05-03 | 1 | 0 |  | Alex.Pu | Jason.Cai | Donna.Chiu
LED Control Module | 1066 | LED Control Module | 13134 | Top Level Design | Marine | 2024-01-08 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  |  |  | 2024-02-19 | 1 | 0 |  | Iris.Wu | Frankie.Lee | Robben.Liu
Product - GDU147XW | 1049 | Product - GDU147XW | 12509 | Product Development Plan | Aviation | 2024-01-03 | [7 empty] | 2024-02-14 | 1 | 0 |  | Stephen.Shen | Jimmy.Kuo | Donna.Chiu Sandy.Lee
Descent Mk3 Series - Large | 1057 | Descent Mk3 Series | 12994 | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-07-08 | 2022-07-22 | 2022-08-05 | 2023-04-07 |  | 2023-11-13 | 1 | 0 |  | Shawn.Huang | Maggie.Chang Viola.Kao | Leol.Chen
Prop Drive Cost Down | 1115 | Prop Drive Cost Down | 16233 | Detailed Design | Marine | 2023-09-18 | 2022-02-14 | 2022-03-07 | 2022-07-08 | 2022-07-22 | 2022-08-08 |  |  | 2023-10-30 | 1 | 0 |  | Iris.Wu | John.Chiu | Nick.Yen
Descent Mk3 Series - Small | 1058 | Descent Mk3 Series | 16205 | Detailed Design | Outdoor | 2023-09-18 | 2021-08-13 | 2021-09-03 | 2022-09-19 | 2022-10-03 | 2022-07-20 | 2023-04-14 | 2023-07-03 | 2023-10-30 | 1 | 0 |  | Daniel.Mao | Viola.Kao Joel.Wu | Franksl.Chen
IMWW23 | 1084 | IMWW23 | 14434 | Top Level Design | OEM Auto | 2023-09-18 |  |  | 2021-11-05 | 2021-11-19 |  |  |  | 2023-10-30 | 1 | 0 |  | Davidsd.Lin Erichw.Wang Shawn.Yu | Jasper.Huang Jeff.Lin | Nick.Yen Jason.Fan
eTrex Solar | 1065 | eTrex Solar | 10901 | Detailed Design | Outdoor | 2023-08-21 | 2021-10-14 | 2021-11-04 | 2022-09-05 | 2022-09-19 | 2023-01-13 |  |  | 2023-10-02 | 1 | 0 |  | PeiRu.Tsai PeiRu.Tsai | Viola.Kao Willycw.Wu Willycw.Wu Viola.Kao | Tina.Yang Franksl.Chen Tina.Yang Franksl.Chen
Premium Dash Cams | 1130 | Premium Dash Cams | 16199 | Top Level Design | Automotive | 2023-07-31 | 2022-07-15 | 2022-08-05 | 2022-09-27 | 2022-10-11 | 2022-12-22 |  |  | 2023-09-11 | 1 | 0 |  | Stephen.Shen | Chloe.Lin2
TXTW22_Drive+3.0 (Taroko) -12.3 DA | 964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Detailed Design | OEM Auto | 2023-07-03 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 |  | 2023-08-14 | 1 | 0 |  | Davidsd.Lin Erichw.Wang Wells.Yu Davidsd.Lin | Jim.Shen Colby.Ren Jeff.Lin Zack.Lin Colby.Ren Jeff.Lin | Nick.Yen Jason.Fan Nick.Yen
Product - G3X/G500TXi Hybrid | 1050 | Product - G3X/G500TXi Hybrid | 12717 | Product Development Plan | Aviation | 2023-07-01 | [7 empty] | 2023-08-11 | 1 | 0
Product - 1.3\" GTR/GNC | 984 | Product - 1.3\" GTR/GNC | 12164 | Development | Aviation | 2023-07-01 | [7 empty] | 2023-08-11 | 1 | 0 |  | Steve.Chiang |  | Allyson.Kuo
Xero L60i Laser Navigator | 1016 | Xero L60i Laser Navigator | 8510 | Detailed Design | Outdoor | 2023-06-26 | 2021-02-25 | 2021-03-18 | 2022-07-15 | 2022-07-29 | 2022-07-22 |  |  | 2023-08-07 | 1 | 3 |  | Alex.Pu | Jason.Cai Jasonch.Chen | Lori.Tsai
Force Kraken Trolling Motor | 978 | Force Kraken Trolling Motor | 12789 | Factory Prototype | Marine | 2023-06-12 | 2019-12-17 | 2020-01-07 | 2022-02-08 | 2022-02-22 |  | 2022-08-04 | 2023-03-10 | 2023-07-24 | 1 | 0 |  | Iris.Wu | Allen.Chu Daniel.Lee Jimmy.Kuo John.Chiu | Tim.Wu
GPSMAP 9000_Black Box | 1122 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-06-05 | 2021-05-11 | 2021-06-01 | 2022-09-12 | 2022-09-26 | 2022-09-06 |  |  | 2023-07-17 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 - 19" | 1051 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-06-05 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-07-17 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 - 24" | 1053 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-06-05 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-07-17 | 1 | 1 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 -27" | 1054 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-06-05 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-07-17 | 1 | 0 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
GPSMAP 9000 - 22" | 1052 | GPSMAP 9000 | 9946 | Factory Prototype | Marine | 2023-06-05 | 2021-05-11 | 2021-06-01 | 2022-05-02 | 2022-05-16 | 2022-06-10 |  |  | 2023-07-17 | 1 | 1 |  | Derek.Cheng Bowman.Lai Stephen.Shen | Allen.Chu Jimmy.Kuo Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen
Venu 3 | 1089 | Venu 3 | 15520 | Factory Prototype | Fitness | 2023-05-29 |  |  | 2021-12-08 | 2021-12-22 | 2022-07-19 | 2022-08-03 |  | 2023-07-10 | 1 | 1 |  | Aaron.Lin | Viola.Kao George.Chang Pattie.Lan | Tina.Yang Alexty.Chang
Venu 3S | 1090 | Venu 3S | 15519 | Factory Prototype | Fitness | 2023-05-29 |  |  | 2021-12-01 | 2021-12-15 | 2022-07-19 |  |  | 2023-07-10 | 1 | 1 |  | Shawn.Huang | Viola.Kao Roger.Huang Stansy.Wang | Alexty.Chang
Venu Sq 3 | 1106 | Venu Sq 3 | 15850 | Cancelled | Fitness | 2023-05-08 | 2021-11-18 | 2021-12-09 | 2022-07-01 | 2022-07-15 |  |  |  | 2023-06-19 | 1 | 0 |  | Anton.Lin | Hao.Cheng Viola.Kao | Tina.Yang Jackhl.Chen
GSD28 | 1068 | GSD28 | 15876 | Detailed Design | Marine | 2023-05-01 | 2021-10-07 | 2021-10-28 | 2022-07-20 | 2022-08-03 | 2022-08-22 | 2022-08-22 | 2023-02-14 | 2023-06-12 | 1 | 0 |  | Bowman.Lai | Charlotte.Chen | Donna.Chiu
Approach Z50 | 949 | Approach Z50 | 12705 | Factory Prototype | Outdoor | 2023-05-01 | 2020-04-13 | 2020-05-04 | 2020-10-28 | 2020-11-11 | 2022-05-13 | 2022-04-06 |  | 2023-06-12 | 1 | 0 |  | Alex.Pu | Charlotte.Chen | Donna.Chiu Robben.Liu
Descent S1 Buoy | 1006 | Descent S1 Buoy | 12799 | Detailed Design | Outdoor | 2023-04-24 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 | 2022-08-15 | 2022-11-14 | 2023-06-05 | 1 | 1 |  | Aaron.Lin | Viola.Kao Daniel.Tsai | Franksl.Chen
Tire Temp Sensor | 1114 | Tire Temp Sensor | 11778 | Detailed Design | Automotive | 2023-04-10 | 2021-12-22 | 2022-01-12 | 2022-03-25 | 2022-04-08 | 2022-08-26 | 2022-09-02 | 2022-12-28 | 2023-05-22 | 1 | 0 |  | Iris.Wu | Jason.Cai | Donna.Chiu Sandy.Lee
BlueNET Gateway | 961 | BlueNET Gateway | 9756 | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-04-21 | 2022-12-28 | 2023-05-15 | 1 | 1 |  | Stephen.Shen | Allen.Chu | Tim.Wu
BlueNET Switch | 962 | BlueNET Switch | 9755 | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-05-19 | 2022-12-28 | 2023-05-15 | 1 | 1 |  | Stephen.Shen | Chloe.Lin2 | Tim.Wu
BMW MGU22/IDC | 815 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2023-04-01 |  | 2019-08-30 | 2020-04-10 | 2020-04-24 | 2020-04-24 |  |  | 2023-05-12 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | James.Chou Jasper.Huang Jasper.Huang James.Chou | Jasper.Huang Mark.Chang Sandy.Lee Joseph.Yen Sandy.Lee
fenix 7X Pro | 1077 | fenix 7X Pro | 16112 | Detailed Design | Outdoor | 2023-03-27 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 |  |  | 2023-05-08 | 1 | 3 |  | Shawn.Huang | Viola.Kao Roger.Huang Stansy.Wang | Jackhl.Chen
GMR xHD3 Domes (18/24xHD replacement) | 1126 | GMR xHD3 Domes (18/24xHD replacement) | 16246 | Detailed Design | Marine | 2023-03-20 | 2022-04-01 | 2022-04-22 | 2022-08-11 | 2022-08-25 | 2022-09-05 |  |  | 2023-05-01 | 1 | 0 |  | Alex.Pu | Darren.Chen Isaac.Wang | Nick.Yen Jason.Fan
Approach S70 | 1088 | Approach S70 | 16176 | Detailed Design | Outdoor | 2023-03-20 | 2021-08-05 | 2021-08-26 | 2022-07-08 | 2022-07-22 | 2022-06-20 |  |  | 2023-05-01 | 1 | 0 |  | Andyjs.Chen | Viola.Kao Daniel.Tsai | Jackhl.Chen
fenix 7S Pro (2022) | 1076 | fenix 7S Pro (2022) | 16108 | Detailed Design | Outdoor | 2023-03-20 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-08-15 | 2022-11-14 | 2023-05-01 | 1 | 3 |  | Dannyhp.Cheng | Viola.Kao Robert.Pan Stansy.Wang | Franksl.Chen
Approach S70s | 1036 | Approach S70S | 15419 | Detailed Design | Outdoor | 2023-03-20 | 2021-08-05 | 2021-08-26 | 2022-07-06 | 2022-07-20 | 2022-06-20 |  |  | 2023-05-01 | 1 | 0 |  | Dannyhp.Cheng | Viola.Kao Kuo.Kuo | Jackhl.Chen
Instinct 2X Solar | 1112 | Instinct 2X Solar | 16020 | Detailed Design | Outdoor | 2023-03-13 | 2022-02-04 | 2022-02-25 | 2022-07-29 | 2022-08-12 | 2022-04-01 |  |  | 2023-04-24 | 1 | 0 |  | Daniel.Mao Andyjs.Chen | Viola.Kao Eason.Chen Arthur.Wang | Lori.Tsai
fenix 7 Pro | 1075 | fenix 7 Pro | 14729 | Detailed Design | Outdoor | 2023-03-13 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-08-26 | 2022-11-25 | 2023-04-24 | 1 | 1 |  | Aaron.Lin | Viola.Kao Robert.Pan Stansy.Wang | Nixon.Pan
Panoptix PS70 - (SSMB) | 833 | Panoptix PS70 - (SSMB) | 10091 | Factory Prototype | Marine | 2023-03-13 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-09-05 | 2022-11-28 | 2023-04-24 | 1 | 0 |  | Derek.Cheng | Jimmy.Kuo | Tim.Wu
EPIX PRO (Gen 2) 51mm | 1094 | EPIX PRO (Gen 2) 51mm | 16218 | Detailed Design | Outdoor | 2023-03-06 | [7 empty] | 2023-04-17 | 1 | 1 |  | PeiRu.Tsai | Viola.Kao Roger.Huang Stansy.Wang | Robben.Liu
Varia eBike Radar Tail Light (eRTL615) | 1102 | Varia eBike Radar Tail Light (eRTL615) | 15837 | Factory Prototype | Fitness | 2023-03-06 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-17 | 1 | 0 |  | PeiRu.Tsai | Lulu.Lee | Ryan.Li
Catalyst KMR - Display | 1120 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-03-06 | 2021-09-20 | 2021-10-11 | 2022-02-24 | 2022-03-10 | 2022-05-23 |  |  | 2023-04-17 | 1 | 4 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
Catalyst KMR - Hub | 1111 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-03-06 | 2021-09-20 | 2021-10-11 | 2022-02-24 | 2022-03-10 | 2022-06-27 |  |  | 2023-04-17 | 1 | 0 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
Catalyst KMR - Camera | 1110 | Catalyst Kart/Moto/Roadster | 15624 | Factory Prototype | Automotive | 2023-03-06 | 2021-09-20 | 2021-10-11 | 2022-02-24 | 2022-03-10 | 2022-06-27 |  |  | 2023-04-17 | 1 | 1 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
EPIX PRO (Gen 2) 47mm | 1093 | EPIX PRO (Gen 2) 47mm | 16217 | Detailed Design | Outdoor | 2023-02-20 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 |  |  | 2023-04-03 | 1 | 0 |  | Aaron.Lin | Viola.Kao Stansy.Wang Robert.Pan | Neo.Lin
EPIX PRO (Gen 2) 42mm | 1092 | EPIX PRO (Gen 2) 42mm | 15803 | Detailed Design | Outdoor | 2023-02-13 | 2021-11-02 | 2021-11-23 | 2022-03-18 | 2022-04-01 | 2022-03-23 | 2022-09-01 | 2022-11-28 | 2023-03-27 | 1 | 2 |  | Daniel.Mao | Viola.Kao Robert.Pan Stansy.Wang | Franksl.Chen
RV Fixed Displays - 7" | 1080 | RV Fixed Displays (7"/10") | 14554 | Factory Prototype | Marine | 2023-02-13 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-07-20 | 2022-06-08 |  | 2023-03-27 | 1 | 0 |  | Bowman.Lai | Allen.Chu John.Chiu | Tim.Wu
RV Fixed Displays - 10" | 1081 | RV Fixed Displays (7"/10") | 14554 | Factory Prototype | Marine | 2023-02-13 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-07-20 | 2022-06-09 |  | 2023-03-27 | 1 | 0 |  | Bowman.Lai | Allen.Chu John.Chiu | Tim.Wu
Foretrex 801/901 | 1078 | Foretrex 801/901 | 14769 | Detailed Design | Outdoor | 2023-02-06 | 2021-10-01 | 2021-10-22 | 2022-03-11 | 2022-03-25 | 2022-07-22 | 2022-09-23 |  | 2023-03-20 | 1 | 0 |  | PeiRu.Tsai | Amyry.Chen Viola.Kao | Neo.Lin
zumo XT2 | 1101 | zumo XT2 | 16069 | Detailed Design | Automotive | 2023-01-30 | 2021-09-15 | 2021-10-06 | 2022-03-08 | 2022-03-22 | 2022-04-14 |  |  | 2023-03-13 | 1 | 3 |  | Derek.Cheng | Frankie.Lee | Nick.Yen
GMR xHD3 Magnetron Open Arrays | 1105 | GMR xHD3 Magnetron Open Arrays | 15804 | Factory Prototype | Marine | 2023-01-30 |  |  | 2022-05-06 | 2022-05-20 | 2022-06-22 |  |  | 2023-03-13 | 1 | 0 |  | Bowman.Lai | Isaac.Wang | Allyson.Kuo
Edge 540 840 | 1069 | Edge 540 840 | 14509 | Factory Prototype | Fitness | 2023-01-30 | 2021-03-11 | 2021-04-01 | 2021-04-14 | 2021-04-28 | 2022-02-07 | 2022-06-03 | 2022-09-23 | 2023-03-13 | 1 | 0 |  | Andyjs.Chen | Viola.Kao George.Chang Pattie.Lan | Leol.Chen
Forerunner 965 | 1103 | Forerunner 965 | 16002 | Factory Prototype | Fitness | 2023-01-09 | 2021-12-17 | 2022-01-07 | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-02-20 | 1 | 1 |  | Anton.Lin | Viola.Kao Johnny.Ko Daniel.Tsai | Alexty.Chang
Forerunner 265s | 1118 | Forerunner 265 | 14529 | Factory Prototype | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 1 |  | Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan
Forerunner 265 | 1107 | Forerunner 265 | 14529 | Factory Prototype | Fitness | 2023-01-03 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-15 | 2022-07-15 | 2022-09-23 | 2023-02-14 | 1 | 2 |  | Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan
Connect 50 transition to Taiwan Manufacturing | 1127 | Connect 50 transition to Taiwan Manufacturing | 16347 | Pilot Run | Marine | 2022-12-19 | [7 empty] | 2023-01-30 | 1 | 0 |  | Derek.Cheng | Charlotte.Chen
ECHOMAP UHD2 (Touch) 7" | 1059 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2023-01-30 | 1 | 1 |  | Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan
ECHOMAP UHD2 (Touch) 6" | 1018 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2021-11-23 | 2022-05-06 |  | 2023-01-30 | 1 | 2 |  | Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan
ECHOMAP UHD2 (Touch) 9" | 1041 | ECHOMAP UHD2 (Touch) | 13095 | Factory Prototype | Marine | 2022-12-19 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2023-01-30 | 1 | 2 |  | Steve.Chiang | Allen.Chu Jason.Cai Isaac.Wang Charlotte.Chen | Nick.Yen Jason.Fan
FUSION - WB675 Hide Away Stereo | 1043 | FUSION - WB675 Hide Away Stereo | 15524 | Factory Prototype | Marine | 2022-12-16 | [7 empty] | 2023-01-27 | 1 | 0 |  | Steve.Chiang | Allen.Chu
Alpha Dog Collar | 856 | Alpha Dog Collar | 7029 | Factory Prototype | Outdoor | 2022-12-09 | 2021-03-15 | 2021-04-05 | 2021-08-09 | 2021-08-23 | 2022-01-10 | 2022-01-25 |  | 2023-01-20 | 1 | 0 |  | Dannyhp.Cheng | Eason.Chen | Robben.Liu
Drive 53 | 1131 | Drive 53 | 16467 | Factory Prototype | Automotive | 2022-12-05 | 2022-06-08 | 2022-06-29 | [5 empty] | 2023-01-16 | 1 | 0 |  | Iris.Wu | Jason.Cai | Jackhl.Chen
eTrex SE | 1044 | eTrex SE | 15843 | Detailed Design | Outdoor | 2022-11-28 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 | 2022-05-23 |  | 2023-01-09 | 1 | 0 |  | Andyjs.Chen | Eason.Chen Viola.Kao Lulu.Lee | Franksl.Chen Neo.Lin
Xero C1 Chronograph | 989 | Xero C1 Chronograph | 12253 | Factory Prototype | Outdoor | 2022-11-21 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-25 | 2022-05-25 | 2022-08-16 | 2023-01-02 | 1 | 0 |  | Shawn.Huang | Viola.Kao Kuo.Kuo | Leol.Chen
Tread 8" OEM w/ CAN | 1063 | Tread 8" OEM w/ CAN | 15955 | Pilot Run | Automotive | 2022-11-14 | [6 empty] | 2022-03-16 | 2022-12-26 | 1 | 0 |  | Derek.Cheng | Johnny.Liu Jason.Cai | Lori.Tsai
vivomove Trend (previously "4") | 1030 | vivomove Trend (previously "4") | 14004 | Factory Prototype | Fitness | 2022-10-31 | 2020-11-13 | 2020-12-04 | 2021-10-01 | 2021-10-15 | 2021-11-03 | 2022-04-18 | 2022-08-05 | 2022-12-12 | 1 | 0 |  | Andyjs.Chen | Joel.Wu Viola.Kao | Leol.Chen
Dash Cam Live (LTE) | 990 | Dash Cam Live (LTE) | 13009 | Factory Prototype | Automotive | 2022-10-24 | 2020-09-18 | 2020-10-09 | 2020-11-30 | 2020-12-14 | 2021-06-14 | 2022-01-07 | 2022-05-16 | 2022-12-05 | 1 | 1 |  | Stephen.Shen | Johnny.Liu Jasonch.Chen | Lori.Tsai
Bounce(Waldo) | 862 | Bounce | 10919 | Pilot Run | Fitness | 2022-10-24 | 2019-09-03 | 2019-09-24 | 2019-10-22 | 2019-11-05 | 2020-04-30 |  | 2022-01-03 | 2022-12-05 | 1 | 0 |  | Shawn.Huang | Viola.Kao Leoyt.Chen | Franksl.Chen
LIIN22 | 1108 | LIIN22 | 16129 | Top Level Design | OEM Auto | 2022-10-11 | [7 empty] | 2022-11-22 | 1 | 0 |  | Shawn.Yu | Jim.Shen Colby.Ren Jeff.Lin
Instinct Hybrid Analog/Digital(Ripley) | 1029 | Instinct Hybrid Analog/Digital | 13084 | Pilot Run | Outdoor | 2022-10-11 |  |  | 2021-12-01 | 2021-12-15 |  | 2022-01-05 |  | 2022-11-22 | 1 | 1 |  | Anton.Lin Anton.Lin | Viola.Kao Eric.Chiang Eric.Chiang Viola.Kao | Alexty.Chang Robben.Liu Robben.Liu Alexty.Chang
Marq (Gen 2) | 972 | Marq (Gen 2) | 13004 | Detailed Design | Outdoor | 2022-10-10 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-11-21 | 1 | 0 |  | Shawn.Huang | Viola.Kao Arthur.Wang | Alexty.Chang
DriveSmart76 Synaptics Redesigns | 1098 | DriveSmart Synaptics Redesigns | 16182 | Pilot Run | Automotive | 2022-09-12 | [7 empty] | 2022-10-24 | 1 | 0 |  | Stephen.Shen Steve.Chiang Iris.Wu Bowman.Lai | Jason.Cai Jasonch.Chen
DriveSmart66 Synaptics Redesigns | 1097 | DriveSmart Synaptics Redesigns | 16182 | Pilot Run | Automotive | 2022-09-12 | [7 empty] | 2022-10-24 | 1 | 0 |  | Stephen.Shen Steve.Chiang Iris.Wu Bowman.Lai | Jason.Cai Jasonch.Chen
Alpha 200/200i Plus (i.MX7 Platform) | 1117 | Alpha 200/200i Plus (i.MX7 Platform) | 16195 | Pilot Run | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 1 | 0 |  | Dannyhp.Cheng Daniel.Mao | Leoyt.Chen
TXTW22_Drive+3.0 (Taroko)-9 DA | 953 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | 10340 | Detailed Design | OEM Auto | 2022-08-24 |  |  | 2021-05-28 | 2021-06-11 | 2021-06-18 | 2021-09-02 |  | 2022-10-05 | 1 | 0 |  | Davidsd.Lin Erichw.Wang Davidsd.Lin Wells.Yu | Jim.Shen Colby.Ren Jeff.Lin Jeff.Lin Zack.Lin Colby.Ren | Nick.Yen Jason.Fan Nick.Yen
GST - MCU 2.0 | 966 | GST - MCU 2.0 | 12155 | Pilot Run | Marine | 2022-08-22 | [7 empty] | 2022-10-03 | 1 | 1 |  | Iris.Wu | Chloe.Lin2
Tread - XL (10") | 948 | Tread XL - Baja Race Edition | 12983 | Pilot Run | Automotive | 2022-08-15 | 2020-02-11 | 2020-03-03 | 2020-06-29 | 2020-07-13 | 2020-12-11 | 2021-08-11 | 2021-10-01 | 2022-09-26 | 1 | 0 |  | Steve.Chiang | Isaac.Wang | Leol.Chen
Venu Sq 2(IMP) | 1023 | Venu Sq 2 | 14949 | Pilot Run | Fitness | 2022-07-28 | 2021-02-10 | 2021-03-03 |  |  |  | 2021-11-23 |  | 2022-09-08 | 1 | 0 |  | Anton.Lin | Hao.Cheng Viola.Kao | Jackhl.Chen
inReach Messenger | 1027 | inReach Messenger | 14539 | Product Launch | Outdoor | 2022-07-25 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-11-10 | 2022-01-03 | 2022-04-06 | 2022-09-05 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Viola.Kao Kuo.Kuo | Neo.Lin Nixon.Pan
Tacx NEO Bike Plus_Shifter | 986 | Tacx NEO Bike Plus | 13644 | Product Launch | Fitness | 2022-06-27 | [5 empty] | 2021-12-01 |  | 2022-08-08 | 1 | 0 |  | Stephen.Shen | Simonyc.Chen John.Chiu | Franksl.Chen
IXWW22 | 985 | IXWW22 | 11792 | Top Level Design | OEM Auto | 2022-06-27 | 2020-04-01 | 2020-04-22 |  |  | 2021-07-12 |  | 2021-12-28 | 2022-08-08 | 1 | 0 |  | Erichw.Wang | Colby.Ren Jeff.Lin | Nick.Yen
BMW MGU22_PL1 | 1028 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0 |  | Davidsd.Lin | James.Chou Jasper.Huang | Jasper.Huang Mark.Chang Sandy.Lee Joseph.Yen Mark.Chang
BMW MGU22_G1 | 1079 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0 |  | Davidsd.Lin | James.Chou Jasper.Huang | Jasper.Huang Mark.Chang Sandy.Lee Joseph.Yen
dezlCam OTR710 & RV 795 | 1033 | dezlCam OTR710 & RV Cam 795 | 15759 | Product Launch | Automotive | 2022-06-13 | [6 empty] | 2022-03-21 | 2022-07-25 | 1 | 0 |  | Bowman.Lai | Simonyc.Chen Allen.Chu | Tim.Wu
Tread Audio System | 1009 | Tread Audio System | 12874 | Pilot Run | Automotive | 2022-06-13 | 2020-11-24 | 2020-12-15 | 2021-03-17 | 2021-03-31 | 2021-07-19 | 2021-08-23 | 2022-01-14 | 2022-07-25 | 1 | 0 |  | Alex.Pu | Isaac.Wang | Tim.Wu
RV/Camper 2022 - 8" | 1061 | RV/Camper 2022 | 15969 | Product Launch | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Frankie.Lee John.Chiu Charlotte.Chen
RV/Camper 2022 - 7" | 1060 | RV/Camper 2022 | 15969 | Product Launch | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Frankie.Lee John.Chiu Charlotte.Chen
Edge Explore 2 | 1045 | Edge Explore 2 | 14994 | Product Launch | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0 |  | Anton.Lin Dannyhp.Cheng | Viola.Kao Arthur.Wang | Nixon.Pan Jackhl.Chen
Tacx NEO Bike Plus | 1100 | Tacx NEO Bike Plus | 13644 | Product Launch | Fitness | 2022-05-30 |  |  | 2020-04-22 | 2020-05-06 |  |  | 2022-03-28 | 2022-07-11 | 1 | 0 |  | Stephen.Shen | Simonyc.Chen John.Chiu | Franksl.Chen
Xero G1(s) SatCom Scouting Camera | 826 | Xero G1(s) SatCom Scouting Camera | 7011 | Product Launch | Outdoor | 2022-05-25 |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  | 2022-07-06 | 1 | 0 |  | Derek.Cheng Derek.Cheng | Frankie.Lee Frankie.Lee | Ken.Kuo Ken.Kuo
dezl OTR Series 2022 - 8" | 1056 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 0 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Allen.Chu Frankie.Lee Isaac.Wang Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022 - 6" | 1074 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-12-20 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 0 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Allen.Chu Frankie.Lee Isaac.Wang Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022-10" | 1055 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 0 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Allen.Chu Frankie.Lee Isaac.Wang Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022 - 7" | 1073 | dezl OTR Series 2022 | 15861 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 0 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Allen.Chu Frankie.Lee Isaac.Wang Jasonch.Chen | Stephanie.Yang Lori.Tsai
HRM-Pro Plus | 1022 | HRM-Pro Plus | 14484 | Production | Fitness | 2022-05-09 | [7 empty] | 2022-06-20 | 1 | 0 |  | ShengChi.Wang | Johnny.Liu
BC50 & BC50 IR | 1002 | BC50 and BC50 IR | 13939 | Product Launch | Automotive | 2022-04-25 | 2020-09-15 | 2020-10-06 | 2020-12-22 | 2021-01-05 | 2021-08-02 | 2021-09-08 | 2021-12-09 | 2022-06-06 | 1 | 0 |  | Steve.Chiang | Johnny.Liu | Leol.Chen
Edge 1040 | 936 | Edge 1040 | 11262 | Production | Fitness | 2022-04-25 | 2020-01-23 | 2020-02-13 | 2020-10-20 | 2020-11-03 | 2021-08-13 | 2021-04-28 | 2021-12-29 | 2022-06-06 | 1 | 0 |  | Anton.Lin | Viola.Kao Joel.Wu | Jackhl.Chen
GHC 50 | 1037 | GHC 50 | 14939 | Production | Marine | 2022-04-18 | [7 empty] | 2022-05-30 | 1 | 0 |  | Stephen.Shen | Charlotte.Chen
Forerunner 255S | 996 | Forerunner 255 and 255 Music | 13179 | Production | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-22 | 2021-12-28 | 2022-05-30 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Jerryy.Lin Viola.Kao Pattie.Lan | Robben.Liu
Forerunner 255 | 1032 | Forerunner 255 and 255 Music | 13179 | Production | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-23 | 2021-12-29 | 2022-05-30 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Jerryy.Lin Viola.Kao Pattie.Lan | Robben.Liu
Forerunner 955 and 955 Solar | 967 | Forerunner 955 and 955 Solar | 12875 | Production | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-05-30 | 0 | 0 |  | Anton.Lin | Viola.Kao Eric.Chiang | Alexty.Chang
2022 vivofit jr. 3 SKUs | 1095 | 2022 vivofit jr. 3 SKUs | 15907 | Product Launch | Fitness | 2022-04-11 |  |  |  |  | 2021-09-13 |  |  | 2022-05-23 | 0 | 0
quatix 7x Solar | 1086 | quatix 7x Solar | 16113 | Production | Marine | 2022-04-06 | [7 empty] | 2022-05-18 | 1 | 0 |  |  | Viola.Kao Hao.Cheng
Tacx Vortex 2M | 1070 | Tacx Vortex 2M | 13589 | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1 |  |  | Claudia.vanRhoon | bianca
Tactix 7 | 1087 | Tactix 7 | 14754 | Production | Outdoor | 2022-03-07 | [7 empty] | 2022-04-18 | 0 | 0 |  |  | Viola.Kao Hao.Cheng
vivosmart 5 (Franklin) | 1034 | vivosmart 5 (Franklin) | 14064 | Production | Fitness | 2022-03-07 | 2020-11-06 | 2020-11-27 | 2021-02-05 | 2021-02-19 | 2021-01-26 | 2021-08-31 | 2021-11-05 | 2022-04-18 | 1 | 0 |  | Anton.Lin | Viola.Kao Daniel.Tsai | Nixon.Pan
Dezl Headset | 1015 | Dezl Headset | 13139 | Production | Automotive | 2022-03-07 | [7 empty] | 2022-04-18 | 1 | 0 |  | ShengChi.Wang | Chloe.Lin2 Jasonch.Chen | Lori.Tsai
BMW MGU22-RSE | 895 | BMW MGU22 | 10718 | Top Level Design | OEM Auto | 2022-03-07 |  | 2019-10-31 | 2020-05-15 | 2020-05-29 | 2020-05-29 |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | James.Chou Jasper.Huang Jasper.Huang | Jasper.Huang Mark.Chang Sandy.Lee Joseph.Yen Sandy.Lee
quatix 7 Sapphire | 1104 | quatix 7 Sapphire | 16114 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao
quatix 7 | 1085 | quatix 7 | 15801 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao
Varia Radar Camera (RCT715) | 955 | Varia Radar Camera (RCT715) | 12714 | Production | Fitness | 2022-02-14 | 2020-03-24 | 2020-04-14 | 2020-12-01 | 2020-12-15 | 2021-04-28 | 2021-04-15 | 2021-10-29 | 2022-03-28 | 1 | 0 |  | Shawn.Huang | Simonyc.Chen Jimmy.Kuo | Jackhl.Chen
D2 Echo (EPIX) | 1040 | D2 Echo (EPIX) | 13079 | Production | Outdoor | 2022-01-17 | [7 empty] | 2022-02-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao
vivomove "Lite" | 979 | vivomove Sport (previously "Lite") | 12989 | Production | Fitness | 2021-11-08 | [7 empty] | 2021-12-20 | 1 | 0 |  | Herry.Lan | Viola.Kao Joel.Wu | Sherry.Shih
"Austin" | 983 | "Austin" | 13684 | Production | Outdoor | 2021-11-01 | 2020-03-05 | 2020-03-26 | 2020-08-31 | 2020-09-14 | 2020-09-15 |  |  | 2021-12-13 | 1 | 0 |  | Aaron.Lin | Leo.Chiu Viola.Kao | Nixon.Pan
Venu 2 Plus | 879 | Venu 2 Plus | 12514 | Production | Fitness | 2021-10-18 | 2020-01-01 | 2020-01-22 | 2020-02-07 | 2020-02-21 | 2020-06-05 |  |  | 2021-11-29 | 1 | 0 |  | Anton.Lin | Steve.Lee Viola.Kao | Alexty.Chang
fenix 7X | 960 | fenix 7X | 13934 | Production | Outdoor | 2021-10-04 | 2020-04-17 | 2020-04-02 | 2022-10-07 | 2022-10-21 |  | 2020-11-06 | 2021-02-15 | 2021-11-15 | 1 | 0 |  | Shawn.Huang | Viola.Kao Hao.Cheng
fenix 7S | 959 | fenix 7S | 13824 | Production | Outdoor | 2021-10-04 | [7 empty] | 2021-11-15 | 1 | 0 |  |  | Viola.Kao Stansy.Wang | Franksl.Chen
One Battery Bike Project | 909 | One Battery Bike Project | 12851 | Production | Fitness | 2021-09-06 | 2019-12-10 | 2019-12-31 | 2020-04-02 | 2020-04-16 | 2020-06-25 |  |  | 2021-10-18 | 1 | 0 |  | Anton.Lin | Pattie.Lan Viola.Kao | Nixon.Pan
NEO 2T Taiwan Production | 1021 | NEO 2T Taiwan Production | 15329 | Production | Fitness | 2021-06-22 | [7 empty] | 2021-08-03 | 1 | 0 |  |  |  | Lori.Tsai
Battery Charger | 998 | Battery Charger | 14544 | Production | Outdoor | 2021-04-26 | [7 empty] | 2021-06-07 | 1 | 0 |  | Dannyhp.Cheng Emma.Lin | Viola.Kao
Venu H(Asia ISO13485 Certification) | 1008 | Asia ISO13485 Certification | 13949 | Production | Fitness | 2021-04-12 | [7 empty] | 2021-05-24 | 1 | 0 |  |  | Viola.Kao Annie.Wang
Venu 2 | 903 | Venu 2 | 13028 | Production | Fitness | 2021-03-15 | [7 empty] | 2021-04-26 | 1 | 0 |  | Shawn.Huang | Leo.Chiu Davidjw.Yang Viola.Kao | Alexty.Chang
Venu 2S | 868 | Venu 2S | 11026 | Production | Fitness | 2021-03-02 | [7 empty] | 2021-04-13 | 1 | 0 |  | Anton.Lin | Viola.Kao | Alexty.Chang
Enduro 2020 | 898 | Enduro 2020 | 12690 | Production | Outdoor | 2021-01-11 | [7 empty] | 2021-02-22 | 1 | 0 |  | Shawn.Huang | Viola.Kao Daniel.Tsai | Chiencheng.Huang
Lumen | 860 | Lumen | 11752 | Production | Fitness | 2020-11-30 | 2019-07-01 | 2019-07-22 | 2019-11-21 | 2019-12-05 |  |  |  | 2021-01-11 | 0 | 0 |  | Herry.Lan | Viola.Kao | Sherry.Shih
Descent T1 Transmitter | 867 | Descent T1 Transmitter | 10190 | Production | Outdoor | 2020-11-02 | 2018-02-07 | 2018-02-28 | 2018-07-11 | 2018-07-25 | 2018-08-31 |  |  | 2020-12-14 | 1 | 0 |  | Anton.Lin Herry.Lan | Davidjw.Yang Viola.Kao Kris.Lo | Franksl.Chen
GPSMAP 64xr/sxr | 900 | GPSMAP 64xr/sxr | 12526 | Production | Outdoor | 2020-08-26 | [7 empty] | 2020-10-07 | 1 | 0 |  | Anton.Lin | Leo.Chiu | Franksl.Chen
Forerunner 745 | 872 | Forerunner 745 | 12183 | Production | Fitness | 2020-07-13 | 2019-03-05 | 2019-03-26 | 2019-08-27 | 2019-09-10 | 2019-10-28 |  |  | 2020-08-24 | 1 | 0 |  | Aaron.Lin | Viola.Kao Jasonyl.Wang | Alexty.Chang
Descent Mk2 | 835 | Descent Mk2 | 9800 | Production | Outdoor | 2020-06-22 | 2019-07-24 | 2019-08-14 | 2019-09-30 | 2019-10-14 | 2020-01-10 |  |  | 2020-08-03 | 1 | 0 |  | Aaron.Lin | Viola.Kao Steve.Lee Davidjw.Yang | Franksl.Chen
Alpha 200i | 848 | Alpha 200i | 7053 | Production | Outdoor | 2020-05-25 | 2018-09-10 | 2018-10-01 | 2019-02-05 | 2019-02-19 | 2019-05-13 |  |  | 2020-07-06 | 1 | 0 |  | Aaron.Lin | Viola.Kao Hao.Cheng
Instinct Solar | 853 | Instinct Solar | 11132 | Production | Outdoor | 2020-05-18 | 2019-03-05 | 2019-03-26 | 2019-08-02 | 2019-08-16 | 2019-08-23 |  |  | 2020-06-29 | 1 | 0 |  | Anton.Lin | Viola.Kao
fenix 6S Solar (2020) | 892 | fenix 6S Solar (2020) | 12689 | Production | Outdoor | 2020-05-11 | 2019-07-05 | 2019-07-26 | 2019-08-02 | 2019-08-16 |  |  |  | 2020-06-22 | 1 | 0 |  | Scott.Ma Anton.Lin | Jasonyl.Wang | Will.Ma
Edge 1030 Plus | 864 | Edge 1030 Plus | 12254 | Production | Fitness | 2020-05-04 | 2019-08-08 | 2019-08-29 | 2019-09-05 | 2019-09-19 | 2019-11-19 |  |  | 2020-06-15 | 1 | 0 |  | Shawn.Huang | Viola.Kao Hao.Cheng | Franksl.Chen
quatix 6 | 889 | quatix 6 | 10410 | Production | Marine | 2020-03-02 | [7 empty] | 2020-04-13 | 0 | 0 |  | Shawn.Huang Emma.Lin | Zack.Weng Daniel.Tsai
Garmin Swim 2 | 811 | Garmin Swim 2 | 7091 | Production | Fitness | 2019-09-23 | 2018-10-08 | 2018-10-29 |  |  | 2019-01-25 |  |  | 2019-11-04 | 0 | 0 |  | Emma.Lin | Hao.Cheng
GT15M Thru-Hull Flush | 1129 | GT15M Thru-Hull Flush | 16387 | Product Development Plan | Marine | [9 empty] | 0 | 0 |  | Iris.Wu | Jimmy.Kuo
dezl headset (2nd Gen) | 1132 | dezl headset (2nd Gen) | 16249 | Product Development Plan | Automotive | [9 empty] | 0 | 0 |  |  | Chloe.Lin2 | Allyson.Kuo
GPSMAP 66sr/66i Plus (i.MX7 Platform) | 1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | 16211 | Pilot Run | Outdoor | [9 empty] | 0 | 0 |  | Anton.Lin Daniel.Mao | Hao.Cheng
GPSMAP 68 | 1091 | GPSMAP 68 | 16137 | Product Development Plan | Outdoor | [9 empty] | 0 | 0 |  |  | Viola.Kao Hao.Cheng
Lily 2 | 1123 | Lily 2 | 15993 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Shawn.Huang | Viola.Kao George.Chang Pattie.Lan | Tina.Yang Alexty.Chang
Tacx NEO 3M | 1109 | Tacx NEO 3M | 15808 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  |  | Robin.deGroot
Descent X1i | 1121 | Descent X1i | 15469 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Viola.Kao Joel.Wu
Tacx Motion Plates | 1082 | Tacx Motion Plates | 14854 | Production | Fitness | [9 empty] | 1 | 1 |  |  | Claudia.vanRhoon | bianca
Enduro 2023 | 1047 | Enduro 2023 | 14704 | Detailed Design | Outdoor |  | 2021-09-15 | 2021-10-06 | 2022-08-30 | 2022-09-13 | 2021-11-09 |  |  |  | 0 | 0 |  | Dannyhp.Cheng | Leoyt.Chen Viola.Kao Stansy.Wang | Neo.Lin
Tacx Sports bottle | 1128 | Tacx Sports bottle | 14164 | Pilot Run | Fitness | [9 empty] | 0 | 0
Approach S42 | 1083 | Approach S42 | 13814 | Production | Outdoor | [9 empty] | 0 | 0 |  | Emma.Lin
Product - Flight Stream Redesign | 977 | Product - Flight Stream Redesign | 13634 | Derivative Product Concept | Aviation | [9 empty] | 0 | 0 |  | Stephen.Shen | Johnny.Liu Jimmy.Kuo
Product - GDU77XW | 1048 | Product - GDU77XW | 12510 | Product Development Plan | Aviation | [9 empty] | 0 | 0 |  |  |  | Donna.Chiu Sandy.Lee
MARQ Carbon | 904 | MARQ Carbon | 11252 | Detailed Design | Outdoor |  | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 | 2022-07-27 | 2022-06-30 |  | 0 | 0 |  | Shawn.Huang | Viola.Kao Eason.Chen | Nixon.Pan
Approach R50 | 1012 | Approach R50 | 10926 | Detailed Design | Outdoor |  | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 | 2022-02-28 |  |  |  | 0 | 0 |  | Steve.Chiang Stephen.Shen | Chloe.Lin2 Johnny.Liu | Nixon.Pan Allyson.Kuo
Pet Tracker | 944 | Pet Tracker | 10666 | Cancelled | Outdoor | [9 empty] | 0 | 0 |  | Shawn.Huang Lionel.Wu | Daniel.Tsai Amelie.Chang