## feature_metrix
New_feature | 2022-10 | 2022-11 | 2022-12 | 2023-01 | 2023-02
ALS | 2 | 1 | 0 | 1 | 6
AOD | 2 | 1 | 0 | 0 | 5
Appearance | 0 | 1 | 0 | 0 | 0
ECG | 2 | 3 | 1 | 1 | 4
Flashlight | 2 | 3 | 1 | 0 | 4
LED | 2 | 0 | 0 | 0 | 0
None | 1 | 9 | 6 | 2 | 2
Skintemperature | 0 | 0 | 0 | 1 | 1
Voiceassistance | 0 | 0 | 0 | 1 | 1
WiFi | 0 | 0 | 0 | 0 | 2
Workouts | 0 | 0 | 0 | 0 | 2
nan | 0 | 0 | 0 | 0 | 2

## overall_oob_mp_pid
projectSizeId | Project_Name | Segment | Phase | status | actualGMLASubmitDate | targetGMLASubmitDate | MP_file_count | MP_Comment | PID_file_count | PID_Comment | PID+MP_count | judgement | Comment
970 | Approach G12 | Outdoor | GMLA2 | Complete | 2020-12-25 | 2020-12-31 | 0 |  | 0 |  | 0 | FALSE
870 | Forerunner 945 LTE | Fitness | GMLA3 | Complete | 2020-12-28 | 2020-12-28 | 0 |  | 0 |  | 0 | FALSE
959 | fenix 7S | Outdoor | GMLA2 | Complete | 2020-12-28 | 2021-01-04 | 0 |  | 0 |  | 0 | FALSE
917 | Dash Cam 47 / 57 / 67W | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-24 | 0 |  | 0 |  | 0 | FALSE
954 | Dash Cam Mini 2 | Automotive | GMLA3 | Complete | 2020-12-28 | 2020-12-21 | 0 |  | 0 |  | 0 | FALSE
866 | Descent Mk2s | Outdoor | GMLA3 | Complete | 2020-12-29 | 2020-12-22 | 0 | K:\PQE\PQE Support Team\OOB Checklist\mk2s | 0 |  | 0 | FALSE | K:\PQE\PQE Support Team\OOB Checklist\mk2s
903 | Venu 2 | Fitness | GMLA3 | Complete | 2020-12-30 | 2020-12-30 | 0 |  | 0 |  | 0 | FALSE
912 | Approach S12 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-04 | 0 | OOB check list is released | 0 |  | 0 | FALSE | OOB check list is released
858 | Approach R10 | Outdoor | GMLA3 | Complete | 2021-01-04 | 2021-01-05 | 0 |  | 0 |  | 0 | FALSE
981 | Xero A1i PRO Bow Sight | Outdoor | GMLA2 | Complete | 2021-01-08 | 2021-01-11 | 0 |  | 0 |  | 0 | FALSE
881 | fenix 7 | Outdoor | GMLA2 | Complete | 2021-01-11 | 2021-01-08 | 3 | Updated | 0 |  | 3 | TRUE | Updated
960 | fenix 7X | Outdoor | GMLA2 | Complete | 2021-01-15 | 2021-01-11 | 0 |  | 0 |  | 0 | FALSE
868 | Venu 2S | Fitness | GMLA3 | Complete | 2021-01-27 | 2021-01-27 | 0 |  | 0 |  | 0 | FALSE
1008 | Venu H(Asia ISO13485 Certification) | Fitness | GMLA3 | Complete | 2021-01-29 | 2021-04-08 | 0 |  | 0 |  | 0 | FALSE
941 | Forerunner 55 | Fitness | GMLA2 | Complete | 2021-02-02 | 2021-02-02 | 0 |  | 0 |  | 0 | FALSE
834 | MSC-10 [Marine Satellite Compass] | Marine | GMLA3 | Complete | 2021-02-02 | 2021-02-01 | 0 |  | 0 |  | 0 | FALSE
963 | Malibu Display | Marine | GMLA3 | Complete | 2021-02-03 | 2021-02-03 | 0 |  | 0 |  | 0 | FALSE
929 | FUSION - RA60 | Marine | GMLA2 | Complete | 2021-02-06 | 2021-02-09 | 0 |  | 0 |  | 0 | FALSE
821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA2 | Complete | 2021-02-08 | 2021-02-18 | 0 |  | 0 |  | 0 | FALSE
970 | Approach G12 | Outdoor | GMLA3 | Complete | 2021-03-04 | 2021-03-04 | 0 |  | 0 |  | 0 | FALSE
909 | One Battery Bike Project | Fitness | GMLA3 | Complete | 2021-03-04 | 2021-02-17 | 0 | Done. | 0 |  | 0 | FALSE | Done.
879 | Venu 2 Plus | Fitness | GMLA2 | Complete | 2021-03-17 | 2021-03-17 | 0 |  | 0 |  | 0 | FALSE
1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA2 | Complete | 2021-03-18 | 2021-03-18 | 0 |  | 0 |  | 0 | FALSE
938 | DriveSmart 66 | Automotive | GMLA2 | Complete | 2021-03-19 | 2021-03-24 | 0 |  | 0 |  | 0 | FALSE
983 | "Austin" | Outdoor | GMLA2 | Complete | 2021-03-26 | 2021-03-29 | 0 |  | 0 |  | 0 | FALSE
1021 | NEO 2T Taiwan Production | Fitness | GMLA3 | Complete | 2021-03-31 | 2021-03-31 | 0 |  | 0 |  | 0 | FALSE
939 | DriveSmart 76 | Automotive | GMLA2 | Complete | 2021-03-31 | 2021-04-02 | 0 | done | 0 |  | 0 | FALSE | done
929 | FUSION - RA60 | Marine | GMLA3 | Complete | 2021-04-07 | 2021-04-07 | 0 |  | 0 |  | 0 | FALSE
940 | DriveSmart 86 | Automotive | GMLA2 | Complete | 2021-04-09 | 2021-04-09 | 0 |  | 0 |  | 0 | FALSE
941 | Forerunner 55 | Fitness | GMLA3 | Complete | 2021-04-12 | 2021-04-13 | 0 |  | 0 |  | 0 | FALSE
976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA2 | Complete | 2021-04-13 | 2021-04-13 | 0 |  | 0 |  | 0 | FALSE
959 | fenix 7S | Outdoor | GMLA3 | Complete | 2021-04-13 | 2021-04-13 | 0 |  | 0 |  | 0 | FALSE
821 | FUSION - Apollo Amplifiers 1 / 4 channel | Marine | GMLA3 | Complete | 2021-04-26 | 2021-04-23 | 0 |  | 0 |  | 0 | FALSE
979 | vivomove "Lite" | Fitness | GMLA2 | Complete | 2021-05-03 | 2021-05-03 | 0 |  | 0 |  | 0 | FALSE
881 | fenix 7 | Outdoor | GMLA3 | Complete | 2021-05-05 | 2021-05-05 | 3 | Updated | 0 |  | 3 | TRUE | Updated
862 | Bounce(Waldo) | Fitness | GMLA2 | Complete | 2021-05-06 | 2021-05-17 | 0 | Released | 0 |  | 0 | FALSE | Released
905 | Instinct 2 | Outdoor | GMLA2 | Complete | 2021-05-11 | 2021-05-11 | 0 |  | 0 |  | 0 | FALSE
971 | Instinct 2S | Outdoor | GMLA2 | Complete | 2021-05-12 | 2021-05-12 | 0 |  | 0 |  | 0 | FALSE
824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA2 | Complete | 2021-05-13 | 2021-05-13 | 0 |  | 0 |  | 0 | FALSE
1026 | dezl watch | Automotive | GMLA2 | Complete | 2021-05-14 | 2021-05-14 | 0 |  | 0 |  | 0 | FALSE
960 | fenix 7X | Outdoor | GMLA3 | Complete | 2021-05-24 | 2021-05-20 | 0 |  | 0 |  | 0 | FALSE
921 | Surround View Camera System | Marine | GMLA2 | Complete | 2021-05-25 | 2021-05-25 | 1 |  | 0 |  | 1 | TRUE
976 | FUSION - AP-DA214 (Zone Amplifier) | Marine | GMLA3 | Complete | 2021-06-01 | 2021-06-04 | 0 |  | 0 |  | 0 | FALSE
1004 | GPSMAP 79 Series | Marine | GMLA2 | Complete | 2021-06-16 | 2021-06-16 | 0 |  | 0 |  | 0 | FALSE
1011 | WDU Cost down (EmpirBus Low cost web server solution) | Marine | GMLA3 | Complete | 2021-06-16 | 2021-06-16 | 0 |  | 0 |  | 0 | FALSE
938 | DriveSmart 66 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-28 | 0 |  | 0 |  | 0 | FALSE
1014 | GMR Fantom 18x/24x | Marine | GMLA2 | Complete | 2021-06-22 | 2021-06-22 | 0 |  | 0 |  | 0 | FALSE
939 | DriveSmart 76 | Automotive | GMLA3 | Complete | 2021-06-22 | 2021-06-24 | 0 | done | 0 |  | 0 | FALSE | done
824 | FUSION - Apollo Amplifiers 6 / 8 channel | Marine | GMLA3 | Complete | 2021-06-23 | 2021-07-05 | 0 |  | 0 |  | 0 | FALSE
940 | DriveSmart 86 | Automotive | GMLA3 | Complete | 2021-06-23 | 2021-06-23 | 0 |  | 0 |  | 0 | FALSE
922 | inReach Mini 2 | Outdoor | GMLA2 | Complete | 2021-06-25 | 2021-06-25 | 1 | Chris by 11/19 | 0 |  | 1 | TRUE | Chris by 11/19
968 | Descent G1 | Outdoor | GMLA2 | Complete | 2021-06-29 | 2021-06-29 | 1 |  | 0 |  | 1 | TRUE
862 | Bounce(Waldo) | Fitness | GMLA3 | Complete | 2021-07-12 | 2021-07-13 | 0 | Released | 0 |  | 0 | FALSE | Released
981 | Xero A1i PRO Bow Sight | Outdoor | GMLA3 | Complete | 2021-07-15 | 2021-07-15 | 0 |  | 0 |  | 0 | FALSE
905 | Instinct 2 | Outdoor | GMLA3 | Complete | 2021-07-19 | 2021-07-16 | 0 |  | 0 |  | 0 | FALSE
971 | Instinct 2S | Outdoor | GMLA3 | Complete | 2021-07-26 | 2021-07-28 | 0 |  | 0 |  | 0 | FALSE
945 | Tread - SXS (8") | Automotive | GMLA2 | Complete | 2021-07-26 | 2021-07-26 | 0 |  | 0 |  | 0 | FALSE
879 | Venu 2 Plus | Fitness | GMLA3 | Complete | 2021-07-30 | 2021-07-29 | 0 |  | 0 |  | 0 | FALSE
826 | Xero G2i SatCom Scouting Camera | Outdoor | GMLA3 | Complete | 2021-08-12 | 2021-10-01 | 0 |  | 0 |  | 0 | FALSE
921 | Surround View Camera System | Marine | GMLA3 | Complete | 2021-09-01 | 2021-09-01 | 1 |  | 0 |  | 1 | FALSE
948 | Tread - XL (10") | Automotive | GMLA2 | Complete | 2021-09-07 | 2021-09-07 | 0 |  | 0 |  | 0 | FALSE
1004 | GPSMAP 79 Series | Marine | GMLA3 | Complete | 2021-09-08 | 2021-09-08 | 0 |  | 0 |  | 0 | FALSE
1014 | GMR Fantom 18x/24x | Marine | GMLA3 | Complete | 2021-09-14 | 2021-09-15 | 0 |  | 0 |  | 0 | FALSE
987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 0 |  | 0 |  | 0 | FALSE
988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA2 | Complete | 2021-09-22 | 2021-09-22 | 0 |  | 0 |  | 0 | FALSE
955 | Varia Radar Camera (RCT715) | Fitness | GMLA2 | Complete | 2021-09-23 | 2021-09-09 | 1 |  | 0 |  | 1 | TRUE
979 | vivomove "Lite" | Fitness | GMLA3 | Complete | 2021-09-27 | 2021-09-23 | 0 |  | 0 |  | 0 | FALSE
983 | "Austin" | Outdoor | GMLA3 | Complete | 2021-10-01 | 2021-10-06 | 0 |  | 0 |  | 0 | FALSE
922 | inReach Mini 2 | Outdoor | GMLA3 | Complete | 2021-10-12 | 2021-10-13 | 1 | Chris by 11/19 | 0 |  | 1 | FALSE | Chris by 11/19
968 | Descent G1 | Outdoor | GMLA3 | Complete | 2021-10-13 | 2021-10-13 | 1 |  | 0 |  | 1 | FALSE
1034 | vivosmart 5 (Franklin) | Fitness | GMLA2 | Complete | 2021-10-18 | 2021-10-20 | 0 |  | 0 |  | 0 | FALSE
1026 | dezl watch | Automotive | GMLA3 | Complete | 2021-10-20 | 2021-10-20 | 0 |  | 0 |  | 0 | FALSE
945 | Tread - SXS (8") | Automotive | GMLA3 | Complete | 2021-10-29 | 2021-11-03 | 0 |  | 0 |  | 0 | FALSE
967 | Forerunner 955 and 955 Solar | Fitness | GMLA2 | Complete | 2021-11-15 | 2021-11-17 | 1 |  | 0 |  | 1 | TRUE
936 | Edge 1040 | Fitness | GMLA2 | Complete | 2021-11-16 | 2021-11-17 | 0 |  | 0 |  | 0 | FALSE
948 | Tread - XL (10") | Automotive | GMLA3 | Complete | 2021-11-17 | 2021-11-17 | 0 |  | 0 |  | 0 | FALSE
1015 | Dezl Headset | Automotive | GMLA2 | Complete | 2021-11-18 | 2021-11-22 | 1 | OOB checklist is as the attachment. | 0 |  | 1 | TRUE | OOB checklist is as the attachment.
1038 | LiveScope Plus (LVS34) | Marine | GMLA2 | Complete | 2021-11-23 | 2021-11-23 | 1 |  | 0 |  | 1 | TRUE
969 | Delta Simple | Outdoor | GMLA2 | Complete | 2021-12-02 | 2021-12-02 | 0 |  | 0 |  | 0 | FALSE
1002 | BC50 & BC50 IR | Automotive | GMLA2 | Complete | 2021-12-03 | 2021-12-03 | 0 |  | 0 |  | 0 | FALSE
1017 | LiveScope XR (LVS62) | Marine | GMLA2 | Complete | 2021-12-06 | 2021-12-15 | 1 |  | 0 |  | 1 | TRUE
955 | Varia Radar Camera (RCT715) | Fitness | GMLA3 | Complete | 2021-12-16 | 2021-12-20 | 1 |  | 0 |  | 1 | FALSE
1032 | Forerunner 255 | Fitness | GMLA2 | Complete | 2021-12-21 | 2021-12-22 | 0 | Released | 0 |  | 0 | FALSE | Released
996 | Forerunner 255S | Fitness | GMLA2 | Complete | 2021-12-22 | 2021-12-22 | 0 | Released | 0 |  | 0 | FALSE | Released
1034 | vivosmart 5 (Franklin) | Fitness | GMLA3 | Complete | 2021-12-27 | 2021-12-27 | 0 |  | 0 |  | 0 | FALSE
1009 | Tread Audio System | Automotive | GMLA2 | Complete | 2022-01-05 | 2022-01-05 | 1 |  | 0 |  | 1 | TRUE
1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 0 | It has been&nbsp;released to FQC. | 0 |  | 0 | FALSE | It has been&nbsp;released to FQC.
1038 | LiveScope Plus (LVS34) | Marine | GMLA3 | Complete | 2022-01-26 | 2022-02-02 | 1 |  | 0 |  | 1 | FALSE
1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA2 | Complete | 2022-01-26 | 2022-01-26 | 0 |  | 0 |  | 0 | FALSE
1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 0 | As the attachment. | 0 |  | 0 | FALSE | As the attachment.
1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Complete | 2022-01-27 | 2022-01-27 | 0 |  | 0 |  | 0 | FALSE
986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA2 | Complete | 2022-02-07 | 2022-02-04 | 0 |  | 0 |  | 0 | FALSE
1015 | Dezl Headset | Automotive | GMLA3 | Complete | 2022-02-08 | 2022-02-08 | 1 | OOB checklist is as the attachment. | 0 |  | 1 | FALSE | OOB checklist is as the attachment.
1055 | dezl OTR Series 2022-10" | Automotive | GMLA2 | Complete | 2022-02-09 | 2022-02-09 | 0 |  | 0 |  | 0 | FALSE
1063 | Tread 8" OEM w/ CAN | Automotive | GMLA2 | Complete | 2022-02-23 | 2022-02-23 | 0 |  | 0 |  | 0 | FALSE
936 | Edge 1040 | Fitness | GMLA3 | Complete | 2022-02-25 | 2022-02-25 | 0 |  | 0 |  | 0 | FALSE
1002 | BC50 & BC50 IR | Automotive | GMLA3 | Complete | 2022-03-02 | 2022-03-03 | 0 |  | 0 |  | 0 | FALSE
1027 | inReach Messenger | Outdoor | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 1 |  | 0 |  | 1 | TRUE
988 | ECHOMAP UHD2 (Keyed) 7" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 0 |  | 0 |  | 0 | FALSE
987 | ECHOMAP UHD2 (Keyed) 5" | Marine | GMLA3 | Complete | 2022-03-03 | 2022-03-03 | 0 |  | 0 |  | 0 | FALSE
1045 | Edge Explore 2 | Fitness | GMLA2 | Complete | 2022-03-03 | 2022-03-03 | 1 |  | 0 |  | 1 | TRUE
967 | Forerunner 955 and 955 Solar | Fitness | GMLA3 | Complete | 2022-03-09 | 2022-03-09 | 1 |  | 0 |  | 1 | FALSE
1009 | Tread Audio System | Automotive | GMLA3 | Complete | 2022-03-11 | 2022-03-14 | 1 |  | 0 |  | 1 | FALSE
1032 | Forerunner 255 | Fitness | GMLA3 | Complete | 2022-03-30 | 2022-03-31 | 0 | Released | 0 |  | 0 | FALSE | Released
996 | Forerunner 255S | Fitness | GMLA3 | Complete | 2022-03-31 | 2022-03-31 | 0 | Released | 0 |  | 0 | FALSE | Released
1017 | LiveScope XR (LVS62) | Marine | GMLA3 | Complete | 2022-04-07 | 2022-04-07 | 1 |  | 0 |  | 1 | FALSE
1023 | Venu Sq 2(IMP) | Fitness | GMLA2 | Complete | 2022-04-08 | 2022-04-11 | 0 |  | 0 |  | 0 | FALSE
1074 | dezl OTR Series 2022 - 6" | Automotive | GMLA3 | Complete | 2022-04-08 | 2022-04-11 | 0 |  | 0 |  | 0 | FALSE
1056 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 0 |  | 0 |  | 0 | FALSE
1073 | dezl OTR Series 2022 - 7" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-11 | 0 | It has been&nbsp;released to FQC. | 0 |  | 0 | FALSE | It has been&nbsp;released to FQC.
1055 | dezl OTR Series 2022-10" | Automotive | GMLA3 | Complete | 2022-04-11 | 2022-04-19 | 0 |  | 0 |  | 0 | FALSE
969 | Delta Simple | Outdoor | GMLA3 | Complete | 2022-04-21 | 2022-04-25 | 0 |  | 0 |  | 0 | FALSE
990 | Dash Cam Live (LTE) | Automotive | GMLA2 | Complete | 2022-04-26 | 2022-04-26 | 1 |  | 0 |  | 1 | TRUE
1063 | Tread 8" OEM w/ CAN | Automotive | GMLA3 | Complete | 2022-04-26 | 2022-04-26 | 0 |  | 0 |  | 0 | FALSE
1045 | Edge Explore 2 | Fitness | GMLA3 | Complete | 2022-05-03 | 2022-05-04 | 1 |  | 0 |  | 1 | FALSE
1027 | inReach Messenger | Outdoor | GMLA3 | Complete | 2022-05-16 | 2022-05-17 | 1 |  | 0 |  | 1 | FALSE
986 | Tacx NEO Bike Plus_Shifter | Fitness | GMLA3 | Complete | 2022-05-17 | 2022-05-17 | 0 |  | 0 |  | 0 | FALSE
1033 | dezlCam OTR710 & RV 795 | Automotive | GMLA3 | Complete | 2022-05-24 | 2022-05-24 | 0 | As the attachment. | 0 |  | 0 | FALSE | As the attachment.
1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 0 |  | 0 |  | 0 | FALSE | nan
1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 0 |  | 0 |  | 0 | FALSE | nan
1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA2 | Complete | 2022-06-27 | 2022-06-27 | 0 |  | 0 |  | 0 | FALSE | nan
1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA2 | Complete | 2022-06-27 | 2022-06-29 | 0 |  | 0 |  | 0 | FALSE
1030 | vivomove Trend (previously "4") | Fitness | GMLA2 | Complete | 2022-07-04 | 2022-07-06 | 1 | None | 0 |  | 1 | TRUE | None
1023 | Venu Sq 2(IMP) | Fitness | GMLA3 | Complete | 2022-07-06 | 2022-07-08 | 0 |  | 0 |  | 0 | FALSE
989 | Xero C1 Chronograph | Outdoor | GMLA2 | Complete | 2022-07-21 | 2022-07-25 | 0 |  | 0 |  | 0 | FALSE
1044 | eTrex SE | Outdoor | GMLA2 | Complete | 2022-08-04 | 2022-08-10 | 2 | None | 0 |  | 2 | TRUE | None
1069 | Edge 540 840 | Fitness | GMLA2 | Complete | 2022-08-22 | 2022-08-22 | 1 | None | 0 |  | 1 | TRUE | None
1118 | Forerunner 265s | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 0 | None | 0 |  | 0 | FALSE | None
1103 | Forerunner 965 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-15 | 1 | None | 0 |  | 1 | TRUE | None
1107 | Forerunner 265 | Fitness | GMLA2 | Complete | 2022-09-12 | 2022-09-13 | 0 | None | 0 |  | 0 | FALSE | None
972 | Marq (Gen 2) | Outdoor | GMLA2 | Complete | 2022-09-14 | 2022-09-14 | 2 |  | 0 |  | 2 | TRUE
1029 | Instinct Hybrid Analog/Digital(Ripley) | Outdoor | GMLA3 | Complete | 2022-09-16 | 2022-09-19 | 0 |  | 0 |  | 0 | FALSE
990 | Dash Cam Live (LTE) | Automotive | GMLA3 | Complete | 2022-09-26 | 2022-09-26 | 1 |  | 0 |  | 1 | FALSE
1131 | Drive 53 | Automotive | GMLA2 | Complete | 2022-09-26 | 2022-09-27 | 0 |  | 2 | None | 2 | TRUE | None
856 | Alpha Dog Collar | Outdoor | GMLA2 | Complete | 2022-09-27 | 2022-09-29 | 0 |  | 0 |  | 0 | FALSE
972 | Marq (Gen 2) | Outdoor | GMLA3 | Complete | 2022-09-29 | 2022-09-29 | 2 |  | 0 |  | 2 | TRUE
1030 | vivomove Trend (previously "4") | Fitness | GMLA3 | Complete | 2022-10-14 | 2022-10-19 | 1 | None | 0 |  | 1 | FALSE | None
962 | GMS 20 Switch | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 0 |  | 2 | LED | 2 | TRUE | LED
961 | GMG 20 Gateway | Marine | GMLA2 | Complete | 2022-10-20 | 2022-10-21 | 0 |  | 2 | LED | 2 | TRUE | LED
1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA2 | Complete | 2022-10-24 | 2022-10-28 | 1 | ALS, AOD, ECG, Flashlight | 0 |  | 1 | TRUE | ALS, AOD, ECG, Flashlight
1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA2 | Complete | 2022-10-31 | 2022-10-31 | 1 | ALS, AOD, ECG, Flashlight | 0 |  | 1 | TRUE | ALS, AOD, ECG, Flashlight
1078 | Foretrex 801/901 | Outdoor | GMLA2 | Complete | 2022-11-03 | 2022-11-03 | 0 |  | 1 | None | 1 | TRUE | None
1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA2 | Complete | 2022-11-03 | 2022-11-09 | 2 | None | 0 |  | 2 | TRUE | None
1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA2 | Complete | 2022-11-07 | 2022-11-07 | 2 | ALS, AOD, ECG, Flashlight | 0 |  | 2 | TRUE | ALS, AOD, ECG, Flashlight
1044 | eTrex SE | Outdoor | GMLA3 | Complete | 2022-11-08 | 2022-11-08 | 2 | None | 0 |  | 2 | TRUE | None
1080 | Serv - 7" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 0 |  | 1 | None | 1 | TRUE | None
1081 | Serv - 10" | Marine | GMLA2 | Complete | 2022-11-10 | 2022-11-10 | 0 |  | 1 | None | 1 | TRUE | None
1101 | zumo XT2 | Automotive | GMLA2 | Complete | 2022-11-15 | 2022-11-15 | 0 |  | 2 | None | 2 | TRUE | None
1076 | fenix 7S Pro (2022) | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-21 | 1 | ECG, Flashlight | 0 |  | 1 | TRUE | ECG, Flashlight
1075 | fenix 7 Pro | Outdoor | GMLA2 | Complete | 2022-11-21 | 2022-11-22 | 1 | ECG, Flashlight | 0 |  | 1 | TRUE | ECG, Flashlight
833 | Panoptix PS70 - (SSMB) | Marine | GMLA2 | Complete | 2022-11-28 | 2022-11-28 | 1 | Appearance | 0 |  | 1 | TRUE | Appearance
1018 | ECHOMAP UHD2 (Touch) 6" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 0 |  | 2 | None | 2 | TRUE | None
1041 | ECHOMAP UHD2 (Touch) 9" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 0 |  | 2 | None | 2 | TRUE | None
1059 | ECHOMAP UHD2 (Touch) 7" | Marine | GMLA3 | Complete | 2022-11-28 | 2022-11-28 | 0 |  | 2 | None | 2 | TRUE | None
1077 | fenix 7X Pro | Outdoor | GMLA2 | Complete | 2022-12-01 | 2022-12-01 | 0 |  | 1 | ECG | 1 | TRUE | ECG
1131 | Drive 53 | Automotive | GMLA3 | Complete | 2022-12-01 | 2022-12-01 | 0 |  | 3 | None | 3 | TRUE | None
1069 | Edge 540 840 | Fitness | GMLA3 | Complete | 2022-12-08 | 2022-12-12 | 1 | None | 0 |  | 1 | FALSE | None
1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA2 | Complete | 2022-12-09 | 2022-12-16 | 0 | None | 0 |  | 0 | FALSE | None
1118 | Forerunner 265s | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-22 | 0 | None | 0 |  | 0 | FALSE | None
1107 | Forerunner 265 | Fitness | GMLA3 | Complete | 2022-12-13 | 2022-12-21 | 0 | None | 0 |  | 0 | FALSE | None
1103 | Forerunner 965 | Fitness | GMLA3 | Complete | 2022-12-15 | 2022-12-19 | 1 | None | 0 |  | 1 | FALSE | None
1112 | Instinct 2X Solar | Outdoor | GMLA2 | Complete | 2022-12-31 | 2023-01-03 | 0 |  | 1 | Flashlight | 1 | TRUE | Flashlight
1101 | zumo XT2 | Automotive | GMLA3 | Complete | 2023-01-10 | 2023-01-10 | 0 |  | 3 | None | 3 | TRUE | None
1090 | Venu 3S | Fitness | GMLA2 | Complete | 2023-01-31 | 2023-01-30 | 0 |  | 1 | Voice assistance, ECG,Skin temperature, ALS, AOD | 1 | TRUE | Voice assistance, ECG,Skin temperature, ALS, AOD
1102 | Varia eBike Radar Tail Light (eRTL615) | Fitness | GMLA3 | Complete | 2023-01-31 | 2023-02-01 | 2 | None | 0 |  | 2 | TRUE | None
1112 | Instinct 2X Solar | Outdoor | GMLA3 | Complete | 2023-02-01 | 2023-02-03 | 0 |  | 1 | Flashlight | 1 | FALSE | Flashlight
1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA2 | Complete | 2023-02-02 | 2023-02-03 | 0 |  | 0 |  | 0 | FALSE | nan
1089 | Venu 3 | Fitness | GMLA2 | Complete | 2023-02-06 | 2023-02-09 | 0 |  | 2 | Voice assistance, ECG,Skin temperature, ALS, AOD | 2 | TRUE | Voice assistance, ECG,Skin temperature, ALS, AOD
856 | Alpha Dog Collar | Outdoor | GMLA3 | Complete | 2023-02-10 | 2023-02-10 | 0 |  | 0 |  | 0 | FALSE
1078 | Foretrex 801/901 | Outdoor | GMLA3 | Complete | 2023-02-12 | 2023-02-17 | 0 |  | 0 |  | 0 | FALSE | nan
1088 | Approach S70 | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 0 |  | 2 |  | 2 | TRUE | None
1088 | Approach S70 | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 0 |  | 2 | ALS, AOD, WiFi, Workouts | 2 | TRUE | ALS, AOD, WiFi, Workouts
1036 | Approach S70s | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 0 |  | 2 |  | 2 | TRUE | None
1036 | Approach S70s | Outdoor | GMLA2 | Complete | 2023-02-15 | 2023-02-15 | 0 |  | 2 | ALS, AOD, WiFi, Workouts | 2 | TRUE | ALS, AOD, WiFi, Workouts
1094 | EPIX PRO (Gen 2) 51mm | Outdoor | GMLA3 | Complete | 2023-02-17 | 2023-02-23 | 2 | ALS, AOD, ECG, Flashlight | 0 |  | 2 | TRUE | ALS, AOD, ECG, Flashlight
1093 | EPIX PRO (Gen 2) 47mm | Outdoor | GMLA3 | Complete | 2023-02-22 | 2023-02-23 | 1 | ALS, AOD, ECG, Flashlight | 0 |  | 1 | FALSE | ALS, AOD, ECG, Flashlight
1092 | EPIX PRO (Gen 2) 42mm | Outdoor | GMLA3 | Complete | 2023-02-23 | 2023-02-24 | 1 | ALS, AOD, ECG, Flashlight | 0 |  | 1 | FALSE | ALS, AOD, ECG, Flashlight
937 | Drive 56 | Automotive | GMLA2 | Incomplete |  | 2021-03-30 | 0 |  | 0 |  | 0 | FALSE
937 | Drive 56 | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1005 | Next Generation Low-Cost Smartband | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1005 | Next Generation Low-Cost Smartband | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1012 | Approach R50 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1012 | Approach R50 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1036 | Approach S70s | Outdoor | GMLA3 | Incomplete |  | 2023-03-09 | 0 |  | 0 |  | 0 | FALSE | nan
1037 | GHC 50 | Marine | GMLA2 | Incomplete |  | 2021-11-10 | 0 |  | 0 |  | 0 | FALSE
1037 | GHC 50 | Marine | GMLA3 | Incomplete |  | 2022-02-04 | 0 |  | 0 |  | 0 | FALSE
1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 0 |  | 0 |  | 0 | FALSE
1042 | dezl OTR Series 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-24 | 0 |  | 0 |  | 0 | FALSE
1057 | Descent Mk3 Series - Large | Outdoor | GMLA3 | Incomplete |  | 2023-09-06 | 0 |  | 0 |  | 0 | FALSE | nan
1057 | Descent Mk3 Series - Large | Outdoor | GMLA2 | Incomplete |  | 2023-06-12 | 0 |  | 0 |  | 0 | FALSE | nan
1083 | Approach S42 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1083 | Approach S42 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1089 | Venu 3 | Fitness | GMLA3 | Incomplete |  | 2023-04-12 | 0 |  | 0 |  | 0 | FALSE | nan
1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1096 | DriveSmart65 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1116 | GPSMAP 66sr/66i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1122 | GPSMAP 9000_Black Box | Marine | GMLA2 | Incomplete |  | 2023-06-02 | 0 |  | 0 |  | 0 | FALSE
1122 | GPSMAP 9000_Black Box | Marine | GMLA3 | Incomplete |  | 2023-08-28 | 0 |  | 0 |  | 0 | FALSE
1123 | Lily 2 | Fitness | GMLA3 | Incomplete |  | 2023-10-04 | 0 |  | 0 |  | 0 | FALSE | nan
1123 | Lily 2 | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1127 | Connect 50 transition to Taiwan Manufacturing | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1132 | dezl headset (2nd Gen) | Automotive | GMLA2 | Incomplete |  | 2023-12-27 | 0 |  | 0 |  | 0 | FALSE | nan
1132 | dezl headset (2nd Gen) | Automotive | GMLA3 | Incomplete |  | 2024-03-25 | 0 |  | 0 |  | 0 | FALSE | nan
1134 | Force Kayak Propulsion System | Marine | GMLA2 | Incomplete |  | 2024-06-18 | 0 |  | 0 |  | 0 | FALSE | nan
1134 | Force Kayak Propulsion System | Marine | GMLA3 | Incomplete |  | 2024-10-08 | 0 |  | 0 |  | 0 | FALSE | nan
1065 | eTrex Solar | Outdoor | GMLA3 | Incomplete |  | 2023-07-19 | 0 |  | 0 |  | 0 | FALSE | nan
1065 | eTrex Solar | Outdoor | GMLA2 | Incomplete |  | 2023-05-11 | 0 |  | 0 |  | 0 | FALSE | nan
1147 | ECHOMAP Ultra 2 - 12" | Marine | GMLA2 | Incomplete |  | 2023-07-06 | 0 |  | 0 |  | 0 | FALSE | nan
1147 | ECHOMAP Ultra 2 - 12" | Marine | GMLA3 | Incomplete |  | 2023-09-28 | 0 |  | 0 |  | 0 | FALSE | nan
1149 | Fusion - RA800 | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1149 | Fusion - RA800 | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1151 | Flush Mount Stainless Steel Camera | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1151 | Flush Mount Stainless Steel Camera | Marine | GMLA3 | Incomplete |  | 2024-03-15 | 0 |  | 0 |  | 0 | FALSE | nan
1157 | Descent T2 Transceiver | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1157 | Descent T2 Transceiver | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA2 | Incomplete |  | 2023-11-08 | 0 |  | 0 |  | 0 | FALSE | nan
1158 | 2024 Value Dash Cams(Mini3) | Automotive | GMLA3 | Incomplete |  | 2024-01-31 | 0 |  | 0 |  | 0 | FALSE | nan
1173 | EPIX (Gen 3) 47mm | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1173 | EPIX (Gen 3) 47mm | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1174 | EPIX (Gen 3) 51mm | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1174 | EPIX (Gen 3) 51mm | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1175 | Instinct 3 Series | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1175 | Instinct 3 Series | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1176 | fenix 8 Series | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1176 | fenix 8 Series | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
780 | Dash Cam Tandem | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
780 | Dash Cam Tandem | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
874 | 2020 RV Series - Unit 7" | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
874 | 2020 RV Series - Unit 7" | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1016 | Xero L60i Laser Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-08-07 | 0 |  | 0 |  | 0 | FALSE | nan
1016 | Xero L60i Laser Navigator | Outdoor | GMLA2 | Incomplete |  | 2023-06-12 | 0 |  | 0 |  | 0 | FALSE | nan
1075 | fenix 7 Pro | Outdoor | GMLA3 | Incomplete |  | 2023-03-22 | 1 | ECG, Flashlight | 0 |  | 1 | FALSE | ECG, Flashlight
1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1117 | Alpha 200/200i Plus (i.MX7 Platform) | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1081 | Serv - 10" | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
775 | zumo X | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
775 | zumo X | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
779 | Approach Z82 | Outdoor | GMLA2 | Incomplete |  |  | 0 | Follow Z80 OOB checklist | 0 |  | 0 | FALSE | Follow Z80 OOB checklist
779 | Approach Z82 | Outdoor | GMLA3 | Incomplete |  |  | 0 | Follow Z80 OOB checklist | 0 |  | 0 | FALSE | Follow Z80 OOB checklist
814 | Varia Radar-Only (RVR315) | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
814 | Varia Radar-Only (RVR315) | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1051 | GPSMAP 9000 - 19" | Marine | GMLA3 | Incomplete |  | 2022-08-29 | 0 |  | 0 |  | 0 | FALSE | nan
1051 | GPSMAP 9000 - 19" | Marine | GMLA2 | Incomplete |  | 2023-03-16 | 0 |  | 0 |  | 0 | FALSE | nan
1053 | GPSMAP 9000 - 24" | Marine | GMLA3 | Incomplete |  | 2022-09-27 | 0 |  | 0 |  | 0 | FALSE | nan
1053 | GPSMAP 9000 - 24" | Marine | GMLA2 | Incomplete |  | 2023-03-16 | 0 |  | 0 |  | 0 | FALSE | nan
1054 | GPSMAP 9000 -27" | Marine | GMLA3 | Incomplete |  | 2022-08-29 | 0 |  | 0 |  | 0 | FALSE | nan
1054 | GPSMAP 9000 -27" | Marine | GMLA2 | Incomplete |  | 2023-03-16 | 0 |  | 0 |  | 0 | FALSE | nan
1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA2 | Incomplete |  | 2022-02-08 | 0 |  | 0 |  | 0 | FALSE
1095 | 2022 vivofit jr. 3 SKUs | Fitness | GMLA3 | Incomplete |  | 2022-03-15 | 0 |  | 0 |  | 0 | FALSE
1024 | Forerunner 255 Basic | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1024 | Forerunner 255 Basic | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1061 | RV/Camper 2022 - 8" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 0 |  | 0 |  | 0 | FALSE
1061 | RV/Camper 2022 - 8" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 0 |  | 0 |  | 0 | FALSE
1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA2 | Incomplete |  | 2023-07-11 | 0 |  | 0 |  | 0 | FALSE | nan
1178 | ECHOMAP Ultra 2 - 10" | Marine | GMLA3 | Incomplete |  | 2023-09-28 | 0 |  | 0 |  | 0 | FALSE | nan
806 | OEM GPS Sensor | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
806 | OEM GPS Sensor | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
882 | fenix 6 Solar (2020) | Outdoor | GMLA2 | Incomplete |  |  | 0 | 4/27 released | 0 |  | 0 | FALSE | 4/27 released
882 | fenix 6 Solar (2020) | Outdoor | GMLA3 | Incomplete |  |  | 0 | 4/27 released | 0 |  | 0 | FALSE | 4/27 released
947 | Tread 8" | Automotive | GMLA2 | Incomplete |  | 2021-08-04 | 0 |  | 0 |  | 0 | FALSE
947 | Tread 8" | Automotive | GMLA3 | Incomplete |  | 2021-10-06 | 0 |  | 0 |  | 0 | FALSE
989 | Xero C1 Chronograph | Outdoor | GMLA3 | Incomplete |  | 2023-05-11 | 0 |  | 0 |  | 0 | FALSE
1019 | Forerunner 255S | Fitness | GMLA2 | Incomplete |  | 2021-11-24 | 0 |  | 0 |  | 0 | FALSE
1019 | Forerunner 255S | Fitness | GMLA3 | Incomplete |  | 2022-03-10 | 0 |  | 0 |  | 0 | FALSE
1145 | Forerunner 165 and 165 Music | Fitness | GMLA2 | Incomplete |  | 2023-08-30 | 0 |  | 0 |  | 0 | FALSE | nan
1145 | Forerunner 165 and 165 Music | Fitness | GMLA3 | Incomplete |  | 2023-11-27 | 0 |  | 0 |  | 0 | FALSE | nan
793 | Occupancy Sensor | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
793 | Occupancy Sensor | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
837 | ECHOMAP 2020 UHD 6" | Marine | GMLA2 | Incomplete |  | 2019-09-12 | 0 |  | 0 |  | 0 | FALSE
837 | ECHOMAP 2020 UHD 6" | Marine | GMLA3 | Incomplete |  | 2019-11-08 | 0 |  | 0 |  | 0 | FALSE
838 | ECHOMAP 2020 UHD 7" | Marine | GMLA2 | Incomplete |  | 2019-11-07 | 0 |  | 0 |  | 0 | FALSE
838 | ECHOMAP 2020 UHD 7" | Marine | GMLA3 | Incomplete |  | 2019-12-30 | 0 |  | 0 |  | 0 | FALSE
1040 | D2 Echo (EPIX) | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1040 | D2 Echo (EPIX) | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1047 | Enduro 2023 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1047 | Enduro 2023 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1062 | RV/Camper 2022-10" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 0 |  | 0 |  | 0 | FALSE
1062 | RV/Camper 2022-10" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 0 |  | 0 |  | 0 | FALSE
1070 | Tacx Vortex 2M | Fitness | GMLA2 | Incomplete |  | 2021-12-06 | 0 |  | 0 |  | 0 | FALSE
1070 | Tacx Vortex 2M | Fitness | GMLA3 | Incomplete |  | 2022-02-17 | 0 |  | 0 |  | 0 | FALSE
1085 | quatix 7 | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 0 |  | 0 |  | 0 | FALSE
1085 | quatix 7 | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 0 |  | 0 |  | 0 | FALSE
1091 | GPSMAP 68 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1091 | GPSMAP 68 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1135 | Rally 110/210 Family | Fitness | GMLA2 | Incomplete |  | 2024-07-26 | 0 |  | 0 |  | 0 | FALSE | nan
1135 | Rally 110/210 Family | Fitness | GMLA3 | Incomplete |  | 2024-11-15 | 0 |  | 0 |  | 0 | FALSE | nan
1148 | Tacx FLUX 3M | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1148 | Tacx FLUX 3M | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1163 | Lily Athlete | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1163 | Lily Athlete | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
855 | RTL515 - Varia Radar Tail light | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
855 | RTL515 - Varia Radar Tail light | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
946 | Overlander 10" | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
946 | Overlander 10" | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1060 | RV/Camper 2022 - 7" | Automotive | GMLA2 | Incomplete |  | 2022-01-12 | 0 |  | 0 |  | 0 | FALSE
1060 | RV/Camper 2022 - 7" | Automotive | GMLA3 | Incomplete |  | 2022-03-23 | 0 |  | 0 |  | 0 | FALSE
1100 | Tacx NEO Bike Plus | Fitness | GMLA2 | Incomplete |  | 2022-03-03 | 0 |  | 0 |  | 0 | FALSE
1100 | Tacx NEO Bike Plus | Fitness | GMLA3 | Incomplete |  | 2022-05-06 | 0 |  | 0 |  | 0 | FALSE
1139 | Cellular Tracking Module | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1139 | Cellular Tracking Module | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1150 | Motorcycle Radar 2023 | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1150 | Motorcycle Radar 2023 | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
820 | FUSION - RA210 | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
820 | FUSION - RA210 | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
823 | FUSION - WB670 Hide Away Stereo | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
962 | GMS 20 Switch | Marine | GMLA3 | Incomplete |  | 2023-03-06 | 0 |  | 0 |  | 0 | FALSE | nan
1006 | Descent S1 Buoy | Outdoor | GMLA3 | Incomplete |  | 2023-03-22 | 0 |  | 0 |  | 0 | FALSE
1006 | Descent S1 Buoy | Outdoor | GMLA2 | Incomplete |  | 2023-04-12 | 0 |  | 0 |  | 0 | FALSE
1068 | GSD28 | Marine | GMLA3 | Incomplete |  | 2023-03-29 | 0 |  | 0 |  | 0 | FALSE | nan
1068 | GSD28 | Marine | GMLA2 | Incomplete |  | 2023-04-25 | 0 |  | 0 |  | 0 | FALSE | nan
1072 | Enduro 2022 | Outdoor | GMLA2 | Incomplete |  |  | 1 |  | 0 |  | 1 | TRUE
1072 | Enduro 2022 | Outdoor | GMLA3 | Incomplete |  |  | 1 |  | 0 |  | 1 | FALSE
1086 | quatix 7x Solar | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1086 | quatix 7x Solar | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1129 | GT15M Thru-Hull Flush | Marine | GMLA3 | Incomplete |  | 2023-05-24 | 0 |  | 0 |  | 0 | FALSE | nan
1129 | GT15M Thru-Hull Flush | Marine | GMLA2 | Incomplete |  | 2023-03-23 | 0 |  | 0 |  | 0 | FALSE | nan
1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1142 | Tread 10" OEM - Kawasaki CAN | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
794 | FUSION - ERX400 | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
794 | FUSION - ERX400 | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
944 | Pet Tracker | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
944 | Pet Tracker | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1105 | GMR xHD3 Magnetron Open Arrays | Marine | GMLA3 | Incomplete |  | 2023-03-23 | 0 | None | 0 |  | 0 | FALSE | None
1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA2 | Incomplete |  | 2024-04-10 | 0 |  | 0 |  | 0 | FALSE | nan
1119 | Xero B60i Laser Navigation Binoculars | Outdoor | GMLA3 | Incomplete |  | 2024-08-06 | 0 |  | 0 |  | 0 | FALSE | nan
1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1153 | Montana 7xx Parts Shortage Redesign | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
844 | dezl OTR/LGV 700 | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
844 | dezl OTR/LGV 700 | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
845 | dezl OTR/LGV 800 | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
845 | dezl OTR/LGV 800 | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA2 | Incomplete |  | 2021-11-29 | 0 |  | 0 |  | 0 | FALSE
1043 | FUSION - WB675 Hide Away Stereo | Marine | GMLA3 | Incomplete |  | 2022-02-23 | 0 |  | 0 |  | 0 | FALSE
1052 | GPSMAP 9000 - 22" | Marine | GMLA3 | Incomplete |  | 2022-09-27 | 0 |  | 0 |  | 0 | FALSE | nan
1052 | GPSMAP 9000 - 22" | Marine | GMLA2 | Incomplete |  | 2023-03-16 | 0 |  | 0 |  | 0 | FALSE | nan
1066 | LED Control Module | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1066 | LED Control Module | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1097 | DriveSmart66 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1099 | DriveSmart86 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
816 | GPSMAP 7x2 Plus | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
816 | GPSMAP 7x2 Plus | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
949 | Approach Z50 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
949 | Approach Z50 | Outdoor | GMLA2 | Incomplete |  | 2022-11-04 | 0 |  | 0 |  | 0 | FALSE
1087 | Tactix 7 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1087 | Tactix 7 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1088 | Approach S70 | Outdoor | GMLA3 | Incomplete |  | 2023-03-09 | 0 |  | 0 |  | 0 | FALSE | nan
1121 | Descent X1i | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1121 | Descent X1i | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1159 | 2024 Value Dash Cams(DC48) | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
802 | CL5 with monitor _YAMAHA | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
802 | CL5 with monitor _YAMAHA | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
803 | CL0/G W/O Display_YAMAHA | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
803 | CL0/G W/O Display_YAMAHA | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1076 | fenix 7S Pro (2022) | Outdoor | GMLA3 | Incomplete |  | 2023-03-13 | 1 | ECG, Flashlight | 0 |  | 1 | FALSE | ECG, Flashlight
1077 | fenix 7X Pro | Outdoor | GMLA3 | Incomplete |  | 2023-02-13 | 0 |  | 1 | ECG | 1 | FALSE | ECG
1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1098 | DriveSmart76 Synaptics Redesigns | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1120 | Catalyst KMR - Display | Automotive | GMLA3 | Incomplete |  | 2023-05-31 | 0 |  | 0 |  | 0 | FALSE | nan
1120 | Catalyst KMR - Display | Automotive | GMLA2 | Incomplete |  | 2023-03-22 | 0 |  | 0 |  | 0 | FALSE | nan
1137 | Edge 1050 | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1137 | Edge 1050 | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
831 | Fantom 254 / 256 | Marine | GMLA2 | Incomplete |  |  | 0 | Follow 5x/12x | 0 |  | 0 | FALSE | Follow 5x/12x
831 | Fantom 254 / 256 | Marine | GMLA3 | Incomplete |  |  | 0 | Follow 5x/12x | 0 |  | 0 | FALSE | Follow 5x/12x
833 | Panoptix PS70 - (SSMB) | Marine | GMLA3 | Incomplete |  | 2023-04-20 | 1 | Appearance | 0 |  | 1 | FALSE | Appearance
842 | Xero L40i Laser Range Navigator | Outdoor | GMLA2 | Incomplete |  | 2023-02-02 | 0 |  | 0 |  | 0 | FALSE | nan
842 | Xero L40i Laser Range Navigator | Outdoor | GMLA3 | Incomplete |  | 2023-05-17 | 0 |  | 0 |  | 0 | FALSE | nan
956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
956 | fenix 6 Solar 2020 Asia | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
978 | Force Kraken Trolling Motor | Marine | GMLA3 | Incomplete |  | 2023-06-13 | 0 |  | 0 |  | 0 | FALSE | nan
978 | Force Kraken Trolling Motor | Marine | GMLA2 | Incomplete |  | 2023-03-08 | 0 |  | 0 |  | 0 | FALSE | nan
1164 | inReach Messenger 2 | Outdoor | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1164 | inReach Messenger 2 | Outdoor | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
904 | MARQ Carbon | Outdoor | GMLA2 | Incomplete |  | 2023-04-12 | 0 |  | 0 |  | 0 | FALSE | nan
904 | MARQ Carbon | Outdoor | GMLA3 | Incomplete |  | 2023-07-05 | 0 |  | 0 |  | 0 | FALSE | nan
961 | GMG 20 Gateway | Marine | GMLA3 | Incomplete |  | 2023-03-06 | 0 |  | 0 |  | 0 | FALSE | nan
1020 | NEO 2T Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1020 | NEO 2T Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1080 | Serv - 7" | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1090 | Venu 3S | Fitness | GMLA3 | Incomplete |  | 2023-04-14 | 0 |  | 0 |  | 0 | FALSE | nan
1111 | Catalyst KMR - Hub | Automotive | GMLA3 | Incomplete |  | 2023-05-31 | 0 |  | 0 |  | 0 | FALSE | nan
1111 | Catalyst KMR - Hub | Automotive | GMLA2 | Incomplete |  | 2023-03-22 | 0 |  | 0 |  | 0 | FALSE | nan
1114 | Tire Temp Sensor | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1114 | Tire Temp Sensor | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1115 | Prop Drive Cost Down | Marine | GMLA2 | Incomplete |  | 2023-05-16 | 0 |  | 0 |  | 0 | FALSE | nan
1115 | Prop Drive Cost Down | Marine | GMLA3 | Incomplete |  | 2023-09-19 | 0 |  | 0 |  | 0 | FALSE | nan
1141 | GPSMAP 9500 | Marine | GMLA3 | Incomplete |  | 2023-09-06 | 0 |  | 0 |  | 0 | FALSE | nan
1141 | GPSMAP 9500 | Marine | GMLA2 | Incomplete |  | 2023-06-21 | 0 |  | 0 |  | 0 | FALSE | nan
787 | HRM-Pro | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
787 | HRM-Pro | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
839 | ECHOMAP 2020 UHD 9" | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
839 | ECHOMAP 2020 UHD 9" | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
975 | GST - Connect 70_ on hold | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
975 | GST - Connect 70_ on hold | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1058 | Descent Mk3 Series - Small | Outdoor | GMLA3 | Incomplete |  | 2023-08-22 | 0 |  | 0 |  | 0 | FALSE | nan
1058 | Descent Mk3 Series - Small | Outdoor | GMLA2 | Incomplete |  | 2023-05-26 | 0 |  | 0 |  | 0 | FALSE | nan
1064 | Flux S/2 Taiwan Production | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1064 | Flux S/2 Taiwan Production | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1082 | Tacx Motion Plates | Fitness | GMLA2 | Incomplete |  |  | 1 |  | 0 |  | 1 | TRUE
1082 | Tacx Motion Plates | Fitness | GMLA3 | Incomplete |  |  | 1 |  | 0 |  | 1 | FALSE
1104 | quatix 7 Sapphire | Marine | GMLA2 | Incomplete |  | 2021-10-21 | 0 |  | 0 |  | 0 | FALSE
1104 | quatix 7 Sapphire | Marine | GMLA3 | Incomplete |  | 2022-01-19 | 0 |  | 0 |  | 0 | FALSE
1106 | Venu Sq 3 | Fitness | GMLA2 | Incomplete |  | 2023-01-10 | 0 |  | 0 |  | 0 | FALSE
1106 | Venu Sq 3 | Fitness | GMLA3 | Incomplete |  | 2023-03-22 | 0 |  | 0 |  | 0 | FALSE
1109 | Tacx NEO 3M | Fitness | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1109 | Tacx NEO 3M | Fitness | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
777 | Approach S62 | Outdoor | GMLA2 | Incomplete |  |  | 0 | 12/25 | 0 |  | 0 | FALSE | 12/25
777 | Approach S62 | Outdoor | GMLA3 | Incomplete |  |  | 0 | 12/25 | 0 |  | 0 | FALSE | 12/25
795 | Overlander | Automotive | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
795 | Overlander | Automotive | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE
1001 | BC50 IR | Automotive | GMLA2 | Incomplete |  | 2021-11-11 | 0 |  | 0 |  | 0 | FALSE
1001 | BC50 IR | Automotive | GMLA3 | Incomplete |  | 2022-02-07 | 0 |  | 0 |  | 0 | FALSE
1110 | Catalyst KMR - Camera | Automotive | GMLA3 | Incomplete |  | 2023-05-31 | 0 |  | 0 |  | 0 | FALSE | nan
1110 | Catalyst KMR - Camera | Automotive | GMLA2 | Incomplete |  | 2023-03-22 | 0 |  | 0 |  | 0 | FALSE | nan
1126 | GMR xHD3 Domes (18/24xHD replacement) | Marine | GMLA3 | Incomplete |  | 2023-05-04 | 0 |  | 0 |  | 0 | FALSE | nan
1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA3 | Incomplete |  | 2023-07-13 | 0 |  | 0 |  | 0 | FALSE | nan
1130 | DC-2023 Premium Dash Cameras | Automotive | GMLA2 | Incomplete |  | 2023-05-01 | 0 |  | 0 |  | 0 | FALSE | nan
1146 | vivoactive 5 | Fitness | GMLA3 | Incomplete |  | 2023-06-27 | 0 |  | 0 |  | 0 | FALSE | nan
1146 | vivoactive 5 | Fitness | GMLA2 | Incomplete |  | 2023-03-20 | 0 |  | 0 |  | 0 | FALSE | nan
1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA2 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan
1156 | GPSMAP 16X3 Chartplotters | Marine | GMLA3 | Incomplete |  |  | 0 |  | 0 |  | 0 | FALSE | nan

## oob_mp
projectSizeId | Project_Name | Description | MP_file | MP_Comment | Status | UpdateUser | UpdateTime
1102 | Varia eBike Radar Tail Light (eRTL615) | OOB inspection SOP | key requirement for oob_ertl615 | None | 1 | chris.kuo@garmin.com | 2023-02-23 17:30
1102 | Varia eBike Radar Tail Light (eRTL615) | OOB inspection SOP | ertl615_010-02788-00 | None | 1 | chris.kuo@garmin.com | 2023-02-23 17:30
1069 | Edge 540 840 | OOB inspection SOP | edge 540&840_010-02694(02695)-xx_a | None | 1 | chris.kuo@garmin.com | 2023-02-13 09:59
966 | GST - MCU 2.0 | OOB inspection SOP |  |  | 2 | jasoncy.hsu@garmin.com | 2023-01-31 15:55
1105 | GMR xHD3 Magnetron Open Arrays | OOB inspection SOP |  | None | 0 | cooper.wang@garmin.com | 2023-01-31 09:14
1044 | eTrex SE | OOB inspection SOP | etrex se_oob checklist_0a | None | 1 | cooper.wang@garmin.com | 2023-01-31 09:09
1044 | eTrex SE | OOB inspection SOP | key requirement for oob_etrex se | None | 1 | cooper.wang@garmin.com | 2023-01-31 09:09
833 | Panoptix PS70 - (SSMB) | OOB inspection SOP | key requirement for oob_ps70 | Appearance | 1 | cooper.wang@garmin.com | 2023-01-31 08:49
1103 | Forerunner 965 | OOB inspection SOP | oob_forerunner 965_0a | None | 1 | cooper.wang@garmin.com | 2023-01-31 07:30
1118 | Forerunner 265 | OOB inspection SOP |  | None | 1 | cooper.wang@garmin.com | 2023-01-31 07:08
1107 | Forerunner 265 | OOB inspection SOP |  | None | 1 | cooper.wang@garmin.com | 2023-01-31 07:07
1097 | DriveSmart Synaptics Redesigns | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-12-30 12:54
1098 | DriveSmart Synaptics Redesigns | OOB inspection SOP |  |  | 1 | bowman.lai@garmin.com | 2022-12-27 17:21
1030 | vivomove Trend (previously "4") | OOB inspection SOP | oob_vivomove trend_0a | None | 1 | cooper.wang@garmin.com | 2022-12-25 17:28
1075 | fenix 7 Pro | OOB inspection SOP | ffp_fenix 7 epix pro series_pdp to oob | ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:37
1076 | fenix 7S Pro (2022) | OOB inspection SOP | ffp_fenix 7 epix pro series_pdp to oob | ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:37
1094 | EPIX PRO (Gen 2) 51mm | OOB inspection SOP | ffp_fenix 7 epix pro series_pdp to oob | ALS, AOD, ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:37
1094 | EPIX PRO (Gen 2) 51mm | OOB inspection SOP | pdp to oob_marq (gen2) | ALS, AOD, ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:37
1092 | EPIX PRO (Gen 2) 42mm | OOB inspection SOP | ffp_fenix 7 epix pro series_pdp to oob | ALS, AOD, ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:36
1093 | EPIX PRO (Gen 2) 47mm | OOB inspection SOP | ffp_fenix 7 epix pro series_pdp to oob | ALS, AOD, ECG, Flashlight | 1 | cooper.wang@garmin.com | 2022-12-19 08:36
983 | "Austin" | OOB inspection SOP |  |  | 1 | cooper.wang@garmin.com | 2022-11-28 20:05
990 | Dash Cam Live (LTE) | OOB inspection SOP | dash cam lte_010-02619-00 10 |  | 1 | chris.kuo@garmin.com | 2022-11-09 12:02
1034 | vivosmart 5 (Franklin) | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-10-31 14:07
868 | Venu 2S | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-10-31 14:05
900 | GPSMAP 64xr/sxr | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-10-27 09:23
867 | Descent T1 Transmitter | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2022-10-27 09:22
892 | fenix 6S Solar (2020) | OOB inspection SOP |  | Will provide the OOB SOP on 4/28. | 1 | kent.liu@garmin.com | 2022-10-27 09:21
835 | Descent Mk2 | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2022-10-27 09:21
853 | Instinct Solar | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2022-10-27 09:20
972 | Marq (Gen 2) | OOB inspection SOP | pdp to oob_marq (gen2) |  | 1 | cooper.wang@garmin.com | 2022-10-24 10:56
972 | Marq (Gen 2) | OOB inspection SOP | oob checklist_marq2 |  | 1 | cooper.wang@garmin.com | 2022-10-24 10:56
1021 | NEO 2T Taiwan Production | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-10-14 14:24
1060 | RV/Camper 2022 | OOB inspection SOP |  |  | 1 | bowman.lai@garmin.com | 2022-10-07 18:07
948 | Tread XL - Baja Race Edition | OOB inspection SOP | tread xl - overland edition_010-02509_x0_a |  | 1 | jasoncy.hsu@garmin.com | 2022-10-06 13:20
948 | Tread XL - Baja Race Edition | OOB inspection SOP | tread xl - baja race(chase) edition_a |  | 1 | jasoncy.hsu@garmin.com | 2022-10-06 13:20
862 | Bounce | OOB inspection SOP | oob-bounce_010-02448-xx_20210710 | Released | 1 | ernest.fu@garmin.com | 2022-10-05 11:43
909 | One Battery Bike Project | OOB inspection SOP |  | Done. | 1 | pattie.lan@garmin.com | 2022-09-20 09:05
1029 | Instinct Hybrid Analog/Digital | OOB inspection SOP | oob_instinct crossover_0a |  | 1 | aalto.lo@garmin.com | 2022-09-19 17:35
936 | Edge 1040 | OOB inspection SOP |  |  | 1 | leo.chiu@garmin.com | 2022-09-19 10:49
864 | Edge 1030 Plus | OOB inspection SOP |  | Richie跟QA確認 | 1 | leo.chiu@garmin.com | 2022-09-19 10:46
872 | Forerunner 745 | OOB inspection SOP |  |  | 1 | leo.chiu@garmin.com | 2022-09-19 10:42
903 | Venu 2 | OOB inspection SOP |  |  | 1 | leo.chiu@garmin.com | 2022-09-19 10:34
1008 | Asia ISO13485 Certification | OOB inspection SOP |  |  | 1 | leo.chiu@garmin.com | 2022-09-19 09:11
1002 | BC50 and BC50 IR | OOB inspection SOP |  |  | 1 | steve.chiang@garmin.com | 2022-09-06 07:19
1037 | GHC 50 | OOB inspection SOP |  |  | 1 | charlotte.chen@garmin.com | 2022-09-05 13:16
985 | IXWW22 | OOB inspection SOP |  |  | 1 | nick.yen@garmin.com | 2022-08-29 11:30
1061 | RV/Camper 2022 | OOB inspection SOP |  |  | 1 | iris.wu@garmin.com | 2022-08-25 10:27
953 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | OOB inspection SOP |  | OOB fixture update software, will come back 8/22, SOP will finish before 8/24 | 0 | simon.ko@garmin.com | 2022-08-22 11:06
1062 | RV/Camper 2022 | OOB inspection SOP |  |  | 1 | charlotte.chen@garmin.com | 2022-07-21 09:11
1023 | Venu Sq 2 | OOB inspection SOP |  |  | 1 | jackhl.chen@garmin.com | 2022-07-12 15:05
1035 | LWIN21 | OOB inspection SOP |  |  | 1 | jeff.lin@garmin.com | 2022-07-12 10:21
1067 | LXTW19 | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2022-07-12 10:15
876 | LFIN20 | OOB inspection SOP |  |  | 1 | jeff.lin@garmin.com | 2022-07-12 09:57
877 | LYAF20 | OOB inspection SOP |  |  | 1 | jeff.lin@garmin.com | 2022-07-12 09:50
1027 | inReach Messenger | OOB inspection SOP | inreach messenger_010-02672-xx_oob checklist_a |  | 1 | chris.kuo@garmin.com | 2022-07-04 10:47
815 | BMW MGU22 | OOB inspection SOP |  |  | 0 |  | 2022-06-13
894 | BMW MGU22 | OOB inspection SOP |  |  | 0 |  | 2022-06-13
1022 | HRM-Pro Plus | OOB inspection SOP |  | FRM 107 project | 2 | chris.kuo@garmin.com | 2022-06-10 10:34
1045 | Edge Explore 2 | OOB inspection SOP | edge explore 2_010-02703-xx_a |  | 1 | chris.kuo@garmin.com | 2022-06-08 09:00
1033 | dezlCam OTR710 & RV Cam 795 | OOB inspection SOP | dezl cam otr_010-02727-xx_checklist_ a | As the attachment. | 1 | wendy.ni@garmin.com | 2022-06-07 12:09
986 | Tacx NEO Bike Plus | OOB inspection SOP | handle bar and shifter nbp_011-06116-00_0a |  | 1 | chris.kuo@garmin.com | 2022-05-30 08:25
955 | Varia Radar Camera (RCT715) | OOB inspection SOP | varia rct715_010-02474-xx & 010-02475-xx & 010-02476-xx & 010-02477-xx & 010-02478-xx _oob checklist |  | 1 | chris.kuo@garmin.com | 2022-05-25 09:40
1073 | dezl OTR Series 2022 | OOB inspection SOP | dezl 610 710 810 1010_checklist | It has been&nbsp;released to FQC. | 1 | wendy.ni@garmin.com | 2022-05-24 13:06
1017 | LiveScope XR (LVS62) | OOB inspection SOP | livescope plus (lvs62)_010-02719-xx_0a |  | 1 | jasoncy.hsu@garmin.com | 2022-05-16 09:45
969 | Delta SE | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2022-05-11 09:39
785 | DGCN20 | OOB inspection SOP |  | PQE has finished OOB inspection SOP | 1 | zack.lin@garmin.com | 2022-05-04 11:31
1032 | Forerunner 255 and 255 Music | OOB inspection SOP | forerunner 255 oob checklist_010-02641-xx_a | Released | 1 | ernest.fu@garmin.com | 2022-05-02 13:14
996 | Forerunner 255 and 255 Music | OOB inspection SOP | forerunner 255 small oob checklist_010-02641-xx_a | Released | 1 | ernest.fu@garmin.com | 2022-05-02 13:07
1055 | dezl OTR Series 2022 | OOB inspection SOP | dezl 610 710 810 1010_checklist |  | 1 | wendy.ni@garmin.com | 2022-04-26 15:03
1056 | dezl OTR Series 2022 | OOB inspection SOP | dezl 610 710 810 1010_checklist |  | 1 | wendy.ni@garmin.com | 2022-04-26 15:00
1074 | dezl OTR Series 2022 | OOB inspection SOP | dezl 610 710 810 1010_checklist |  | 1 | wendy.ni@garmin.com | 2022-04-25 17:52
945 | Tread - Overland Edition | OOB inspection SOP |  |  | 1 | lori.tsai@garmin.com | 2022-04-15 10:47
967 | Forerunner 955 and 955 Solar | OOB inspection SOP | fr955_oob checklist_010-02638-xx_a |  | 1 | ernest.fu@garmin.com | 2022-04-11 15:07
1072 | Enduro 2022 | OOB inspection SOP | enduro 2022_oob checklist |  | 1 | cooper.wang@garmin.com | 2022-04-08 13:56
971 | Instinct 2S | OOB inspection SOP |  |  | 1 | steve.lee@garmin.com | 2022-04-06 10:19
1082 | Tacx Motion Plates | OOB inspection SOP | oob motion plates neo2t |  | 1 | claudia.vanrhoon@garmin.com | 2022-03-30 19:49
988 | ECHOMAP UHD2 (Keyed) | OOB inspection SOP | echomap uhd2 |  | 1 | jasoncy.hsu@garmin.com | 2022-03-24 09:19
987 | ECHOMAP UHD2 (Keyed) | OOB inspection SOP | echomap uhd2 |  | 1 | jasoncy.hsu@garmin.com | 2022-03-24 09:17
1009 | Tread Audio System | OOB inspection SOP | tread audio package_checklist _010-02646-xx |  | 1 | wendy.ni@garmin.com | 2022-03-23 11:39
881 | fenix 7 | OOB inspection SOP | fenix 7 & epix _ skus | Updated | 1 | cooper.wang@garmin.com | 2022-03-16 14:32
881 | fenix 7 | OOB inspection SOP | fenix 7_appearance spec | Updated | 1 | cooper.wang@garmin.com | 2022-03-16 14:32
881 | fenix 7 | OOB inspection SOP | fenix 7_oob checklist | Updated | 1 | cooper.wang@garmin.com | 2022-03-16 14:32
941 | Forerunner 55 | OOB inspection SOP |  |  | 1 | alexty.chang@garmin.com | 2022-03-14 14:03
895 | BMW MGU22 | OOB inspection SOP |  | No need for RSE | 2 | sandy.lee@garmin.com | 2022-03-03 17:57
1038 | LiveScope Plus (LVS34) | OOB inspection SOP | 010-02706-xx_0a |  | 1 | jasoncy.hsu@garmin.com | 2022-03-02 15:40
981 | Xero A1i PRO Bow Sight | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2022-03-01 15:15
1015 | Dezl Headset | OOB inspection SOP | dezl headset_010-02581-xx_oob checklist | OOB checklist is as the attachment. | 1 | wendy.ni@garmin.com | 2022-02-25 11:25
1064 | Flux S/2 Taiwan Production | OOB inspection SOP |  |  | 2 | lori.tsai@garmin.com | 2022-02-22 20:38
782 | LYWW20 | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2022-01-24 14:16
893 | PGWW20 | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2022-01-19 10:26
968 | Descent G1 | OOB inspection SOP | oob checklist_descent g1 |  | 1 | cooper.wang@garmin.com | 2022-01-13 09:07
1026 | dezl watch | OOB inspection SOP |  |  | 1 | wendy.ni@garmin.com | 2021-11-29 13:35
821 | FUSION - Apollo Amplifiers | OOB inspection SOP |  |  | 1 | allen.chu@garmin.com | 2021-11-19 14:21
922 | inReach Mini 2 | OOB inspection SOP | 010-02602-xx_oob checklist_a | Chris by 11/19 | 1 | chris.kuo@garmin.com | 2021-11-17 17:32
979 | vivomove Sport (previously "Lite") | OOB inspection SOP | oob_vvm sport _20210914 |  | 1 | ernest.fu@garmin.com | 2021-11-12 00:34
979 | vivomove Sport (previously "Lite") | OOB inspection SOP | oob_vvm sport _20210914 |  | 1 | ernest.fu@garmin.com | 2021-11-12 00:34
921 | Surround View Camera System | OOB inspection SOP | surround view camera_oob checklist _010-02482-00_a |  | 1 | jasoncy.hsu@garmin.com | 2021-11-04 15:46
1007 | Alpha 200 | OOB inspection SOP |  |  | 1 | chris.kuo@garmin.com | 2021-10-01 09:02
1014 | GMR Fantom 18x/24x | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-09-27 09:25
959 | fenix 7S | OOB inspection SOP |  |  | 1 | cooper.wang@garmin.com | 2021-09-24 14:47
960 | fenix 7X | OOB inspection SOP |  |  | 1 | cooper.wang@garmin.com | 2021-09-24 14:46
1004 | GPSMAP 79 Series | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-09-24 11:54
870 | Forerunner 945 LTE | OOB inspection SOP |  |  | 1 | alexty.chang@garmin.com | 2021-09-10 08:41
1011 | WDU Cost down (EmpirBus Low cost web server solution) | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-08-25 14:57
905 | Instinct 2 | OOB inspection SOP |  |  | 1 | cooper.wang@garmin.com | 2021-08-23 17:41
940 | DriveSmart 86 | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-08-20 14:07
929 | FUSION - RA60 | OOB inspection SOP |  |  | 1 | bowman.lai@garmin.com | 2021-08-19 11:03
913 | Quick Power Adapter | OOB inspection SOP |  |  | 1 | daniel.lee@garmin.com | 2021-08-12 10:09
954 | Dash Cam Mini 2 | OOB inspection SOP |  |  | 1 | lori.tsai@garmin.com | 2021-08-12 08:42
934 | LYIN20 | OOB inspection SOP |  |  | 1 | zack.lin@garmin.com | 2021-07-28 19:29
784 | APGC20 | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2021-07-12 11:19
938 | DriveSmart 66 | OOB inspection SOP |  |  | 1 | wendy.ni@garmin.com | 2021-07-08 17:06
939 | DriveSmart 76 | OOB inspection SOP |  | done | 1 | daniel.lee@garmin.com | 2021-07-07 15:23
824 | FUSION - Apollo Amplifiers | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-07-01 09:52
879 | Venu 2 Plus | OOB inspection SOP |  |  | 0 |  | 2021-06-28
783 | Honda MKSA | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2021-06-16 11:10
807 | Daimler_VIS20_2020 | OOB inspection SOP |  |  | 1 | colby.ren@garmin.com | 2021-06-16 11:05
976 | FUSION - AP-DA214 (Zone Amplifier) | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-06-07 10:09
970 | Approach G12 | OOB inspection SOP |  |  | 1 | sherry.shih@garmin.com | 2021-06-01 11:43
897 | GPSMAP 66sr | OOB inspection SOP |  | Provide to FQC before 6/5 | 1 | sherry.shih@garmin.com | 2021-05-31 10:40
863 | Edge 130 Plus | OOB inspection SOP |  |  | 1 | jasonyl.wang@garmin.com | 2021-05-24 10:28
858 | Approach R10 | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2021-05-07 14:00
890 | GNA 10 {Jog Lever Adapter} | OOB inspection SOP |  |  | 1 | jimmy.kuo@garmin.com | 2021-04-28 11:41
827 | GPS 24xd (Dual frequency, 19x replacement) | OOB inspection SOP |  |  | 1 | albertth.chen@garmin.com | 2021-04-02 09:38
834 | MSC-10 [Marine Satellite Compass] | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-03-22 13:36
854 | Montana 7xx | OOB inspection SOP |  |  | 1 | sherry.shih@garmin.com | 2021-03-15 18:14
963 | Malibu Display | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-03-15 15:27
991 | FR245 and FR245M redesign (ASIA SKUs) | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2021-03-11 11:12
843 | Venu Sq (Entry-level smartwatch) | OOB inspection SOP |  |  | 1 | davidjw.yang@garmin.com | 2021-02-05 16:43
917 | Dash Cam 47 / 57 / 67W | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-02-01 09:09
769 | Striker Cast | OOB inspection SOP |  |  | 1 | james.tsao@garmin.com | 2021-01-27 18:11
912 | Approach S12 | OOB inspection SOP |  | OOB check list is released | 1 | ernest.fu@garmin.com | 2021-01-26 23:02
770 | Rally XC200/100 | OOB inspection SOP |  |  | 2 | audon.peng@garmin.com | 2021-01-18 16:44
846 | Catalyst | OOB inspection SOP |  |  | 1 | albertth.chen@garmin.com | 2021-01-18 15:56
847 | 2020 RV Series - Dock, 7\", 8\", 10\" Displays | OOB inspection SOP |  |  | 1 | steve.chiang@garmin.com | 2021-01-08 14:15
866 | Descent Mk2s | OOB inspection SOP |  | K:\PQE\PQE Support Team\OOB Checklist\mk2s | 1 | abner.tsai@garmin.com | 2021-01-06 11:14
840 | Tread | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2021-01-05 14:05
891 | PGWW20 | OOB inspection SOP |  |  | 0 |  | 2021-01-04
920 | Garmin PowerSwitch | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2020-12-30 10:35
898 | Enduro 2020 | OOB inspection SOP |  | Will review the Fenix 6 OOB and transfer to Plant Q. | 1 | abner.tsai@garmin.com | 2020-12-29 11:06
982 | Striker Vivid (Updated Scanning Sonar Color Pallets) | OOB inspection SOP |  |  | 2 | bowman.lai@garmin.com | 2020-12-22 15:09
849 | Alpha 10 | OOB inspection SOP |  | due date:12/18 | 1 | chris.kuo@garmin.com | 2020-12-09 11:15
814 | Varia Radar-Only (RVR315) | OOB inspection SOP |  |  | 1 | sherry.shih@garmin.com | 2020-12-03 14:39
855 | RTL515 - Varia Radar Tail light | OOB inspection SOP |  |  | 1 | sherry.shih@garmin.com | 2020-12-03 12:00
787 | HRM-Pro | OOB inspection SOP |  |  | 1 | johnny.liu@garmin.com | 2020-11-27 15:43
860 | Lumen | OOB inspection SOP |  |  | 1 | kris.lo@garmin.com | 2020-11-13 10:52
771 | Rally RS200/100 | OOB inspection SOP |  | Follow Vactor 3. | 1 | audon.peng@garmin.com | 2020-11-09 10:54
886 | GPSmap 7x3/9x3/12x3 | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2020-10-23 13:38
885 | GPSmap 7x3/9x3/12x3 | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2020-10-23 13:32
884 | GPSmap 7x3/9x3/12x3 | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2020-10-23 13:31
794 | FUSION - ERX400 | OOB inspection SOP |  |  | 2 | bowman.lai@garmin.com | 2020-10-23 10:58
828 | aera 760 | OOB inspection SOP |  |  | 2 | albertth.chen@garmin.com | 2020-10-20 11:07
896 | vivofit jr. 3 | OOB inspection SOP |  |  | 1 | ernest.fu@garmin.com | 2020-10-16 11:35
919 | GT36/GT56 UHD Transducers | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2020-10-14 10:42
774 | Xero X1i Crossbow Scope | OOB inspection SOP |  |  | 1 | chris.kuo@garmin.com | 2020-09-18 14:03
871 | Forerunner 955 | OOB inspection SOP |  |  | 0 |  | 2020-09-14
851 | Forerunner 955 | OOB inspection SOP |  |  | 0 |  | 2020-09-14
775 | zumo X | OOB inspection SOP |  |  | 1 | derek.cheng@garmin.com | 2020-09-07 10:00
781 | LSTW20 | OOB inspection SOP |  |  | 1 | davidsd.lin@garmin.com | 2020-08-25 14:54
789 | BMW MGU MY20 | OOB inspection SOP |  |  | 0 |  | 2020-08-25
874 | 2020 RV Series - Dock, 7", 8", 10" Displays | OOB inspection SOP |  |  | 1 | ben.kao@garmin.com | 2020-08-18 15:24
899 | DAB+ Box | OOB inspection SOP |  |  | 0 |  | 2020-08-10
804 | OEM CL5 and CL0 Engine Display | OOB inspection SOP |  | Ready. | 1 | audon.peng@garmin.com | 2020-08-03 15:57
861 | Descent Mk2s | OOB inspection SOP |  |  | 0 |  | 2020-07-27
831 | Fantom 254 / 256 | OOB inspection SOP |  | Follow 5x/12x | 2 | chris.kuo@garmin.com | 2020-07-14 15:19
826 | Xero G2i SatCom Scouting Camera | OOB inspection SOP |  |  | 0 |  | 2020-06-29
856 | Alpha Dog Collar | OOB inspection SOP |  |  | 0 |  | 2020-06-29
931 | GST - WSU - Transition to Twn Mfg | OOB inspection SOP |  |  | 2 | jasoncy.hsu@garmin.com | 2020-06-17 11:42
956 | fenix 6 Solar 2020 Asia | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2020-06-03 09:27
927 |  | OOB inspection SOP |  |  | 0 |  | 2020-06-01
816 | GPSMAP 7x2/9x2/12x2 Plus | OOB inspection SOP |  |  | 2 | kent.liu@garmin.com | 2020-05-22 12:06
832 | ASIA: 15\" Portrait Radar/Sonar display | OOB inspection SOP |  |  | 1 | ken.kuo@garmin.com | 2020-05-06 15:55
882 | fenix 6 Solar (2020) | OOB inspection SOP |  | 4/27 released | 1 | robben.liu@garmin.com | 2020-04-28 08:13
823 | FUSION - WB670 Hide Away Stereo | OOB inspection SOP |  |  | 1 | chris.kuo@garmin.com | 2020-04-27 17:47
848 | Alpha 200i | OOB inspection SOP |  |  | 1 | chris.kuo@garmin.com | 2020-04-27 09:31
802 | OEM CL5 and CL0 Engine Display | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-04-22 13:41
767 | OnDeck (Telematics) | OOB inspection SOP |  |  | 1 | jasoncy.hsu@garmin.com | 2020-04-17 09:34
817 | GPSMAP 7x2/9x2/12x2 Plus | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2020-04-16 14:08
839 | ECHOMAP 2020 UHD | OOB inspection SOP |  |  | 1 | kent.liu@garmin.com | 2020-04-16 13:58
845 | dezl OTR/LGV 800 | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-04-13 16:01
830 | dezl OTR/LGV 1000 | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-04-13 15:58
838 | ECHOMAP 2020 UHD | OOB inspection SOP |  |  | 1 | jimmy.kuo@garmin.com | 2020-03-31 13:19
780 | Dash Cam Tandem | OOB inspection SOP |  |  | 1 | lori.tsai@garmin.com | 2020-03-30 15:08
818 | GPSMAP 7x2/9x2/12x2 Plus | OOB inspection SOP |  |  | 1 | derek.cheng@garmin.com | 2020-03-27 13:14
803 | OEM CL5 and CL0 Engine Display | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-03-26 16:45
779 | Approach Z82 | OOB inspection SOP |  | Follow Z80 OOB checklist | 1 | chris.kuo@garmin.com | 2020-03-25 08:56
844 | dezl OTR/LGV 700 | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-03-23 15:35
808 | 2020 Dezl | OOB inspection SOP |  |  | 0 |  | 2020-03-02
809 | 2020 Dezl | OOB inspection SOP |  |  | 0 |  | 2020-03-02
810 | 2020 Dezl | OOB inspection SOP |  |  | 0 |  | 2020-03-02
820 | FUSION - RA210 | OOB inspection SOP |  |  | 1 | chris.kuo@garmin.com | 2020-02-15 09:12
865 | Descent Mk2 | OOB inspection SOP |  |  | 0 |  | 2020-01-27
889 | quatix 6 | OOB inspection SOP |  |  | 0 |  | 2020-01-27
875 | AAIN20 | OOB inspection SOP |  |  | 1 | jeff.lin@garmin.com | 2020-01-06 18:50
902 | inReach Mini Dive Case | OOB inspection SOP |  |  | 0 |  | 2020-01-06
829 | 2020 RV Series - Dock, 7\", 8\" 10\" Displays | OOB inspection SOP |  |  | 0 |  | 2020-01-06
806 | OEM GPS Sensor | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2020-01-02 18:36
777 | Approach S62 | OOB inspection SOP |  | 12/25 | 1 | robben.liu@garmin.com | 2019-12-23 15:57
805 | OEM Heading Sensor | OOB inspection SOP |  |  | 1 | audon.peng@garmin.com | 2019-11-20 17:05
837 | ECHOMAP 2020 UHD | OOB inspection SOP |  |  | 1 | sandy.lee@garmin.com | 2019-11-14 08:53
852 | Varia eBike Radar (eRVR315, eRDU) | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2019-10-30 17:21
801 | GMI 50 | OOB inspection SOP |  |  | 0 |  | 2019-10-28
773 | Impact Plate Radar | OOB inspection SOP |  |  | 0 |  | 2019-08-19
811 | Garmin Swim 2 | OOB inspection SOP |  |  | 0 |  | 2019-08-12
790 | vivomove 3 (Classic & Premium) | OOB inspection SOP |  |  | 0 |  | 2019-08-12
873 | GPSMAP 86x | OOB inspection SOP |  |  | 0 |  | 2019-08-05
791 | vivomove 3 (Premium) | OOB inspection SOP |  |  | 0 |  | 2019-07-29
792 | vivomove 3 (Sport) | OOB inspection SOP |  |  | 0 |  | 2019-07-29
768 | USB SD-Card Reader | OOB inspection SOP |  |  | 0 |  | 2019-07-15
793 | Occupancy Sensor | OOB inspection SOP |  |  | 1 | robben.liu@garmin.com | 2019-07-02 12:05
798 | Venu | OOB inspection SOP |  |  | 0 |  | 2019-06-24
766 | GAD 13 | OOB inspection SOP |  |  | 0 |  | 2019-06-24
908 | Xero S1 Trapshooting Trainer | OOB inspection SOP |  |  | 0 |  | 2019-06-03
907 | Xero S1 Trapshooting Trainer | OOB inspection SOP |  |  | 0 |  | 2019-06-03
887 | Xero S1 Trapshooting Trainer | OOB inspection SOP |  |  | 0 |  | 2019-06-03
786 | GI 275 | OOB inspection SOP |  |  | 0 | kent.liu@garmin.com | 2019-05-29 15:24
836 | PRO 550 Plus EMEA | OOB inspection SOP |  |  | 0 |  | 2019-05-20
812 | Xero S1 Trapshooting Trainer | OOB inspection SOP |  |  | 0 |  | 2019-05-13
795 | Overlander | OOB inspection SOP |  |  | 0 |  | 2019-04-30
796 | vivoactive 4 Large MIP | OOB inspection SOP |  |  | 0 |  | 2019-04-15
797 | vivoactive 4S | OOB inspection SOP |  |  | 0 |  | 2019-04-15
800 | eTrex 22x/32x | OOB inspection SOP |  |  | 0 |  | 2019-04-08
799 |  | OOB inspection SOP |  |  | 0 |  | 2019-04-08
935 | GHP Reactor Kicker | OOB inspection SOP |  |  | 0 |  | 2019-03-18
880 | Alpha 100 | OOB inspection SOP |  |  | 0 |  | 2012-07-23
932 | GST - MCU 2.0 | OOB inspection SOP |  |  | 0 |  | 1899-12-31
930 | Instinct 2 | OOB inspection SOP |  |  | 0 |  | 1899-12-31
1042 | dezl OTR Series 2022 | OOB inspection SOP |  |  | 0
914 | Rally RK200/100 | OOB inspection SOP |  |  | 0
1043 | FUSION - WB675 Hide Away Stereo | OOB inspection SOP |  |  | 0
1028 | BMW MGU22 | OOB inspection SOP |  |  | 0
1040 | D2 Echo (EPIX) | OOB inspection SOP |  |  | 0
944 | Pet Tracker | OOB inspection SOP |  |  | 0
937 | Drive 56 | OOB inspection SOP |  |  | 0
943 | Product - GSA 28 -2X | OOB inspection SOP |  |  | 0
1070 | Tacx Vortex 2M | OOB inspection SOP |  |  | 0
1100 | Tacx NEO Bike Plus | OOB inspection SOP |  |  | 0
1079 | BMW MGU22 | OOB inspection SOP |  |  | 0
1087 | Tactix 7 | OOB inspection SOP |  |  | 0
1117 | Alpha 200/200i Plus (i.MX7 Platform) | OOB inspection SOP |  |  | 0
1122 | GPSMAP 9000 | OOB inspection SOP |  |  | 0
1124 | Next gen GMR magnetron domes (18/24xHD replacement) | OOB inspection SOP |  |  | 0
1086 | quatix 7x Solar | OOB inspection SOP |  |  | 0
1108 | LIIN22 | OOB inspection SOP |  |  | 0
1095 | 2022 vivofit jr. 3 SKUs | OOB inspection SOP |  |  | 0
1099 | DriveSmart Synaptics Redesigns | OOB inspection SOP |  |  | 0
1106 | Venu Sq 3 | OOB inspection SOP |  |  | 0
1104 | quatix 7 Sapphire | OOB inspection SOP |  |  | 0
975 | GST - Connect 70 | OOB inspection SOP |  |  | 0
1083 | Approach S42 | OOB inspection SOP |  |  | 0
998 | Battery Charger | OOB inspection SOP |  |  | 0
1001 | BC50 and BC50 IR | OOB inspection SOP |  |  | 0
973 | GNA-10 [Jog Lever Adapter] | OOB inspection SOP |  |  | 0
1005 | vivosmart 5 (Franklin) | OOB inspection SOP |  |  | 0
1024 | Forerunner 255 Small | OOB inspection SOP |  |  | 0
1085 | quatix 7 | OOB inspection SOP |  |  | 0
950 | Mercury | OOB inspection SOP |  |  | 0
1096 | DriveSmart Synaptics Redesigns | OOB inspection SOP |  |  | 0
825 | FUSION - Tune Free Amplifiers | OOB inspection SOP |  |  | 0
1019 | Forerunner 255 and 255 Music | OOB inspection SOP |  |  | 0
947 | Tread - SXS Edition | OOB inspection SOP |  |  | 0
946 | Tread XL - Overland Edition | OOB inspection SOP |  |  | 0
949 | Approach Z50 | OOB inspection SOP |  |  | 0
994 | GPSMAP 65/65s | OOB inspection SOP |  |  | 0
965 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | OOB inspection SOP |  |  | 0
1951 |  | OOB inspection SOP |  |  | 0
1003 | Marine Sensor Gateway | OOB inspection SOP |  |  | 0
964 | TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | OOB inspection SOP |  |  | 0
1046 | GHP Reactor Kicker | OOB inspection SOP |  |  | 0
974 | 2021 Ice Fishing | OOB inspection SOP |  |  | 0
1063 | Tread 8" OEM w/ CAN | OOB inspection SOP |  |  | 0
989 | Xero C1 Chronograph | OOB inspection SOP |  |  | 0
992 | GPSMAP 65/65s | OOB inspection SOP |  |  | 0
942 | TD 50 (5" OEM Display) | OOB inspection SOP |  |  | 0
1006 | Descent S1 Buoy | OOB inspection SOP |  |  | 0

## oob_pid
projectSizeId | Phase | PID_file | PID_Comment | Item_Name | Status | UpdateUser | UpdateTime
961 | GMLA2 | key requirement for oob_bluenet | LED | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:27
961 | GMLA2 | re bluenet key requirement for oob | LED | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:27
962 | GMLA2 | key requirement for oob_bluenet | LED | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:27
962 | GMLA2 | re bluenet key requirement for oob | LED | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:27
1018 | GMLA3 | echomap uhd2 (touch) - 6吋7吋9吋oob checklist | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:06
1018 | GMLA3 | echomap uhd2 (touch) - 6 & 7 & 9_key requirement from pdp | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:06
1036 | GMLA2 | ffp_approach s70 series_pdp to oob |  | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-11-23 21:07
1036 | GMLA2 | ffp_approach s70 series_pdp to oob | ALS, AOD, WiFi, Workouts | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-02-03 08:57
1041 | GMLA3 | echomap uhd2 (touch) - 6吋7吋9吋oob checklist | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:08
1041 | GMLA3 | echomap uhd2 (touch) - 6 & 7 & 9_key requirement from pdp | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:08
1059 | GMLA3 | echomap uhd2 (touch) - 6吋7吋9吋oob checklist | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:07
1059 | GMLA3 | echomap uhd2 (touch) - 6 & 7 & 9_key requirement from pdp | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:07
1077 | GMLA2 | ffp_fenix 7 epix pro series_pdp to oob | ECG | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-19 08:38
1077 | GMLA3 | pr_fenix 7 epix pro series_pdp to oob | ECG | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-19 08:38
1078 | GMLA2 | ffp_foretrex801901_pdp to oob | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-31 07:23
1080 | GMLA2 | serv (7 & 10)_key requirement from pdp | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:13
1081 | GMLA2 | serv (7 & 10)_key requirement from pdp | None | OOB planning readiness | Closed | jasoncy.hsu@garmin.com | 2022-12-21 17:13
1088 | GMLA2 | ffp_approach s70 series_pdp to oob |  | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-11-23 21:06
1088 | GMLA2 | ffp_approach s70 series_pdp to oob | ALS, AOD, WiFi, Workouts | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-02-03 12:35
1089 | GMLA2 | ffp_venu 3 series_pdp to oob | Voice assistance, ECG,Skin temperature, ALS, AOD | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-31 20:35
1089 | GMLA2 | ffp_venu 3 series_pdp to oob | Voice assistance, ECG,Skin temperature, ALS, AOD | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-31 20:36
1090 | GMLA2 | ffp_venu 3 series_pdp to oob | Voice assistance, ECG,Skin temperature, ALS, AOD | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-31 20:36
1101 | GMLA2 | key requirement for oob_zumo xt2 | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-20 08:25
1101 | GMLA2 | re zumo xt2 oob checklist discussion | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-20 08:25
1101 | GMLA3 | key requirement for oob_zumo xt2 | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-24 08:43
1101 | GMLA3 | re zumo xt2 oob checklist discussion | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-24 08:43
1101 | GMLA3 | zumo xt2_010-02781-xx_oob checklist | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2023-01-24 08:43
1112 | GMLA2 | pdp to oob_instinct 2x solar | Flashlight | OOB planning readiness | Closed | aalto.lo@garmin.com | 2023-01-31 08:20
1112 | GMLA3 | pdp to oob_instinct 2x solar | Flashlight | OOB planning readiness | Closed | aalto.lo@garmin.com | 2023-01-31 08:21
1131 | GMLA3 | key requirement for oob_drive 53 | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:01
1131 | GMLA3 | re drive 53 oob checklist discussion | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:01
1131 | GMLA3 | drvie53_010-02858-xx_oob_checklist_0a | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:01
1131 | GMLA2 | key requirement for oob_drive 53 | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:01
1131 | GMLA2 | re drive 53 oob checklist discussion | None | OOB planning readiness | Closed | cooper.wang@garmin.com | 2022-12-25 17:01