## Sheet1
ItemNameType | ProcessType | Item | ItemName | CountCountESN | Retest | CountESN | CooperComment | Comment(red=shareinCFTmeeting)
18825 | FR165_RT3 | 42 | ALS Luminance (WLED ON) | 48/539 | 8.91 | 539 | 下IOP。天馬跟Truly會回傳不同值讓測試程式辨識 | [FIXED] TWEE: Already asked TW SE to split test item based on display model for FFP
18823 | FR165_AutoRT1 | 38 | GPS_L1 by ref_1% non_recheck(music) | 30/542 | 5.54 | 542 | 改BOM for music SKU。Basic沒有問題 | [ONGOING] TWEE: antenna design issue, adding fix for FFP
18821 | FR165_AutoHT | 33 | GPS_L1 by ref non_recheck(music) | 25/546 | 4.58 | 546 |  | [ONGOING] TWEE: antenna design issue, adding fix for FFP
18735 | FR165_PRNP | 34 | 燒入¦MultiUpdater USB Update | 30/712 | 4.21 | 712 | Basic SKU出問題。Music沒有問題 | [FIXED] TWEE: Basic PRNP software issue
18734 | FR165_AutoATE | 129 | NRF1P8(basic) | 24/710 | 3.38 | 710 |  | [FIXED] TWEE: iATE froze, updated ITMXP commands to prevent freezing
18828 | FR165_FT3 | 42 | ALS Luminance (WLED ON) | 17/528 | 3.22 | 528 |  | [FIXED] TWEE: Already asked TW SE to split test item based on display model for FFP
8837 | Airtight_table | 120 | 壓力不足_負壓 | 13/472 | 2.75 | 472 | 線上設備問題? 看有無集中在哪port
18821 | FR165_AutoHT | 117 | GPS_L1 by ref non_recheck(basic) | 15/546 | 2.75 | 546 |  | [ONGOING] TWEE: antenna design issue, adding fix for FFP
18825 | FR165_RT3 | 30 | (WiFi) Access AP | 14/539 | 2.6 | 539 |  | [ONGOING] TWEE: Need to do a cycle test since they all happened on the same machine, maybe there was interference.
18824 | FR165_RT2 | 194 | VEXT D-OVSS_white page16% delta_OFF-ON | 12/541 | 2.22 | 541 |  | [ONGOING] TWEE: Need to ask TW SW to update ITMXP
18828 | FR165_FT3 | 9 | (Discharge)電池電壓¦(Discharge)Battery Voltage | 11/528 | 2.08 | 528 |  | [IGNORE] TWEE: Many units were left discharging while fixing issues, shouldn't happen in future builds.
18833 | FR165_GSensor | 11 | Calibration | 11/528 | 2.08 | 528 |  | [ONGOING] TWEE: Need to do a cycle test to check. FR265 and SQ2 changed xpRepeat from 3 to 5 and added a new FailCommand during MP. Perhaps they saw the same problem
8837 | Airtight_table | 117 | 變形量絕對值超出規格_負壓 | 9/472 | 1.91 | 472
8837 | Airtight_table | 124 | 連續斜率異常_正壓 | 9/472 | 1.91 | 472
18827 | FR165_FT2 | 38 | NFC Test | 10/528 | 1.89 | 528 | Cycle test沒問題 | [ONGOING] TWEE: Need to do a cycle test to check
18823 | FR165_AutoRT1 | 128 | CPLC Head Byte II | 10/542 | 1.85 | 542 |  | [FIXED] TWEE: ITMXP reading wrong response, fixed by TWSE
18734 | FR165_AutoATE | 82 | Average External Supply Current in Test Mode with battery present | 13/710 | 1.83 | 710 |  | [FIXED] TWEE: iATE wrong channel, updated ITMXP commands
18827 | FR165_FT2 | 194 | VEXT D-OVSS_white page16% delta_OFF-ON | 9/528 | 1.7 | 528 |  | [ONGOING] TWEE: Need to ask TW SW to update ITMXP
8837 | Airtight_table | 118 | 連續斜率異常_負壓 | 8/472 | 1.69 | 472
18824 | FR165_RT2 | 37 | Minimum Battery Voltage Required for Shipping | 9/541 | 1.66 | 541 |  | [FIXED] TWEE: Forgot to follow battery spec
18826 | FR165_AutoFT1 | 189 | GPS_L1 by ref_1% non_recheck(basic) | 8/529 | 1.51 | 529 |  | [ONGOING] TWEE: Golden was unsealed. Will have unsealed golden and sealed golden in Golden was using unsealed. Spec will be adjusted in PR
18822 | FR165_RTESN | 15 | Get Unit Type from BOM | 8/548 | 1.46 | 548 |  | [FIXED] TWEE: IT/SW Web service getAllLevelBOM issue.
18845 | FR165_OHRM_RearCase | 71 | (ILP LED ON) LED1A_PD1 AVG | 1/70 | 1.43 | 70 |  | [IGNORE] TWEE: Operator forgot to remove protective film (TD Allan Kuo)
18845 | FR165_OHRM_RearCase | 12 | 馬達共振頻率 | 1/70 | 1.43 | 70 |  | [FIXED] TWEE: LRA was not properly attached to the test fixture (TD Allan Kuo)
18734 | FR165_AutoATE | 54 | VDDPA_WIFIon | 10/710 | 1.41 | 710 |  | [ONGOING] TWEE: 2x units Q701 cold joint (SMT PE checking), 5x units spec not wide enough
18826 | FR165_AutoFT1 | 184 | Get L1 ATT | 7/529 | 1.32 | 529 |  | [IGNORE] TWEE: Operator forgot to do golden calibration
18819 | FR165_AutoCT | 36 | GPS_L1 by ref non_recheck(music) | 7/547 | 1.28 | 547 |  | [ONGOING] TWEE: antenna design issue, adding fix for FFP
18826 | FR165_AutoFT1 | 123 | NFC Antenna Self-test Tx Current | 6/529 | 1.13 | 529 |  | [FIXED] TWEE: Removed test item since it's already tested at RTESN
8837 | Airtight_table | 107 | INI變形量絕對值超出規格 | 5/472 | 1.06 | 472
8837 | Airtight_table | 123 | 變形量絕對值超出規格_正壓 | 5/472 | 1.06 | 472
18827 | FR165_FT2 | 195 | VEXT LMP delta_10%-0% | 5/528 | 0.95 | 528
18825 | FR165_RT3 | 9 | (Discharge)電池電壓¦(Discharge)Battery Voltage | 5/539 | 0.93 | 539