## New Production Status Summary
Project Name | Phase | Category | MP Date | Concept Review | Stretage Review | DFM Review | Mechanical Design Review | Tooling Begins | FP Build | PR Build | Dashboard | Closure Report | High Ongoing | Comment | SMD PE | ASSY PE | MPM
Xero B60i Laser Navigation Binoculars | Top Level Design | Outdoor | 2024-03-22 | 2022-04-20 | 2022-05-11 | 2023-03-15 | 2023-03-29 | 2023-04-05 |  |  | 2024-05-03 | 1 | 0 |  | Alex.Pu | Jason.Cai
LED Control Module | Top Level Design | Marine | 2024-01-08 | 2022-07-06 | 2022-07-27 | 2023-02-14 | 2023-02-28 |  |  |  | 2024-02-19 | 1 | 0 |  | Iris.Wu | Frankie.Lee
Descent Mk3 Series | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-01-03 | 2022-01-17 | 2022-08-05 |  |  | 2023-11-13 | 1 | 0 |  | Shawn.Huang | Maggie.Chang Viola.Kao | Leol.Chen
Descent Mk3 Series | Detailed Design | Outdoor | 2023-10-02 | 2021-08-13 | 2021-09-03 | 2022-07-08 | 2022-07-22 | 2022-08-05 | 2023-04-07 |  | 2023-11-13 | 1 | 0 |  | Shawn.Huang | Maggie.Chang Viola.Kao | Leol.Chen
IMWW23 | Top Level Design | OEM Auto | 2023-09-18 |  |  | 2021-11-05 | 2021-11-19 |  |  |  | 2023-10-30 | 1 | 0 |  | Eric.Wang Davidsd.Lin | Jasper.Huang Jeff.Lin | Nick.Yen Stephanie.Yang
Prop Drive Cost Down | Detailed Design | Marine | 2023-08-14 | [7 empty] | 2023-09-25 | 1 | 0 |  | Iris.Wu | John.Chiu
Venu 3 | Detailed Design | Fitness | 2023-05-29 |  |  | 2022-01-21 | 2022-02-04 | 2022-07-19 |  |  | 2023-07-10 | 1 | 0 |  | Aaron.Lin | Viola.Kao Pattie.Lan | Alexty.Chang
Venu 3S | Detailed Design | Fitness | 2023-05-29 |  |  | 2021-12-01 | 2021-12-15 | 2022-07-19 |  |  | 2023-07-10 | 1 | 0 |  | Shawn.Huang | Viola.Kao Stansy.Wang | Alexty.Chang
MARQ Carbon | Detailed Design | Outdoor | 2023-05-22 | 2021-02-04 | 2021-02-25 | 2021-08-23 | 2021-09-06 | 2021-04-13 | 2022-07-27 | 2022-06-30 | 2023-07-03 | 1 | 0 |  | Shawn.Huang | Eason.Chen Amelie.Chang | Nixon.Pan
Venu Sq 2 Plus | Detailed Design | Fitness | 2023-05-08 | 2021-11-18 | 2021-12-09 | [5 empty] | 2023-06-19 | 1 | 0 |  | Herry.Lan | Hao.Cheng Viola.Kao
Force Pivot Style Trolling Motor | Factory Prototype | Marine | 2023-05-08 | 2019-12-17 | 2020-01-07 | 2022-03-08 | 2022-03-22 | 2022-05-02 | 2022-05-06 | 2023-01-13 | 2023-06-19 | 1 | 0 |  | Iris.Wu | Wilson.Chen John.Chiu Allen.Chu Daniel.Lee Jimmy.Kuo | Tim.Wu
GSD28 | Detailed Design | Marine | 2023-05-01 | 2021-10-07 | 2021-10-28 | 2022-07-20 | 2022-08-03 | 2022-08-22 |  |  | 2023-06-12 | 1 | 0 |  | Bowman.Lai | Charlotte.Chen
GPSMAP 9000 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
GPSMAP 9000 | Detailed Design | Marine | 2023-04-03 | 2021-05-11 | 2021-06-01 | 2022-05-03 | 2022-05-17 | 2022-05-31 |  |  | 2023-05-15 | 1 | 1 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
BlueNET Gateway | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-04-18 | 2022-12-28 | 2023-05-15 | 1 | 0 |  | Stephen.Shen | Allen.Chu | Tim.Wu
BlueNET Switch | Factory Prototype | Marine | 2023-04-03 | 2021-03-17 | 2021-04-07 | 2021-10-01 | 2021-10-15 | 2022-02-17 | 2022-05-18 | 2022-12-28 | 2023-05-15 | 1 | 1 |  | Stephen.Shen | Chloe.Lin2 | Tim.Wu
Forerunner 965 | Detailed Design | Fitness | 2023-04-03 |  |  | 2022-02-21 | 2022-03-07 | 2022-02-21 |  |  | 2023-05-15 | 1 | 0 |  | Herry.Lan | Viola.Kao Daniel.Tsai | Alexty.Chang
BMW MGU22 | Top Level Design | OEM Auto | 2023-04-01 |  |  | 2020-04-10 | 2020-04-24 |  |  |  | 2023-05-12 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | Jasper.Huang James.Chou Jasper.Huang James.Chou | Jasper.Huang Joseph.Yen Mark.Chang Sandy.Lee Joseph.Yen Sandy.Lee Jasper.Huang Jasper.Huang
Varia eBike Radar Tail Light (eRTL615) | Detailed Design | Fitness | 2023-03-06 | 2021-10-21 | 2021-11-11 | 2022-03-14 | 2022-03-28 |  |  |  | 2023-04-17 | 1 | 0 |  | PeiRu.Tsai | Eason.Chen | Ryan.Li
Catalyst Kart/Moto/Roadster | Detailed Design | Automotive | 2023-03-06 | 2021-09-20 | 2021-10-11 | 2022-02-24 | 2022-03-10 | 2022-05-23 |  |  | 2023-04-17 | 1 | 0 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
Catalyst Kart/Moto/Roadster | Detailed Design | Automotive | 2023-03-06 | 2021-12-13 | 2022-01-03 | 2022-02-24 | 2022-03-10 | 2022-05-24 |  |  | 2023-04-17 | 1 | 6 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
Catalyst Kart/Moto/Roadster | Detailed Design | Automotive | 2023-03-06 | 2021-12-13 | 2022-01-03 | 2022-02-24 | 2022-03-10 | 2022-05-24 |  |  | 2023-04-17 | 1 | 2 |  | Stephen.Shen Steve.Chiang | Frankie.Lee | Allyson.Kuo Sandy.Lee
Tire Temp Sensor | Detailed Design | Automotive | 2023-03-06 | 2021-12-22 | 2022-01-12 | 2022-04-14 | 2022-04-28 | 2022-08-12 |  |  | 2023-04-17 | 1 | 0 |  | ShengChi.Wang | Jason.Cai | Donna.Chiu Sandy.Lee
Xero L60i Laser Navigator | Detailed Design | Outdoor | 2023-02-13 | 2021-02-25 | 2021-03-18 | 2022-05-16 | 2022-05-30 | 2022-06-10 |  |  | 2023-03-27 | 1 | 0 |  | Alex.Pu | Jason.Cai Jasonch.Chen | Lori.Tsai
Enduro 2023 | Detailed Design | Outdoor | 2023-02-13 | 2021-09-15 | 2021-10-06 | 2022-03-04 | 2022-03-18 | 2021-11-09 |  |  | 2023-03-27 | 1 | 0 |  | Dannyhp.Cheng | Leoyt.Chen Amelie.Chang
Descent S1 Buoy | Detailed Design | Outdoor | 2023-02-13 | 2020-03-25 | 2020-04-15 | 2020-11-03 | 2020-11-17 | 2020-11-23 |  |  | 2023-03-27 | 1 | 0 |  | Kevin.Chu | Viola.Kao Daniel.Tsai | Franksl.Chen
zumo XT2 | Top Level Design | Automotive | 2023-02-06 |  |  | 2022-02-18 | 2022-03-04 | 2022-05-26 |  |  | 2023-03-20 | 1 | 0 |  | Derek.Cheng | Frankie.Lee | Nick.Yen
Approach Z50 | Factory Prototype | Outdoor | 2023-02-06 | 2020-04-13 | 2020-05-04 | 2020-10-28 | 2020-11-11 | 2022-04-29 | 2022-04-06 |  | 2023-03-20 | 1 | 0 |  | Alex.Pu | Charlotte.Chen | Donna.Chiu Robben.Liu
Approach S70S | Detailed Design | Outdoor | 2023-01-30 | 2021-08-05 | 2021-08-26 | 2021-12-06 | 2021-12-20 | 2022-04-18 |  |  | 2023-03-13 | 1 | 0 |  | Dannyhp.Cheng | Kuo.Kuo Amelie.Chang | Jackhl.Chen
Edge 540 840 | Factory Prototype | Fitness | 2023-01-30 | 2021-03-11 | 2021-04-01 | 2021-04-14 | 2021-04-28 | 2022-02-07 | 2022-06-03 | 2022-09-23 | 2023-03-13 | 1 | 0 |  | Andyjs.Chen | Pattie.Lan Viola.Kao | Leol.Chen
Panoptix PS70 - (SSMB) | Factory Prototype | Marine | 2023-01-30 |  | 2021-08-05 | 2021-11-25 | 2021-12-09 | 2022-02-01 | 2022-07-28 | 2022-10-20 | 2023-03-13 | 1 | 0 |  | Derek.Cheng | Albertth.Chen John.Chiu | Tim.Wu
Foretrex 801/901 | Detailed Design | Outdoor | 2023-01-23 | 2021-10-01 | 2021-10-22 | 2022-01-28 | 2022-02-11 | 2022-05-27 |  |  | 2023-03-06 | 1 | 0 |  | PeiRu.Tsai | Amyry.Chen Amelie.Chang | Neo.Lin
GMR xHD3 Magnetron Open Arrays | Detailed Design | Marine | 2023-01-16 |  |  | 2022-04-13 | 2022-04-27 | 2022-05-10 |  |  | 2023-02-27 | 1 | 0 |  | Bowman.Lai | Isaac.Wang Wilson.Chen | Stephanie.Yang
Forerunner 265 | Detailed Design | Fitness | 2023-01-02 | 2021-12-24 | 2022-01-14 | 2022-03-30 | 2022-04-13 | 2022-06-17 |  |  | 2023-02-13 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan
LYWW24 | Top Level Design | OEM Auto | 2022-12-30 | [7 empty] | 2023-02-10 | 1 | 0 |  | Davidsd.Lin Erichw.Wang | Jim.Shen Zack.Lin Colby.Ren | Nick.Yen
fenix 7X Pro | Detailed Design | Outdoor | 2022-12-19 | [7 empty] | 2023-01-30 | 1 | 0 |  | Shawn.Huang | Amelie.Chang Stansy.Wang | Jackhl.Chen
fenix 7S Pro (2022) | Detailed Design | Outdoor | 2022-12-19 | 2021-09-07 | 2021-09-28 | 2021-12-28 | 2022-01-11 | 2022-01-14 |  |  | 2023-01-30 | 1 | 0 |  | Herry.Lan | Viola.Kao Stansy.Wang | Franksl.Chen
fenix 7 Pro | Detailed Design | Outdoor | 2022-12-19 | 2021-09-27 | 2021-10-18 | 2021-12-28 | 2022-01-11 | 2022-01-14 | 2022-06-17 | 2022-09-08 | 2023-01-30 | 1 | 0 |  | Aaron.Lin | Amelie.Chang Stansy.Wang | Nixon.Pan
RV Fixed Displays (7"/10") | Detailed Design | Marine | 2022-12-05 | 2021-06-11 | 2021-07-02 | 2022-03-03 | 2022-03-17 | 2022-05-16 | 2022-06-09 |  | 2023-01-16 | 1 | 0 |  | Bowman.Lai | Allen.Chu John.Chiu | Tim.Wu
Approach R50 | Detailed Design | Outdoor | 2022-11-28 | 2020-05-14 | 2020-06-04 | 2021-07-09 | 2021-07-23 | 2022-02-28 | 2022-05-20 | 2022-06-30 | 2023-01-09 | 1 | 0 |  | Steve.Chiang ShengChi.Wang | Chloe.Lin2 Johnny.Liu | Nixon.Pan Allyson.Kuo
Xero C1 Chronograph | Factory Prototype | Outdoor | 2022-11-21 | 2020-09-22 | 2020-10-13 | 2021-07-15 | 2021-07-29 | 2022-02-25 | 2022-05-25 | 2022-08-16 | 2023-01-02 | 1 | 0 |  | Kevin.Chu | Viola.Kao Kuo.Kuo | Leol.Chen
RV Fixed Displays (7"/10") | Detailed Design | Marine | 2022-11-07 | 2021-06-11 | 2021-07-02 | 2022-03-04 | 2022-03-18 | 2022-03-21 | 2022-06-08 |  | 2022-12-19 | 1 | 1 |  | Bowman.Lai | Allen.Chu John.Chiu | Tim.Wu
vivomove Trend (previously "4") | Factory Prototype | Fitness | 2022-10-31 | 2020-11-13 | 2020-12-04 | 2021-10-01 | 2021-10-15 | 2021-11-03 | 2022-04-18 | 2022-08-05 | 2022-12-12 | 1 | 0 |  | Andyjs.Chen | Joel.Wu Viola.Kao | Leol.Chen
ECHOMAP UHD2 (Touch) | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2022-11-21 | 1 | 0 |  | Steve.Chiang | Allen.Chu Isaac.Wang Albertth.Chen Wilson.Chen Jason.Cai Charlotte.Chen | Stephanie.Yang Lori.Tsai
ECHOMAP UHD2 (Touch) | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2021-11-23 |  |  | 2022-11-21 | 1 | 0 |  | Steve.Chiang | Allen.Chu Isaac.Wang Albertth.Chen Wilson.Chen Jason.Cai Charlotte.Chen | Stephanie.Yang Lori.Tsai
ECHOMAP UHD2 (Touch) | Factory Prototype | Marine | 2022-10-10 | 2021-02-18 | 2021-03-11 | 2021-11-24 | 2021-12-08 | 2022-01-14 |  |  | 2022-11-21 | 1 | 1 |  | Steve.Chiang | Allen.Chu Isaac.Wang Albertth.Chen Wilson.Chen Jason.Cai Charlotte.Chen | Stephanie.Yang Lori.Tsai
Alpha Dog Collar | Factory Prototype | Outdoor | 2022-10-03 | 2021-03-15 | 2021-04-05 | 2021-08-09 | 2021-08-23 | 2022-01-10 | 2022-01-25 |  | 2022-11-14 | 1 | 1 |  | Dannyhp.Cheng | Eason.Chen | Robben.Liu
TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | Detailed Design | OEM Auto | 2022-10-03 |  |  | 2021-10-15 | 2021-10-30 | 2021-11-26 | 2022-01-14 |  | 2022-11-14 | 1 | 0 |  | Wells.Yu Davidsd.Lin Erichw.Wang Wells.Yu Davidsd.Lin | Zack.Lin Colby.Ren Jeff.Lin Zack.Lin Colby.Ren Jeff.Lin | Nick.Yen Sandy.Lee Nick.Yen
FUSION - WB675 Hide Away Stereo | Factory Prototype | Marine | 2022-09-28 | [7 empty] | 2022-11-09 | 1 | 0 |  | Steve.Chiang | Allen.Chu
Instinct Hybrid Analog/Digital | Factory Prototype | Outdoor | 2022-09-19 |  |  | 2021-12-01 | 2021-12-15 |  | 2022-01-05 |  | 2022-10-31 | 1 | 0 |  | Anton.Lin | Eric.Chiang Amelie.Chang | Alexty.Chang Robben.Liu
eTrex SE | Detailed Design | Outdoor | 2022-09-12 | 2021-06-28 | 2021-07-19 | 2021-12-07 | 2021-12-21 | 2022-01-07 |  |  | 2022-10-24 | 1 | 0 |  | Andyjs.Chen | Eason.Chen Amelie.Chang | Neo.Lin Franksl.Chen
Alpha 200/200i Plus (i.MX7 Platform) | Pilot Run | Outdoor | 2022-08-29 | [7 empty] | 2022-10-10 | 1 | 0 |  | Daniel.Mao Dannyhp.Cheng | Leoyt.Chen
Marq (Gen 2) | Detailed Design | Outdoor | 2022-08-22 | 2021-03-03 | 2021-03-31 | 2021-08-16 | 2021-08-30 | 2021-09-07 |  |  | 2022-10-03 | 1 | 0 |  | Shawn.Huang | Arthur.Wang Amelie.Chang | Alexty.Chang
GST - MCU 2.0 | Pilot Run | Marine | 2022-08-22 | [7 empty] | 2022-10-03 | 1 | 0 |  | Iris.Wu | Chloe.Lin2
Dash Cam Live (LTE) | Factory Prototype | Automotive | 2022-08-08 | 2020-09-18 | 2020-10-09 | 2020-11-30 | 2020-12-14 | 2021-06-14 | 2022-01-07 | 2022-05-16 | 2022-09-19 | 1 | 3 |  | Stephen.Shen | Johnny.Liu Jasonch.Chen | Lori.Tsai
Bounce | Pilot Run | Fitness | 2022-08-01 | 2019-09-03 | 2019-09-24 | 2019-10-22 | 2019-11-05 | 2020-04-30 |  | 2022-01-03 | 2022-09-12 | 1 | 0 |  | Shawn.Huang | Viola.Kao Leoyt.Chen Annie.Wang | Franksl.Chen
Venu Sq 2 | Pilot Run | Fitness | 2022-07-18 | [5 empty] | 2021-11-23 |  | 2022-08-29 | 1 | 0 |  | Herry.Lan | Hao.Cheng Viola.Kao | Jackhl.Chen
TXTW22_Drive+3.0 (Lawrence DA & Taroko EB) | Detailed Design | OEM Auto | 2022-07-08 |  |  | 2021-05-28 | 2021-06-11 | 2021-06-18 | 2021-09-02 |  | 2022-08-19 | 1 | 0 |  | Wells.Yu Davidsd.Lin Erichw.Wang Davidsd.Lin Wells.Yu | Zack.Lin Colby.Ren Jeff.Lin Jeff.Lin Zack.Lin Colby.Ren | Nick.Yen Sandy.Lee Nick.Yen
Tread XL - Baja Race Edition | Pilot Run | Automotive | 2022-07-04 | 2020-02-11 | 2020-03-03 | 2020-06-29 | 2020-07-13 | 2020-12-11 | 2021-08-11 | 2021-10-01 | 2022-08-15 | 1 | 0 |  | Steve.Chiang | Isaac.Wang | Leol.Chen
IXWW22 | Top Level Design | OEM Auto | 2022-07-04 | [6 empty] | 2021-12-28 | 2022-08-15 | 1 | 0 |  | Erichw.Wang | Colby.Ren Jeff.Lin | Nick.Yen
Tacx NEO Bike Plus | Pilot Run | Fitness | 2022-06-27 | [5 empty] | 2021-12-01 |  | 2022-08-08 | 1 | 0 |  | Stephen.Shen | Simonyc.Chen John.Chiu | Franksl.Chen
Tacx NEO Bike Plus | Pilot Run | Fitness | 2022-06-27 |  |  | 2020-04-22 | 2020-05-06 |  |  |  | 2022-08-08 | 1 | 0 |  | Stephen.Shen | Simonyc.Chen John.Chiu | Franksl.Chen
BMW MGU22 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Jasper.Huang Joseph.Yen Mark.Chang Sandy.Lee Mark.Chang
BMW MGU22 | Top Level Design | OEM Auto | 2022-06-20 | [7 empty] | 2022-08-01 | 1 | 0 |  | Davidsd.Lin | Jasper.Huang James.Chou | Jasper.Huang Joseph.Yen Mark.Chang Sandy.Lee
dezlCam OTR710 & RV Cam 795 | Pilot Run | Automotive | 2022-06-13 | [6 empty] | 2022-03-21 | 2022-07-25 | 1 | 1 |  | Bowman.Lai | Simonyc.Chen Allen.Chu | Tim.Wu
inReach Messenger | Pilot Run | Outdoor | 2022-06-13 | 2021-03-03 | 2021-03-24 | 2021-08-16 | 2021-08-30 | 2021-11-10 | 2022-01-03 | 2022-03-25 | 2022-07-25 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Kuo.Kuo Amelie.Chang | Neo.Lin Nixon.Pan
DriveSmart Synaptics Redesigns | Pilot Run | Automotive | 2022-06-09 | [7 empty] | 2022-07-21 | 1 | 0 |  | Stephen.Shen Steve.Chiang Iris.Wu Bowman.Lai | Jason.Cai Jasonch.Chen
RV/Camper 2022 | Factory Prototype | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Frankie.Lee John.Chiu Charlotte.Chen
RV/Camper 2022 | Factory Prototype | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Frankie.Lee John.Chiu Charlotte.Chen
RV/Camper 2022 | Factory Prototype | Automotive | 2022-06-06 | 2021-07-14 | 2021-08-04 |  |  | 2021-11-22 |  |  | 2022-07-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Frankie.Lee John.Chiu Charlotte.Chen
Tread Audio System | Pilot Run | Automotive | 2022-06-06 | 2020-11-24 | 2020-12-15 | 2021-03-17 | 2021-03-31 | 2021-07-19 | 2021-08-23 | 2022-01-14 | 2022-07-18 | 1 | 1 |  | Alex.Pu | Isaac.Wang | Tim.Wu
Enduro 2022 | Pilot Run | Outdoor | 2022-05-30 | [6 empty] | 2022-02-14 | 2022-07-11 | 1 | 0 |  | PeiRu.Tsai | Leoyt.Chen Hao.Cheng Amelie.Chang | Robben.Liu
Tread 8" OEM w/ CAN | Pilot Run | Automotive | 2022-05-30 | [6 empty] | 2022-03-16 | 2022-07-11 | 1 | 1 |  | Derek.Cheng | Johnny.Liu Jason.Cai | Lori.Tsai
Edge Explore 2 | Pilot Run | Fitness | 2022-05-30 | [5 empty] | 2021-12-09 | 2022-03-16 | 2022-07-11 | 1 | 0 |  | Kevin.Chu Dannyhp.Cheng | Viola.Kao Arthur.Wang | Nixon.Pan Jackhl.Chen
LiveScope XR - New Transducer | Pilot Run | Marine | 2022-05-23 | 2021-02-26 | 2021-03-19 | 2021-07-16 | 2021-07-30 | 2021-08-11 | 2021-08-19 |  | 2022-07-04 | 1 | 1 |  | Derek.Cheng | Albertth.Chen John.Chiu | Ryan.Li
Delta SE | Pilot Run | Outdoor | 2022-05-16 | 2020-08-21 | 2020-09-11 | 2020-12-28 | 2021-01-11 | 2021-07-01 | 2021-07-30 | 2022-03-09 | 2022-06-27 | 1 | 0 |  | Kevin.Chu | Viola.Kao Arthur.Wang | Robben.Liu
dezl OTR Series 2022 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 1 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Frankie.Lee Isaac.Wang Wilson.Chen Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-12-20 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 1 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Frankie.Lee Isaac.Wang Wilson.Chen Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-15 | 2022-03-02 | 2022-06-20 | 1 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Frankie.Lee Isaac.Wang Wilson.Chen Jasonch.Chen | Stephanie.Yang Lori.Tsai
dezl OTR Series 2022 | Product Launch | Automotive | 2022-05-09 | 2021-07-21 | 2021-08-11 | 2021-08-31 | 2021-09-14 | 2021-11-12 | 2021-12-06 | 2022-03-04 | 2022-06-20 | 1 | 0 |  | Stephen.Shen Iris.Wu Bowman.Lai | Frankie.Lee Isaac.Wang Wilson.Chen Jasonch.Chen | Stephanie.Yang Lori.Tsai
HRM-Pro Plus | Pilot Run | Fitness | 2022-05-09 | [7 empty] | 2022-06-20 | 1 | 0 |  | ShengChi.Wang | Johnny.Liu
DriveSmart Synaptics Redesigns | Pilot Run | Automotive | 2022-05-06 | [7 empty] | 2022-06-17 | 1 | 0 |  | Stephen.Shen Steve.Chiang Iris.Wu Bowman.Lai | Jason.Cai Jasonch.Chen
BC50 and BC50 IR | Product Launch | Automotive | 2022-04-25 | 2020-09-15 | 2020-10-06 | 2020-12-22 | 2021-01-05 | 2021-08-02 | 2021-09-08 | 2021-12-09 | 2022-06-06 | 1 | 0 |  | Steve.Chiang | Johnny.Liu | Leol.Chen
Xero G1(s) SatCom Scouting Camera | Pilot Run | Outdoor | 2022-04-18 |  |  | 2019-08-26 | 2019-09-09 | 2020-03-27 |  |  | 2022-05-30 | 1 | 0 |  | Derek.Cheng Derek.Cheng | Frankie.Lee Frankie.Lee | Ken.Kuo Ken.Kuo
GHC 50 | Pilot Run | Marine | 2022-04-18 | [7 empty] | 2022-05-30 | 1 | 0 |  | Stephen.Shen | Charlotte.Chen
Forerunner 255 and 255 Music | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-23 | 2021-12-29 | 2022-05-30 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Jerryy.Lin Pattie.Lan Amelie.Chang | Robben.Liu
Forerunner 255 and 255 Music | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2021-02-01 | 2021-02-15 | 2020-12-11 | 2021-09-22 | 2021-12-28 | 2022-05-30 | 1 | 0 |  | Herry.Lan Andyjs.Chen | Jerryy.Lin Pattie.Lan Amelie.Chang | Robben.Liu
Forerunner 955 and 955 Solar | Product Launch | Fitness | 2022-04-18 | 2019-07-24 | 2019-08-14 | 2020-10-12 | 2020-10-26 | 2020-10-21 |  | 2021-12-22 | 2022-05-30 | 1 | 2 |  | Anton.Lin | Viola.Kao Eric.Chiang Annie.Wang | Alexty.Chang
Edge 1040 | Product Launch | Fitness | 2022-04-18 | 2020-01-23 | 2020-02-13 | 2020-10-20 | 2020-11-03 | 2021-08-13 | 2021-04-28 | 2021-12-29 | 2022-05-30 | 1 | 0 |  | Anton.Lin | Joel.Wu Amelie.Chang | Jackhl.Chen
2022 vivofit jr. 3 SKUs | Pilot Run | Fitness | 2022-04-11 |  |  |  |  | 2021-09-13 |  |  | 2022-05-23 | 1 | 0
ECHOMAP UHD2 (Keyed) | Product Launch | Marine | 2022-04-06 | 2020-06-29 | 2020-07-20 | 2021-01-19 | 2021-02-02 | 2021-03-02 |  | 2022-01-14 | 2022-05-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Wilson.Chen John.Chiu | Ken.Kuo
ECHOMAP UHD2 (Keyed) | Product Launch | Marine | 2022-04-06 |  |  |  |  | 2021-03-02 |  | 2022-01-14 | 2022-05-18 | 1 | 0 |  | Iris.Wu Bowman.Lai | Wilson.Chen John.Chiu | Ken.Kuo
Tacx Vortex 2M | Cancelled | Fitness | 2022-03-14 | 2020-05-05 | 2020-05-26 | [5 empty] | 2022-04-25 | 1 | 1 |  |  | Claudia.vanRhoon | bianca
vivosmart 5 (Franklin) | Production | Fitness | 2022-03-07 | 2020-11-06 | 2020-11-27 | 2021-02-05 | 2021-02-19 | 2021-01-26 | 2021-08-31 | 2021-11-05 | 2022-04-18 | 1 | 0 |  | Kevin.Chu | Viola.Kao Daniel.Tsai | Nixon.Pan
Dezl Headset | Product Launch | Automotive | 2022-03-07 | [7 empty] | 2022-04-18 | 1 | 0 |  | ShengChi.Wang | Chloe.Lin2 Jasonch.Chen | Lori.Tsai
BMW MGU22 | Top Level Design | OEM Auto | 2022-03-07 |  |  | 2020-05-15 | 2020-05-29 |  |  |  | 2022-04-18 | 1 | 0 |  | Davidsd.Lin Davidsd.Lin | Jasper.Huang James.Chou Jasper.Huang | Jasper.Huang Joseph.Yen Mark.Chang Sandy.Lee Sandy.Lee
Panoptix LiveScope HD (LVS34HD Transducer) | Production | Marine | 2022-03-01 | 2021-03-01 | 2021-03-22 | 2021-07-16 | 2021-07-30 | 2021-08-09 | 2021-08-12 | 2021-12-10 | 2022-04-12 | 1 | 0 |  | Derek.Cheng | Albertth.Chen John.Chiu | Ryan.Li
quatix 7 Sapphire | Pilot Run | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao
quatix 7 | Production | Marine | 2022-02-14 |  |  |  |  | 2021-06-21 |  |  | 2022-03-28 | 0 | 0 |  |  | Leo.Chiu Viola.Kao
Varia Radar Camera (RCT715) | Product Launch | Fitness | 2022-02-14 | 2020-03-24 | 2020-04-14 | 2020-12-01 | 2020-12-15 | 2021-04-28 | 2021-07-05 |  | 2022-03-28 | 0 | 0 |  | Shawn.Huang | Simonyc.Chen Jimmy.Kuo | Jackhl.Chen
D2 Echo (EPIX) | Production | Outdoor | 2022-01-17 | [7 empty] | 2022-02-28 | 0 | 0 |  |  | Leo.Chiu Amelie.Chang
Descent G1 | Production | Outdoor | 2022-01-03 | 2020-07-24 | 2020-08-14 |  |  | 2020-12-14 |  |  | 2022-02-14 | 0 | 0 |  | Anton.Lin | Viola.Kao Eason.Chen | Franksl.Chen
vivomove Sport (previously "Lite") | Production | Fitness | 2021-11-08 | [7 empty] | 2021-12-20 | 1 | 0 |  | Herry.Lan | Joel.Wu Amelie.Chang | Sherry.Shih
"Austin" | Production | Outdoor | 2021-11-01 | 2020-03-05 | 2020-03-26 | 2020-08-31 | 2020-09-14 | 2020-09-15 |  |  | 2021-12-13 | 1 | 0 |  | Aaron.Lin | Leo.Chiu Amelie.Chang | Nixon.Pan
Venu 2 Plus | Production | Fitness | 2021-10-18 | 2020-01-01 | 2020-01-22 | 2020-02-07 | 2020-02-21 | 2020-06-05 |  |  | 2021-11-29 | 1 | 0 |  | Kevin.Chu | Steve.Lee Amelie.Chang | Alexty.Chang
fenix 7X | Production | Outdoor | 2021-10-04 | 2020-04-17 | 2020-04-02 | 2022-10-07 | 2022-10-21 |  | 2020-11-06 | 2021-02-15 | 2021-11-15 | 0 | 0 |  | Shawn.Huang | Hao.Cheng Amelie.Chang
fenix 7S | Production | Outdoor | 2021-10-04 | [7 empty] | 2021-11-15 | 1 | 0 |  |  | Amelie.Chang Stansy.Wang | Franksl.Chen
fenix 7 | Production | Outdoor | 2021-10-04 | 2020-02-04 | 2020-02-25 | 2020-05-18 | 2020-06-01 | 2020-06-17 |  |  | 2021-11-15 | 1 | 0 |  | Aaron.Lin | Leo.Chiu Amelie.Chang | Nixon.Pan
One Battery Bike Project | Production | Fitness | 2021-09-06 | 2019-12-10 | 2019-12-31 | 2020-04-02 | 2020-04-16 | 2020-06-25 |  |  | 2021-10-18 | 1 | 0 |  | Kevin.Chu | Pattie.Lan Amelie.Chang | Nixon.Pan
NEO 2T Taiwan Production | Production | Fitness | 2021-06-22 | [7 empty] | 2021-08-03 | 1 | 0 |  |  |  | Lori.Tsai
Battery Charger | Production | Outdoor | 2021-04-26 | [7 empty] | 2021-06-07 | 1 | 0 |  | Dannyhp.Cheng Emma.Lin | Viola.Kao
Asia ISO13485 Certification | Production | Fitness | 2021-04-12 | [7 empty] | 2021-05-24 | 1 | 0 |  |  | Annie.Wang Amelie.Chang
Venu 2 | Production | Fitness | 2021-03-15 | [7 empty] | 2021-04-26 | 1 | 0 |  | Shawn.Huang | Leo.Chiu Davidjw.Yang Amelie.Chang | Alexty.Chang
Venu 2S | Production | Fitness | 2021-03-02 | [7 empty] | 2021-04-13 | 1 | 0 |  | Anton.Lin | Amelie.Chang | Alexty.Chang
Enduro 2020 | Production | Outdoor | 2021-01-11 | [7 empty] | 2021-02-22 | 1 | 0 |  | Shawn.Huang | Daniel.Tsai Amelie.Chang | Chiencheng.Huang
Lumen | Production | Fitness | 2020-11-30 | 2019-07-01 | 2019-07-22 | 2019-11-21 | 2019-12-05 |  |  |  | 2021-01-11 | 0 | 0 |  | Herry.Lan | Amelie.Chang | Sherry.Shih
Descent T1 Transmitter | Production | Outdoor | 2020-11-02 | 2018-02-07 | 2018-02-28 | 2018-07-11 | 2018-07-25 | 2018-08-31 |  |  | 2020-12-14 | 1 | 0 |  | Anton.Lin Herry.Lan | Davidjw.Yang Viola.Kao Kris.Lo | Franksl.Chen
GPSMAP 64xr/sxr | Production | Outdoor | 2020-08-26 | [7 empty] | 2020-10-07 | 1 | 0 |  | Kevin.Chu | Leo.Chiu | Franksl.Chen
Forerunner 745 | Production | Fitness | 2020-07-13 | 2019-03-05 | 2019-03-26 | 2019-08-27 | 2019-09-10 | 2019-10-28 |  |  | 2020-08-24 | 1 | 0 |  | Aaron.Lin | Jasonyl.Wang Amelie.Chang | Alexty.Chang
Descent Mk2 | Production | Outdoor | 2020-06-22 | 2019-07-24 | 2019-08-14 | 2019-09-30 | 2019-10-14 | 2020-01-10 |  |  | 2020-08-03 | 1 | 0 |  | Aaron.Lin | Davidjw.Yang Viola.Kao Steve.Lee | Franksl.Chen
Alpha 200i | Production | Outdoor | 2020-05-25 | 2018-09-10 | 2018-10-01 | 2019-02-05 | 2019-02-19 | 2019-05-13 |  |  | 2020-07-06 | 1 | 0 |  | Aaron.Lin | Hao.Cheng Amelie.Chang
Instinct Solar | Production | Outdoor | 2020-05-18 | 2019-03-05 | 2019-03-26 | 2019-08-02 | 2019-08-16 | 2019-08-23 |  |  | 2020-06-29 | 1 | 0 |  | Anton.Lin | Amelie.Chang
fenix 6S Solar (2020) | Production | Outdoor | 2020-05-11 | 2019-07-05 | 2019-07-26 | 2019-08-02 | 2019-08-16 |  |  |  | 2020-06-22 | 1 | 0 |  | Scott.Ma Kevin.Chu | Jasonyl.Wang | Will.Ma
Edge 1030 Plus | Production | Fitness | 2020-05-04 | 2019-08-08 | 2019-08-29 | 2019-09-05 | 2019-09-19 | 2019-11-19 |  |  | 2020-06-15 | 1 | 0 |  | Shawn.Huang | Hao.Cheng Amelie.Chang | Franksl.Chen
quatix 6 | Production | Marine | 2020-03-02 | [7 empty] | 2020-04-13 | 0 | 0 |  | Emma.Lin Shawn.Huang | Daniel.Tsai Zack.Weng
Garmin Swim 2 | Production | Fitness | 2019-09-23 | 2018-10-08 | 2018-10-29 |  |  | 2019-01-25 |  |  | 2019-11-04 | 0 | 0 |  | Emma.Lin | Hao.Cheng
GPSMAP 86x | Production | Marine | 2019-09-09 |  |  |  |  | 2019-02-11 |  |  | 2019-10-21 | 1 | 0 |  | Aaron.Lin | Daniel.Tsai
GPSMAP 9000 | Detailed Design | Marine | [9 empty] | 0 | 0 |  | Derek.Cheng Bowman.Lai ShengChi.Wang | Jimmy.Kuo Albertth.Chen Charlotte.Chen Jasonch.Chen John.Chiu | Nick.Yen Stephanie.Yang
EPIX PRO (Gen 2) 51mm | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Amelie.Chang Hao.Cheng | Robben.Liu
EPIX PRO (Gen 2) 47mm | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Aaron.Lin | Amelie.Chang Eric.Chiang | Neo.Lin
GPSMAP 66sr/66i Plus (i.MX7 Platform) | Pilot Run | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao Kevin.Chu | Hao.Cheng
Approach S70 | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Andyjs.Chen | Viola.Kao Daniel.Tsai | Jackhl.Chen
GPSMAP 68 | New Product Concept | Outdoor | [9 empty] | 0 | 0 |  |  | Hao.Cheng Amelie.Chang
LIIN22 | Top Level Design | OEM Auto | [9 empty] | 0 | 0 |  | Wells.Yu | Zack.Lin Colby.Ren Jeff.Lin
quatix 7x Solar | Pilot Run | Marine | [9 empty] | 0 | 0 |  |  | Viola.Kao Hao.Cheng
Instinct 2X Solar | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Daniel.Mao Andyjs.Chen | Viola.Kao Amyry.Chen
LWIN21 | Product Launch | OEM Auto | [9 empty] | 0 | 0 |  | Wells.Yu | Jeff.Lin
Tacx NEO 3M | Top Level Design | Fitness | [9 empty] | 0 | 0 |  |  | Robin.deGroot
EPIX PRO (Gen 2) 42mm | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | Herry.Lan | Stansy.Wang | Franksl.Chen
Descent X1i | Top Level Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Viola.Kao Joel.Wu
Tacx Motion Plates | Production | Fitness | [9 empty] | 1 | 1 |  |  | Claudia.vanRhoon | bianca
Tactix 7 | Production | Outdoor | [9 empty] | 0 | 0 |  |  | Hao.Cheng Amelie.Chang
Alpha 200 | Production | Outdoor | [9 empty] | 1 | 0 |  | Aaron.Lin | Jerryy.Lin Amelie.Chang | Jackhl.Chen
Forerunner 265 | Detailed Design | Fitness | [9 empty] | 0 | 0 |  | Herry.Lan Andyjs.Chen | Viola.Kao Amyry.Chen | Nixon.Pan
Approach S42 | Production | Outdoor | [9 empty] | 0 | 0 |  | Emma.Lin
Product - Flight Stream Redesign | Derivative Product Concept | Aviation | [9 empty] | 0 | 0 |  | Stephen.Shen | Johnny.Liu Jimmy.Kuo
Product - G3X/G500TXi Hybrid | Product Development Plan | Aviation | [9 empty] | 0 | 0
LYAF20 | Pilot Run | OEM Auto | [9 empty] | 0 | 0 |  | Davidsd.Lin | Colby.Ren Jeff.Lin
LFIN20 | Production | OEM Auto | [9 empty] | 1 | 0 |  |  | Jun.Yen Jeff.Lin | Jasper.Huang Jun.Yen
Product - GDU77XW | Product Development Plan | Aviation | [9 empty] | 0 | 0 |  |  |  | Donna.Chiu Sandy.Lee
Product - GDU147XW | Product Development Plan | Aviation | [9 empty] | 0 | 0 |  | Stephen.Shen | Jimmy.Kuo | Donna.Chiu Sandy.Lee
Product - 1.3\" GTR/GNC | Development | Aviation | [9 empty] | 0 | 0 |  | Steve.Chiang
eTrex Solar | Detailed Design | Outdoor | [9 empty] | 0 | 0 |  | PeiRu.Tsai | Hao.Cheng Amelie.Chang
Pet Tracker | Cancelled | Outdoor | [9 empty] | 0 | 0 |  | Shawn.Huang Lionel.Wu | Daniel.Tsai Amelie.Chang
DGCN20 | Product Launch | OEM Auto | [9 empty] | 1 | 0 |  | Davidsd.Lin ShengChi.Wang | Zack.Lin Jasper.Huang Colby.Ren | Jun.Yen Nick.Yen
LXTW19 | Production | OEM Auto | [9 empty] | 0 | 0 |  | Paul.Hou Sen.Huang | Davidsd.Lin Jasper.Huang Colby.Ren