## sheet1
Risk | Segment | Project Name | Phase | GMLA Submit Date | Category | No | Questionnaire | Reason | plan | issueOwner | targetDate | closeDate | status
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 105-03888-00 & 105-03889-00: Wait for new rear case to verify ASSY screw | After retested with new cover, result is passed. | MFG ME | 2021-06-10 16:00:00.0000000 +00:00 | 2021-06-25 10:33:23.3957621 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Process validation | 2.D-14 | Golden sample and bad sample preparation plan -- Sample Q'ty | Need Fusion team to provide the golden sample | EE has confirmed with Design team, Fusion will add the golden request into PR FRM-178 directly. | MFG EE | 2021-06-24 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Wrong screw size of rear case which is made by supplier. The screws will strip after tightening. | MME has provided the new part with tooling modification to PE for checking the screw-in/out cycling is passed. | MFG ME | 2021-05-23 16:00:00.0000000 +00:00 | 2021-05-27 16:05:52.3054658 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | 6 CH (1) Power off Current Draw: Completed but wait for function test (2) Mechanical shock: Testing (3) Mechanical vibration: Testing 8 CH (1) Power off Current Draw: Completed but wait for function test (2) Mechanical shock: Testing (3) Mechanical vibration: Testing | After retested with right Dim. screw part, result is passed. | MFG ME | 2021-06-10 16:00:00.0000000 +00:00 | 2021-06-25 10:31:42.7699130 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #2 | 2021-02-08 16:59:07.9766140 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | Fixture ESD is not completed | PQE finishes the testing and the result is passed on 4/20, also ESOP has updated in the same date. (SP010145) | PQE | 2021-02-19 16:00:00.0000000 +00:00 | 2021-04-27 16:55:26.8786926 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #2 | 2021-02-08 16:59:07.9766140 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | No CPK data. NPI need to discuss with EE to figure out the critical cpk items and comment it. | FFP CPK under 1.33 had been adjusted the SPEC by EE already. | NPI | 2021-02-25 16:00:00.0000000 +00:00 | 2021-04-06 10:43:51.8645314 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #2 | 2021-02-08 16:59:07.9766140 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 105-03876-00/105-03843-00 No ATE1 & ATE2 strain gauge result. | Testing result has passed on system. | PQE | 2021-02-19 16:00:00.0000000 +00:00 | 2021-04-06 09:36:52.1676445 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME FA rate: 1 Ch 96.55% (145-03225-02) 4 Ch 97.06 (145-03225-03) | ME finished on 5/3. | MFG ME | 2021-05-02 16:00:00.0000000 +00:00 | 2021-05-03 12:08:36.8157848 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | 750-00139-03/04 fixture is still waiting for Fusion team's feedback to specify the spec. | EE decides to use the results of #90 as IQC inspection spec. The max value we plan to use is < 70nH. | MFG EE | 2021-05-06 16:00:00.0000000 +00:00 | 2021-05-11 15:56:04.0638574 +08:00 | 1
2 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1 Ch: (1) ATE 17.81% (Class D FET Temp (-10) 6.85%) (2) PreFT 11.48% (600W 50Hz 4ohm Level (BP) 6.56%) 4 Ch: (1) ATE 89.61% (Class D 420kHz LegA(-10) 37.66%) (2) ATE2 79.69% (Z2L THD+N (BP) 40.63%) | 1 CH : 1. ATE 17.81% (Class D FET Temp (-10) 6.85%) and ATE 89.61% (Class D 420kHz LegA(-10) 37.66%)=> EE has modified spec. (1 & 4 CH) 2. Pre FT yield rate is caused from equipment error, after fix the equipment, it has passed after cycle testing. 4 CH : 1. ATE2 : Due to BNC cable contacted with the testing cabinet to cause shielding issue, so AE has changed the SMA cable and add heat-shrink tube on cable as below showed already. After confirmed the MP status, all issues had been closed without happening again. | NPI | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-19 10:24:59.8995198 +08:00 | 1
2 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | 1 Ch: ATE 94.52% / PreFT 96.72% 4 Ch: ATE 83.12% | 1. ATE : Class D FET Temp (-10)=> modify spec. (1&4 CH) 2. Pre FT yield rate is caused from equipment error, after fix the equipment, it has passed after cycle testing. After confirmed the MP status, all issues had been closed without happening again. | NPI | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-19 10:25:15.4729818 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | OOB checklist is not ready | As attached. | PQE | 2021-05-06 16:00:00.0000000 +00:00 | 2021-05-11 15:55:32.2311929 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | 750-00139-03/04 fixture is still waiting for Fusion team's feedback to specify the spec. | EE decides to use the results of #90 as IQC inspection spec. The max value we plan to use is < 70nH. | MFG EE | 2021-05-06 16:00:00.0000000 +00:00 | 2021-05-11 15:52:53.3228153 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Product validation | 3.B-7 | CC test plan is ready for MP | CC test plan is not ready | No CH/HT request after MP, Lab confirms for CC with vibration * 2 pcs is OK. | TWN Lab | 2021-04-27 16:00:00.0000000 +00:00 | 2021-04-28 12:06:39.8721277 +08:00 | 1
3 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | EE still discuss with Fusion team and wait for feedback. | MPS has been released, ECO# 222732. | MFG EE | 2021-05-16 16:00:00.0000000 +00:00 | 2021-05-19 10:22:46.8021567 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01065-10 & 004-01065-40 are still v001. EE will keep discussing with Fusion | MPS has been released, ECO# 222732. | MFG EE | 2021-05-16 16:00:00.0000000 +00:00 | 2021-05-19 10:22:34.7000254 +08:00 | 1
2 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #3 | 2021-04-26 20:27:54.4075373 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | Need Fusion to release 174-packaging instruction | IR#139430 has been released | NPI | 2021-05-17 16:00:00.0000000 +00:00 | 2021-05-19 10:19:38.9542930 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #2 | 2021-02-08 16:59:07.9766140 +08:00 | Product validation | 2.B-4 | Release unit level appearance standard for FFP -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) -- Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | Need to update appearance standard | As attached. | MFG ME | 2021-02-19 16:00:00.0000000 +00:00 | 2021-04-06 10:41:03.5495512 +08:00 | 1
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Others | 2.F-8 | Customer complaint (0km/ field) process have been defined and agreed with customer -- Claimed parts return flow -- Complaint refund flow -- Test rack setup in customer side or oversea office | Flow proposal is updated. But need to further discuss with BMW. |  | PQE |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Others | 2.F-7 | Product logistic flow has been set up internally -- Need to include escalation flow or mechanism | Under discussing with Global team. |  | Logistic |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Others | 2.F-6 | Product logistic flow has been defined and agreed with customer | Under discussing with Global team. |  | BD |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Others | 2.F-5 | Recycle container review -- How many containers are needed according to latest forecast -- How are the containers maintained, repaired, and replaced | Need to finalized the container for delivery |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Supply chain/ supply of part | 2.E-11 | Customer requirement of safety stock flow down -- Product safety stock -- Material safety stock | Under discussion by Global team. |  | BD |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Supply chain/ supply of part | 2.E-9 | Review critical parts 長期供貨合約 to make sure parts supply stable -- Base on latest critical parts list (in MPM system) | Awating for design fixed |  | SS |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Supply chain/ supply of part | 2.E-6 | Key flows agreement by Garmin and new supplier -- Change management flow by supplier -- Change management flow by customer | This is responsible by Olathe SS |  | SS |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | Need to further confirm material status for D build. |  | PID |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Supply chain/ supply of part | 2.E-1 | The relevant supply chain have been finalized (2nd source selection for critical parts in MPM system) | 2nd is still under evaluating. |  | MFG ME/DE |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Process development | 2.C-4 | Release preliminary flow chart for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Need to get latest CC/SC into flow chart and PFMEA. |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | DVT result is ETA 2021/M |  | TWN Lab |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | Flange could be broken and current facing with detached fans after shipment. |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product development | 2.A-13 | Unit/ Accessory: Test coverage rate evaluation (Target: 90%) - Base on customer requirement to evaluate test coverage rate - If no special requirement, base on 004- MPS to evaluate test coverage rate | Test coverage rate is still under developing by SW and EE. | Current Test coverage rate is 80% and aim to reach 90% by end of Jun. | EE | 2021-06-29 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product development | 2.A-11 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | No 004 in BOM | This project will use JAMA to release MPS content. | EE | 2021-06-29 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | Still have many SW issue, but tracking with JIRA and Top 20 issue weekly meeting. |  | MFG EE |  |  | 0
1 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Product development | 2.A-1 | DFM report_ product design related -- Special characteristic should be included | No SC included in DFM |  | NPI |  |  | 0
1 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan SMT:ATE-(ANT power level switch 、speaker Vpp、Average Battery current mode、V3P0、DISP3P0、conducted GPS/Glonass sensitivity C/N、turn current、LTE CW measure、VWBATT) ASSY: FT1-(Glonass wight、FT1-72)、FT2-(WiFi Power、Weight)、 | <SMT ATE> - Misjudge/Fixtures – resolved - V1P2 SW issue, OLA will help to remove this item in MPS for PR build – closed - LTE chip pre-booting, LTE module needs to pre-boot for sure, EE will verify the LTE pre-boot combination in PRNP for PR – ongoing @Yeh, Steven <ASSY/TEST> CT(19.06%) HT(12.08%)-Compen C/No by ref – Tracking( first time we implement the auto chamber in PR) RT1(21.06%)-ALS Luminance (WLED ON) – resolved RT2(25.46%)-Touch Screen Check– resolved FT1(14.75%)-Battery Voltage : PR will charge the unit after VT and before FT1. @Wang, Annie FT2(10.83%)-LTE Rx Value – resolved ST(40.5%)-Play Sound File – resolved ProdScan(50.52%)- Battery Voltage @Wang, Annie PR will charge the unit after ST and before Product Scan. Airtight_table_5bar(20.16%)-Tracking(new membrane 5ATM implement) | NPI | 2021-06-13 16:00:00.0000000 +00:00 | 2021-07-20 09:05:59.7413880 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | PRNP fixture is NG but have action plan | Will implement the air ionizer for static elimination in PR/MP SOP/control plan modifying. | PQE | 2021-05-11 16:00:00.0000000 +00:00 | 2021-05-17 09:55:14.9161035 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Process validation | 2.D-16 | Process outsourcing parts evaluation result -- Cpk/ yield rate/ UPH data should be ready | No corresponding doc.( Cpk/yield/UPH ) uploaded for this section. | @Huang, Golden @Cheng, Chris the vendor-side capability run completed and YR%/Cpk/UPH has almost reached the target. | MFG ME/DE | 2021-05-12 16:00:00.0000000 +00:00 | 2021-05-17 09:55:33.6831411 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | SW issue: 1. Unit display blanking 2. Product scan(Check difference from time of DUT and system time) | [CR] display flicker in LCM bonding. Root cause/analysis: After skip CLK and test 50pcs raw material with extended flex for fixture connection, 100% display pass by skipping CLK without noise/flick Action: will Check this issue in PR build [OLA]Product scan – Root cause/analysis: OLA team are still investigating on this, we raised this issue to OLA as attached Action: OLA confirm they need PR result for improvement SW No found in PR | MFG EE | 2021-06-17 16:00:00.0000000 +00:00 | 2021-07-20 09:05:40.0368532 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Product validation | 2.B-4 | Release unit level appearance standard for FFP -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) -- Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | No unit level appearance standard data upload to PR web | @Huang, Golden @Cheng, Chris completed the appearance standard document. | MFG ME | 2021-05-11 16:00:00.0000000 +00:00 | 2021-05-17 09:54:49.6393375 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Only "wifi conducted output power"(Cpk1.85) can meet target. Other 12 test items can't. | Further details in attached. We will have 3 main way to improve: 1.) Fixture Alignment Enhance 2.) SW Issue Fix 3.) Testing Spec revise based on the FFP Test data Keep track in PR | NPI | 2021-04-15 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Others | 3.F-7 | Product logistic flow have been set up internally -- Need to include escalation flow or mechanism -- Review if any change on logistic flow need to be flow down internally | 依Logistic & BD所回覆，尚待以下2點完成合同簽訂：1.第三方物流倉庫，已經按照客戶要求,正在於吉利西安RDC商洽合同內容，預計3月能正式簽署合同。2.杭州灣項目的第三方物流公司已確定，合同預計在4月完成簽署。(2021/2/9) | For KX11, the contract is going sign flow. Not impact the delivery of KX11. For KX11西安RDC合同, change target completed the contract in 6/15. | Logistic | 2021-06-14 16:00:00.0000000 +00:00 | 2021-08-19 13:44:24.2354596 +08:00 | 1
2 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | 依NPI所回覆，仍尚待DE提出Lens來料異常(刮傷、撞傷...)改善對策。(2021/2/9) | 013-00791-00原材外觀檢驗標準已與供應商於2020/11合意完成，並更新於圖面ver. A中 page2， 後續IQC進料檢驗及產線判定皆可以此為參考標準。 | NPI | 2021-02-22 16:00:00.0000000 +00:00 | 2021-02-23 03:20:22.9966667 +00:00 | 1
4 | OEM Auto | LYWW20 | GMLA #3 | 2021-04-09 16:16:29.8845979 +08:00 | Process validation | 3.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | 浸泡機 Grounding system need to be improved to meet WQ000505 | Add the grounding cable, est. completed by 4/15. PQE will provide the verify result before 4/23. PQE verify result in 4/15 and result passed | PDO | 2021-04-22 16:00:00.0000000 +00:00 | 2021-04-15 14:32:16.3345170 +08:00 | 1
4 | OEM Auto | LYWW20 | GMLA #3 | 2021-04-09 16:16:29.8845979 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | VT1 test fixture ESD test failed, dissipative material need to be used in the test fixture and improve contact with ESD table | VT1 fixture will be replaced conduct plinth and base, est. completed by 4/16. PQE will provide verify result on 4/23. PQE conflim check pass in 4/21. | PDO | 2021-04-22 16:00:00.0000000 +00:00 | 2021-04-21 13:52:11.4473861 +08:00 | 1
2 | OEM Auto | LYWW20 | GMLA #3 | 2021-04-09 16:16:29.8845979 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ATE-BT retry rate: 13.68% (Top2 retry items: Drift Rate (Low) & BER (Low)) LYWW20_PRNP-STA retry rate: 16.84% (Top2 retry items; 藍芽1 TX Power on¦BT1 TX Power Test & 藍芽2 TX Power on¦BT2 TX Power Test) LYWW20_FT1 retry rate: 14.64% (Top2 retry items: BT1 TX Power Test & 關機電流¦Turn off current) | 1. ATE-BT retry rate: 13.68% Top2 retry items:(a) Drift Rate (Low) & (b) BER (Low). (a) Caused by fail retry / (b) This frequency band was easy affected by AP noise, EE placed the solution to close test item and use other test to detect HW failure. 3/25 implement. 2.LYWW20_PRNP-STA retry rate: 16.84% Top2 retry items: (a) 藍芽1 TX Power on¦BT1 TX Power Test & (b) 藍芽2 TX Power on¦BT2 TX Power Test. (a) & (b) are affected by production line environment noise, remove this test from ATE, move to FT1 test by Shielding Box. 3/30 implement. 3. LYWW20_FT1 retry rate: 14.64% Top2 retry items: (a) BT1 TX Power Test & (b) 關機電流¦Turn off current. (a) Improve the test program IOP, make sure can receive the signal. (b) Root caused by HT temperature relate to high current, remove this test from FT1 to FT2 to solve issue. 3/30 implement and cycle test 50 times. After生試Build-2 and review the test result, EE check there’s known retry rate of BER caused by environment affect. | MFG EE | 2021-08-08 16:00:00.0000000 +00:00 | 2021-08-26 20:08:23.4186764 +08:00 | 1
4 | OEM Auto | LYWW20 | GMLA #3 | 2021-04-09 16:16:29.8845979 +08:00 | Process validation | 3.D-4 | MSA result check and action plan for fail item or no MSA test base on latest test plan | MSA test result is under calculate, will be ready by 4/16 | Due to lack bad sample, PQE delay the MSA measurement schedule. The MSA result will be completed by 4/30. MSA report updated and reviewed in 4/30. | PQE | 2021-04-29 16:00:00.0000000 +00:00 | 2021-05-04 11:16:17.3637618 +08:00 | 1
4 | OEM Auto | LYWW20 | GMLA #3 | 2021-04-09 16:16:29.8845979 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | Need to update peak temp. information for 804-00004-27/ 804-00005-48 | Olathe update the peak temperature by 4/12. 1. 804-00004-27, GCM155R71H222KA37D Cap,Cer,2200pF,10%,50V,X7R,0402,Size2,AutoOEM Peak Temperature: 260 degree C. 2. 804-00005-48, GRT155C71A105KE13D Cap,Cer,1uF,10%,10V,X7S,0402,Size 2,AOEM Peak Temperature: 260 degree C | EE | 2021-04-12 16:00:00.0000000 +00:00 | 2021-04-13 12:19:19.0051272 +08:00 | 1
2 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 依MPM & NPI所回覆，CCM測試站大約有8%不良率，CFT暫時對策會在無塵室使用氣槍進行鏡頭清潔。並於後續量產觀察。(2021/2/9) | In 1st MP job: -MB_ATE/ECU-General FT/AA-MTF still have high retry items and give resolution in 1st MP job. Next job would be hold in April, keep tracking. In 2nd MP job: -Still found some the unit reboot 1-time during B/I, EE is analyzing the root cause in B/I and normal temperature. Next job would be hold in May, keep tracking. In 3rd MP job: Fix B/I issue by SW V2.3, see the retry rate update in MP report. | NPI | 2021-05-30 16:00:00.0000000 +00:00 | 2021-08-19 13:43:30.1062611 +08:00 | 1
2 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | 依MPM & NPI所回覆，CCM測試站大約有8%不良率，CFT暫時對策會在無塵室使用氣槍進行鏡頭清潔。並於後續量產觀察。(2021/2/9) | In 1st MP job, the CCM_W FYR is already up to 98.3%, and the AA-MTF is already up to 97.6%, | NPI |  | 2021-04-09 17:51:23.0716011 +08:00 | 1
1 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | 依MPM & NPI所回覆，鏡頭保護蓋，ECO#218729已經發出，但尚未Release。(2021/2/9) | ECO#:218729 is released, packing setting confirm completed. | NPI | 2021-02-22 16:00:00.0000000 +00:00 | 2021-02-23 03:22:43.9400000 +00:00 | 1
1 | OEM Auto | DGCN20 | GMLA #3 | 2021-02-22 17:34:40.1503890 +08:00 | Process development | 3.C-6 | Update control plan for PR build (vA) -- Key characteristic should be included and must correspond with D/PFMEA -- Control method for key characteristics should be flow down from D/ PFMEA to control plan -- Fixture/ Meter/ Equipment list (Type info.) & parameter should be updated in CP -- (AOEM) Regular requalification should be included | 依NPI所回覆，CP文件與PFMA&Flow cahrt有落差需要同步再次Review。(ex:SMT, ASSY..)(2021/2/9) Update:因CP & Flow chart文件內容確實存有落差，故NPI & DPQE雙方將再另闢會議進行細部Review，規劃於21WK11完成此項目。(※維持評定黃燈列入待辦)(2021/2/22) | DGCN20_ECU/Camera Control Plan文件 PQE與NPI PE於3/5核對一致性完成. | PQE | 2021-03-11 16:00:00.0000000 +00:00 | 2021-03-08 05:37:54.9033333 +00:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | No ver.A in PR build 1. 6 CH 010-02284-60 / 011-05184-00 / 012-03888-00 / 015-05184-XX 2. 8 CH 010-02284-80 / 011-05185-00 / 012-03889-00 / 015-05185-XX | All parts already updated to version A | NPI/ME/DE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 11:47:18.2426722 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | 105-03889-00 ASSY screw & ASSY top case screw are incomplete. 6/22 receive bottom case and plan to finish on this week | 105-03889-00 ASSY screw & ASSY top case screw are incomplete. 6/22 receive bottom case and plan to finish on this week | PQE | 2021-06-28 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | It will be still ongoing to discuss with supplier. | We will make Garmin and supplier aligned for 750-00139-03/-04 testing before 7/16 | MFG EE | 2021-07-15 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 16 parts on BOM not been version A before pilot run (1)PCB sub-assemblies: 012-03851-D1/D2/J1 (2)Plastic Molded Parts: 145-03260-00/40/41/20/90/B0/10/50/60/A0/30/70 (3) Lens module 013-00866-00 | Plastic Molded Parts 145-03260-00/40/41/20/90/B0/10/50/60/A0/30/70 : There would be a design change after PR2 build, so drawing release is delayed. We plan to release A before 10/E and complete FA before 11/E. | MFG ME | 2021-10-30 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Process validation | 3.D-14 | Golden sample and bad sample ready and registered in internal system -- Expired date set-up for golden sample and bad sample | Need to add VT/ST/PIR golden sample for testing calibration on the next build. | ME/OE have provided the Golden sample for the calibration before testing | PQE | 2021-08-18 16:00:00.0000000 +00:00 | 2021-08-19 15:37:19.9485118 +08:00 | 1
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 1. 6 CH: 7 items are waiting for result. 2. 8 CH: All 12 test items are not started. | 6 CH: 4 items are waiting for result. 8 CH: 9 items are waiting for result. | TWN Lab | 2021-07-01 16:00:00.0000000 +00:00 |  | 0
2 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 6 CH 1. SMT (1) ATE: 43.68%: GeneralCurrent(lin) (-60) (2) ATE2: 16.28%: Z3R Level (BP) 2. ASSY (1) FT1 13.33%: Z1 Level (BP) (2) FT2 22.67%: Z3 Level (BP) 8 CH 1. SMT (1) ATE 55.17%: Open Current 14.4V (-80) (2) ATE2 24.71%: Z1L Level (BP) 2. ASSY (1) FT1 42.65%: Z4 Level (BP) | 6 CH 1. SMT (1) ATE: 43.68%: GeneralCurrent(lin) (-60): All units pass after discussed with OLA and adjusted the SPEC. (2) ATE2: 16.28%: Z3R Level (BP): The MFG team are still discussing about this issue. The preliminary analysis is that the flux residue leads to poor contact. 1. Add visual inspection after MPS. 2. SMT PE will keep monitor the issue on MP. 2. ASSY (1) FT1 13.33%: Z1 Level (BP) (2) FT2 22.67%: Z3 Level (BP) The fixture for PR is temporary version which caused the magnet position unstable. The final fixture will be ready before MP and will avoid this problem. 8 CH 1. SMT (1) ATE 55.17%: Open Current 14.4V (-80) The steel plate for MPS was defective causing the short circuit. PDO has been asked to modify the steel plate, and will be completed on 6/29. (2) ATE2 24.71%: Z1L Level (BP) The MFG team is still discussing this issue. The preliminary analysis is that the flux residue leads to poor contact. 1. Add visual inspection after MPS. 2. SMT PE will keep monitor the issue on MP. 2. ASSY (1) FT1 42.65%: Z4 Level (BP) The fixture for PR is temporary version which caused the magnet position unstable. The final fixture will be ready before MP and will avoid this problem. | NPI | 2021-07-08 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk data will be checked by NPI and aligned with EE. |  | NPI |  |  | 0
1 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #3 | 2021-06-23 16:37:49.1349785 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME parts FA rate. 1. 6 CH: 96% (125-00583-02) 2. 8 CH: 96% (125-00583-03) | Material FA will be complete before 7/9. | MFG ME | 2021-07-08 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 4 fail items (1) Salt Fog (1/1 NG): 72H: 1pcs rust on the bushing. 168H: rust on two of the hinge pins. (2) Accelerated Weathering Xenon (1/1 NG): The case surface on 144 hrs become yellowing and found the lens deformation. (Unit can power on and work normally) (3) Accelerated Weathering UV (1/1 NG): UV-B 200 hours. Housing discolor under 160 hrs. (4) Shipping Vibration (3/4 NG): 010-12940-00/010-12940-01/010-12940-02 found scratch and abrasion mark after vibration. | (1) Salt Fog: OLA test would complete before 09/16. We would wait it for comparison. (Waived) (2) Accelerated Weathering Xenon: Discolor is acceptable. Thermal couple and part-level test proved deformation is only a fake alarm. Issue closed. (3) Accelerated Weathering UV: This is acceptable and approved. Issue closed. (4) Shipping vibration: Issue solved after applying plastic/bubble bag. Issue closed. | MFG ME | 2021-09-23 16:00:00.0000000 +00:00 | 2021-09-22 19:49:40.1782077 +08:00 | 1
2 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | Appearance issues (1) Dents: 27.89% (53/190) (2) Scratches: 5.79% (11/190) (3) The mark on the lens is not cleared: 8.95% (17/190) (4) Scratch on the inside of the glass: 1.58% (3/190) (5) Poor surface and foreign matter on the inside of the glass: 8.42% (16/190) (6) Poor surface: 1.05% (2/190) (7) Dirt: 0.53% (1/190) (8) Foreign matter on LCM: 1.05% (2/190) (9) Deformation of LCM adhesive foam: 0.53% (1/190) | Housing vendor IQC for housing cosmetic / package method will be check & modify - MME checkpoint : 08/E Set up travel card to record this issue for each station. @Lee, Frankie - PR2 ongoing checkpoint : 08/24 start assembly (Postpone to 09/06 start) PR2 : Found root cause of dents (please find above report content) @Lee, Frankie PR2 : New cosmetic issue been found and need keep tracking (please find above report content) @Hung, Jay(Optics) No issue found on PR3 | NPI/ME/DE | 2022-01-25 16:00:00.0000000 +00:00 | 2022-01-26 14:57:48.4429584 +08:00 | 1
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 17 items are not started: Water / Dust Resistance/ Condensation Test/ Body and Wearable Chemicals/ Spark Plug/ Electrostatic Discharge (ESD) Immunity test/ RF Immunity Radiated...etc Salt Fog is under testing The expected complete date:2021/8/27 | ELOT still under testing., The test summary report will provide before 8/31. | TWN Lab | 2021-08-30 16:00:00.0000000 +00:00 | 2021-09-22 19:52:39.6234271 +08:00 | 1
2 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Yield Rate not meet the target >= 97% ASSY (1) RTMTF 85.59% (2) PIR 85.91%: | 1. Lens material quality issue cause RTMTF fail issue, (This is expected issue before build start, due to build qty's increase and been force to use bad parts. Had implement all good parts in PR2, PR2 is ongoing.) 2. PIR issue was cause by power supply issue, after EE modified input current in PR1, issue had been closed. Keep monitoring in PR2. (232 of 234 units pass test after modification) PR2 : RTMTF & PIR yield all higher than 97% (Postpone to 09/06 start) | MFG EE | 2021-09-12 16:00:00.0000000 +00:00 | 2021-09-22 19:53:36.4008041 +08:00 | 1
2 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate not meet the target <10% 1.SMT (1) ATE 21.11%: BATTERY PACK turn on current(1) 2.ASSY (1) FT 60.79% C/No by ref (Idle) (2) VT2 34.05%: 讀取Program參數 (3) VT1 30.17%: Reason (4) PIR 24.79%: IR-led test (5) ST 20.43%: 麥克風頻率測試(ASR)¦MIC Freq. Test(ASR) (6) RTESN 19.07: Battery 1 Voltage. ADC (7) HT_CCMB 19.07: C/No (8) CCM_3in1 18.8: Check ALS brightness (lux) (9) CT 11.02: Sensor Temperature | 1. ATE battery pack current retry was 5.56% [Test point was polluted by flux. Olathe EE will move the via out of VBAT1] 2. FT - C/no 11.5% retry: Spec issue and been modified PR1 - Golden sample tolerance been ignore, found this issue during build and EE update spec to resolved. [Closed] 3. CCM 3in1 15.38% - It was caused by iridium & non iridium spec not be separate. No retry issue after separate iridium & non-iridium spec. [Closed] 4. IR-led retry issue 14.1%: Same as yield part, power supply had been modified in PR1 and keep monitoring in PR2 - Checkpoint 09/M. 5. VT1 &2 : VT program show PASS but ITMXP show fail. PDO & PE had modified VT program before PR2, plan to update more test data after 08/25 (PR ASSY). PR2 : All ASSY test item retry rate had reduced and lower than 10%. | NPI | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-22 19:54:36.1318638 +08:00 | 1
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk not meet the target <1.33 1.SMT_mainboard (1) Battery 1 Voltage.ADC: 1.18 (2) Ext Voltage.ADC: 0.74 2.ASSY (1) RT_C/No: 0.55 (2) CCM 3in1_ALS brightness(lux): 0.4 (3) Iridium_Tx CH120 by Ref: 1.03 (4) Iridium_Iridium Tx CH240 by Ref: 0.95 (5) FT_C/No by ref (Idle): 0.66 | Please refer to retry & yield - mitigation plan. All action been implement in PR2 , and plan to update Cpk by 09/M. | NPI | 2021-09-23 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Total 14 items not defined the VIP on FA system (011-05054-17/011-05097-A0/011-05186-00/115-03291-00/115-03292-00/145-03260-XX/320-00629-13/700-00112-15) | Had checked with MME, we plan to finish turn A by the end of Aug and finish FA in the middle of Sep. | MFG ME | 2021-09-14 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero G1(s) SatCom Scouting Camera | GMLA #3 | 2021-08-12 08:51:39.0951456 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 81%. 21 items are still under FA progressing. | Plastic Molded Parts 145-03260-00/40/41/20/90/B0/10/50/60/A0/30/70 : There would be a design change after PR2 build, so drawing release is delayed. We plan to release A before 10/E and complete FA before 11/E | MFG ME | 2021-11-29 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Alpha Dog Collar | GMLA #1 | 2022-01-07 14:39:33.8084448 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain Gauge measurement did not start yet since the router fixture is not ready. Wait tooling part ready and begin to verify the screwing strain. | De-panel measurement: Wait to verify the router fixture Screwing measurement: Wait to verify the tooling case. | PQE | 2022-04-28 16:00:00.0000000 +00:00 | 2022-03-03 13:27:49.1535570 +08:00 | 1
1 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Product validation | 3.B-7 | CC test plan is ready for MP | LAB need to establish the CC test plan | Lab had finished CC plan setting on 02/02 | TWN Lab | 2021-02-01 16:00:00.0000000 +00:00 | 2021-02-06 06:46:06.9566667 +00:00 | 1
1 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | 1 test item is not completed. Accelerated weathering xenon is testing. Plan to finish the ELOT on 2/8 | Q sun is ongoing and plan to finish on 02/09 | TWN Lab | 2021-02-08 16:00:00.0000000 +00:00 | 2021-03-29 15:27:07.2936662 +08:00 | 1
2 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%: ATE (Antenna) 22.07% / ATE (MB) 10.54% / CT 35.35% / Gyro Cal 10.53% / Glue 11.9% / VT 13.1% | Base on PR build result, this issue still open. Need monitoring in next job order. (1st MP) CT : Plan to change high-power soldering iron and re-training OP. [Tracking small build result - Had finished all training & test in WK12] ATE : Had modified ATE fixture (Pin length ) after PR, and verified 5pcs cycle test all passed (lower limit sample) Glue & VT issue : Had reset glue volume spec and need monitoring 1st MP glue result. | NPI | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
1 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | CPK < 1.33: CT C/No & HT C/No | Base on PR build result, this issue still open. Need monitoring in next job order. (1st MP) Need keep monitoring "Yield & retry " relate action implement result. No plan to modify any spec for now. | NPI | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
1 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Others | 3.F-1 | Direct labor -- Training has been taken within schedule and should be completed before MP -- (AOEM) Update Training Matrix if any new training requirement from CFT/ customer -- (AOEM) The record should be updated in HR system | Need to train the direct labor for soldering process before MP | igh power soldering training is not finish yet. Plan to finish all training on 02/08 | NPI/PQE | 2021-03-07 16:00:00.0000000 +00:00 | 2021-03-29 15:29:36.0969811 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | FA parts below will be completed before MP 290-00042-00 290-00075-00 291-00179-00 291-00179-02 | 290-00042-00 290-00075-00 291-00179-00 291-00179-02 All turned to Rev.A | MFG EE/ME/DE |  | 2021-08-23 10:36:48.2778469 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | Need to provide the information of verification report | PDO fixture verification report as attached | PDO/AE |  | 2021-08-23 22:41:16.8683283 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-14 | Golden sample and bad sample preparation plan -- Sample Q'ty | Can't find sample preparation plan or any comment on PRweb | GPS/ALS/ECG/OHRM's Golden are at least 1 ready on WK14. | MFG EE | 2021-04-22 16:00:00.0000000 +00:00 | 2021-03-29 15:44:38.7363375 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | Retest rate : Low Power Mode Current (AVR) 3.82%, TP SW Version of CT(1.97%)/HT(0.82%)/RTESN(0.16%), Barometer Temperature (1.04%) | ATE: 1.) Fixture Alignment Improve 2.) Fixture USB Connection unstable 3.) Fixture Topgate Issue All will be fixed by PR Kickoff. OHRM: Shorten the wire length in fixture to reduce the distortion | MFG EE | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | Lens push-out force test is waiting for samples, can't judge if this item can catch design review meeting or not. | ME will provide the sample by the end of this week. ELOT Completed by 04-09 | TWN Lab | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process development | 2.C-1 | Any update of critical process/ equipment/ measurement method of special characteristics -- Special characteristics flow down from drawing/ top area concern -- ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ Displacement ruler -- Check if DFM report updated and prototype report for any process/ parameter change | Can't find SC(reflow, SPI and X-ray) in SMT process | Pls see the attached. The Flow Chart is revised | NPI | 2021-03-25 16:00:00.0000000 +00:00 | 2021-03-29 13:58:20.6867465 +08:00 | 1
2 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. ATE 25.35%_USB Connection 2. PRNP 22.57%_Turn current 4.215V 3. AUTO_CT 16.19%_Touch Panel Test s5 4. AUTO_HT 15.19%_Touch Panel Noise Test guard 5. AUTO_RT 10.35%_Charging status check/ Touch Panel Test touch 6. ALS_RT 20.07%_ALS Luminance (WLED ON) 7. RT2 22.07%_LTE Rx Value 8. DeformationVT(3atm) 27.91%_連續斜率異常_負壓 9. Airtight_table(5atm) 13.75%_變形量絕對值超出規格_常壓 10. AUTO_FT 12.37%_Battery Voltage 11. FT2 13.78%_Battery Voltage 12. FT3 15.59%_Different with Golden sample (Gop) 13. ST 38.81%_[Diff]Speaker 1000Hz 14. ALS_FT 21.36%_ALS Luminance (WLED ON) 15. ProdScan 46.23%_Check Battery Voltage | actions will verify in PR2 build on WK4 <SMT> ATE 25.35%_USB Connection –Closed Most of the ATE YR%/Retry% is caused by the unexpected LTE chip rework in PR <ASSY/TEST> AUTO_CT 16.19%& HT 15.19%_Touch Panel Test – Closed [Touch Panel Noise Test] Touch Panel Test retry. DE determined with Olathe for the limit spec setting and completed ALS_RT 20.07%_ALS Luminance (WLED ON) – Closed [ALS Luminance] caused by the fixture WLED pad dirty, had modified the fixture and resolved. RT2 22.07%_LTE Rx Value – Closed [LTE Rx Value/LTE CW Measure Band]: 1st time to test different LTE bands so the best limit spec. EE has completed the optimizing Deformation VT(3atm) 27.91% & Airtight table(5atm) 13.75% –Closed PE adjusted the test method to improve the rest rate by assembly the mic cap + tape. AUTO_FT 12.37%_ FT2 13.78%_ ProdScan 18.65%_Check Battery Voltage – Tracking PE added a charging station to boot the device, voltage need >3.86V. @Wang, Annie ST 38.81%_[Diff]Speaker 1000Hz – ongoing ALS_FT 21.36%_ALS Luminance (WLED ON) – ongoing Top 1. Product Scan _46.23%_ Check Battery Voltage Root Cause : MEE monitors the Unit battery power to avoid low power when it is shipped to customers and cannot be turned on Action : Add Charging Station between VT station and FT 1 station Evidence : Control Plan Top 2. ST 38.81%_[Diff]Speaker 1000Hz Root Cause : Speaker diaphragm is sucked on the speaker magnet after CC immersion and VT Action : Standing > 30 mins after immersion test / VT once testing ST station Evidence : Top 3. DeformationVT(3atm) 27.91%_連續斜率異常_負壓 Root Cause : The rest rate is abnormal by continuous slope Action : PE adjusted the test method to improve the rest rate by assembly the mic cap + tape. | NPI | 2021-11-04 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | 1. 5.2.10.1 Body and Wearable Chemicals NG 2. 5.2.9 Accelerated weathering UV NG There is no action plan for test fail items. |  | TWN Lab |  |  | 0
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | CPK<1.33 : SMT:Turn current 4.215V、VW1P8、Average Battery Current in Test Mode with GPS active ASSY: C/No、Touch Panel Noise Test、GPS_ (L1 only) by ref、Glonass_65 by ref、ALS Luminance (WLED ON)、Power Box Sampling (Avg_Avg)、Glonass_72 by ref、Glonass_78 by ref、LTE Rx Value、LTE CW Measure Band20、LTE CW Measure Band12、LTE CW Measure Band3、[Diff]Mic 1KHz amp. to dbfs、LTE CW Measure Band28 | actions will verify in PR2 build on WK4 <SMT> ATE 25.35%_USB Connection –Closed Most of the ATE YR%/Retry% is caused by the unexpected LTE chip rework in PR <ASSY/TEST> AUTO_CT 16.19%& HT 15.19%_Touch Panel Test – Closed [Touch Panel Noise Test] Touch Panel Test retry. DE determined with Olathe for the limit spec setting and completed ALS_RT 20.07%_ALS Luminance (WLED ON) – Closed [ALS Luminance] caused by the fixture WLED pad dirty, had modified the fixture and resolved. RT2 22.07%_LTE Rx Value – Closed [LTE Rx Value/LTE CW Measure Band]: 1st time to test different LTE bands so the best limit spec. EE has completed the optimizing Deformation VT(3atm) 27.91% & Airtight table(5atm) 13.75% –Closed PE adjusted the test method to improve the rest rate by assembly the mic cap + tape. AUTO_FT 12.37%_ FT2 13.78%_ ProdScan 18.65%_Check Battery Voltage – Tracking PE added a charging station to boot the device, voltage need >3.86V. @Wang, Annie ST 38.81%_[Diff]Speaker 1000Hz – ongoing ALS_FT 21.36%_ALS Luminance (WLED ON) – ongoing | NPI | 2021-11-04 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | In Queue: Blue x 27 items not completed. Female x 29 items not completed. Neutral x 25 items not completed. |  | TWN Lab |  |  | 0
2 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process development | 3.C-2 | Review Machine/ Fixture list and ETA (need to meet build plan) -- Schedule of any modification or adjustment can meet PR build -- (New equipment) Defined operation/ maintenance SOP and official release before PR | Need to follow the battery wire AOI equipment/fixture readiness->Due date: 1/4 | the AOI inspection equipment will verify in Asia PR2 & WW small build by 1/8. | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Material FA are not ready ME: 60% DE: 0% |  | MFG ME/DE |  |  | 0
2 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | 010-02403-00: There is no 174 been released | Need OLA helps to provide the 174-document | NPI | 2020-12-30 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process development | 3.C-4 | Update flow chart for PR build -- key characteristic should be included and must correspond with D/PFMEA | ASSY flow chart need to modify | Under Revise | NPI | 2021-02-19 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | ASSY SOP need to update | ESOP of MP Version will be complete by the end of WK Packing SOP (SP01033) 2020/1/29 released | NPI | 2021-02-21 16:00:00.0000000 +00:00 | 2021-02-22 02:01:01.0400000 +00:00 | 1
1 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | 500-02000-14 :60K Free Sample available but not yet approved to MP, waiting USA TI to update. | Action has implemented and have positive result in PR2, pls see the update in MP Checklist. SMT: ATE 30.12%->6.48% ASSY: RTESN 13.2%->8.1%/ RT1 18.9%->5.2%/ VT 10.0%->1.9%/ FT1 15.9%->4.7%/ FT2 12.0%->8.2% | NPI | 2021-02-07 16:00:00.0000000 +00:00 | 2021-02-22 02:03:11.7800000 +00:00 | 1
1 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Process validation | 3.D-7 | PR UPH/Capacity evaluation result review -- Action plan if UPH/ Capacity cannot meet latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | PUR gluing UPH lower than expected, need NPI PE to improve before MP | NPI PE is under investigation UPH improvement of PUR glue station. Base on the demand plan, the peak of weekly production plan is 200pcs. UPH 20 is barely acceptable but will cause labor costs higher than expected. Issue close - Base on latest ramp , this UPH won;t cause any issue. | NPI | 2021-02-25 16:00:00.0000000 +00:00 | 2021-03-29 15:25:05.4960489 +08:00 | 1
2 | Marine | MSC-10 [Marine Satellite Compass] | GMLA #3 | 2021-02-02 15:51:33.5706365 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | Yield rate < 97%. ASSY: CT 95.96% / Glue 84.52% | Base on PR build result, this issue still open. Need monitoring in next job order. (1st MP) CT : Plan to change high-power soldering iron and re-training OP. [Tracking small build result - Had finished all training & test in WK12] ATE : Had modified ATE fixture after PR, and verified 5pcs cycle test all passed (lower limit sample) | NPI | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | Preliminary 174-00471-00 document cannot be released for PR. (NRL) | 174-00471-00 can be released following 013-00916-00 being approved on 1/18 if no further concern. [Robben] Released on 1/5, IR#134996 | NPI | 2021-01-21 16:00:00.0000000 +00:00 | 2021-01-25 01:11:19.7200000 +00:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT is not completed. -Test: 2 -In Queue: 41 | Estimate completed on 1/25 if the carry cases arrive TW on 1/11 in time. [2/2] 2/2 Completed | TWN Lab | 2021-01-24 16:00:00.0000000 +00:00 | 2021-02-02 04:25:37.1300000 +00:00 | 1
3 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Two issues with red light. Both are related to unit SW, need to be reviewed by design team. | Two red light issues are mainly addressed high retry caused by not mature SW and App. Waiting for new SW and App release. [Robben] The design team plans to release SW and APP in the end of Feb and fix for the factory issue, [Robben 4/14] No NG occurred in PR2 with new APP and new SW released. | NPI | 2021-02-27 16:00:00.0000000 +00:00 | 2021-04-14 09:13:14.0885293 +08:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Since FA is not complete, 21 items not release IQC VIP | Temp VIP were uploaded on FA system 145-03299-00/20 are waiting Ola release new drawing for FA, FA due date 1/18 145-03299-60/70 145-03347-00/10 and 011-05157-40/50 are waiting Supplier upload FA documents, due date 1/18 | MFG EE/ME/DE | 2021-01-19 16:00:00.0000000 +00:00 | 2021-01-11 02:53:57.8933333 +00:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 105-03985-00 of version A does not decide for the next build. | Compliance concern blocks PCB risk buy. Discussed with the design team, we decided to preparing PCB raw material in advance and wait for compliance result. | PID | 2021-01-30 16:00:00.0000000 +00:00 | 2021-06-02 09:12:42.3364951 +08:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Total 24 ME parts is progressing, completed rate is 59% >> 011-05157-xx/145-03299-xx/145-03347-xx | Remaining 6 ME parts is progressing, will be done by 1/29 | MFG ME/DE |  | 2021-03-17 07:45:41.3866667 +00:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process development | 2.C-4 | Release preliminary flow chart for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Can't find SC(reflow, SPI and X-ray) in SMT process | Pls see the attached. The Flow Chart is revised | NPI | 2021-03-25 16:00:00.0000000 +00:00 | 2021-03-29 13:58:28.8935748 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | 015-05163-2X / 3X need to confirm by PR PV result | all in Rev.A | MFG ME/DE |  | 2021-08-23 10:30:26.2146661 +08:00 | 1
1 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | See reference 1. 002-S0009-04 is NRL 2. 29 items not update to A Rev. | 006 SW haven't turn A | NPI/ME/DE |  |  | 0
2 | Fitness | Bounce(Waldo) | GMLA #3 | 2021-07-12 22:50:02.1827203 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04016-00 cannot be finalize | 1. 006-SW related 2. 234-00381-00 spring bar turned 0A 3. 007/190 – Package related turned 0A 006 SW, Kid Tracker, LTE Modem - ongoing (5/4) | MFG ME | 2022-03-30 16:00:00.0000000 +00:00 | 2022-05-04 09:27:12.8279311 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | "PRNP" is on-going, "Screw" and "press connector" is NG but we plan applying underfill on NG component. | Fail: I800, I801, I706, we will apply underfill to robust adhesive strength of NG components | PQE |  | 2021-03-29 17:05:15.7615812 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-16 | Process outsourcing parts evaluation result -- Cpk/ yield rate/ UPH data should be ready | Can't find result or any comment on PRweb | Pls see the attached for FFP rear case VT test data. (Black 1st Yield: 81.78% / White 1st Yield: 97.08%) | MFG ME/DE | 2021-03-18 16:00:00.0000000 +00:00 | 2021-03-29 14:54:37.3628134 +08:00 | 1
3 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | Need 174 packing instruction to update the packing SOP. | 174-00531-00 is add. | NPI |  | 2021-01-26 00:51:57.9100000 +00:00 | 1
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | 190-02515-95 is NRL. | Release on 01-20, version A | NPI |  | 2021-01-26 00:51:15.3566667 +00:00 | 1
2 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | High retry rate, but with actions. ASSY:CH 29%/HT 21%/FT1 31%/Airtight 21%/RT2 61%/RT1 22%/Baro 15%/iFT2 38%/Product scan/DeformationVT_Configuration1 25% SMT: 35~56% | Action take but still not reach the target, working with OLA in current, weekly track. | NPI | 2021-03-11 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | SMT&ASSY Cpk>1.33, but with action. LCM Cpk: Need NPI to release it. | Action take but still not reach the target, working with OLA in current, weekly track. | NPI | 2021-03-11 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | Need 174 packing instruction to create the Packing SOP. | Need OLA helps to provide the 174-document for PACK SOP define | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | SMT >100V: PRNP tester ASSY >100V: Screwing fixture、press Batt. | SMT: Revise the upper case raw material and pass. ASY: Revise and pass on 01-22 | PQE | 2021-01-21 16:00:00.0000000 +00:00 | 2021-01-22 02:03:40.4666667 +00:00 | 1
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Need to apply the strain gage test for Lid assy process. | estimate to complete by 1/4 | PQE | 2021-01-03 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | High retry rate(>10%), but wuth action. SMT 31.24%/RTESN 16%/Button 22.4%/CT 13%/HT 14%/10 ATM 76%/FT1 88%/FT2 28.5%/FT3 31%/G sensor 21%/M sensor 24%/Gyro 14%/Baro 15%/Felica 25% | the retry actions/analysis as table below, will update the Asia PR2 verification results. | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | EE have added comments in CPK report. | the retry actions/analysis as table below, will update the Asia PR2 verification results. | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | ASSY: Screwing fixture and conn pressing fixture->Screwing fixture > 100V and need to use the antistatic material. | Confirmed the fixture material is antistatic, Pre-MP/MP will implement the antistatic-fans and define to the SOP for improvement. | PQE | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Red light: Battery wire found damage after ELOT Action: 1. SOP defined the OP battery wire fix method 2. Implement the new PCB screw manual fixtures 3. ME is confirming with the vendor to combine two battery wires stick together | [MP Action#1] : implement the AOI inspection to inspect the wire position which to decrease the risk. [Long Term] : moving the battery connector down and modify the gap(need > 1.4mm from the edge of the PCB. [MP Action#2] : TWN MME/PE provided a suggestion for the ASSY method which to add a foam as a spacer (Please OLA team helps to comment) | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate 37%: 61 item open. | The current completion rate is raised to 53%, MME-Albert will reach 100% before 2021/1/5 | MFG ME/DE | 2021-01-04 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent Mk2s | GMLA #3 | 2020-12-29 05:56:20.5830000 +00:00 | Supply chain/ supply of part | 3.E-12 | Incoming raw material quality from supplier | Material issue: R/C Screw stripped (fail rate is 4~7% ) | [Action] : vendor quality improvement(The screw hole depth is 0.5mm longer than the drawing)/ set the vendor VIP inspection SOP | MFG ME | 2020-12-30 16:00:00.0000000 +00:00 | 2020-12-24 15:51:19.1670000 +00:00 | 1
1 | Marine | GT36/GT56 UHD Transducers | GMLA #1 | 2020-12-03 18:26:36.2100000 +00:00 | Product development | 1.A-1 | Release TWN strategy review document -- Special characteristic should be included -- Top Design Concerns (TDCs) -- Top Manufacturing Concerns (TMCs) | 456 |  |  |  |  | 0
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | Preliminarily OOB checklist did not release before PR | OOB released on 1/26 | PQE | 2021-01-25 16:00:00.0000000 +00:00 | 2021-01-28 15:34:29.4100000 +00:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | BOM structure review: 211-73160-60 should be added one more. | One screw and one tape still need to be added [2/2]ECO#217403 | NPI | 2021-01-24 16:00:00.0000000 +00:00 | 2021-02-02 04:26:20.3233333 +00:00 | 1
2 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | APP is not mature and caused high retry (>30%) at radar chamber | Most of high retry resulted from not steady SW and App. Still wait for the new SW and new App release and we will prepare about 30 PR units for validation before preMP. [Robben] The design team plans to release SW and APP in the end of Feb and fix for the factory issue, [Robben 4/14] No NG occurred in PR2 with new APP and new SW released. | NPI | 2021-02-27 16:00:00.0000000 +00:00 | 2021-04-14 09:12:12.6002679 +08:00 | 1
1 | Outdoor | Approach R10 | GMLA #3 | 2021-01-04 17:41:21.9583607 +08:00 | Supply chain/ supply of part | 3.E-12 | Incoming raw material quality from supplier | 011-05157-10/011-05157-20 Appearance issues need continuous improvement | paint masking fixture for 011-05157-10 have been improved, the scratch should be eliminated on next incoming material | MFG ME | 2021-01-07 16:00:00.0000000 +00:00 | 2021-01-11 02:54:36.8566667 +00:00 | 1
3 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | Need to take action for below E-lot fail items: Drop fail/Tumble fail/Water boiling fail/Body and wearable chemicals fail/TST fail | 1.) ILP Fail after Tumble: Waive: The coating of rear case lens is damaged, same prcoess/thickness as other model. 2.) Unit abnormal power on/off: Closed, will have underfill glued. | TWN Lab | 2021-01-21 16:00:00.0000000 +00:00 | 2021-01-22 01:19:49.3800000 +00:00 | 1
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process development | 3.C-4 | Update flow chart for PR build -- key characteristic should be included and must correspond with D/PFMEA | Need to flow down the Special characteristic of DFM to assy flow chart. ASSY critical process: A2.1/T6 | Revise and re-upload the document on 12-28 | NPI |  | 2021-01-26 00:52:25.4233333 +00:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Product development | 2.A-1 | DFM report_ product design related -- Special characteristic should be included | Can't find SC(reflow, SPI and X-ray) in SMT process | Pls see the attached. The Flow Chart is revised. | NPI | 2021-04-22 16:00:00.0000000 +00:00 | 2021-03-29 13:54:33.7063539 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | Olathe SW has passed new SW patch(006-B3906-00). SW issue will be tracked at next build. | SW released by 2/22, ECO#219469 | MFG EE | 2021-02-21 16:00:00.0000000 +00:00 | 2021-03-02 05:35:42.0866667 +00:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | There are some test undergoing. All the test will be finished until 1/17. | ELOT complete by 1/18 | TWN Lab | 2021-01-17 16:00:00.0000000 +00:00 | 2021-01-28 01:15:52.1166667 +00:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #3 | 2021-07-30 11:18:06.1672588 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | Not version A 011- *9 117 - *3 145- *3 161- *1 250- *1 |  | NPI/ME/DE |  |  | 0
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | IQC fixture is not ready due to FA not completed. -145-03249-14 -145-03249-15 | Plan to complete on WK5 | MFG EE/ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA are not ready: ME 91% | 100% in current | MFG ME/DE | 2021-02-19 16:00:00.0000000 +00:00 | 2021-02-22 02:04:06.8600000 +00:00 | 1
2 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% but with action plan to improved SMT: AutoATE ASSY: RTESN、RT1、VT、FT1、FT2 | Action has implemented and have positive result in PR2, pls see the update in MP Checklist. SMT: ATE 30.12%->6.48% ASSY: RTESN 13.2%->8.1%/ RT1 18.9%->5.2%/ VT 10.0%->1.9%/ FT1 15.9%->4.7%/ FT2 12.0%->8.2% | NPI | 2021-02-19 16:00:00.0000000 +00:00 | 2021-02-22 02:02:37.3900000 +00:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 1. Screw main board (I900 failed): Under discussion. 2. Lid pressing(I900 failed): NPI will modify the fixture before next build. | - I900 screw main board: no related issue on PR build. After aligned with CFT in close meeting. This issue can be closed. - lid pressing: strain test PASS on 2/23 | PQE | 2021-03-09 16:00:00.0000000 +00:00 | 2021-05-19 13:00:12.7770891 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Ant Power Cpk < 1.33 with action plan. | Fixture verified in PR | NPI | 2021-03-29 16:00:00.0000000 +00:00 | 2021-05-19 13:00:48.5015825 +08:00 | 1
1 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan to improved ASSY: GIONASS、C/No by Ref | Action has implemented and have positive result in PR2, pls see the update in MP Checklist. | NPI | 2021-02-19 16:00:00.0000000 +00:00 | 2021-02-20 00:46:48.2333333 +00:00 | 1
3 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | one Red light issue:High retest rate due to C/N test items. | EE修改測試程式，多下一次Command與貼軟泡棉固定FPC，已於PR2試跑中途修正. 18.9%->1.8% | NPI | 2021-02-21 16:00:00.0000000 +00:00 | 2021-02-22 02:00:03.5400000 +00:00 | 1
1 | Fitness | Venu 2S | GMLA #3 | 2021-01-27 23:32:09.6877308 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | PPAP/ FA of all ME parts will be completed before MP | All the version of BOM is in MP phase. | MFG EE/ME/DE | 2021-02-19 16:00:00.0000000 +00:00 | 2021-02-20 00:47:31.1866667 +00:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | The upper lid of PRNP jig will be changed to another material. | The jig has been verified & pass on 1/12 | PQE | 2021-01-11 16:00:00.0000000 +00:00 | 2021-01-14 05:14:49.0900000 +00:00 | 1
1 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | The upper lid of PRNP jig will be changed to another material. | The jig has been verified & pass on 1/12 | PQE | 2021-01-11 16:00:00.0000000 +00:00 | 2021-01-14 05:14:55.6900000 +00:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product development | 2.A-13 | Unit/ Accessory: Test coverage rate evaluation (Target: 90%) - Base on customer requirement to evaluate test coverage rate - If no special requirement, base on 004- MPS to evaluate test coverage rate | Need further update for D sample |  | EE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | Add Q to control plan |  | MFG ME |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | Follow up |  | PQE |  |  | 0
2 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | Preliminary 174- document cannot be released before PR | Pls refer to the BOM of 010-02383-01 The 174 is add in the BOM. | NPI |  | 2021-01-26 00:34:44.9833333 +00:00 | 1
3 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | Test coverage rate hasn't been evaluated | 100% of draft, design team will released the final version by the end of next week. | MFG EE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT is not completed but can be finished before design review meeting. In Queue: 6 items | All PR 4 SKUs complete on WK4, refer to LMS0007127-2 | TWN Lab |  | 2021-01-26 01:04:18.2300000 +00:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-14 | Golden sample and bad sample preparation plan -- Sample Q'ty | Comment as feedback |  | MFG EE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | Follow up |  | PID |  |  | 0
1 | Fitness | Venu 2 Plus | GMLA #3 | 2021-07-30 11:18:06.1672588 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 79% DE 20% |  | MFG ME/DE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Supply chain/ supply of part | 2.E-6 | Key flows agreement by Garmin and new supplier -- Change management flow by supplier -- Change management flow by customer | Responsible by Olathe SS |  | SS |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Supply chain/ supply of part | 2.E-9 | Review critical parts 長期供貨合約 to make sure parts supply stable -- Base on latest critical parts list (in MPM system) | Update after design fixed |  | SS |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Supply chain/ supply of part | 2.E-11 | Customer requirement of safety stock flow down -- Product safety stock -- Material safety stock | Under discussion |  | BD |  |  | 0
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 6 items haven't been version A | 3 items are housing, already A-rev. 3 items are HRM shielding tape relevant (249-01448-xx), already A-rev. | MFG ME | 2021-07-01 16:00:00.0000000 +00:00 | 2021-07-13 09:31:34.4522768 +08:00 | 1
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | A 98%: 145-03249-14/15: Not completed and will finish in two weeks. | Plan to complete on WK5 | MFG EE/ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | MPS haven't updated to version A in 5/5 | TWN EE has provided expected spec for vevA MPS by 5/21, Test coverage will be updated after verA MPS released (ECO#224113). | MFG EE | 2021-05-20 16:00:00.0000000 +00:00 | 2021-06-02 11:36:27.0714422 +08:00 | 1
1 | Fitness | Forerunner 945 LTE | GMLA #3 | 2020-12-28 06:50:47.7870000 +00:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA 98%: 145-03249-14/15: Not completed. | Plan to complete on WK5 | MFG ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | Test coverage achievement: 75% Olathe will review the test yield distribution to revise MPS sepc | Ver.A MPS released (ECO#224113) on 6/2. All test items are validated and covered by the latest MPS. | MFG EE | 2021-07-01 16:00:00.0000000 +00:00 | 2021-07-13 09:31:50.5305199 +08:00 | 1
3 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | Can't find clean room sop on PRweb in 5/5 | CR SOP updated on 5/5 | NPI | 2021-05-04 16:00:00.0000000 +00:00 | 2021-05-10 15:31:05.7851700 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | (10,39,2) IOP can’t remove the test mode, WW SW v2.13 manifest are different from BOM | IOP (10,39,2) issues has been resolved by adding the IOP (10,1486,2) in the PACK station. Manifest issue was caused by SW ECO#218462 on the timing of PR SMT. | NPI/PQE | 2021-05-04 16:00:00.0000000 +00:00 | 2021-05-10 15:31:24.8373163 +08:00 | 1
1 | Fitness | Venu 2 Plus | GMLA #3 | 2021-07-30 11:18:06.1672588 +08:00 | Product validation | 3.B-11 | CC test result | 1. immersion NG (7/60) 2. re-test ST NG (4/60) | 1. immersion NG (7/60) > overweight root cause : muti-waterproof interface malfunction Action : Olathe have agree to lower spec from 5 bar to 3 bar maximum. 2. re-test ST NG (4/60) > ST NG in 5k & 7K Root cause : membrane can't fully recovered before ST. Action : Define curing 50°C/1hr + standing in room temp 8 hrs before ST. Validation : 4 units passed ST after action introduced | PQE |  | 2021-07-30 14:14:36.2085067 +08:00 | 1
2 | Fitness | Venu 2 Plus | GMLA #3 | 2021-07-30 11:18:06.1672588 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ASSY 1. AutoHT - 16.96% - Glonass_78 2. FT2 - 14.14% - (DAC Calibration) DAC1_24uA 3. G-sensor - 34.44% - ECG impedance short | 1. G-sensor - 34.44% - ECG impedance short [Problem] test result out of LSL (95K~200K ohm) [Root cause] Environment noise affect test reading [Action] Introduce USB isolator to filter noise 2. AutoHT - 16.96% - Glonass_78 [Problem] test result are 20~30db (LSL : 30db) [Root cause] spec and real performance are mismatch [Action] Shift LSL from 30 db to 20 db 3. FT2 - 14.14% - (DAC Calibration) DAC1_24uA [Problem] Test program didn't receive return value from DUT [Root cause] Test program waiting time is too short (0 sec) to receive return value from DUT [Action] Extend delay time from 0 sec to 0.5 sec [Validation] Fix bug immediately in 7/6, rest of DUTs passed test | MFG EE |  |  | 0
1 | Fitness | Venu 2 Plus | GMLA #3 | 2021-07-30 11:18:06.1672588 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. conducted glonass _78 0.94 2. Low power mode current 0.36 |  | NPI |  |  | 0
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | Can't find Instruction menu- 190-02837-90/190-02837-91, can’t see the 174-document for 010-02540-31 and -39 | 190- are released in 9/13 174- have been released. | NPI | 2021-07-06 16:00:00.0000000 +00:00 | 2022-03-21 13:58:46.8878012 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process validation | 3.D-5 | Check verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine -- Action plan if verification result fail | Cpk of lens rotation angle < 1 | No fail ever happened for all Fenix 7 series due to this issue. Confirmed the spec of rotation angle between HRM lens and rear cases within 2 degree is acceptable. | NPI | 2021-05-30 16:00:00.0000000 +00:00 | 2021-06-23 17:57:30.7881194 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA complete rate 36% | FA complete rate: 94%, housing, and watchband FA on-going. @Lin, Philip FA complete rate: 100% in 5/13 | MFG ME | 2021-07-29 16:00:00.0000000 +00:00 | 2022-03-21 14:13:19.6351855 +08:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Others | 2.F-3 | Define skill requirements (defined in WH000005) of each station | Follow up in D sample |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | AA equipment not done |  | PQE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product development | 2.A-1 | DFM report_ product design related -- Special characteristic should be included | Please input CC/SC |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | Top 20 issue tracking |  | MFG EE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product development | 2.A-11 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004-not yet released to BOM |  | EE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | Check |  | TWN Lab |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-1 | Any update of critical process/ equipment/ measurement method of special characteristics -- Special characteristics flow down from drawing/ top area concern -- ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ Displacement ruler -- Check if DFM report updated and prototype report for any process/ parameter change | comment as feedback |  | NPI |  |  | 0
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | USB Connection NG due to SW issues, host SW after 4.01 may resolve it | Confirmed as SW issue, update to SW 4.01 and verified OK. | MFG EE | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-19 11:27:10.5053664 +08:00 | 1
3 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | 1. Accelerated Weathering UV fail (2/4 NG): Discolor case 2. Tumble fail (6/7 NG) 3. Button focused drop test fail (11/12 NG) | 1. Accelerated Weathering UV (2/4 NG):ID has accepted the amount of discoloration seen in these test samples. 2. Tumble fail (6/7 NG), crack on LRA FPC: 10 pcs units validated PASS after adding gluing. 3. Button focused drop test (11/12 NG): Olathe waive this issue and decide to use orignial spring. | TWN Lab | 2021-07-01 16:00:00.0000000 +00:00 | 2021-07-02 11:44:47.0786494 +08:00 | 1
2 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | ClickTest 94.09% (Button4_Stroke 5.43%) | EE have comment this item is only for reference in PR phase, MP will not introduce this test item. | NPI | 2021-05-04 16:00:00.0000000 +00:00 | 2021-05-10 15:32:46.6704047 +08:00 | 1
2 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. AutoATE 28.18% (Solar charging current 4.97%) ASSY 1. RTESN 15.94%(Get LCM Job Result 4.37%) 2. CT 22.12%(Battery temp 9.53%) 3. HT 11.18%(Beidou by ref 3.07%) 4. Airtight 19.23%(負壓7.91%) 5. FT1 29.76%(VEXT Current 18.03%) 6. FT2 32.52%(ANT_Power 8.57%) 7. FT3 10.73%(LRA calibration 3.58%) 8. Gyro 14.49%(Check Baro Test Data 2.02%) 9. Solar 11.13%(Average VSOL 2.42%) 10. prodscan 60.72%(Manifest Check - maponly 7.53%) | 1. Product scan(60.72%) “Manifest Check - maponly” (7.53%) Root cause : DUT SW(ver.8) and Test SW (ver.9)(ECO#219551, 3/11) are mismatch Action plan : Both version will match each other in next build. 2 .FT2(32.52%): “ANT_power” (8.6%) Root cause : The frequency of antenna is 2.3G Hz, can't meet target 2.4G Hz. Action plan : Shorten the length of antenna to meet 2.4G (ECO#221478, 4/1), EPIX2 validation completed and antenna length finalized. 3. FT1(29.76%) “VEXT Current” (18.03%): Root cause : Battery is almost full so charging current is lower than lower sepc limit Action plan : Add "charging complete" page (in 3.95V) and show it on display to prevent battery overcharging Above actions will be implemented and verified in preMP. | MFG EE | 2021-09-16 16:00:00.0000000 +00:00 | 2022-03-21 14:45:17.0433893 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Items are applicable for Cpk: Fenix7_Solar_HT GPS_L5 Cpk 1.02 | 1.GPS related: Have reselected new golden sample and will verify in preMP. @Huang, Sam(EE) 2. Current related: Ver.A MPS released (ECO#224113) on 6/2. Spec reviewed without issues. Will verify in preMP. @Huang, Sam(EE) Bezel laser etching area shifted cause GPS_L5 poor performance, bezel supplier had add fixture and mylar to detect any shift. | MFG EE | 2021-09-16 16:00:00.0000000 +00:00 | 2022-03-21 15:06:03.6016866 +08:00 | 1
1 | Outdoor | fenix 7 | GMLA #3 | 2021-05-05 13:20:06.7452102 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Housing delayed due to the new supplier tooling instability. Have changed back to the original supplier for PR build as mitigation plan, but still causing sub-assy material (-3x) ~1 week delay. | The supplier (JGP) housing has been validated on EPIX FFP2 build without issues. | MFG ME | 2021-05-20 16:00:00.0000000 +00:00 | 2021-06-23 17:56:47.8106440 +08:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-3 | (AOEM) Release preliminary PFMEA / (Consumer) DFM report_ process review for FFP build -- Special characteristic should be included and must correspond with D/PFMEA -- Poka-Yoke/ LL should be taken into account in PFMEA -- Ergonomically designed (人因工程設計) should be taken into account to all work station | Some specs in c/r PFMEA are still missing |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-4 | Release preliminary flow chart for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | comment as feedback |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-6 | Release preliminary control plan (v001) -- Special characteristic should be included and must correspond with D/PFMEA -- (AOEM) Regular requalification should be included | Need further updates in D sample |  | PQE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-8 | Define traceability resolution -- SMT traceability resolution (By panel/ by SO#) -- Critical parts/ Sub process (EX: LCM/ PCBA)/ Accessories -- Production program setup should be finish before FFP (ex: MES/ Line controller/ ITMXP testing/…) | Follow up |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-2 | MSA test plan update (Focus on any change that need to re-do MSA) -- Refer to control plan "measurement system" (TQ0263) -- Chang of key characteristics -- New machine/ critical process (Defined by customer or RD/PE/QA/EE) -- Line transfer | Need further updates in D sample |  | PQE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-4 | MSA result check and action plan for fail item or no MSA test base on latest test plan | Follow up |  | PQE |  |  | 0
3 | OEM Auto | PGWW20 | GMLA #3 | 2021-09-07 10:19:55.9010593 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | 如MPM所回覆前殼模具將移往新供應商試模，並確認是否可達到新規格要求 | Verify OOB of "新模達產審核" 9/30 build, the 新模 DTS result meet the customer requirement. | NPI | 2021-09-06 16:00:00.0000000 +00:00 | 2021-09-08 13:55:10.6803586 +08:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Others | 2.F-5 | Recycle container review -- How many containers are needed according to latest forecast -- How are the containers maintained, repaired, and replaced | No related discussion |  | NPI |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Others | 2.F-7 | Product logistic flow has been set up internally -- Need to include escalation flow or mechanism | Need TWN MPM comment |  | Logistic |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Others | 2.F-8 | Customer complaint (0km/ field) process have been defined and agreed with customer -- Claimed parts return flow -- Complaint refund flow -- Test rack setup in customer side or oversea office | Closed |  | PQE |  |  | 0
1 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process development | 2.C-6 | Release preliminary Control Plan (v001) -- Special characteristic should be included and must correspond with D/PFMEA -- (AOEM) Regular requalification should be included | CP is not ready | Plan to finish CP before 06/04 | PQE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-22 18:58:45.4287955 +08:00 | 1
1 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No max. peak temp definition (1) 012-04060-00: 575-00056-00 / 500-01757-C3 / 330-01845-00 (2) 012-04060-D1: 500-01757-C2 | After checking with OLA EE, the max temperature setting will be 260C. Need update in system. | NPI | 2021-06-02 16:00:00.0000000 +00:00 | 2021-06-22 18:57:07.5211768 +08:00 | 1
1 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Camera: CPK < 1.33 1. 6 Direction confirm items (0.49 ~ 0.83) 2. Max Angle Error and HTMTF | Same issue with retry rate items- Please refer to the above column. Need SW update in FFP2. @Lee, Frankie [Not fixed in FFP2, waiting for next SW update] | NPI | 2021-07-29 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ ASSY/ LCM) -- Measurement position and result | Fixture ESD measurement is incomplete | Due to WFH, PQE will back to office and plan to finish fixture ESD validation on 06/09 | PQE | 2021-06-08 16:00:00.0000000 +00:00 | 2021-06-22 18:55:39.0230493 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 2 items testing: Power off Current Draw/Supply Voltage Dropout 32 items are not started: Salt Fog/Water /Dust Resistance...etc The expected complete date:2021/7/17 | <update 7/20>目前 LAB 部份 已經完成 91.84 % ，剩下化學 和 UV的測試還在進行 https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=14215&phaseId=19535&location=TW <8/4> All completed | TWN Lab | 2021-07-25 16:00:00.0000000 +00:00 | 2021-08-04 11:40:11.1885622 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 012-04233-00 Peak temperature review: 492-00008-07/717-00023-04 no component temperature | Both 492-00008-07/717-00023-04 are updated. | NPI | 2021-06-30 16:00:00.0000000 +00:00 | 2021-07-01 21:00:18.8786346 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk not meet the target <1.33 1.SMT_ATE (1) ANT Conducted Output Power (ch39) Diff: 0.8 (2) ANT Conducted Output Power (ch78) Diff: 0.98 (3) Iridium Tx Burst CH01 diff: 0.91 (4) Iridium Tx Burst CH120 diff:0.85 (5) TCXOVDD(1.2&1.8V): -0.88 (6) Iridium Tx Burst CH240 diff: 0.83 (7) CNo GPS 16: 0.88 2.ASSY (1) HT: C/No by ref: 1.24 (2) FT1: C/No by ref: 1.56 (3) FT1: BT 中頻測試¦BT CW Medium: 0.86 (4) FT1: BT 高頻測試¦BT CW High: 0.77 (5) FT3: Iridium Tx CH01 by Ref: 0.87 (6) FT3: Iridium Tx CH120 by Ref: 0.78 (7) FT3: Iridium Tx CH240 by Ref: 0.67 (8) FT3: Iridium Rx RSSI dBm diff: 0.99 (9) Compass: Heading AVG: 1.04 | 1.SMT_ATE (1)(2) 2G4 antenna modification in next versionis still not confirmed by Yarmouth. (3)(4)(6) It was related to 012-03302-00 production.Not much we could do in IRmini2 ATE unless Yarmouth EE agree to modify upper limit or provide new golden sample. (5) component date code issue.we already isolated all 2016 date code components from warehouse. (7) The distribution seems ok. Will modify the golden sample cal CN for better CPK. 2.ASSY (1)(2)The CN offset due to temperature is acceptable.Also the fixture of CTHTFT1will be modified to get more stable test result. (3)(4)2G4 antenna modification in next versionis still not confirmed by Yarmouth. (5)(6)(7)(8) FT3 used old power box-->fixed. FT3 fixture modification --> wait for assy PE. (9)Acceptable. | MFG EE | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-29 20:09:34.9583543 +08:00 | 1
1 | Outdoor | Instinct 2 | GMLA #2 | 2021-05-11 17:37:50.9132378 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Critical test items : VAFE 0.4 Critical station : LCD/solar panel thickness 0.72, Lens/display thickness 0.79 | "Critical test items : VAFE 0.4 >> <VAFE>4 polars in the distribution. However, retry < 1%, keep monitoring. In PR build, 2 polars showed because 2 kinds of battery setting. The distribution is relative concentrate. Should be low risk. Critical station : LCD/solar panel thickness 0.72, Lens/display thickness 0.79 >> Introduce floating fixture to cover the material tolerance" | MFG EE | 2021-07-08 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Instinct 2 | GMLA #2 | 2021-05-11 17:37:50.9132378 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | We saw shortage risk on Ti components (500-01224-10/500-10415-00/500-10117-00) and the design team will submit alternative PCB without Ti component solution. This change will cause MP date shift to 8/9 for the time being. | The design team will issue alternative PCB with 012-04094-FK for PR (end of June) and MP (8/9). [5/27]Sufficient Ti parts are allocated with Alpha PCB to support MP on 8/9. | PID | 2021-07-08 16:00:00.0000000 +00:00 | 2021-05-27 19:43:27.7109795 +08:00 | 1
1 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | High risk to impact the MP due to PCB vendor extend LT & design team can't finalize MP PCB drawing in time. | PUR team had updated ETA and meet MP plan | PID | 2021-03-04 16:00:00.0000000 +00:00 | 2021-03-07 08:50:20.4600000 +00:00 | 1
1 | Marine | GT36/GT56 UHD Transducers | GMLA #2 | 2020-12-03 18:31:46.7200000 +00:00 | Product development | 2.A-5 | Design lockdown for critical parts (015- drawing include critical parts info.) -- Review all material in critical parts list -- Special characteristic should be included | [5 empty] | 0
1 | Marine | GT36/GT56 UHD Transducers | GMLA #2 | 2020-12-03 18:31:46.7200000 +00:00 | Product development | 2.A-6 | All ME parts should be tooled parts | [5 empty] | 0
1 | Marine | GT36/GT56 UHD Transducers | GMLA #2 | 2020-12-03 18:31:46.7200000 +00:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | [5 empty] | 0
1 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Product development | 2.A-10 | Verify the test program of SMT and ASSY station before FFP build for new SW release | IOP not supported items: 1. BIST 2. ACC/Gyro Sensor Static Test 3. Burn-in 4. ACC/Gyro RAW data 5. Green/Red LED status auto reported by IOP 6. Common IOP in normal mode (product request, get ESN, mode check.) 7. CCMW SW Issue: 1. unstable OCP test. 2. unstable image sensor test. 3. ACC/Gyro cal data missing. | Cause : SW issue Action : Add extra FFP2 and implement new SW of D3. Need keep tracking FFP2 test result. Validation owner : @Wu, Peter(EE) Start FFP2 : 06/01 Check point : 06/09 [Not fixed in FFP2, waiting for next SW update] RTESN + CT + HT : 1 working day Burn-in : 1 working day CCMW+ Distortion : 2 working days FT + ACC + Gyro : 2 working days | MFG EE | 2021-08-12 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GT36/GT56 UHD Transducers | GMLA #2 | 2020-12-03 18:31:46.7200000 +00:00 | Product development | 2.A-2 | Update critical parts/ Component list if BOM update -- Maintained in MPM system | [5 empty] | 0
2 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 20.8% - C/No GLONASS_78 ASSY 1. HT 14.88% - GlONASS 78 CNo by ref 2. FT3 17.21% - (4000Hz) dBSPL+A | SMT <Closed>ATE 20.8% - C/No GLONASS_78 Root cause : spec and chip performance mismatch Action : redefine LSL from 41db to 39db Validation : lower retry rate from 20.8% to 2.9% ASSY <Closed> 1. HT 14.88% - GlONASS 78 CNo by ref Root cause : solar SKU have different performance from non-solar SKU, but only one test program and test spec. Action : Divide test program into "Solar SKU" and "Non-solar SKU" featuring different test spec. <Closed>2. FT3 17.21% - (4000Hz) dBSPL+A >> test results out of USL Root cause : AE is still exploring test spec Action : USL move from 85db to 95dB | NPI | 2021-08-17 16:00:00.0000000 +00:00 | 2021-07-30 13:37:04.7420384 +08:00 | 1
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. Ship mode Current 0.42 ASSY 1. FT1 non-solar C/No by ref 0.42 | SMT 1. Ship mode Current 0.42 Root cause : current spec can't filter outlier Action : redefine test spec to 5~30uA. ASSY 1. FT1 non-solar C/No by ref 0.42 Root cause : golden sample is 1dB higher than medium of all units. | NPI | 2021-08-19 16:00:00.0000000 +00:00 | 2021-08-20 12:54:29.3146635 +08:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | Confirmed | PQE has provide OOB on 1/14 | PQE | 2021-01-13 16:00:00.0000000 +00:00 | 2021-02-03 08:34:05.5133333 +00:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | 190-02790-90 is NRL | 190-02790-90 is released before MP | NPI | 2021-01-13 16:00:00.0000000 +00:00 | 2021-02-03 08:34:34.0500000 +00:00 | 1
2 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate did not meet target but with action plan to improved SMT: ATE、Multiupdater >10% ASSY: FT1、iFT2 > 10% | SMT: Multi updater retry 10.4% Monitor > USB Update 6.6%, The packet size set as default (996) to increase the programming time. Testing suggests the max packet size should be set 804 to do updating. After applying this solution on APAC PR & G12 FFP, there is no retry found. (0/167) SMT: ATE 14% Solved > #1 Battery boot up current 5.5% > E400/E401 were cracked by the PRNP/ATE fixtures. Action: Rework all E400/E401 and modified the fixtures to avoid this problem. #2 USB connection 3.8% Monitor> 1. Fixtures reliability issue, apply USB 1.0 for verification with 30 cycles in 4 ports, no retry. (0/120) ASSY: FT1 18% Solved > #1 GPS Radiated Sensitivity 8.8% > Apply IOP for reaching better GPS signal without noise. Use 5 units to do the cycle test (10 cycle/1unit, run 2 times)，no retry in 100 times. | NPI | 2021-01-03 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan to improved SMT : GPS sensitivity、off mode Avg. Batt. cur. ASSY : GPS Radiated Sensitivity | Cpk/ Ppk < 1.33 with action plan to improved SMT : GPS sensitivity / ASSY : GPS Radiated Sensitivity Monitor SMT : GPS Sensitivity > AE had confirmed the fixture with cable and soldering, the CNo difference between 2ports are in 1dB. Monitor ASSY : GPS Radiated Sensitivity > Original CPK 0.86, new spec +/-1.5dB will be implemented in MP. Estimate to see higher cpk. | NPI | 2021-01-03 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | ASSY: Screwing、Attach Batt. are NG | PQE has helped to complete fixture ESD measurment on 1/26. All fixtures pass, only 1 battery fixture No.227656 蓋子NG > 使用時需增加靜電風扇 | PQE | 2021-01-25 16:00:00.0000000 +00:00 | 2021-02-03 08:52:19.7333333 +00:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process validation | 3.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | ASSY: Screwing、Attach Batt. are NG | PQE has helped to complete fixture ESD measurment on 1/26. All fixtures pass, only 1 battery fixture No.227656 蓋子NG > 使用時需增加靜電風扇 | PQE | 2021-01-25 16:00:00.0000000 +00:00 | 2021-02-03 08:57:23.2733333 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | PRNP high retry is mostly related to long PRNP time. In PR1, delay time was modified to fix the issue in short term, while SW is planned to resolve this issue in PR2, keep tracking. | No cradle long PRNP time issue was found in PR3. | MFG EE | 2021-04-28 16:00:00.0000000 +00:00 | 2021-04-28 10:16:47.4840303 +08:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Product validation | 3.B-4 | Release unit level appearance standard for PR -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) --Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | Unit appearance standard is not released. Need to update it. | Most of them follow WQ000015. A unit appearance standard for specific areas is provided and uploaded by 4/16 on PRWEB 2.0/PID checklist/<230> FA & VIP review | MFG ME | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-16 17:15:00.0449706 +08:00 | 1
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Process validation | 3.D-6 | Provide PVP (Process Verification Plan) result of critical process -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check (Preparation: define which critical process should apply SPC, ex: SPI/ voiding) | CR CPK: 1. Lens/solar panel y-Alignment : 0.91 2. Lens solar/display thickness : 0.88 3. Lens/display thickness : 0.94 | Clean room will apply floating bonding fixture on the 2 duplicate tooling build validation. Introduce the floating fixture. The result as below. 1. Lens/solar panel y-Alignment : 0.91→1.05 2. Lens solar/display thickness : 0.88→1.24 3. Lens/display thickness : 0.94→1.15 | NPI | 2021-08-04 16:00:00.0000000 +00:00 | 2021-07-22 21:23:06.8924006 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Process validation | 2.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result | Need PDO to provide the verification result of Lens pressing fixture. | PDO has provided the pression fixture verification result. | PDO/AE | 2021-07-01 16:00:00.0000000 +00:00 | 2021-07-02 08:47:37.1958077 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | Raw material quality issue cause the leakage from the front case(145-03710-00) | 145-03710-00 tooling modification completed, LCM-related dimensions are in spec | MFG ME/DE | 2021-06-29 16:00:00.0000000 +00:00 | 2021-06-30 17:20:53.4398334 +08:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 145-03394-90 cannot be released to vA before PR | 145-03394-90 is released | MFG ME/DE | 2021-01-07 16:00:00.0000000 +00:00 | 2021-01-12 06:36:59.5000000 +00:00 | 1
2 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | Preliminary 174- document cannot be released before PR | 174-00533-00 is released | NPI |  | 2021-01-25 02:22:42.5866667 +00:00 | 1
1 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | CT scan is in queue, not completed | Finished on 02/22 | TWN Lab |  | 2021-03-02 23:30:58.0966667 +00:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | Olathe SW is fixing issues reported by S12 testers. Will release Rev. B on 1/14/2021. | Closed . PR SW had provide before PR. MP SW released on 1/26. | MFG EE |  | 2021-01-26 07:17:13.5166667 +00:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #3 | 2021-10-19 13:51:42.3458355 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 161- parts is not Ver.A (Aries) |  | MFG ME/DE |  |  | 0
3 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | Have action plan but wait for OLA comment main sealing leakage that VT-5atm for Black and VT-3atm for Blue failed | 1. Immersion fail at main sealing > tear down unit and found no glue adhesion on housing*2/ bezel*1 > Additional 90 pcs immersion test for ethanol cleaning Pass pre-ELOT & post-ELOT. MP will apply main sealing cleaning. Consider running change in late April & May. 2. I101 fail after 100 tumble > Fail rate 50% (3/6). Apply RTV & underfill on I101 and retest tumble > All Pass (6/6). With cost consideration, apply RTV in MP. 3. ESD fail at Air -25kv > Retest 20 times with ± 30kv showed pass in TW, Olathe comment not blocker. 4. Sunscreen & DEET cause housing & button etching > Olathe waive the issue due to the PC 141R material limitation is known. | TWN Lab |  | 2021-02-03 08:27:26.0500000 +00:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #3 | 2021-10-19 13:51:42.3458355 +08:00 | Product development | 3.A-11 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | Not include 004- parts |  | EE |  |  | 0
1 | OEM Auto | BMW MGU22-RSE | GMLA #3 | 2021-10-19 13:51:42.3458355 +08:00 | Product development | 3.A-13 | Unit/ Accessory: Test coverage rate evaluation (Target: 100%) - Base on customer requirement to evaluate test coverage rate - If no special requirement, base on 004- MPS to evaluate test coverage rate | Test coverage rate is below under target |  | EE |  |  | 0
2 | OEM Auto | BMW MGU22-RSE | GMLA #3 | 2021-10-19 13:51:42.3458355 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | I450 MB, EB, AA(Before curing) retry rate over target 5% |  | NPI |  |  | 0
3 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | No Packing SOP released | SOP( ESOP SP010158) is released | NPI |  | 2021-01-25 02:23:56.6600000 +00:00 | 1
1 | OEM Auto | BMW MGU22-RSE | GMLA #3 | 2021-10-19 13:51:42.3458355 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) |  |  | MFG ME/DE |  |  | 0
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | IQC fixture is not ready due to FA VIP not finished ( Showed as attachment ,ME*27+DE*1 ) | ME IQC fixture is transferred. FA tracking (1/26 update) ME 77% (12/66) >> ETA before 2/1 EE 0% (0/1) >> battery life cycle 500 takes longer time ETA 3/1 2/8 update Engineer parts FA 100% | MFG EE/ME/DE |  | 2021-02-08 10:00:16.4500000 +00:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | PR 1.0 and PR 1.5 will finish before Pre-MP | PR & PR 1.5 are complete | TWN Lab |  | 2021-01-26 07:17:43.4100000 +00:00 | 1
1 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Process validation | 3.D-6 | Check verification result of critical process (PVP) -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check (Preparation: define which critical process should apply SPC, ex: SPI/ voiding) -- Action plan if verification result fail | X-shift CPK 1.24, PUR thickness CPK 1.03 (9 o'clock), 1.26(12 o'clock) | There is a small run to verify the result, plan to have the verification by 02-09. | NPI | 2021-02-08 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | FA VIP not finished ( Showed as attachment ,ME*27+DE*1 ) | 2/2 FA update ME 100% , EE 0% (0/1) Remain 1 item > Battery It is under life cycle 500 times, estimate to complete on 3/1. 2/8 update All engineers part FA 100% | MFG EE/ME/DE |  | 2021-02-09 05:48:47.9966667 +00:00 | 1
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 35%, DE 12% (see reference) | FA for ME/DE parts document will be uploaded by 9/3 | MFG ME/DE | 2021-09-02 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | Some ME parts are not v0A. (011*5/ 145*8/ 252*1/ 253*3/ 320*2/ 325*1/ 414*1) | 3 parts (145-03400-20, 145-03400-00, 320-01483-00) are not v0A yet as compliance is not completed, estimated to turn A by 7/E. @Cheng, Tom all A-rev | MFG ME | 2021-07-29 16:00:00.0000000 +00:00 | 2021-08-04 20:34:38.1800338 +08:00 | 1
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Batt. will pull in for Pre-MP | Reallocate Pre-mp quantity due to battery constraint. | PID | 2021-01-03 16:00:00.0000000 +00:00 | 2021-02-03 08:58:37.7400000 +00:00 | 1
2 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | Test type 0.678 with yield 93.33% | This station is for data collecting and will use the real unit feeling to discuss with Design TeamThe Castor click feeling is acceptable, no extra test required in MP. | NPI | 2021-02-08 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | C:38.57%, 0.183:24.82%, 0.191:20.73%, 0.161:20%, 0.173:19,64%, 0.508:18.93%, 0.2001:18.64%, 0.192:12.5% | PR 1 - [Action]Fine-tune the laser parameters of bezel(千里眼)*12 failures in PVD (12/259=4.63%)*2 failures in Paasivated (2/170=1.17%)PR 2 CT:26.83%(22/82)*2 failures in PVD (2/114=1.75%)*4 failure s in Paasivated (4/89=4.49%)[Action]1.Issue on the PR Web2.Mylar to isolate the bezel lug to touch the PCB PadRetry rate =3%(1/30)Pre-MP: MPM suggest to do 300 pcs small build validation | NPI | 2021-02-08 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | Fixture ESD is not completed. Measurement will be completed on WK9. | QE Jason will finish ESD measurement by WK09 | PQE | 2021-03-11 16:00:00.0000000 +00:00 | 2021-03-29 15:31:22.3362522 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | Need MME provided the critical requirement in assembly VIP | ME will finish in this week. | MFG ME | 2021-12-02 16:00:00.0000000 +00:00 | 2021-12-24 15:04:07.0457755 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #2 | 2021-04-09 13:23:52.4724997 +08:00 | Product development | 2.A-5 | Design lockdown for critical parts (015- drawing include critical parts info.) -- Review all material in critical parts list -- Special characteristic should be included | 320-01461-00 & 320-01462-10 Cables will be updated to change the softness. New samples will be verified in the PR build. | The changes include the PVC material change to 75A, the GND wire change to 28AWG, and the short between GND and shell. Softness test completed. Cable SR modified and verified PASS. | MFG ME | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:37:52.2368422 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 3 items not started. 1 items are under testing. The expected complete date:2021/11/19 | Failed test item: 1. connector bending : confirmed it was a misjudgment. 2. Sand slurry test: The bottom feeling back to normal after washing the unit. OLA confirm this item passes the test. | TWN Lab | 2021-12-09 16:00:00.0000000 +00:00 | 2021-12-10 16:00:13.5353795 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process development | 2.C-8 | Define traceability resolution -- SMT traceability resolution (By panel/ by SO#) -- Critical parts/ Sub process (EX: LCM/ PCBA)/ Accessories bundle requirement -- Production program setup should be finish before FFP (ex: MES/ Line controller/ ITMXP testing/…) | The bundle program did not ready due to the battery D/C (361-00135-00) has not defined. | 361-00135-00 has released to Rev.A. | MFG EE | 2021-12-09 16:00:00.0000000 +00:00 | 2021-12-10 15:11:06.2376628 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk not meet the target <1.33 1.SMT (1) Pre-boot_ Conducted GPS L1 Sensitivity: 0 (2) Pre-boot_ Conducted GPS L5 Sensitivity: 0 2.ASSY (1) FT1_GPS_(L1 only) by ref: 0.66 (2) FT2_GPS_L5 by ref: 0.47 | 1.SMT (1) Pre-boot_ Conducted GPS L1 Sensitivity: 0 FP2 preboot fixture GPS tuning is not ready, EE has finetuned preboot fixture and made sure all preboot ports within 1dB difference. (2) Pre-boot_ Conducted GPS L5 Sensitivity: 0 L5 is easily to be influenced by BLE dongle , has told PE add this instruction into SOP. 2.ASSY (1) FT1_GPS_(L1 only) by ref: 0.66 Cable arrangement affects L1/L5 CN reading a lot, has asked PE to add this instruction into SOP. (2) FT2_GPS_L5 by ref: 0.47 GPS L5 value is easily to be influenced by 2.4G cable, has told PE add this instruction into SOP. | MFG EE | 2022-01-06 16:00:00.0000000 +00:00 | 2021-12-24 15:04:22.5000451 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process validation | 2.D-15 | Define outsourcing parts -- ASSY VIP/ appearance STD should be ready for outsourcing supplier | Outsourcing parts (011-05029-10/11) need to provide ASSY VIP to supplier | Outsourcing parts ASSY VIP had provided to supplier. | NPI (OSP) | 2021-11-16 16:00:00.0000000 +00:00 | 2021-11-17 17:37:19.5176722 +08:00 | 1
1 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Although Process Capability Analysis indicate 10 tests can't meet Cpk target, EE have feedback action plans | PR 1 - [Action]Fine-tune the laser parameters of bezel(千里眼)*12 failures in PVD (12/259=4.63%)*2 failures in Paasivated (2/170=1.17%)PR 2 CT:26.83%(22/82)*2 failures in PVD (2/114=1.75%)*4 failure s in Paasivated (4/89=4.49%)[Action]1.Issue on the PR Web2.Mylar to isolate the bezel lug to touch the PCB PadRetry rate =3%(1/30)Pre-MP: MPM suggest to do 300 pcs small build validation | NPI | 2021-02-08 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Although PR have critical issues, all issues have com ed up with Action Plan | Lens module pop out after tumble/drop 1. Root Cause: Due to the glue residue of mask tape(3M 851J), the ink surface energy was decreased, which resulted in poor adhesion of lens to PUR. 2. Action: Change protective film from 3M to PET film, and keep monitoring in next build | NPI | 2021-02-08 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Venu 2 | GMLA #3 | 2020-12-30 04:56:58.6270000 +00:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA complete rate:81% (see reference "Union tooling BOM") | The FA of housing and band hasn’t been done yet. Will finish them by the end of this month. | MFG ME/DE | 2021-01-30 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Process validation | 2.D-7 | FFP UPH/Capacity evaluation result review -- Action plan if UPH/ Capacity cannot meet latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | No SMT/ Clean room UPH & Labor cost evaluation report. ASSY need to add more fixture to increase UPH | PE had updated UPH & Labor cost on 02/06 and All PR fixture is ready. | NPI |  | 2021-03-02 23:32:28.8666667 +00:00 | 1
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | Final FP_Black RF Immunity Conducted is In Queue | Complete by the end of next week | TWN Lab | 2021-02-25 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Approach S12 | GMLA #3 | 2021-01-04 18:54:24.9621378 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Material FA are not ready ME: 42 % DE: 50 % | 2/2 FA update ME 100% , EE 0% (0/1) Remain 1 item > Battery It is under life cycle 500 times, estimate to complete on 3/1. 2/8 update All engineers part FA 100% | MFG ME/DE |  | 2021-02-09 05:49:10.4900000 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | [3/3] PR1 ELOT only needs USB bending, tumble, and drop but hasn't started yet. Lab will arrange the test schedule. | ELOT completed by 3/5. See LMS-0011259-5-TW. | TWN Lab | 2021-03-04 16:00:00.0000000 +00:00 | 2021-03-09 07:28:38.3166667 +00:00 | 1
3 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | 1. No PACK SOP released / 2. Need to update TEST SOP | Both SOP are updated on 3/8 | NPI | 2021-03-07 16:00:00.0000000 +00:00 | 2021-03-16 09:23:11.6200000 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process development | 3.C-6 | Update control plan for PR build (vA) -- Key characteristic should be included and must correspond with D/PFMEA -- Control method for key characteristics should be flow down from D/ PFMEA to control plan -- Fixture/ Meter/ Equipment list (Type info.) & parameter should be updated in CP -- (AOEM) Regular requalification should be included | CP is not released | CP is completed by 3/12 | PQE | 2021-03-11 16:00:00.0000000 +00:00 | 2021-03-16 09:57:36.1600000 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | 012-04119-01 MB: No Max. peak temp on 461-10058-00 | Max temp. updated on the system by 3/12. | NPI | 2021-03-11 16:00:00.0000000 +00:00 | 2021-03-16 09:24:51.6000000 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | OOB checklist is not completed | OOB checklist is completed by 3/26 | PQE | 2021-03-25 16:00:00.0000000 +00:00 | 2021-04-16 17:15:34.9895543 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Product development | 2.A-5 | Design lockdown for critical parts (015- drawing include critical parts info.) -- Review all material in critical parts list -- Special characteristic should be included | There is a ST retry 10.91% problem. Re-assemble the set will pass ST test. Modify 145-03617-00 rib length for new alignment feature and track result at PR build. | Modify 145-03617-00 tooling of Rib length for new alignment feature and track result at PR, tooling modify plan to completed before 4/9. @Chuang, Max(ME) | MFG ME/DE | 2021-04-08 16:00:00.0000000 +00:00 | 2021-06-03 09:57:13.5527096 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | There are 7 items undergoing. All the tests will be completed on 3/23. | 1. CT scan: test Pass on 4/9. 2. Thermal measurement: test Pass on 4/9. 3. RF Immunity Conducted: test Pass on 4/9. | TWN Lab | 2021-03-30 16:00:00.0000000 +00:00 | 2021-06-22 18:04:29.6162807 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | 1. SMT: (1) 100% BK current(CpK: 0.7) (2) BT CW Low(Cpk: 0.29) 2. ASSY: (1) CT CN (Cpk: 0.68) (2) HT CN (Cpk: 0.85) (3) FT CN (Cpk: 0.51) (4) Right Mic Max Amp(Cpk: 0.67) (5) Left Mic Max Amp(Cpk: 0.67) | SMT: 1. 100% BK current: Olathe approve adjust spec, but spec waiting for Olathe confirm before PR, keep tracking. @Chen, Leon 2. BT CW Low: Fixture difference. No actual failure boards. EE will adjust fixture then verify if improve. @Chen, Leon ASSY: 1. CT CN: EE analyzing. @Chen, Leon 2. HT CN: EE analyzing. @Chen, Leon 3. FT-CN: CompenCNo modify spec as 45.5 ~50.5, EE think this is low concern. @Chen, Leon 4. Right Mic Max Amp Now didn’t define upper limit, PE will confirm the upper limit with SE before PR. @Chen, Jason(PE) 5. Left Mic Max Amp: Now didn’t define upper limit, PE will confirm the upper limit with SE before PR. @Chen, Jason(PE) | NPI | 2021-04-08 16:00:00.0000000 +00:00 | 2021-06-22 18:06:13.9222896 +08:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | PR2 is requested to verify Hall Effect switch on battery pack and magnet on cradle for pogo pin corrosion issue | PR2 completed on 3/6. | NPI | 2021-03-05 16:00:00.0000000 +00:00 | 2021-03-09 07:54:35.6266667 +00:00 | 1
2 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | Field rate < 97% (1) Battery pack: ATE 95.42% (2) Cradle: VT 94.86% | FYR for PR2 are greater than 97% for all test stations. No LED current issue and VT issue in PR2. | NPI | 2021-03-05 16:00:00.0000000 +00:00 | 2021-03-16 09:58:23.5400000 +00:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Supply chain/ supply of part | 2.E-1 | The relevant supply chain have been finalized (2nd source selection for critical parts in MPM system) | 2nd source of the critical parts will be selected after the PR build. | Olathe has verified TCXO 2nd source and no issue. | MFG ME/DE | 2021-04-08 16:00:00.0000000 +00:00 | 2021-06-22 18:07:16.7282747 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #2 | 2021-04-09 13:23:52.4724997 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | 1. BT CW Medium: 1.02/ High: 0.79 2. CT C/N: 0.83 | 1.BT CW Medium: No BT CW Cpk issue in PR. 2. C/N: verified new golden sample with no obvious retry in PR. | MFG EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:21:34.5455836 +08:00 | 1
2 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% (1) Battery pack: ATE 12.5% / FT 24.27% (2) Cradle: PRNP 30.7% / RTESN 16.2% / HT 12.09% / VT 16% | 1. Battery pack ATE: Verified Pass in PR2. 2. Battery pack FT: FT high retry is mostly contributed by “battery minimum shipping voltage” as batteries are insufficient charged. SOP has defined 30 min charging time and will use a fixture to control charging time by LED light. Will verify in pre-MP. @Lan, Pattie 3. Cradle PRNP: Issue resolved and verified Pass in PR3. 4. Cradle RTESN: Verified Pass in PR2 5. Cradle HT: Verified Pass in PR2 6. No VT issue in PR2. | NPI | 2021-08-29 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Process development | 3.C-13 | BOM structure review (if any part needs to be added or changed after build) -- Lost parts/ wrong level/ wrong qty -- Include auxiliary material (副料) | 1. Instruction menu (NRL)- 190-02068-65 & 190-02863-90/-91/-92/-94 2. No “Box” (170-02563-01) in the BOM.(Only 010-02626-13) | ECO#228630 | NPI | 2021-08-04 16:00:00.0000000 +00:00 | 2021-08-18 15:29:46.9873231 +08:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | ESD measurement is not completed | ESD measurement completed by 5/21. ESD fail on battery attaching fixtures and cradle unit dispensing fixtures. SOP modified to add air ionizer for the assy process. | PQE | 2021-05-20 16:00:00.0000000 +00:00 | 2021-06-23 18:07:33.7079849 +08:00 | 1
3 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | VT issue is planned to modify glue dispensing speed and glue amount. Will verify in PR2. | VT verified PASS in PR2 | NPI | 2021-03-05 16:00:00.0000000 +00:00 | 2021-03-16 09:59:28.5466667 +00:00 | 1
1 | Fitness | One Battery Bike Project | GMLA #3 | 2021-03-04 15:19:42.2078278 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME FA rate 44%. Total 37 GPN are not up-to date. (1) Wait for supplier: 33 / (2) ME reviewing: 3 / (3) No FA ID: 1 | ME FA rate: 66%, estimated to complete before MP. @Cheng, Tom | MFG ME | 2021-08-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Need to verify 012-04211-00 ATE/Pre-boot/Lid assembly strain gauge | ATE : Pass Pre-boot : pass PRNP : pass Lid : pass | PQE | 2022-01-20 16:00:00.0000000 +00:00 | 2022-01-24 08:17:41.0638667 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #2 | 2021-03-31 19:35:43.4594342 +08:00 | Product development | 2.A-5 | Design lockdown for critical parts (015- drawing include critical parts info.) -- Review all material in critical parts list -- Special characteristic should be included | 320-01461-00/10 & 320-01462-00/20 Cables will be updated to change the softness. New samples will be verified in the PR build. | The changes include the PVC material change to 75A, the GND wire change to 28AWG, and the short between GND and shell. Softness test completed.Cable SR modified and verified PASS. | MFG ME | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:38:19.7582849 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #2 | 2021-03-31 19:35:43.4594342 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT finish rate 93.33%. 2 items are incomplete (CT scan & Thermal measurement) and will be completed on 4/12. | All ELOT tests completed, see LMS0009539 for details. by 4/12. | TWN Lab | 2021-04-11 16:00:00.0000000 +00:00 | 2021-04-16 17:18:42.4193112 +08:00 | 1
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 249-01444-20 006 700-00149-01 002 700-00149-11 002 011-05321-00 003 012-04094-JT 008 | 006-D9396-00 should be released by 8/23 | NPI/ME/DE | 2021-08-22 16:00:00.0000000 +00:00 | 2021-09-01 15:24:38.5555214 +08:00 | 1
3 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Product Package Drop NG (1/1) Problem : Watch band with scratch | Root cause : watch band use new material (R4000), but inner box use previous one (Instinct 1) Action : redesign inner box and re-validation in 7/21 (Passed) | TWN Lab | 2021-07-22 16:00:00.0000000 +00:00 | 2021-07-21 14:40:21.4733550 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Many items cannot meet the cpk 1.33 | CN / WiFi Cpk is not acceptable. EE is analyzing the CN / WIFI to see if the spec can be adjust and more actions(about antenna dimension modification), for more details please refer to Issue page. | NPI | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Instinct 2 | GMLA #3 | 2021-07-19 14:55:31.7718931 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | 1. For ASIA SKU, 006-D5459-0X in the BOM list but not show in unit inventory > By pass checking in PR, will update SW 2. For ASIA SKU 006-D8021-13 isn't in 010-BOM > will add it to BOM | 1. <Close>SW is released in 7/30 2. <Closed> 006-D8021-13 have added in BOM in 7/29 | PQE | 2021-07-27 16:00:00.0000000 +00:00 | 2021-08-03 11:33:01.0996353 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | ESD result hasn't completed. | PQE will measure the ESD from SMT/ ASSY fixtures. [Jason 1/22] Measured in 1/13 and passed | PQE |  | 2021-03-29 15:59:46.2660099 +08:00 | 1
3 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | 2 critical issues are opening. (1) Battery would influence the signal of wifi and BLE (2) ESD NG (ELOT) | 1. ESD solution =>Origin tape full + copper foil full + FPC copper foil 2. button fail at 90cm drop and tumble. => Design team decided to keep original design. 3. LED issue at 90cm drop and tumble. => modify the front case and passed 4. Packing, unit abrasion => will apply a protection film. 5. Power off current draw(BAT) => solve with new PCB in PR2 | NPI | 2021-02-05 16:00:00.0000000 +00:00 | 2021-03-29 15:59:54.9537821 +08:00 | 1
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-16 | Process outsourcing parts evaluation result -- Cpk/ yield rate/ UPH data should be ready | evaluation result is not ready | Review in PR1 Close Meeting | MFG ME/DE | 2021-03-18 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GT36/GT56 UHD Transducers | GMLA #1 | 2020-12-03 18:26:36.2100000 +00:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 456 |  |  |  |  | 0
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #1 | 2021-06-01 08:39:10.8985045 +08:00 | Product development | 1.A-11 | Unit: Review preliminary 004- document for WP -- Release to version 001 -- Add-in BOM | Due to there will be still some adjustments in the near future. PM will finalize the SKU and IR 010- in succession. | The main development skus on 010-02493-02 and -04, the BOM are including 004- MPS file now. Will extend on other skus if customer decide other function in future. | EE |  | 2021-06-02 09:47:24.6580408 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #1 | 2021-06-01 08:39:10.8985045 +08:00 | Product validation | 1.B-9 | Special label requirement for engineering samples have been defined and agreed with customer | PM needs to check label requirement on FP phase | PM confirm no special label requirement of engineer units from customer. | EPM |  | 2021-06-02 20:31:59.4230443 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 7 Uncompleted items: Spark plug / RF Immunity Radiated / Drop / Battery Disconnect Drop / Connector Bending / Click ratio / XRF | All test item will be complete on 9/15. | TWN Lab | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-16 13:41:48.8224262 +08:00 | 1
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004 is not added-in BOM | ECO#212784 has released and tuned to version A. Has informed CFT to add to the BOM | MFG EE | 2021-03-10 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | underfill on I307 | Underfill as protection to the components. | PQE | 2021-02-21 16:00:00.0000000 +00:00 | 2021-02-21 23:58:29.4833333 +00:00 | 1
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Raw material of R/C have Different height of antenna spring contact issue | Review in PR1 Close Meeting | MFG ME | 2021-03-18 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Product development | 2.A-12 | Design lockdown for critical parts (015- drawing includes critical parts info.) -- Review all material in critical parts list -- Special characteristic should be included | Due to drawing is not confirm by customer, the critical parts dimension is not confirm. Customer will confirm before 3/31. | Customer needs one more week to check drawing, internal drawing completion date to 4/20. | ME/DE | 2022-04-19 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | TXTW22 BOM has 19 components no max reflow temperature. NPI and EE wiil update the temperature in BOM before 4/22. | estimate complete Peak temperature review / SMT VIP / New component design review / Minimum component review before 4/22. | NPI | 2022-04-21 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | Finish will be decided after testing | MME is working with OLA mE for further confirmation and next check point : 09/13 Just clarify design issue last week. 9/9: All drawings have been released. There are three item for running changes. 1. 125-00622-12 (slots) 2. 125-00623-00 (coating) 3. 211-00261-20 (screw head size) | MFG ME | 2021-09-12 16:00:00.0000000 +00:00 | 2021-09-22 19:58:46.4759851 +08:00 | 1
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 010/001/013/017/125/161/211/K00 cannot be version A before PR | 09/06 : Only left 001/004/006 (Qty=0 GPN) & K00 not turn A yet. 004/006 : Still tracking with OLA team for new SW release and confirm 004 for MP. - Checkpoint : 09/15 Postponed to 10/13 K00 : 211-00261-20 not turn A yet. Target to finish A release by 09/15. - MME Jay SW ECO release : 10/21 | NPI/ME/DE | 2021-10-12 16:00:00.0000000 +00:00 | 2021-10-21 15:56:02.8223571 +08:00 | 1
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01066-00/01 are still v002 after PR build. It should be v0A. | TWN EE had update some items need adjustment to OLA team and we are waiting for OLA EE release A version 004. | MFG EE | 2021-09-29 16:00:00.0000000 +00:00 | 2021-09-30 18:31:46.0091119 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Product development | 3.A-5 | Update drawing version if any design change (tolerances need to be well defined in the drawing as well) | Some 145 material need to be modified | Trial shot will execute on 1/6 and FA will release before 2/1. [3/5] 145 FA completed | MFG ME/DE | 2021-03-07 16:00:00.0000000 +00:00 | 2021-03-29 15:59:20.3722700 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | Some ME/DE parts are not vA. DE parts 013-00968-00 / 013-00968-01 / 145-03697-00 / 145-03698-00 ME parts 011-05491-30 / 145-03378 ~ 81 / 145-03633 ~ 38 / 249-01567-00 ~ 01 / 320-01425-00 / 320-01425-10 | ME parts]Trial shot will execute on 1/6 and FA will release before 2/1. [DE parts] will release official drawings before 1/8 and FA will complete before 2/1. [Final update] 1. ME: All completed by 2021/3/8 2. DE: 013-00968-00 / 013-00968-01 / 145-03697-00 / 145-03698-00 have turn A but will release vB | MFG ME/DE | 2021-03-04 16:00:00.0000000 +00:00 | 2021-03-29 15:59:24.8568113 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01056-00 version is still 001 in PR phase. It should be 0A version. | EE Nathan has noted the design team and keeps tracking. [Robben 1/22] 004-01056-00 has been released on 1/5 ECO#201515 | MFG EE |  | 2021-03-29 15:59:28.5435574 +08:00 | 1
3 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | ELOT failed DC 47: 4 failed items (Power off current draw(BAT)/ESD/ Tumble/ Shipping vibration) DC 57: 8 failed items (UV-A/ Power off current draw(BAT)/ High temp./ ESD/ Drop*2/ Tumble/ Shipping vibration) | 1. ESD solution =>Origin tape full + copper foil full + FPC copper foil 2. button fail at 90cm drop and tumble. => Design team decided to keep original design. 3. LED issue at 90cm drop and tumble. => modify the front case and passed 4. Packing, unit abrasion => will apply a protection film. 5. Power off current draw(BAT) => solve with new PCB in PR2 | TWN Lab | 2021-02-05 16:00:00.0000000 +00:00 | 2021-03-29 15:59:32.7641957 +08:00 | 1
2 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | SMT: DC 57 MB ATE 96.55% ¦¦¦ ASSY: DC 47 FT 95.71% / DC 57 FT 92.31% | [ATE] 2pcs Y101 shift and bypassed by the operator caused this item failed [AMBA]Start Download [Assy]EE is analyzing the CN / WIFI to see if the spec can be adjust and more actions(about antenna dimension modification), for more details please refer to Issue page. | NPI | 2021-01-31 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT: DC 47 MB ATE 19.54% / DC 57 MB ATE 12.07% ¦¦¦ ASSY: DC 47 FT 27.14% & RTMTF 20.55% & Product scan 40.74% / DC 57 ST 15.38% & FT 34.62% & Product scan 27.93% / DC 67 Product scan 15.38% | [ATE] Test computer was not steady on 3 in 1 at first time but got solved after following jobs. [Assy]We mainly focus on high retry on CN value at FT. EE is analyzing the CN / WIFI to see if the spec can be adjust and more actions(about antenna dimension modification), for more details please refer to Issue page. | NPI | 2021-01-31 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Some VIP of ME/DE parts are ready because FA is not finished | ME parts]Trial shot will execute on 1/6 and FA will release before 2/1. [DE parts] will release official drawings before 1/8 and FA will complete before 2/1. [Final update] 1. ME: All completed by 2021/3/8 2. DE: 013-00968-00 / 013-00968-01 / 145-03697-00 / 145-03698-00 have turn A but will release vB FA completed on 5/4 | MFG EE/ME/DE | 2021-03-22 16:00:00.0000000 +00:00 | 2021-05-04 15:04:47.0017638 +08:00 | 1
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Material shortage on 560-00263-01. Keep reviewing the material status. | 560-00263-01 & 560-00263-04 arrived on 5/29 | PID |  | 2021-05-04 15:04:03.7647886 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Process validation | 2.D-2 | MSA test plan update (Focus on any change that need to re-do MSA) -- Refer to control plan "measurement system" (TQ0263) -- Chang of key characteristics -- New machine/ critical process (Defined by customer or RD/PE/QA/EE) -- Line transfer | MSA plan should include critical process and special characteristics, but EE was not define special characteristics yet. Special characteristics will define before 4/29 and MSA will check in PR build. | PQE is still under discussing with EE, expect finish before next pilot run before 6/6. | PQE | 2022-06-05 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam 47 / 57 / 67W | GMLA #3 | 2020-12-28 01:34:17.8000000 +00:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Confirmed by DPQE. Some FA of ME and DE parts are not completed. (1) DC 47 ME 82% / DE 40% (2) DC 57 ME 89% / DE 50% (3) DC 67 ME 88% / DE 33% | ME parts]Trial shot will execute on 1/6 and FA will release before 2/1. [DE parts] will release official drawings before 1/8 and FA will complete before 2/1. [Final update] 1. ME: All completed by 2021/3/8 2. DE: 013-00968-00 / 013-00968-01 / 145-03697-00 / 145-03698-00 have turn A but will release vB 013-00968-xx FA completed on 5/4 | MFG ME/DE | 2021-03-22 16:00:00.0000000 +00:00 |  | 0
2 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT: Processor board ATE: 23.27% / Amp board ATE1: 14.73% / Amp board Audio_ATE2: 20.16% 2. ASSY: HT 36.08% / FT1 19.59% / FT2 29.9% | Processor board ATE: 23.27% Root cause : Antenna board position cause test unstable, AE had adjusted fixture and verified. Amp board ATE1: 14.73% EE will increase the repeat times & retry pass. Fixture pin crooked (Had fixed & retry pass) Amp board Audio_ATE2: 20.16% DAB generator sometimes crash (Need to reboot DAB generator & retry pass) – This test item only for data collection and remove in MP. HT 36.08% After data analysis. OP tested the same fail unit twice in FT 1 and cause AMP1 &2 temperature reading error. Need keep monitoring in 1st MP after re-training. FT1 19.59% ESN3365614693 cause retry and need EE help to analysis. [Suspect OP press wrong button during test - monitoring] FT2 29.9% Rear conn & fixture not well connection. Same issue as FFP and we don’t have solution for now. | NPI | 2021-05-06 16:00:00.0000000 +00:00 |  | 0
2 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT: Processor board ATE: 23.27% / Amp board ATE1: 14.73% / Amp board Audio_ATE2: 20.16% 2. ASSY: HT 36.08% / FT1 19.59% / FT2 29.9% | Processor board ATE: 23.27% Root cause : Antenna board position cause test unstable, AE had adjusted fixture and verified. Amp board ATE1: 14.73% EE will increase the repeat times & retry pass. Fixture pin crooked (Had fixed & retry pass) Amp board Audio_ATE2: 20.16% DAB generator sometimes crash (Need to reboot DAB generator & retry pass) – This test item only for data collection and remove in MP. HT 36.08% After data analysis. OP tested the same fail unit twice in FT 1 and cause AMP1 &2 temperature reading error. Need keep monitoring in 1st MP after re-training. FT1 19.59% ESN3365614693 cause retry and need EE help to analysis. [Suspect OP press wrong button during test - monitoring] FT2 29.9% Rear conn & fixture not well connection. Same issue as FFP and we don’t have solution for now. | MFG EE | 2021-05-06 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | ASSY Cpk cannot meet 1.33. FT2_Zone1 Subout 0.039 / Lineout L 0.216 / Lineout R 0.152 / FT_Zone1 Speaker Out R 0.203 / Speaker Out L 0.090 / Zone2_Speaker Out L 0.276 | EE found Cpk data has issue and some of them is wrong. Will need PE provide update of ASS Cpk data. NPI PE still have data system issue until 04/20, will provide manual summary data on 04/21. And we will need EE feedback before 04/23. | NPI | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Salt fog is ongoing | Only left 1 item ongoging. Retest request of salt fog. | TWN Lab | 2021-09-12 16:00:00.0000000 +00:00 | 2021-09-22 19:59:45.6441740 +08:00 | 1
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 500-01757-C3 Max peak temp is 260, but don't update in agile | This IC just release drawing recently and we are tracking peak temp data been updated. | NPI | 2021-09-29 16:00:00.0000000 +00:00 | 2021-10-21 15:56:57.2841126 +08:00 | 1
2 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | 1. BB_VT2 93.33%: 小漏氣_超過洩漏量門檻 2. Camera_HTMTF 95.67%: MTF Ave (UR) 3. Camera_FT2 96.08%: (No.1) Device current - from testBB 4. Camera_VT3 92%: 小漏氣_超過洩漏量門檻 | Camera HTMTF : After check with PE and units had been fixed. FYR also had been update to 99.61% Camera FT2 FYR update to 97.09 % same as above. The data of previous report is not correct. Camera VT3 FYR update to 98.0 % same as above. The data of previous report is not correct. (it relate to close meeting's timing) | NPI | 2021-09-07 16:00:00.0000000 +00:00 | 2021-09-08 16:57:58.7587539 +08:00 | 1
2 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. BB_ATE 72.58%: Verify 1Gbps Link ASSY 1. BB_HT 15.56%: (No.4) BIST error count 2. BB_Gyro_Calibration 45.45%: MotorAInitial 3. BB_VT2 20%: 小漏氣_超過洩漏量門檻 4. Camera_VT2 22.83%: 大漏氣_未抽至1120 5. Camera_HTMTF 32.4%: MTF Ave (UR) 6. Camera_CCM_W 11.11%: LSC Calibration 7. Camera_Distortion 64.68%: Distortion Calibration 8. Camera_VT3 36%: 大漏氣_未抽至1120 | SMT Black box 1. ATE: Verify 1Gbps link Root cause: It was caused by fixture pin connection issue. Action: EE/AE change test method and use cable to test this connector instead of fixture pins. ASSY Camera 2. Distortion Action: It's SW issue so OLA will fix SW. ASSY Black box 3. Gyro Analysis: Gyro setting issue happened when test beginning. A lot of retry was cause by cable (not fixing well). Action: EE will provide golden sample for this station to prevent it happen again in next order. | NPI | 2021-11-03 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | No CPK data in PRWeb | Will update in system by 09/09 | NPI | 2021-09-08 16:00:00.0000000 +00:00 | 2021-09-22 20:00:45.6117318 +08:00 | 1
3 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Process validation | 3.D-13 | Review MP block issue (PR issue in PRWeb) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | MP block issue in FFP is still ongoing. Meshinator issue & Unit SW missing->9/15 New SW release by OLA. | 1. New SW issue :(D3 – Camera features & image quality) Analysis: Color shift between cameras is noticeable Action: OLA will fix this probem by SW update. (10/21) Need to wait PR2 verification result. 11/04 | NPI | 2021-11-03 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate cannot meet the target (100%) 1. ME parts: 74% (79/107) 2. DE parts: 0% (0/1) | Already reach 90% and left some parts below is still under discussion with OLA. 011-05293-10 011-05294-20 125-00622-12 125-00622-22 210-00119-00 330-01875-00 | MFG ME/DE | 2021-10-28 16:00:00.0000000 +00:00 |  | 0
3 | Marine | Surround View Camera System | GMLA #3 | 2021-09-01 16:24:55.1825197 +08:00 | Supply chain/ supply of part | 3.E-12 | Raw material quality issue from supplier | Metal cap has serious cosmetic issue during PR which is caused by vendor. Need to improve the package method before MP | MME had asked vendor to modified process & package. Will implement in 1st MP and we also change protective file in our assembly process. Will monitoring 09/15-lot assembly result. No new issue been found so far. (PR2 ongoing) | MFG ME | 2021-09-23 16:00:00.0000000 +00:00 | 2021-09-22 20:01:49.9325094 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Process validation | 2.D-4 | MSA result check and action plan for fail item or no MSA test base on latest test plan | MSA item which about dimension will check when drawing confirm by customer. Drawing confirm will before 3/31 and dimension measurement will be PR build. | PQE is still under discussing with EE, expect finish before next pilot run before 4/29. | PQE | 2022-05-30 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Process validation | 2.D-7 | FFP UPH/Capacity evaluation result review -- Action plan if UPH/ Capacity cannot meet latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | MP PRNP software change, UPH 44-> 28. NPI will check SW behavior and improve UPH in PR build. | check the SW behavior affect PRNP UPH in pilot run. [5/23 update] Load unload: 30 sec 9” Main board average pass time: 330 sec (UPH: 40) 12” Main board average pass time: 305 sec (UPH: 43) | NPI | 2022-05-30 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Wait design fixed | MME already completed the material inspection from suppiler report. | MFG ME | 2022-03-30 16:00:00.0000000 +00:00 | 2022-03-23 10:24:04.6671683 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 9 BOM parts not been version A before pilot run (1)Sub-assemblies part: 011-05489-01/011-04512-22/011-05489-11/011-05489-31/011-05489-50 (2)ME Parts:115-03878-00/253-01442-00 (3) LCD and Lens module:440-00306-20/470-00847-00 | We will reflect those GPNs to the design team and check every week. (2)ME Parts: 115-03878-00/253-01442-00 have turned A (3) DE parts :440-00306-20/470-00847-00 have turned to revA | ME/DE | 2021-11-18 16:00:00.0000000 +00:00 | 2021-11-08 11:15:21.8649376 +08:00 | 1
2 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | 174-00550-00 packing instruction not released | 174-00550-00 has turned A on 10/27 | NPI | 2021-11-18 16:00:00.0000000 +00:00 | 2021-10-27 16:38:38.6519099 +08:00 | 1
3 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 2 ELOT fail items (1) Connector Bending (1/2 NG): 50 Cycles VT fail (2) Tumble (1/1 NG): 100 drop, 1m. VT fail | (1)Connector bending is not the cause since there's no leakage found at the USB connector. The leak point is at the power button(overmold fracture), will perform power bottom cycle test on 3 more units. 10/22 Re-do the cycles test and no VT fail problem. Lab. update: 10/22重測pass, 已將connector bending 的測試結果改為pass. (2 Failure description: ‧ Tumble 80 cycles VT fail (1/1) Root cause: ‧ 下水抓漏發現洩漏位置是前殼與display lens之間漏 Action: ‧ FFP 時測了1pcs+ Olathe Lab(Tucson)測了Tumble 2pcs，也沒發生問題 ‧ 預計加測2 pcs看結果 -Owner: Lab (due date:11/15)->重測2台pass, 風險較低, CFT接受此結果進行MP, 工程同步改善供應商清潔製程, 避免汙染造成點膠接力下降. Evidence: . LMS-XXXXX (due date:11/15) | TWN Lab | 2021-10-21 16:00:00.0000000 +00:00 | 2021-10-25 11:45:15.6751284 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing:3 items are not started. 2 items are under testing. The expected complete date:2021/10/25 | The expected complete date:2021/10/25 | TWN Lab | 2021-10-24 16:00:00.0000000 +00:00 | 2021-10-20 17:04:21.9854383 +08:00 | 1
2 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT retry rate did not meet the target <=10% (1) ATE 19.07%: 3.6V Battery Current, Idle w/GPS Assy retry rate did not meet the target <=10% (1) VT2 23.48%:小漏氣_超過洩漏量門檻 (2) VT1 22.26%:小漏氣_超過洩漏量門檻 (3) M-sensor test 12.98%: Check Unit Roll on 0 degree | SMT retry rate did not meet the target <=10% (1) ATE 19.07%: 3.6V Battery Current, Idle w/GPS >>SW mistakenly close GPS IC in test mode causing low current in 1st batch. Fixed by adding GPS IOP. Assy retry rate did not meet the target <=10% (1) VT2 23.48%:小漏氣_超過洩漏量門檻 >> fixture fixed in 40 units build. (2) VT1 22.26%:小漏氣_超過洩漏量門檻 >> fixture fixed in 40 units build. (3) M-sensor test 12.98%: Check Unit Roll on 0 degree>> updated FW for g-sensor stepping motor. | NPI | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-15 09:55:14.7581487 +08:00 | 1
1 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Material inspection VIP is not ready: 115-03878-00/145-03710-00/145-03710-01/211-00673-00/253-01442-00/330-02017-00 | Will have them ready before Asia PR build start @Sun, Jacky 115-03878-00/253-01442-00 VIP completed on 10/28 | MFG ME | 2021-11-18 16:00:00.0000000 +00:00 | 2021-10-28 09:47:57.8180561 +08:00 | 1
3 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | The supplier provides 12K per week now, shortage will show in 2022 Q1; PUR team should pull in more capacity for 145-02808-00. | 145-02808-00 max capacity 120k/week and shortage will start on WK51. (no impact MP start) Keep monitoring capacity extension to 150k@Huang, Jane(Purchasing) [@Liu, Robben 10/28]No impact on MP schedule but deficit will show from WK03 2022. Capacity expansion is likely to catch the deficit. | MPM | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-26 08:29:29.6799389 +08:00 | 1
2 | Outdoor | inReach Mini 2 | GMLA #3 | 2021-10-12 11:48:55.6294595 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 81% (6 items FA progressing: 115-03878-00/145-03710-00/145-03710-01/211-00673-00/253-01442-00/330-02017-00) | @Sun, Jacky 115-03878-00turn A 145-03710-0X: FA completed 211-00673-00:FA completed 252-00607-00: FA completed 330-02017-00:FA completed 253-01442-00:FA completed 440-00306-20/470-00847-00 FA completed | MFG ME | 2021-11-25 16:00:00.0000000 +00:00 | 2021-11-29 09:15:25.3041019 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Others | 2.F-5 | Recycle container review -- How many containers are needed according to latest forecast -- How are the containers maintained, repaired, and replaced | 1st Packing introduction will be release on 3/E by NPI. | NPI PE will check the recycle container packing in PR build. FCST also update in WK17, also follow LXTW19 logistic flow. Check the entire recycle container Qty is enough or not. [5/13 updated] Recycle container will continue follow LXTW19 FCST to use. | NPI | 2022-05-12 16:00:00.0000000 +00:00 | 2022-05-28 01:53:10.4506013 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Others | 2.F-6 | Product logistic flow has been defined and agreed with customer | Logistic flow still discuss with customers | Per checked, continue to use the D+2.0 shipping method (follow LXTW). | BD |  | 2022-03-23 19:06:07.9017301 +08:00 | 1
1 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Others | 2.F-7 | Product logistic flow has been set up internally -- Need to include escalation flow or mechanism | Logistic flow still discuss with customers | Per checked, continue to use the D+2.0 shipping method (follow LXTW). | Logistic |  | 2022-03-23 19:06:11.8406834 +08:00 | 1
3 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Not been tested yet. Lab will receive all ELOT units on 6/22. ELOT plan to be finished before 7/9. | 1. TST backlight no function: confirmed as R427 cracked issue found in Assy, fixed. 2. UVA fail: moisture damages DRAM due to unit limitation (not waterproof). Not a real issue. 3. Product package drop bright mark issue: ECO implemented to increase protective film length to cover the edge. 4. Vibration unit auto shut down: caused by type C cable wiggle. Will running change to add a rubber to resolve the issue on 8/E. Confirmed low risk on the current design. @Chuang, Max(ME) | TWN Lab | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 18:02:11.6197082 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Not been tested yet. | Lab will receive all ELOT units on 6/22. ELOT planned to be finished before 7/9. @Wu, Steve 6/30 1. ELOT Test status: Finished Rate: 68.09% ; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=9539&phaseId=&location= 7/2 1. ELOT Test status: Finished Rate: 70.21% ; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=9539&phaseId=&location= ELOT completed by 7/9 | TWN Lab | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 13:50:08.4186171 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Product validation | 3.B-11 | CC test result | LMS-0016987 CT failed 3 pcs with TP ghost touch. DE updates firmware V0.99 and the issue is solved. It will be tested with more units. 6/30 CC Test result: Close; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=16987&phaseId=&location= | FW update to 0.99 and verify Pass, keep tracking in Pre-MP. [8/3] No ghost touch issue in MP, close. | DE | 2021-07-22 16:00:00.0000000 +00:00 | 2021-08-03 13:32:16.9292961 +08:00 | 1
2 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | VT2 96.97% / FT1 96.91% / FT2 95.88% | VT failure units : Cause by o-ring assembly error. All 3 units can pass VT after re-assemble o-ring. [Will keep monitoring assembly SOP & training in 1 st MP] FT1 & FT2 failure units : After EE investigate FT failure units and found out the units are good and the failure was cuase by "OP press wrong button during testing". ["Gain button"] SOP had record this before PR, need keep monitoring training and 1st MP test result. | NPI | 2021-05-06 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 105-03942-00 ETA delay 2 weeks. It may have risk on MP schedule | PCB material delay and cause MP date postpone 2 weeks. (From 04/14 to 04/27) Vendor can;t provide PCB in time, due to vendor capacity issue. Will keep tracking PCB ETA. And update new ramp for design team. [ETA: 04/23] PUR team update ETA in WK16, ETA pull in from 04/23 to 04/16. It is not MP blocker anymore. | PID | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-20 17:34:28.3009378 +08:00 | 1
1 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME: 97%. 1 item is not up-to-date. 330-01834-00 Connector FA is not ready | ME had finished all FA before 04/09. And all data had update in TWN FA system. | MFG ME | 2021-04-08 16:00:00.0000000 +00:00 | 2021-04-13 12:12:16.7139279 +08:00 | 1
1 | Outdoor | Approach Z50 | GMLA #1 | 2021-03-03 11:02:29.2017720 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04145-01_v2 De panel => NG 105-04146-00_v3 De panel => NG | 105-04145-01/105-04146-00 need re-layout PCB and change to router process. [0311] The design team will release panel design on 3/19 OLA time. [0319]ECO220196 | PQE | 2021-03-18 16:00:00.0000000 +00:00 | 2021-04-09 14:10:44.1010017 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | HTMTF testing parameter is not included in 004-01071-00 | Update the operating temp. range & time into 004- Doc for HTMTF & HT station. (Follow the mail discussion among Mason & Tommy, Temp: -15C to +45C, Time: 20 mins in oven [PR version is updated] | EE | 2021-09-30 16:00:00.0000000 +00:00 | 2021-10-29 16:32:08.1788874 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 42 items are not started. 6 items are under testing. The expected complete date:2021/10/6 | Complete on 9/2 | TWN Lab | 2021-09-23 16:00:00.0000000 +00:00 | 2021-09-27 09:41:51.2864729 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Need to verify the strain of 105-04247-00 PRNP fixture before PR build. | The strain measurement of 105-04247-00 PRNP fixture will be implemented before 10/1. -------------------------------------------------------- 105-04247-00 V4 & 105-04247-10 V5 PRNP pass | PQE | 2021-10-14 16:00:00.0000000 +00:00 | 2021-10-15 13:24:04.6766420 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | Long LT of 105-04247-X0 might not meet the schedule | 105-04247-00/10 are waiting for final drawing and approval for MP. 012-04247-30 2nd source IC are under verification [105-04247-00/10 PR version are released ] | PID | 2021-10-31 16:00:00.0000000 +00:00 | 2021-10-29 16:34:09.2953054 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | (1)330-01916-01 raw material with bad coplanarity pin (2)011-05639-00 dust in lens. (Out of spec. 0.2mm) | [monitor yield rate in PR] (1) The inspection fixture has been improved in vendor site, keep monitoring the next batch coplanarity in PR build. Also, coplanarity fixture will be added in IQC and define the inspection frequency. (2) Has report to vendor and waiting for the improving actions | MFG ME/DE | 2021-10-31 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan SMT : Current issue/ ANT Power Level / ASSY : GLONASS、C/No by Ref.、Power Box Sampling | Action take and will review in PR1 Close Meeting. | NPI | 2021-03-18 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | SMT : PRNP is failed but have action plan ASSY : Press Batt. Fixture、Attach Batt. Fixture are failed but will be modified | Fixture has revised and will be retest in WK11 | PQE | 2021-03-11 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | SMT : PRNP is failed but have action plan ASSY : Press Batt. Fixture、Attach Batt. Fixture are failed but will be modified | Fixture has revised and will be retest in WK11 | PQE | 2021-03-11 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | Appearance issues are found but with action plan | Most defects from bezel raw material. ME to ask supplier to improve it. close. see 2.5% failed on bezel appearance in PR. | NPI | 2021-02-08 16:00:00.0000000 +00:00 | 2021-04-07 17:06:36.7600056 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | 16 tests can't be completed by 12/29 | Complete all ELOT and passed | TWN Lab | 2021-01-07 16:00:00.0000000 +00:00 | 2021-04-07 17:07:06.3398717 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | 105-04159-00 PMIC fail. AE may receive new needle on 6/23 and ask QC re-test again | Re-test with new needle completed and PASS | PQE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-06-30 09:42:00.6159559 +08:00 | 1
2 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | 174- doc is not released | NPI PE Simon will provide package picture for PjM on 04/13 and we will keep tracking 174-document release. Estimate : 04/20. 04/21 : design team had update 174-document but not add in BOM yet | NPI | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 24 items did not turn rev.A on the BOM. (011-05029-XX/117-01389-10/145-03193-00...etc) | DE : All items had turned into Rev.A ME: All items had turned into Rev.A | MFG ME/DE | 2022-04-21 16:00:00.0000000 +00:00 | 2022-05-06 12:49:35.4700919 +08:00 | 1
1 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004- MPS is not released to v0A. Final spec. is ongoing | EE had update 004 (rev.A) in Bom on 04/09. [ECO #219098] | MFG EE | 2021-04-08 16:00:00.0000000 +00:00 | 2021-04-13 09:22:14.6745917 +08:00 | 1
1 | Marine | FUSION - RA60 | GMLA #3 | 2021-04-07 15:32:46.8497960 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | OOB checklist is not ready | PQE plan to finished OOB on 04/16. [2 weeks before 1st MP start 04/27] | PQE | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-20 17:33:05.3297493 +08:00 | 1
2 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. ATE 48.79%_suspend current 2. PMIC 28.23%_PMIC program (DSx6) 3. FT 23.58%_HP(L)_Peak Voltage 4. ST 44.7%_Amp Golden Value Different 5. ProductScan 29.03%_Manifest Check 6. CT 11.11%_CompenCNo | 1. ATE 48.79%_suspend current(23.19%) -This issue is related to DRAM IC and can be fixed by reworking the DRAM. NO issues found on pre-MP/MP 2. ST 44.7% _Amp Golden Value Different(7.58%) -Root cause: It is caused by the deviation between Non-Alexa and Alexa SKUs. -Action: ME KuoChich will provide separate golden samples and adjust test program, will verify in Pre-MP. NO issues found on pre-MP. 3. ProdScan 29.03% -Root cause: It is the first time doing packing in T2, NPI retried FQC packing setting of different SKU units and caused a high retry rate. -Action: Environment setting is done, it won't happened at later phase. | NPI | 2021-07-15 16:00:00.0000000 +00:00 | 2021-07-22 13:54:23.6135732 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Pre-boot fixture I704 fail, but NPI will introduce new fixture(add probe) in PR | PE & PQE confirmed close and work well in PR | PQE | 2021-04-06 16:00:00.0000000 +00:00 | 2021-04-07 17:09:15.9126339 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Pre-boot fixture I704 fail, but NPI will introduce new fixture(add probe) in PR | PE and PQE confirmed pass and work well in PR | PQE | 2021-04-06 16:00:00.0000000 +00:00 | 2021-04-07 17:11:19.7049923 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | 1 unit failed on FT3: No function on SS key (ESN:3404199193/TST_-40℃ to 85℃) | Button board and button positioning pillar interference problem. Already modified the tooling. | PQE | 2022-03-03 16:00:00.0000000 +00:00 | 2022-03-04 15:28:48.1653983 +08:00 | 1
2 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate not meet the target <10% ※ASSY 1. RT1 (50.17%)_GPS_L1 by ref 2. RT2 (23%)_與 AP 連線¦(WiFi) Access AP 3. FT1 (18.77%)_GPS_L1 by ref 4. FT3 (8.33%)_電池百分比¦batt. percentage 5. CT (13.67%)_ANTCW TX(CW BOX) CH57 6. HT (10.39%)_GPS_L5 by ref | ※ASSY 1. RT1 (50.17%)_GPS_L1 by ref Asia PR2 will apply different spec for solar/non solar and 2.4G power move to RT2/FT2, will close this item then if seeing positive result. Result positive - issue close. 2. RT2 (23%)_與 AP 連線¦(WiFi) Access AP Issue solved by moving ANTCW test item before WIFI connection test item.- issue close. 3. FT1 (18.77%)_GPS_L1 by ref Asia PR2 will apply different spec for solar/non solar and 2.4G power move to RT2/FT2, will close this item then if seeing positive result. Result positive - issue close 4. FT3 (8.33%)_電池百分比¦batt. percentage Some units have low battery due to retest. (change the retry to 8.33% can be by pass) - issue close 5. CT (13.67%)_ANTCW TX(CW BOX) CH57 Under analysis by design team. not MP blocker_vendor will update the SW - issue close 6. HT (10.39%)_GPS_L5 by ref Vendor has been asked to add visual inspection to make sure no residue left the antenna. - issue close | NPI | 2022-04-07 16:00:00.0000000 +00:00 | 2022-04-19 16:29:56.7931855 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk not meet the target >=1.33 ※ SMT 1. Solar VOC (40mA):0.46 2. Solar Harvest Count (charging 40mA):0.95 ※ ASSY 1. CT_GPS_L5 by ref: 0.48 2. HT_GPS_L1 by ref:0.66 3. HT_GPS_L5 by ref:0.21 4. RT1_GPS_L1 by ref:0.2413 5. RT1_GPS_L5 by ref:0.71 6. FT1_GPS_L1 by ref:0.27 7. FT1_GPS_L5 by ref:0.71 | MFG PE and EE agree to by pass this item - issue close | NPI | 2022-03-30 16:00:00.0000000 +00:00 | 2022-04-01 11:36:45.6587646 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT: 1. 10% BK current 0.21 2. WiFi Power 2.4G diff with GS 0.81 3. C/No¦Snr 1.03 4. USB startup current 1.3 5. PVSYS 1.31 ASSY: 1. CT/HT/FT CompenCNo 0.6/0.54/0.83 2. Drift - Compare with RTESN 1.13 3. Compen C/No by ref 0.74 4. Amp Golden Value Different 1.09 | ATE: Wifi power: Need to provide new golden sample and verify in pre-MP. Others are low risk. New golden sample provided for production with low retry rate, close. Assy: No CN related high retry issue was found in PR. No drift related fail was found in PR. Low risk. CN spec modified and expected to reduce retry in 2nd MP, close. | NPI | 2021-07-15 16:00:00.0000000 +00:00 | 2021-08-03 13:33:49.4799889 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Some FA of ME and DE parts are not completed. Completed rate: 1. ME 92% 2. DE 0% | CLA and cable FA completed 7/16. Display FA completed. | MFG ME/DE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 13:55:56.4256171 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-6 | Check verification result of critical process (PVP) -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check -- Action plan if verification result fail | Solar thickness can't meet Cpk target but have action plan | Will check in PR2. | NPI | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Inspection VIP not ready: ※ME parts: 145-03193-XX/145-03688-00/145-03739-0X...total 32 part GPN) ※DE parts: 011-05920-2X/362-00115-10/439-05157-0X/440-00305-00...total 9 part GPN) | Complete all items. | MFG ME/DE | 2022-03-30 16:00:00.0000000 +00:00 | 2022-04-19 17:02:55.0272220 +08:00 | 1
2 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 14% - ME part 51 items not ready - DE part 9 items not ready | - ME part 10 items not ready - DE part 3 items not ready | MFG ME/DE | 2022-05-19 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Critical testing item can't meet Cpk target but have improvement plan | Will check in PR2. | NPI | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | Screw rear case & housing/Screw PCB on rear case fail but have action plan | 3/8 Assy fixture test Pass | PQE | 2021-03-07 16:00:00.0000000 +00:00 | 2021-03-09 09:57:56.1133333 +00:00 | 1
4 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Product validation | 3.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT is not completed but can be finished before Pre MP . In Queue: 4 items(5.4.4、CT scan、Low temp operation) Test: 2 items (5.2.9) | PR2 is close to MP date, lab is still ongoing. Major items r reviewed and pass. 鹽霧 Tumble ESD Fail(WAIVE): - 鹽霧生鏽是因為PCB上的調試電路在兩個引腳之間產生浮動電荷，從而導致腐蝕 工程回覆MP不會調整電路所以不會有這狀況發生 - Tumble / ESD (WAIVE) OLA: 與FR45水準相同 [Darwin(LAB)] has upload the files in cheklist | TWN Lab | 2021-04-29 16:00:00.0000000 +00:00 | 2021-04-23 14:25:10.3917459 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-14 | Golden sample and bad sample preparation plan -- Sample Q'ty | Can't find golden sample and bad sample preparation plan in PID checklist | Close. With golden samples in PR | MFG EE | 2021-02-28 16:00:00.0000000 +00:00 | 2021-04-07 17:16:21.0418216 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Bezel & solar quality will be verified in next small build | Bezel raw material quality will be improved in PR - @Yang, Howard close. see 2.5% failed on bezel appearance in PR. | MFG ME | 2021-02-08 16:00:00.0000000 +00:00 | 2021-04-07 17:16:43.8727576 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | 1. RedPine SW is not mature (006-B3651-01) 2. Flashlight can't be turned on. Olathe provide new SW (006-B3907-00) 3. GPS can't receive L5. Olathe provide new SW (006-B3865-01/006-B3866-01) | SW issue has been fixed during FFP. | MFG EE | 2021-02-09 16:00:00.0000000 +00:00 | 2021-02-03 08:47:42.6133333 +00:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | Design review date: 1/19. All test will be finished until 1/21. | Design review date: 1/19. All test will be finished until 1/21. [0121 update] ELOT finished, no other failure found. | TWN Lab | 2021-02-09 16:00:00.0000000 +00:00 | 2021-02-03 08:49:51.5800000 +00:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 011-05514-0A, 011-05513-0A, 011-05513-30, 015-05513-3X, 161-05472-00, K00-01246-00 are not released to version A | All parts are A-rev | NPI/ME/DE | 2021-07-21 16:00:00.0000000 +00:00 | 2021-07-22 13:44:50.5074242 +08:00 | 1
3 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT is planned to be finished before 7/9. | 1. HT 5.5V fail: no issue is found in OLA. Confirmed to waive and approved for MP. 2. HT 4.5V fail: see 3.B-6 for details. 3. Drop fail (1/6): The fail unit has done the TST before, and it is over-testing. Total fail rate: 1/9 (including Olathe). Low risk as the actual use condition (car interior) will also not land on the hard floor. 4. Vibration unit auto shut down: caused by type C cable wiggle. Will running change to add a rubber to resolve the issue. Confirmed low risk on the current design. | TWN Lab | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 18:03:21.4772144 +08:00 | 1
2 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | LCM lift issue is found with unglued unit. Olathe agree to use glued unit as MP type. ME will test two countermeasures. 1. The vendor will have a tooling trial 6/22 to see if the flatness can be improved by adjusting the parameter. 2. Clamp the display and front case while applying glue on 6/22. | Issue: LCM lift is found on unglued units. Root cause: Case warpage. Action: All the units will be glued, in addition, ME will try two solutions as below, 1. The vendor will have a tooling trial on 6/22 to see if the flatness can be improved by adjusting the parameter. 2. Clamp the display and front case while applying glue. The reworked units with clamp solution test PASS. Plan to have PR2 on WK30 for validation. PR2 validated PASS with the solution, close. | MFG ME | 2021-07-22 16:00:00.0000000 +00:00 | 2021-08-03 14:13:03.4921107 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is planned to be finished and summarized before 7/9. | Lab received units on 6/16 and planned to provide ELOT results before 7/2. 7/2 ELOT Test status: Finished Rate: 78.72% https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=9457&phaseId=&location= Uncompleted item section 5.4 / XRF / Drop / Clcik Ration / CT Scan ELOT completed by 7/9. | TWN Lab | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 13:43:06.5725887 +08:00 | 1
2 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. ATE 28.5%_suspend current 2. ST 16.57%_left MIC Freq. 3. FT 25.61%_Compen C/No by ref 4. ProdScan 36.89%_Download manifest from DUT | 1. ATE 28.5%_suspend current - This issue is related to DRAM IC and can be fixed by reworking the DRAM. No suspend current issue on PR2. 2. ST 16.57%_left MIC Freq. - Engineering test PASS on DS66 that will attach tape to fix FPC. Confirmed to attach FPC by tape and engineering test PASS. 3. FT 25.61%_Compen C/No by ref - 2nd source Unictron antenna units have a lower average CNR, confirmed to be removed from BOM. 4. ProdScan 36.89%_Download manifest from DUT - Root cause: It is the first time doing packing in T2, NPI retried FQC packing setting of different SKU units and caused a high retry rate. -Action: Environment setting is done, it won't happened at later phase. | MFG EE |  | 2021-07-22 13:58:46.1191011 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-5 | Check verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine -- Action plan if verification result fail | There is a high VT test retry issue in FFP build and NPI will make new fixture to decrease gap between F/C and middle frame. | NPI will make new fixture to decrease gap between F/C and middle frame. [PR] In PR, new fixture of F/C pressing is verified with good result. | NPI | 2021-04-15 16:00:00.0000000 +00:00 | 2021-07-07 13:40:35.9115233 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. ATE - C/No¦Snr 0.72 2. ATE - 100% BK current 0.74 3. ATE - BT CW Medium 0.8 4. ATE - BT CW Low 0.94 5. ATE - BT CW High0.93 ASSY 1. CT/HT/FT CompenCNo 0.88/1.23/0.51 2. FT Compen C/No by ref 0.57 | SMT: 100% BK current will adjust the test specifications and no retry occur in other items. Other items no concern per TWN EE confirm with OLA. ASSY : No CN related high retry issue was found in PR. Keep monitor related items in MP. | NPI | 2021-08-19 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | HT GPS_L1, FT1 wifi power, FT1 ANT power, LED1A_PD1 Cpk are less than 1.33 | [Update] PR result in attached 1. CT high retry rate is caused by GPS L5. Will have L5 golden and auto chamber to reduce variance in PR. --> PR 2 CT retry 9.1% 2. FT1 wifi/ANT -> will change ANT design to fix better in PR / will use auto chamber in PR and adjust ANT position on fixture again. --> PR 2 FT1 retry 16.6% 3. LED1A -> will modify pressing fixture at supplier side. --> fixture been modified and verified in PR | NPI | 2021-04-18 16:00:00.0000000 +00:00 | 2021-07-07 14:30:28.8236895 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Some FA of ME and DE parts are not completed. Completed rate: 1. ME 76% 2. DE 0% | CLA/Cables FA completed by 7/16. Display FA completed by 7/16. | MFG ME/DE | 2021-07-15 16:00:00.0000000 +00:00 | 2021-07-22 13:43:21.5134338 +08:00 | 1
1 | Automotive | DriveSmart 66 | GMLA #3 | 2021-06-22 11:10:11.5055856 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Some FA of ME and DE parts are not completed. Completed rate: 1. ME 76% 2. DE 0% | CLA/Cables FA completed by 7/16. Display FA completed by 7/16. | MFG ME/DE | 2021-07-15 16:00:00.0000000 +00:00 | 2021-07-22 13:43:27.8727924 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | The cover of PRNP/Screw fixture didn't pass ESD test | Replace cover with static-proof one, will modify fixture material in next build. [0319 update] Implement new material with PRNP cover and passed. | PQE | 2021-03-18 16:00:00.0000000 +00:00 | 2021-04-12 14:50:01.9154123 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-12 | High risk/ process ESD risk review -- Performed dynamic measurement to SMT/ LCM/ Assy process (EX: Measured ESD of film/ tape removal ) -- Action plan for risk operation (ESD overvoltage) | The cover of PRNP/Screw fixture didn't pass ESD test | Replace cover with static-proof one, will modify fixture material in next build. [0319 update] Implement new material with PRNP cover and passed. | PQE | 2021-03-18 16:00:00.0000000 +00:00 | 2021-04-12 14:50:24.8626064 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Bezel forging part's dimension will be verified at next build. | Bezel forging part's dimension will be inspected with fixture in Pilot run build. | MFG ME | 2021-04-18 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Product development | 2.A-10 | Verify the test program of SMT and ASSY station before FFP build for new SW release | Non-ready IOP: - Clear unlock code IOP 10/166 (reported issue to Olathe SE) - Clear wifi connection information IOP 10/1847 (Only do 5G http download test and skip 2.4G in FFP, fixed in SW v0.83) | TW SW keeps discuss with OLA SW. SW issue is expected to be finished before 8/19. _SW Damon. Update] PR SW will ready on 9/7. | MFG EE | 2021-09-06 16:00:00.0000000 +00:00 | 2021-10-28 11:35:30.5943866 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | Yield loss of the scratch on soft rubber is 100%. ME will ask OLA to add masking tape on soft rubber parts. | Will add protection tape in next build. _ME Bob. [Update] Still remain 35.8% failure rate in PR, solution hasn’t been defined. Update in G3 same item 3.B-6. | MFG ME | 2021-11-04 16:00:00.0000000 +00:00 | 2022-03-16 17:19:33.1735052 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 011-05583-1A 011-05585-1A 011-05532-02 011-05532-19 011-05532-56 011-05532-62 015-05532-0X 011-05585-3A 011-05585-5A 011-05585-7A 011-05585-AA 161-05473-00 K00-01246-07 are lower than version A. | All parts are A-rev by 7/16. | NPI/ME/DE | 2021-07-15 16:00:00.0000000 +00:00 | 2021-07-22 13:47:20.6898556 +08:00 | 1
2 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | 1. ATE 96.14%_suspend current 2. ST 95.45%_dark screen 3. RTESN: 88.61%_dark screen | 1. ATE 96.14% -6 pcs fail on “suspend current”. NO issues found on pre-MP/MP -2 pcs fail on “VPER1”, under analysis. Confirmed as PMIC component issue. Low retry in MP. 2. ST 95.45%/ RTESN 88.61%_dark screen -Root cause: ATE_V4 fixture interfere PCB_V5, and cause some board's component R427 to crack. -Action: AE and EE will both check the interference when PCB changes to the next version. No issue on pre-MP/MP | NPI | 2021-07-13 16:00:00.0000000 +00:00 | 2021-07-22 13:53:02.2207885 +08:00 | 1
2 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | 174-00568-00 not release | Waiting for package release, keep tracking. ----------------------------------------------------------------------- Production release on 3/9 | NPI | 2022-03-17 16:00:00.0000000 +00:00 | 2022-03-17 11:07:08.5912727 +08:00 | 1
3 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT issue found ※ Non Solar SKU 1. High Temp., Max Voltage Life_85℃/5.5V (1/1) 2. High Temp., Min Voltage Life_85℃/4.5V(1/1) 3. Electrostatic Discharge (ESD) Immunity test (2/2) 4. Product Package Drop (2/2) ※ Solar SKU 1. Storage Hot/Cold Unit Performance_-40℃ to 85℃ (1/1) 2. Salt Fog (1/1) 3. High Temp., Min Voltage Life_85℃/4.5V(1/1) 4. Electrostatic Discharge (ESD) Immunity test (1/2) | ※ Non Solar SKU 1. High Temp., Max Voltage Life_85℃/5.5V: Weather cap broken. Tooling modified for strengthen per ECO#238608.- issue close 2. High Temp., Min Voltage Life_85℃/4.5V Will do the running change on FPC, not MP blocker. - issue close 3. Electrostatic Discharge (ESD) Immunity test: Already retested and passed, design team agrees to allow users to select the transformer of 010-13023-01. - issue close 4. Product Package Drop (2/2) Passed the drop test after changed the package materials. - issue close ※ Solar SKU 1. Storage Hot/Cold Unit Performance_-40℃ to 85℃: Same as non-solar SKU item 1.- issue close 2. Salt Fog (1/1) The stains are light and only occur at lasered artwork location which anodizing layer is weaker due to laser etching. This is to be deemed waiver per condition and process limitation. - issue close 3. High Temp., Min Voltage Life_85℃/4.5V Same as non-solar SKU item 1.- issue close 4. Electrostatic Discharge (ESD) Immunity test: Already retested and passed, design team agrees to allow users to select the transformer of 010-13023-01. - issue close | TWN Lab | 2022-03-22 16:00:00.0000000 +00:00 | 2022-03-23 13:41:12.3768988 +08:00 | 1
1 | Fitness | Edge 1040 | GMLA #3 | 2022-02-25 15:20:17.7715426 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing. The expected complete date is 3/5 | ELOT complete. | TWN Lab | 2022-03-17 16:00:00.0000000 +00:00 | 2022-03-18 15:45:03.6393477 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | LMS 10462-6 Finished Rate: 42.55% Completed items: 20 In completed items: 27 Fail items: 5 Expected Completed Date: 8/13 | LMS 10462-6 Finished Rate: 69.81% Fail items: 9 Expected Completed Date: 8/13_Lab Steve | TWN Lab | 2021-08-19 16:00:00.0000000 +00:00 | 2021-10-28 11:37:57.0004692 +08:00 | 1
3 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Material is risky for MP, especailly below 013-00970-00: ETA wk29, 013-00971-00: ETA wk29, 105-04158-00: ETW wk28, 320-01461-00: only 200pcs LTA, 320-01461-10: only 200pcs LTA, 320-01462-00: only 200pcs LTA, 320-01462-10: only 200pcs LTA, 717-00198-00: 300pcs*wk27 & 19.4k*wk30, 717-00198-01: 2nd source antenna 351pcs on hand. | Materials are ready for pre-MP on 7/12. | PID | 2021-07-18 16:00:00.0000000 +00:00 | 2021-07-08 16:28:10.5059882 +08:00 | 1
1 | Automotive | DriveSmart 76 | GMLA #3 | 2021-06-22 15:15:02.6567788 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Some FA of ME and DE parts are not completed. Completed rate: 1. ME 92% 2. DE 0% | CLA and cable FA completed 7/16. Display FA completed. | MFG ME/DE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-22 13:56:04.6604232 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | There is no peak temperature of 522-00094-01. (012-04166-20) Wait for OLA's reply. | Already informed OLA on 7/21. Wait for OLA's reply. _NPI Derek. -OLA added information on 522-00094-01. (260) | NPI | 2021-08-12 16:00:00.0000000 +00:00 | 2021-08-03 10:20:42.6158270 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Process validation | 2.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result | Need to provide the information of verification report |  | PDO/AE |  |  | 0
4 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01077-00 is not added-in BOM | 004-File is MP version and + in 010-02562-XX already | MFG EE | 2021-04-29 16:00:00.0000000 +00:00 | 2021-04-20 14:28:17.6100424 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | BOM cannot meet ver. A in PR build (see attachment) 010- / 011- / 015- / 145- / 161- / 190-1 / 252- / K00- | 161-, 190- not turn A. Need PjM’s help to push for A-rev. @Lyman, Lindsey | NPI/ME/DE | 2021-07-01 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ ASSY/ LCM) -- Measurement position and result | Screwing Fixture is failed |  | PQE |  |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | 1. Housing cosmetic issue 2. TP function issue |  | MFG ME/DE |  |  | 0
3 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 26 test items are ongoing. Need to check the test result on 7/13. 7/2 6 test items are ongoing. Need to check the test result on 7/13. | 1. UVA fail: moisture damages DRAM due to unit limitation (not waterproof). Not a real issue. 2. Drop fail: confirmed as display module issue. Confirmed as low risk and move forward as the crack occurred after 2 rounds of face down drop. 3. Vibration unit auto shut down: caused by type C cable wiggle. Will running change to add a rubber to resolve the issue on 8/E. Confirmed low risk on the current design. | TWN Lab | 2021-07-12 16:00:00.0000000 +00:00 | 2021-08-03 14:10:19.2793753 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 26 test items are ongoing. Need to check the test result on 7/13. | ELOT planned to be finished before 7/13 @Wu, Steve 6/30 ELOT Test status: Finished Rate: 85.42% ; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=11957&phaseId=&location= 7/2 ELOT Test status: Finished Rate: 87.50% ; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=11957&phaseId=&location= ELOT complete by 7/13 | TWN Lab | 2021-07-12 16:00:00.0000000 +00:00 | 2021-07-22 14:06:05.6239305 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Product validation | 3.B-11 | CC test result | 8 unit fail on ST and FT after CC test | ST issue is related to the short FPC design, see 3.D-13 for details. @Chuang, Max(ME) FT PASS after retest. 6/30 CC Test result: Inprogress ; https://etrex8.garmin.com:8888/LMS/HeaderCreatePageInit.action?headerId=17223&phaseId=&location= | PQE | 2021-08-15 16:00:00.0000000 +00:00 | 2021-08-17 21:55:20.4896637 +08:00 | 1
2 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | ATE 94.91%: Suspend current | Root cause is still TBD. Plan to have PR2 on DS76 for socket programming process as mitigation plan. @Chen, Leon Both socket and PMIC verified on 76/66 PASS. Keep tracking DS86 MP status. | NPI | 2021-09-09 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04174-00 (v01) is not production released | 007-04174-00 is releasing to version A by ECO#233569 on 11/18 | MFG ME | 2021-11-17 16:00:00.0000000 +00:00 | 2021-11-18 14:36:15.6468935 +08:00 | 1
2 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT (1) ATE 30.24%: Battery startup current 2. ASSY with Alexa sku (1) ST 77.7%: left MIC sealed MAX Amp. (2) FT2 30.41%: Compen C/No by ref 3. ASSY with non-Alexa sku (1) ST 18.41%: Speaker AMP (2) FT2 57.89%: Battery Volt. (3) ProdScan 28.57%: Manifest Check | Top 3 issue item (1) ST 77.7%: left MIC sealed MAX Amp. Related to the short FPC design, see 3.D-13 for details. @Chuang, Max(ME) (2) FT2 57.89%: Battery Volt. Suspected that units were not shut down after test completed and run out of battery. Will check all units were charged before B/I and reinforce training. @Liu, Johnny (3) FT2 30.41%: Compen C/No by ref PR spec is tighter than previous build. Will review the spec and update before pre-MP. @Chen, Leon | NPI | 2021-09-09 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Process validation | 3.D-13 | Review MP block issue (PR issue in PRWeb) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | ST high retry (37.84%) and noise: Left MIC sealed MAX Amp | S/T: Fixing FPC by glue engineering test PASS. 30 pcs small build with 3 condition test completed. Plan to apply glue to fix Mic, which is validated PASS on DS86 PR2. L/T: ECO to increase FPC length by 0.5mm, validated OK on DS86 PR2. | NPI | 2021-08-15 16:00:00.0000000 +00:00 | 2021-08-17 21:54:49.9802090 +08:00 | 1
1 | Automotive | DriveSmart 86 | GMLA #3 | 2021-06-23 13:40:24.8281002 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate ME 81%: 11 items are not up-to-date DE 100% | CLA/Cables FA completed. | MFG ME | 2021-07-30 16:00:00.0000000 +00:00 | 2021-07-22 14:10:29.2170341 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | ASSY: (1) CT-GPS_L1 by ref: 0.98 (2) CT-GPS_L5 by ref: 0.92 (3) CT-Galileo by ref: 0.74 (4) HT-GPS_L1 by ref: 1.21 (5) ST-Mic Amp Diff. with Golden: 0.53 (6) FT1-GPS_L1 by ref: 0.82 (7) FT1-GPS_L5 by ref: 0.94 (8) FT1-外部CN值: 0.5 (9) Baro-0.5 ATM diff with golden: 0.69 | Top 3 of 2.D-10 are same as 2.D-9 top 3 ASSY: Update in G3 3.D-10 (1) ST-Mic Amp Diff. with Golden: 0.53 -Root cause: The value of the golden ST sample is not in the middle of the distribution. -Action: AE KuoChih provides a new golden sample on 7/28._Done (2) [Close] FT1-外部CN值: 0.5 -Root cause: The testing fixture didn't supply power and caused the USB disconnection. - Action: Build code in fixture's iATE board to keep supplying power during FT. - Evidence: Already finished during FFP. (3) [Close] Baro-0.5 ATM diff with golden: 0.69 -Root cause: Designed Baro meter IC requires specific stable time after SMT (1~2 wks roughly). -Action: Discussed with Olathe and confirmed spec will be loosen from 150 to 300 pa as other products using this IC. -Evidence: No high retry issue was reported in PR | EE | 2021-11-21 16:00:00.0000000 +00:00 | 2022-03-16 17:20:25.3990597 +08:00 | 1
2 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. RTESN 19.42%: Iridium Tx CH01 2. VT1 13.21%: Leakage 1120 3. CT 15.38%: Unit Temp. 4. HT 20.19%: Check ProductionMap 5. G Sensor: 16.35%: Diff Y 6. Gyro 18.27%: Gyro Data X-axis (CCW #1) 7. ST 68.27%: WiFi Access AP (2.4G) 8. VT2 54.81%: 小漏氣_超過洩漏量門檻 9. Compass 10.58%: [Compass]Vector Error 10. FT 41.35%: GPS_L1 by ref 11. Baro 14.56%: Get Golden Unit Pressure | Top 3 1. ST 68.27% - Fail item: WiFi Access AP (2.4G) - Root cause: SW issue due to improper ITMXP program setting. - Action: EE adjust IOP sequence for test stability, and cycle test pass. Tracking on Pre-MP. 2. VT2 54.81% - Fail item: 小漏氣_超過洩漏量門檻 - Root cause: SD door module leaked due to dust - Action: PE define the clean method into SOP and VT2 pass after clean. Tracking on Pre-MP. 3. FT 41.35% - Fail item: GPS_L1 by ref - Root cause: OP retry 3 failed units too many times (4~5 times) - Action: Re-calibration and pass FT. EE will define the calibration method to SOP. Tracking on Pre-MP. | NPI | 2021-12-09 16:00:00.0000000 +00:00 | 2022-02-21 10:03:11.5458405 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | 1. GPS_L1 by ref: 0.56 2. GPS_L5 by ref: 0.78 3. External CN: 0.26 | All items are confirmed by EE, and all items would be OK. | MFG EE | 2021-11-18 16:00:00.0000000 +00:00 | 2021-11-18 14:23:14.4410779 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Supply chain/ supply of part | 2.E-1 | The relevant supply chain of 2nd source selection for critical parts in MPM system have been finalized | 2nd source for coaxial cable is under discussion. | Got 2nd source sample alreay. _ME Bob | ME | 2021-08-05 16:00:00.0000000 +00:00 | 2021-10-28 11:32:31.3952428 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. 開機電流4.1 V & 3.8V 0.69 & 0.84 2. LDO12 0.77 3. 常溫充電電流 0.29 4. MIC1 MAX Amp 0.82 5. ABS Raw_Accel_X & Y 0.49 & 0.41 ASSY No Cpk data. Need to upload it to PRWeb and implement the action for Cpk < 1.33 item | MT: Item (1) (2) (4) (5) EE confirm it would be OK. Item (3): Adjust USL SPEC to 600mA by 9/17. ASSY: All items are confirmed by EE, and all items would be OK. | EE | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-30 16:03:09.3156167 +08:00 | 1
1 | Outdoor | Descent G1 | GMLA #1 | 2021-04-03 08:24:22.4103144 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Complete De-panel test by 5/7, Screw test by 4/16 | Complete De-panel test by 5/7, Screw test by 4/16 all have been completed, and result Pass | PQE | 2021-05-06 16:00:00.0000000 +00:00 | 2021-05-31 09:08:34.6608119 +08:00 | 1
1 | Outdoor | Delta Simple | GMLA #1 | 2021-04-26 17:57:59.4898304 +08:00 | Product validation | 1.B-2 | ELOT plan | No ELOT test plan created on the LMS system | ELOT test plan for WP2 have been created on 5/4. | ME | 2021-05-03 16:00:00.0000000 +00:00 | 2021-05-04 19:39:18.7371385 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ ASSY/ LCM) -- Measurement position and result | ESD measurement is not finished | ESD measurement is complete on 9/30. | PQE | 2021-09-29 16:00:00.0000000 +00:00 | 2021-09-30 16:00:06.5797683 +08:00 | 1
1 | Outdoor | Descent G1 | GMLA #2 | 2021-06-29 16:44:14.7262153 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Top 3 critical items 1. ANT Power(CH57) 0.5 2. C/No 0.91 3. C/No GLONASS_65 0.96 | C/No dropped: EE @Chang, Jeffrey(EE) continue analyzing, suspected may be related to the interference of the FP test environment, continuous to verify more units to proof | MFG EE | 2021-09-29 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Delta Simple | GMLA #2 | 2021-12-02 17:27:57.0174302 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 11 items are not started. 2 items are under testing. The expected complete date:2021/12/28 | ELOT complete | TWN Lab | 2021-12-21 16:00:00.0000000 +00:00 | 2021-12-22 15:23:00.4539630 +08:00 | 1
1 | Outdoor | Approach G12 | GMLA #2 | 2020-12-25 09:13:44.4670000 +00:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT results are not complete. 19 item still under testing: Thermal shock/Temperature and Humidity Cycle Test/Salt Fog/Mechanical Vibration/Tumble…etc The expected complete date:2021/1/10 | ELOT progress: 100%, Complete on 2021-01-21 | TWN Lab |  | 2021-02-06 13:49:15.6366260 +08:00 | 1
1 | Outdoor | Approach G12 | GMLA #2 | 2020-12-25 09:13:44.4670000 +00:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Low CPK of BLE/GPS which not meet the 1.33 target | For low CPK of BLE, Olathe and TW EE has adjusted the USL/LSL in MPS rev.B to meet the performance of BLE radiated power in CT. For low CPK of GPS, EE and PE has optimized the fixture setup inside the production chamber to reduce the impact of cable. Verify result in PR. CPK of BLE in CT: 0.35 CPK of GPS in CT:0.67 | NPI |  | 2021-02-06 13:49:24.3511780 +08:00 | 1
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | Need to update ASSY VIP for FFP | Completed and uploaded in PR web on 4/14. | MFG ME | 2021-04-13 16:00:00.0000000 +00:00 | 2021-04-14 16:11:22.8577677 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Product development | 2.A-5 | Design lockdown for 015- drawing -- Special characteristic should be included -- Process development should meet 015- drawing | 015-05578-0X is NRL |  | MFG ME/DE |  |  | 0
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-5 | Check verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine -- Action plan if verification result fail | 1. "-" type screwing machine is under verification 2. Gearbox electrical fixture is under verification (ETA 5/7) | Change to Jade’s screw in PR. Plan to verify with small amount of units before PR starts.  ETA of new screw  5/31*1K  Arrange small build for verification (new screw + PR gearbox) before PR [6/21] small build of new screw + examined gearbox shows positive, keeps tracking result in PR | NPI | 2021-05-26 16:00:00.0000000 +00:00 | 2021-06-29 18:04:55.7753281 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT ongoing, est complete date: 11-26. |  | TWN Lab |  |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Process development | 2.C-3 | Release preliminary PFMEA -- Special characteristic should be included and must correspond with D/PFMEA -- Poka-Yoke/ LL should be taken into account in PFMEA -- Ergonomically designed (人因工程設計) should be taken into account to all work station | No SMT PFMEA updated |  | NPI |  |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | Prod Scan fail: GPS time offset issue but have action plan | Working with Design Team | MFG EE | 2021-05-06 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process development | 3.C-3 | (AOEM) update PFMEA / (Consumer) DFM report_ process review for PR build -- Special characteristic should be included and must correspond with D/PFMEA -- Poka-Yoke/ LL should be taken into account in PFMEA -- Ergonomically designed (人因工程設計) should be taken into account to all work station | CR / SMT flow chart from DFM need to update | Waiting for PIC to renew the file. | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process development | 3.C-4 | Update flow chart for PR build -- key characteristic should be included and must correspond with D/PFMEA | CR / SMT part of key characteristic is not meet DFM critical process items | Waiting for PIC to renew the file. | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
4 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Strain gauge result FAIL with action plan MB: I307 screwing、buckle Conn are NG | Implement Underfill in I307. | PQE | 2021-04-29 16:00:00.0000000 +00:00 | 2021-04-20 13:55:04.6545364 +08:00 | 1
3 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | UV-A and ESD test failed and are under analysis | 1. UV-A were acceptable and by-passed by Olathe. 2. ESD tape design has its constrain and could not cover all risk components. Design is under discussion. | TWN Lab | 2021-01-14 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | No IQC fixture due to FA VIP not finished | 1. ME: FA of 011-05302-20, 013-00797-03 and 145-03421-00 are still undergoing. 2. DE: FA will be ready after MTF resolution is defined. | MFG EE/ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | RTESN < 97% | Failure rate occurred on RTESN was component damage. Implemented sorting test to evaluate process improvement. | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT: ATE ASSY: RTESN、CCM_B、ST、CCM_3in1、RTMTF、HTMTF、CT/HT、Image_Check、FT | 1. ATE - CAP (1st ) (6.76%): EE adjusted the testing programming and loose the upper limit from 4 to 4.8. 2. RTESN- 轉測試模式¦Switch to test mode/(WiFi) Creat AP (20.5/6.5%): component damage, implemented sorting process in each process in pre-MP phase. 3. ST- 喇叭平均振幅差值(6K)¦VOL Average Amp.6K Difference (12.17%): All units passed the test, should re-define the distance b/w unit and noise meter. | NPI | 2021-02-25 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Some of SMT CPK issue not meet target but have action plan | ATE grounding will be checked and implemented in pre-MP | NPI | 2021-02-25 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | MTF variance is unstable | One FRM178 for MTF check started on 12/28, will have result updated by 1/8. | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | No Supplier inspection preparation due to FA VIP not finished | 1. ME: FA of 011-05302-20, 013-00797-03 and 145-03421-00 are still undergoing. 2. DE: FA will be ready after MTF resolution is defined. | MFG EE/ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME FA Rate: 86%; DE FA Rate : 0% | 1. ME: FA of 011-05302-20, 013-00797-03 and 145-03421-00 are still undergoing. 2. DE: FA will be ready after MTF resolution is defined. | MFG ME/DE | 2021-01-28 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No 805-C8330-JD Max peak Temp. |  | NPI |  |  | 0
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-16 | Process outsourcing parts evaluation result -- Cpk/ yield rate/ UPH data should be ready | No corresponding doc.( Cpk/yield/UPH ) uploaded for this section. | OSP PE will provide related document for outsourcing review. 5/31 update yield rate & fixture list in vendor site | MFG ME/DE | 2021-05-30 16:00:00.0000000 +00:00 | 2021-05-31 15:36:29.3064235 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | several items drawing have not turn A may shortage next build 1. MB PCB 2. LRA FPC 3. Battery | High risk on battery ETA for MP 1. MB PCB  Already set material preparation. 2. LRA FPC  Already set material preparation. 3. Battery  Due to ELOT fail, the material preparation is not approved. 5/E FFP Q-sun/ UVB fail 6/25 Modify SW & PCBA to solve wak up issue under HT 7/1 Design team approved for setting battery MP 7/2~ Buyer set PO and keep tracking ETA for MP | PID | 2021-07-08 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT results are not complete. Water Dust Resistance /Accelerated Weathering UV still under testing The expected complete date:2021/1/15 | FFP ELOT completed on 1/12 Salt fog failure: Will run another 48 hrs. test in Olathe see if the specification should be adjusted. Update: FFP ELOT completed before 1/22. | TWN Lab | 2021-01-21 16:00:00.0000000 +00:00 | 2021-08-26 14:48:39.0958035 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #2 | 2021-05-12 14:49:06.6247015 +08:00 | Product validation | 2.B-4 | Release unit level appearance standard for FFP -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) -- Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | Can't find any reference or comment on PRweb in 5/12 | @Chien, Jason(ME) will refer to WQ-000563 for this stage. If there are any further requirements, the specific document will be released later. | MFG ME | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-17 09:58:02.8828665 +08:00 | 1
1 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT is on-going and can be completed by 3/31 | ELOT completed by 3/31 | TWN Lab | 2021-03-30 16:00:00.0000000 +00:00 | 2021-04-01 10:19:09.3215078 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #2 | 2021-05-12 14:49:06.6247015 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | VBAT current (GNSS on BL off) 0.36, VEXT Charge Current(GNSS on) 1.17, No assy CPK | Vbat current - EE adjusted the test procedures. Vext charge current – EE adjusted the upper and lower limit spec and added the fail command | NPI | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-17 09:58:21.2275570 +08:00 | 1
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | Salt Fog is testing. (until 4/15) | Salt fog test completed on 4/14, the result is pass (refer to LMS-0012423-3-TW). | TWN Lab | 2021-04-13 16:00:00.0000000 +00:00 | 2021-04-14 16:11:34.0312876 +08:00 | 1
1 | Outdoor | Delta Simple | GMLA #1 | 2021-04-26 17:57:59.4898304 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04401-00_V2 De-Panel strain measurement fail. I100 strain force measured to 488 um/mm (spec:350) | The v2 panel use v-cut design. NPI PE is disguising with designer to change the de-panel design from v-cut to mouse bite. The strain gauge will be remeasured in v3. [8/31] The v2 panel use v-cut design. Have modified the de-panel design from v-cut to mouse bite in v3. Strain gauge still fail, router will be implemented in FFP de-panel process. | NPI/PQE | 2021-08-05 16:00:00.0000000 +00:00 | 2021-08-31 15:23:24.7265050 +08:00 | 1
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | 1. SMT Auto Power-On Crnt 14.4V 0.91 & Auto Power-On Crnt 28.8V 0.71 / 2. No ASSY Cpk result. | Will relax specification in PR. Update: Keep tracking in GMLA3 | EE | 2021-04-28 16:00:00.0000000 +00:00 | 2021-06-24 23:17:24.6922448 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #2 | 2021-12-20 18:48:32.4156611 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | CT/HT temperature Cpk<1.33 => Parameter setting on-going. FT BT level test Cpk<1.33 => Golden re-build. | PE will tune the oven speed setting, verify in 2022/Jan PR build. | NPI | 2022-01-20 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | IXWW22 | GMLA #2 | 2021-12-20 18:48:32.4156611 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | CT/HT temperature Cpk<1.33 => Parameter setting on-going. FT BT level test Cpk<1.33 => Golden re-build. | EE send the calibrated golden sample on 12/23, verify in 2022/Jan PR build. PR-1/PR-2 BT verification are still fail, issue not solven. Keeps open. | MFG EE | 2022-03-03 16:00:00.0000000 +00:00 |  | 0
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | ASSY screw PCB fixture: 475V >> NG (Spec: < 100V). Need NPI to evaluate new material or add an ionic fan in process | Under solution evaluation, will have re-measurement result on 4/21. | PQE | 2021-04-20 16:00:00.0000000 +00:00 | 2021-06-24 23:17:36.2391351 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | ME will fix the VIP/fixture before FA finish (plan on 11/15) | ME Bob will fix the VIP/fixture before FA finish before 11/15. Postponed to 11/29. | MFG EE/ME/DE | 2021-11-28 16:00:00.0000000 +00:00 | 2022-03-16 17:21:05.1031684 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Yield < 97% ASSY: 1. VT1 (71.05%)-大漏氣_未抽至1120. 2. VT2 (75.93%)-Same issue as VT1. | Issue: VT1 (71.05%)/ VT2 (75.93%) -Fail item: 大漏氣_未抽至1120 -Root cause: Front case was modified for VT fail issue after FFP, but the pressing fixture of LCM/ front case wasn't modified for the new design. LCM and front case wasn't attached flattly and caused VT to fail. -Action: Modify the pressing fixture and produce 40 units to test VT. -Evidence: All the 40 units pass the VT and ELOT. All pre-MP front case 300 pcs passed VT1. Retry of VT2 had been reduced to under 10% in MP, | NPI | 2021-12-02 16:00:00.0000000 +00:00 | 2022-03-16 17:22:09.5383995 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% SMT: 1. ATE (26.67%)_Conducted GPS Sensitivity C/No L1 ASSY: 1. VT1 (157.89%)_大漏氣_未抽至1120 2. VT2 (59.26%)_大漏氣_未抽至1120 3. CT (53.67%)_Galileo 4. RTESN (53.42%)_GPS_10_L1/L5 5. HT (31.8%)_Galileo 6. ST (31.34%)_Mic Amp Diff. with Golden 7. G sensor (21.76%)_Diff Y 8. FT (19.63%)_GPS_L1/L1 by ref 9. FT_Iridium (19.44%)_Iridium Tx CH01 by Ref 10. Baro (11.63%)_0.5 ATM diff with golden 11. Compass (11.16%)_M-Sensor_X_STDEV | Top 3: 1. VT1 (157.89%) -Fail item: 大漏氣_未抽至1120 -Root cause: All units retest VT1 again after pressing the LCM. -Action: Same as 3.D-8. 2. VT2 (59.26%) -Fail item: 大漏氣_未抽至1120 -Root cause: Newcomer didn’t find the VT nozzle is loose that cause high retry. -Action: Ask the operator to measure the flow by a flow meter and test the golden sample before DUT. Define VT equipment's flow measurement in the SOP. -Evidence: The preparation items are noted in SP010516_Ver 02. 3. CT (53.67%) -Fail item: Galileo -Root cause: GPS signal is detected, but Galileo can't be detected. It might be related to the new SW. -Action: EE tests 20 times with DUT after CT. The failed mode can't be reproduced. It will be tracked at pre-MP. No issue found in pre-MP and MP on 6k units . | NPI | 2021-12-02 16:00:00.0000000 +00:00 | 2022-03-16 17:23:42.0142126 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004 is not added-in BOM | PM will update 004 in BOM in next ECO release [6/24] 004 MPS is updated under 010 BOM | MFG EE | 2021-06-13 16:00:00.0000000 +00:00 | 2021-06-24 17:14:07.0995106 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product development | 2.A-10 | SW release to production line for FFP build -- SMT & ASSY: Test verification result | SW issue : 1. watch hand shifting while disconnecting USB under SW v0.71 (Solved) 2. High retest rate at 24 Hr ( after ) testing station (No action) | EE will send 40 units to FT1/FT2. Plan to re-test 24hrs test with latest SW version. [6/24] Due to insufficient units amount, test 7pcs units with new SW, result positive. Monitor new SW with large amount in PR build. | MFG EE | 2021-06-23 16:00:00.0000000 +00:00 | 2021-07-06 15:21:54.7982579 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | No ASSY VIP data upload to PR web | ASSY VIP have been provided in attach. | MFG ME | 2021-05-19 16:00:00.0000000 +00:00 | 2021-05-20 16:05:59.6523524 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product validation | 2.B-4 | Release unit level appearance standard for FFP -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) -- Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | No unit level appearance standard data upload to PR web | MFG ME comment cosmetic standard will follow WQ015 | MFG ME | 2021-05-09 16:00:00.0000000 +00:00 | 2021-05-11 10:28:16.9811157 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | The solution of dust and scratch need to be follow up. | DE & PE will provide the improvement of scratch dial (raw material) & ASY process [5/26] DE comments will use tooled samples and qualified based on IIS in PR. Keep monitoring in PR build with GMLA#3 | NPI | 2021-05-27 16:00:00.0000000 +00:00 | 2021-07-06 15:32:42.8338934 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product validation | 2.B-8 | (AOEM) DVP&R / (Consumer) ELOT report summary (progress review) -- Review DVP&R schedule -- Review ELOT completed status | ELOT is not completed In Queue : 5(Water / Dust Resistance) Testing : 2 (Accelerated Weathering Xenon/UV) | All test items are completed | TWN Lab | 2021-05-03 16:00:00.0000000 +00:00 | 2021-05-11 09:12:32.3366284 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | 805-C70R8-BF/ 575-A0125-34 are no peak Temp. | 805-C70R8-BF/ 575-A0125-34 max reflow peak have been updated | NPI | 2021-05-18 16:00:00.0000000 +00:00 | 2021-05-19 15:04:18.2846084 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | ASSY 3 items strain fail : 1. in PR gearbox screwing I601 strain 392 (spec 250) 2. screw screwing I701 strain 222 (spec 150) 3. connector I400 strain 540 (spec 250) | Underfill will be implemented on IC I601, I701, I400 in PR build | PQE | 2021-06-29 16:00:00.0000000 +00:00 | 2021-05-19 11:29:09.1520267 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan 1. SMT: ATE-(ADC1)VOHRLED/V3P0 2. ASSY: RT1/FT1(Motor Vibration Z) RT2(check Low power mode current ALS Calibration Factor(CF)) FT2 (check Low power mode current) | The specification with low CPK items will be modified in PR build. Keep monitor in PR. | NPI | 2021-07-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ LCM) -- Measurement position and result | Sub-assy unit line test fixture is NG | PQE will provide the retest result of fail fixture. | PQE | 2021-07-18 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | 1. Scratch, spot on the dial(145-03631-40) 2. Gearbox issue (370-00043-00) 3. watch hands (115-03533-01 / 115-03533-11 ) | 1. Follow 2.B-6 mitigation 2. Follow 2.D-13 mitigation 3. High rate of adjusting in white watch hand  Redefine the flatness checking criteria with vendor > Apply inspection in PR material | MFG ME | 2021-05-27 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 145-03344-00, 234-00306-02 haven't updated to ver.A | 145-03344-00 234-00306-02 Will ask for updating to A version. @Yang, Howard @Rau, Cheryl confirmed by 7/16 meeting | MFG ME | 2021-05-30 16:00:00.0000000 +00:00 | 2021-07-16 14:09:21.0281190 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | MPS have added-in BOM, but haven't turn A | @Lin, Peter(EE) Will ask for updating MPS.(ECO#224113) | MFG EE | 2021-05-13 16:00:00.0000000 +00:00 | 2021-06-02 11:40:29.4222890 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT: 1.ATE_LDO8_1.04 2.ATE_LDO9_1.24 3.ATE_WiFi Power_2.4G_0.21 ASSY: 4.CT_GPS_L1 by ref (CT)_0.71 5.CT_GPS_L5 by ref (CT)_0.52 6.CT_Galileo by ref (CT)_0.95 7.HT_GPS_L1 by ref (HT)_0.57 8.HT_GPS_L5 by ref (HT)_0.76 9.HT_Galileo by ref (HT)_0.88 10.ST_Mic Amp Diff. with Golden (ST)_0.63 11.M sensor_M-Sensor_X_STDEV_0.43 12.M sensor_M-Sensor_Y_STDEV_0.6 13.M sensor_M-Sensor_Z_STDEV_0.49 14.FT1_GPS_L1 by ref_0.54 15.FT1_GPS_L5 by ref_0.53 16.FT1_外部CN值_0.49 | Top 3. 1. ST -Fail item: Mic Amp Diff. with Golden (ST)_0.63 -Root cause: Previous SW would turn speaker off when detecting test cable with low battery status. -Action: Had put a charging station before ST and add “check battery voltage” before speaker test items in WK04 and improved retry rate significantly (31.4% > 13.5%) -Evidence: No retry from WK08 to WK10. 2. FT1 -Fail item: 外部CN值_0.49 -Root cause: It is suspected the different tightness between the mount and the unit. -Action: Need to be updated. 3. CT/HT/FT1 -Fail item: GPS_L1 by ref_0.52~0.76 -Root cause: C/No related items in CT/HT/FT can't meet 1.33 due to tightened specification. -Action: Need to be updated. | NPI | 2021-12-02 16:00:00.0000000 +00:00 | 2022-03-16 17:25:47.8224274 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | There are 60 items without VIP. (Refer to the attachment) | FA completed | MFG EE/ME/DE | 2021-11-28 16:00:00.0000000 +00:00 | 2022-03-16 17:21:19.1379755 +08:00 | 1
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 013-00968-00 / 145-03698-00 are not A Rev. | DE parts are pending on MTF resolution. One FRM178 for MTF check started on 12/28, will have result updated by 1/8. Drawing was estimated to be released by 1/15. | MFG ME/DE | 2021-01-14 16:00:00.0000000 +00:00 |  | 0
4 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process validation | 3.D-6 | Check verification result of critical process (PVP) -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check (Preparation: define which critical process should apply SPC, ex: SPI/ voiding) -- Action plan if verification result fail | Can't find Pilot run parameters / conclusion in latest OBVP on PRweb in 4/13 | @Tian, Ron @Cheng, James will update OBVP by 4/16. Updated on 4/16 | NPI | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-20 13:33:08.8710395 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process validation | 3.D-7 | PR UPH/Capacity evaluation result review -- Action plan if UPH/ Capacity cannot meet latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | add screw glue process and UPH is changed to 108 which cannot meet target (172) | @Wang, Stan(PE) @Yang, Howard to update the latest UPH after PR2 and see if we can optimize it UPH ramp up completed, UPH=172 confirmed by 7/16 meeting | NPI | 2021-05-30 16:00:00.0000000 +00:00 | 2021-07-16 14:10:49.7767491 +08:00 | 1
2 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | FT2 46.74%, HT 33.05%, Gyro 28.09%, CT 20.55%, FT1 19.15%, GSensor : 19.01%, MSensor 17,21%, VT 12.41%, ATE 24.93%, Preboot 19.59% | Will verify all items in PR2. * GPS related (FT2, CT, HT, FT1): (a) Auto chamber stability: will do cycle test in WK16. - @Huang, Tommy @Lin, Peter(EE) (b) Spring not contact well: apply fixture to help to keep springs in-place and ask for outsourcing to ASSY better - @Wang, Stan(PE) @Mark Hsueh (Mark.Hsueh@garmin.com) * G/M sensor: (a)the equipment need to be calibrated regularly - @Wang, Stan(PE) * VT: (a) screw retract: will add screw glue process and to be verified in PR2 - @Yang, Howard @Wang, Stan(PE) * ATE/ Preboot (a) Fixture: Will modify fixture and do cycle test - @Lin, Peter(EE) | MFG EE | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
4 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk < 1.33 : GPS, Power Box Sampling BL on normal, VEXT current, VSOL voltage/in current, Galileo1, Solar harvest, VBAT current(G3B on BK off) | Most of items are with actions and will verify in PR2. Solar harvest is still TBD. @Lin, Peter(EE) | MFG EE | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | VT 2% failed because screw retract | PR critical issue is screw between front case and Bezel retreated after burn in, we will glue fastened screw and verify VT in PR2 (~5/5) VT issue closed, confirmed by 7/16 meeting | MFG ME | 2021-05-30 16:00:00.0000000 +00:00 | 2021-07-16 14:11:19.8567817 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate : 105/246 = 42.7% | ME: 98% PACK :96% EE/DE all 100% (2022/3/11) | MFG ME | 2021-05-30 16:00:00.0000000 +00:00 | 2022-03-11 13:57:18.0014095 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #2 | 2021-09-22 18:07:03.5597006 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Accelerated Weathering UV is ongoing | Had finished test and found keypad painting cracked. After checking with design team : Waived this issue and this test item is just for reference. | TWN Lab | 2021-09-28 16:00:00.0000000 +00:00 | 2021-09-29 14:08:25.5927437 +08:00 | 1
1 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Product development | 2.A-10 | Verify the test program of SMT and ASSY station before FFP build for new SW release | Version 0.28 SW not ready for Assy testing on FFP build. Need update version 0.36 to solve the testing issue. | Engineering SW is under verification, expected to release FFP2 SW on 5/3 | MFG EE | 2022-05-02 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004-00865-00 has been released but need to add into 010-01781-XX BOM | Will ask Olathe update BOM before small build. ‧004-00865-00 [3/19 Update] was released in BOM 0n 2021/02/19 ‧005-01230-00 [5/11 Update] Released by ECO#222444 | MFG EE | 2021-02-18 16:00:00.0000000 +00:00 | 2021-08-26 14:51:39.2449256 +08:00 | 1
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | Need MME provides ASSY VIP and measure the screw torque to NPI PE. | ASSY VIP has already been provided to NPI PE during FFP. Screw torque will be updated on W4. | MFG ME | 2021-01-21 16:00:00.0000000 +00:00 | 2021-08-26 14:49:55.9474263 +08:00 | 1
1 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | 1.SMT (1) ATE_V3P4BB (3.23~3.57): 1.19 (2) ATE_Ext Voltage.ADC: 0.74 2.Assy Testing (1) CT_C/No: 0.53 (2) HT_C/No: 0.49 (3) ST_喇叭平均震幅差值(1K): 0.97 (4) ST_1k Hz microphone amplitude difference: 1.02 (5) FT1_C/No: 0.83 (6) FT1_Main LTE Band4 TX 1737.0 MHz: 0.12 (7) FT1_Main LTE Band12 RX 737.5 MHz: 0.12 | 1. SMT: Pending on EE's update 2. Assy: Due to unstable SW in FFP, Cpk value is judged for reference in FFP. Will update Cpk based on FFP2 result. | NPI | 2022-06-16 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Supply chain/ supply of part | 2.E-12 | Incoming raw material quality from supplier | Raw material issue from supplier: 117-01599-40/50/60/70 125-00626-00 Should be verified on next build | Will have one small build to verify mount function prior to PR. Update: No issue was reported regarding 117 and 125 parts during mount small build. | MFG ME | 2021-03-18 16:00:00.0000000 +00:00 | 2021-08-26 14:49:36.8251438 +08:00 | 1
1 | Fitness | Forerunner 255S | GMLA #2 | 2021-12-22 20:32:55.7975659 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No 915-01102-F0 Max peak Temp. | We have already informed component engineer to add it. And it was fixed on 12/27. | NPI | 2021-12-26 16:00:00.0000000 +00:00 | 2021-12-23 11:36:43.0255453 +08:00 | 1
1 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process development | 2.C-4 | Release preliminary flow chart for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Clean room "LOCA bonding" can't find any special marking on flow chart | Flow chart updated to include the description of critical process. See PID checklist/flow chart/CR flow chart for the details. |  | 2021-03-30 16:00:00.0000000 +00:00 | 2021-04-01 10:29:28.6638307 +08:00 | 1
1 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process validation | 2.D-6 | Check verification result of critical process (PVP) -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check -- Action plan if verification result fail | Items for Cpk less than 1.33 : Bezel thickness, I-ring process alignment, LOCA bonding Z-axis | T-shape bezel etching (bonding feature) is inconsistent for bonding alignment. Drawing has been updated. Will define the spec and communicate with suppliers for improvement. Validate OK in FFP2 by 5/4. | NPI/ME/DE | 2021-05-03 16:00:00.0000000 +00:00 | 2021-05-04 18:17:27.5917598 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | DE parts: 100% ME parts: 74% (50 items are not-up-to-date ) | FA cannot start without RevA releasing, parts are pending on Olathe revision, deadline of RevA releasing is 11/11. - All ME parts released to RevA on 11/12. - ME parts: 83% (33 items are not-up-to-date ) | MFG ME | 2021-11-28 16:00:00.0000000 +00:00 | 2022-03-16 17:21:29.6998481 +08:00 | 1
1 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process validation | 2.D-10 | FFP Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | WiFi power : 1.23, ANT_power 2457Hz : 0.75, FT1_GPS_L1 by ref : 1, CT_GPS_L1 by ref : 1.04, HT_GPS_L1 by ref : 1.21. FT1_GPS_L5, FT1_Glonass_65, CT_GPS_GPS_L5, CT_Glonass_65, HT_GPS_L5 less than 0 | - Units act pretty consistent in HW testing in both GPS & 2.4G, no action is required from a design perspective. - From the manufacturing view: 2.4G: Units distributed pretty well, the reason of lower Cpk is because of its formula. No action is need, keep monitoring the unit’s performance will be enough. GPS: Cpk in FFP2 look good and consistent (greater than 1), close. | MFG EE | 2021-05-13 16:00:00.0000000 +00:00 | 2021-06-23 18:03:19.8451122 +08:00 | 1
2 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | 174-00525-00 is NRL on 12/18 | Insert design modification is under discussion. Will update 174 document accordingly | NPI | 2021-01-07 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1.ESD Fail: (1/2) - LED malfunction but can recovered by reesting 2.UVA (1/2), UVB (1/2) - housing discoloring 3.Drop: Side button damage (3/6) - Switch board broken 4.Tumble*2, button damage (1/1) - Same as above 5.Button focused drop: (1/1) - Same as above | [Solved] 1. ESD Class C NG (1/2) > LED malfunction but recovered by resting Root cause : ESD strike promote GND voltage to 0.9V, it trigger LED over temperature protection, which cause malfunction Action plan : Update SW to skip the big variance of GND voltage, and reset LED function automatically. Result : Lab retest 1 unit with new SW and it passed in 6/10. [Solved] 2. UVA (1/2), UVB (1/2) NG > housing discoloring Root cause : material property limitation Action plan : Discuss judgement with design team Result : Design team waive it. [Solved] 3. Drop: Side button damage NG (3/6) > as below 4. Tumble: button damage NG (1/1) > as below 5. Button focused drop NG (1/1) > Root cause : Switch board broken due to mechanism can't endure external force Action Plan : Promote spring rate from 0.75 N/mm to 1.36 N/mm. But results are negative. Design team had defined the issue as non-MP blocker. ECO#224865 turn rev. A. | TWN Lab | 2021-06-14 16:00:00.0000000 +00:00 | 2021-06-15 11:04:10.3768970 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | LMS complete rate 81% (2 testing, 19 in queue) | 5/27 progress 91.89%. Left Item “Product package drop” 6/4 progress 95% Left CT scan result 6/18 reached 100% | TWN Lab | 2021-06-17 16:00:00.0000000 +00:00 | 2021-06-21 11:43:08.5148781 +08:00 | 1
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01055-00 is 001 Rev.on 12/18 | Still awaiting Olathe to release 004 RevA. | MFG EE | 2021-01-14 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Mini 2 | GMLA #3 | 2020-12-28 09:43:36.9670000 +00:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | Refer PR issue on 12/18 | SW cannot replicate issues but CCM_B fail rate can be improved. Will have SD card in unit for further analysis on pre-MP units is same failure occurs. | MFG EE | 2021-03-04 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | IQC fixture is not ready due to FA VIP not finished ( 145-03640-XX) | Will be completed by the MP | MFG EE/ME/DE | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #1 | 2021-07-12 15:01:33.0485318 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain gugue not verified sice last WP build (105-04410-00 de-panel/012-04410-0X PCBA screwing) | The strain gauge will be implemented after the first factory Prototype. | PQE |  | 2022-01-20 09:58:12.7161169 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #1 | 2021-02-01 15:45:14.4727398 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | De-panel and ASSY screw are not completed on time. DPQE will finish it on next build | 105-04305-10 ASSY screw wait for front/back case. | PQE | 2021-03-11 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | FYR < 97% but with action plan to improve SMT: ATE(94.49%) | Observe in Pre-MP Build. Pls see the PR Meeting Minutes for Action implemen | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% but with action plan to improve SMT: ATE (12.17%) ASSY: RT1(13.7%)、RT2(16.1%)、FT2(14.6) | Observe in Pre-MP Build. Pls see the PR Meeting Minutes for Action implement | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
4 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan to improved SMT: Conducted GPS Sensitivity C/N ASSY: Power Box Sampling | Observe in Pre-MP Build. Pls see the PR Meeting Minutes for Action implement | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
4 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | press batt./ Attach Batt. / ATE / PRNP fixtures will recheck in Pre-MP phase | Pass in 04-21 test by PQE after the materails of fixture has changed. | PQE | 2021-04-29 16:00:00.0000000 +00:00 | 2021-04-22 08:23:25.1021962 +08:00 | 1
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | PPAP/ FA of all ME parts will be completed before MP | The verificatiion will be ready before MP. | MFG EE/ME/DE | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 684-00137-00 has shortage risk from 012-04162-99(ECO#221514) | Action ongoing: Finding 2nd source / Pull in delivery | PID | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 55 | GMLA #3 | 2021-04-12 03:12:43.8034680 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME part :83%:145-03640-XX are not ready | Closed | MFG ME/DE | 2021-04-29 16:00:00.0000000 +00:00 | 2021-04-20 15:06:42.6454089 +08:00 | 1
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Keep tracking the PCB actual ETA. It may have shortage risk concern on MP build | 1.105- ETA [PUR team had pulled in- Closed] 2.320- ETA [Had aligned with PID for new shipment plan - Closed] 3.145-01451-00 / 145-00312-00 will need PUR team help to confirm LTA. [closed] | PID | 2021-03-04 16:00:00.0000000 +00:00 | 2021-03-09 01:28:22.2800000 +00:00 | 1
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME part: FA rate 89% (Left 7 items). 6 of 7 items are waiting for supplier. The last 1 is reviewing by engineering team. | Plan to finish all FA by 02/E. [6 of 7 items are waiting for supplier document and 1 is reviewing by engineering team.] @Lin, Gilbert(ME Marine) | MFG ME/DE | 2021-02-25 16:00:00.0000000 +00:00 | 2021-03-09 01:28:38.1133333 +00:00 | 1
1 | Aviation | Product - 1.3\" GTR/GNC | GMLA #2 | 2020-12-03 18:12:27.6330000 +00:00 | Product development | 2.A-2 | Update critical parts/ Component list if BOM update -- Maintained in MPM system | [5 empty] | 0
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #2 | 2022-02-07 17:57:04.0806893 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004-01118-00 not released to the BOM. | ECO#237628 has been submitted. Need design help to update the MPS. ECO#237628 has been submitted. MPS released on 2/9 | MFG EE | 2022-02-17 16:00:00.0000000 +00:00 | 2022-03-01 10:23:35.0560083 +08:00 | 1
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #2 | 2022-02-07 17:57:04.0806893 +08:00 | Process validation | 2.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result | No button test fixture verification report from PDO | the est complete date of 1st click ratio equipment 2/14 -> mid-March since the component delivery delay of EtherCAT modules & EtherCAT cards As ISO PM0002 defined, before transferring the equipment to OSP vendor, need PDO team complete the verification report. PI/PTE/PDO team completed the verification ontime before PR start | PDO/AE | 2022-03-20 16:00:00.0000000 +00:00 | 2022-05-18 09:36:59.3095082 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | MB: 340-00266-00 No Max. peak temperature | After confirmed the document, it sets up on 260 degree C. | NPI | 2021-06-16 16:00:00.0000000 +00:00 | 2021-06-17 18:20:56.0023924 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | 1. SMT (1) SUPCAP: 0.13 (2) VBATSENSE: 0.96 (3) V5P0USB: 0.67 2. ASSY (1) CNo GPS 16: 1.24 (2) CNo GLONASS 78: 1.13 | Modify SPEC in 004-MPS, and design team released it on 6/29. | EE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-07-02 13:44:25.4695675 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ ASSY/ LCM) -- Measurement position and result | Main board screw fixture: Incomplete. | After change material of fixture, the ESD protection pass. | PQE | 2021-07-07 16:00:00.0000000 +00:00 | 2021-07-12 13:28:57.4133569 +08:00 | 1
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #2 | 2022-02-07 17:57:04.0806893 +08:00 | Process validation | 2.D-15 | Define outsourcing parts -- ASSY VIP/ appearance STD should be ready for outsourcing supplier | 011-05662-00/011-05662-11 Assy VIP and appearance STD is not ready. | 3/10 MME completed ASSY VIP/ appearance STD Transferred to OSPPE for vendor FA preparation | NPI (OSP) | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-11 08:50:00.5232355 +08:00 | 1
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #2 | 2022-02-07 17:57:04.0806893 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | The Snapdome (340-00268-01) misalignment cause some position's click ratio lower than specification. | MME will discuss the result of Shanyo domes with DME before 2/11. We will also start the test of Snaptron new samples on 2/14. Snaptron quality issues (Low Risk) – Pass  Snaptron’s 210sets arrived and start verify the quality improvement - 2/23~2/24: SMT Assy/Test – completed - 2/25~3/2: MME quality verification – Pass - 3/3: Verification final result + SHIP to Tacx – Pass Shanyo dome array verify – completed  Shanyo’s 200sets has arrived and the verification result is positive – Pass | MFG ME/DE | 2022-03-10 16:00:00.0000000 +00:00 | 2022-04-11 13:51:02.6789750 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #2 | 2021-09-22 18:04:20.4510995 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Accelerated Weathering UV is ongoing | Had finished test and found keypad painting cracked. After checking with design team : Waived this issue and this test item is just for reference. | TWN Lab | 2021-09-28 16:00:00.0000000 +00:00 | 2021-09-29 14:08:18.0752126 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 440-00283-20 is not A Rev. |  | NPI/ME/DE |  |  | 0
1 | Automotive | Tread Audio System | GMLA #2 | 2022-01-05 16:15:40.4025766 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | There is no peak temperature of 520-G4053-Q1 (012-04336-00). NPI has notified OLA EE. | NPI has notified OLA EE to add peak temperature in Agile. | NPI |  | 2022-03-08 09:14:30.6806079 +08:00 | 1
1 | Automotive | Tread Audio System | GMLA #2 | 2022-01-05 16:15:40.4025766 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33: ※SMT 1. Zone1 Speaker Out L - THD + N ( 0.76) ※ASSY_FT 1. BT Radiated Output Power @2441MHz (0.06) 2. Zone2 R - Power (1.21) | EE plan to edit parameter then verify cycle in next build. | MFG EE |  |  | 0
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #2 | 2021-09-22 18:04:20.4510995 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 1. 105-04305-80: ASSY Screw result is NG (748 um/m). Cannot meet the target (350um/m) 2. 105-04305-00: ASSY Screw (front case & rear case) is incomplete. Wait for NPI to provide the press fixture. | The 5” strain measuring results at FL1 is 748 um/m, which is over the target SPEC (350 um/m). However, 7” unit’s report could still meet the target SEPC (results: 323.3 um/m). We adopted the sealing gasket at the SD card slot area. The screw layout condition at the 5” unit can provide a better compressing condition comparing with the 7” unit. It is reasonable that deformation/ strain in 5” is now greater than 7". Had decide to apply underfill in PR. PR FRM178 pending. | PQE | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #2 | 2021-09-22 18:04:20.4510995 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | GPS relate test item had poor cpk result for ATE/CT/HT/FT2 | EE plan to modify test spec before PR start and test connection issue should be resolve in PR. All Cpk data will be update & review in PR. All actions are pending, because of PR FRM178 delay. (Compliance issue) | NPI | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | 145-03659-1X/6X haven't been updated yet. Both are planned to be finished all the drawings before 11/8 | 145-03659-1X/6X are planned to be finished all the drawings before 11/8 [11/5] 145-03659-1X/6X are released with ver_0A. | MFG ME/DE | 2021-11-07 16:00:00.0000000 +00:00 | 2021-11-12 16:29:41.3293352 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | No ASSY VIP report | ME already submit the ASSY VIP | MFG ME | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 10:16:33.5435040 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Product validation | 2.B-4 | Release 010- unit level appearance standard for FFP -- Define A/ B/ C/ D level and acceptable criteria -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) -- Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | No unit level appearance standard | The appearance standard will follow WQ000015. | MFG ME | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 16:11:29.2067061 +08:00 | 1
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #1 | 2021-07-12 15:01:33.0485318 +08:00 | Product development | 1.A-2 | Define critical parts/ component for BOM material (Input from design team; output is critical parts list) -- Critical patrs list have been well defined and review by CFT in DFM meeting (maintained in MPM system) -- (AOEM) AOER requirement review for critical parts | Critical parts not defined on union tooling BOM. (011-05662-A0 did not add on the MPM system.) | 1. Need Olathe help to add the union tooling BOM of 011-05662-A0 BOM into 011-05328-60. -->011-05662-A0 does not belong in 011-05328-60 because 011-05328-60 is the kit of tools the customer receives to assemble the bike. The Shifters + Handlebar assembly belongs in the 010 as it’s packaged separate in the box (in other words, it’s not assembled onto the bike). PjM will make updates to the 010s. 2. Critical parts has been defined. Need to add on MPM system. | MFG ME |  | 2021-07-27 12:23:31.4321869 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 18"/24" Black: ELOT is incomplete. LAB receives test units and starts testing on 6/19. Most of all items are incomplete. | Black SKU: All test item passed. | TWN Lab | 2021-07-20 16:00:00.0000000 +00:00 | 2021-08-02 09:20:19.1701667 +08:00 | 1
3 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Thermal shock (1/2 NG): VT fail 2. Shipping Vibration (1/1 NG): Abrasion | 1. Thermal shock: VT fail (Closed) - Root cause: The new tape of TESA is used in order to pass the drop, and leak issue might result from insufficient pressure of pneumatic cylinder. But the VT fail rate is 10% after increasing pressure (3.3 --> 5.8kg/cm2). - Action: Use back to the old PSB tape - Evidence: LMS-0010937-5 Thermal shock (ID 353744): Verify 3 units by using PSB tape. 11/1 VT2 pass. 2. Shipping Vibration: Abrasion - Analysis: There is abrasion on Slide lock and Roll bar mount - Root cause: Poor protection on accessories and find the abrasion on Slide lock and Roll bar mount - Action: Add 172-00020-28 (Polybag) to pack the accessories so it can protect them during shipping - Evidence: LMS-0018565-2，Shipping vibration 11/19 1 pcs pass | TWN Lab | 2021-11-25 16:00:00.0000000 +00:00 | 2021-11-24 12:03:06.2724211 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process development | 2.C-6 | Release preliminary Control Plan (v001) -- Special characteristic should be included and must correspond with D/PFMEA -- (AOEM) Regular requalification should be included | CP is not ready | CP finished on 6/30. | PQE | 2021-06-29 16:00:00.0000000 +00:00 | 2021-07-15 13:44:25.3631394 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | SXS: There are 36 items not turned A yet. Overland: There are 35 items not turn A yet. As the attachments. | Olathe released revA ECO provided MP approval on 11/19. | NPI/ME/DE | 2021-11-14 16:00:00.0000000 +00:00 | 2021-11-22 13:49:51.4715486 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | SXS: 007-04041-00_001, 007-04075-01_002 Overland: 007-04042-00_001, 007-04075-00_002 | ELOT packing vibration test completed on 10/29, solution of issues below are under determination. - Worn mount: Add plastic bag for protection. - Deformed packing box: Considered acceptable since only accessory box was deformed. *SXS: 007-04041-00_0A 007-04075-01_0A *Overland: 007-04042-00_0A 007-04075-00_0A (ECO# 232581 & 233569) Worn mount: 172-00020-28 plastic bag had been added to BOM for protection.- Deformed packing box: Olathe judged that accessory box damage is acceptable. Design change is not required. | MFG ME | 2021-11-21 16:00:00.0000000 +00:00 | 2021-11-18 13:42:59.4462517 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 5 items are not started 1. Water / Dust Resistance 2. Drop 3. Battery Disconnect Drop 4. Product Package Drop 5. Power On / Off test | All test items were complete by 11/24. | TWN Lab | 2021-11-23 16:00:00.0000000 +00:00 | 2021-11-24 12:04:09.9461248 +08:00 | 1
3 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Failed Test Item: 1. Body and Wearable Chemicals 2. Product Package Drop 3. Operating Hot/Cold Unit Performance 4. Drop 5. Button focused drop test | [Closed]1. Button focused drop test (2/2)- Unit auto reboot after drop 2 cycles (PR2 pass) Root cause : 1. LRA didn't in right position cause connector (330-01154-24) which connecting battery suffer unexpected external force during ELOT. 2. connector pin with poor wetting, causing solder crack after ELOT Action: 1. Optimize SOP for outsourcing, ask OP to attach LRA lean against alignment feature. 2. short term : Enlarge stencil opening from 0.508mm to 0.65mm, make sure stencil and pad size is 100% match. Long term : Optimize pad/stencil/component size in part data to prevent same issue re-happened. Evidence : Validation (re-test Elot) is on-going, target date : 12/15 [Close]2. Shipping Vibration (1/1) - Watch band Side surface abrasion & marking Root cause: f-flute scratch watch band Action: Enlarge f-flute opening Evidence : ECO#231480 [Closed]3. tumble test (1/2)(PR2 pass) Failure description: Solar test fail Root cause: FPC (105-04272-F0) crack cause by bending 180 degrees once. Action: Introduce 3mm*3mm*2mm sponge, bending 90 degrees twice at different location Evidence : ECO#232888, Validation (re-test Elot) is on-going, target date : 12/15 | TWN Lab | 2021-12-14 16:00:00.0000000 +00:00 | 2021-12-30 15:48:41.1759127 +08:00 | 1
1 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 11 test items are under testing. | will apply the PR2 ELOT test and estimate to complete by 11/29, all completed - Closed | TWN Lab | 2021-10-28 16:00:00.0000000 +00:00 | 2021-12-30 15:49:10.7253653 +08:00 | 1
2 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Process development | 3.C-2 | Review Machine/ Fixture list and ETA (need to meet build plan) -- Schedule of any modification or adjustment can meet PR build | EE's ATE fixture need to track | <Failure description> 1st OSP ATE fixture is lack during the trail build. we transfer 1 fixture to vendor side urgently, and after trail build the OSP fixture was ready on 10/22 and verified pass. <Root cause> EE/AE mis-aligned, the fixture material didn't ready on time, cause delay 1~1.5 wks. it's a human error. <Action> AE will set a lesson learn for long-term, EE/AE will based on MPM's build schedule arranging and confirm the fixture due-date to MPM. | NPI | 2021-10-24 16:00:00.0000000 +00:00 | 2021-10-26 09:17:29.0500798 +08:00 | 1
1 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | For ASIA 1. 006-D8952-00’s SW version would be become 0 after Product Scan station 2. 010-02604-33 can’t pass the 3D fix on the Product Scan station. 3. Some Asia sku units can’t receive the 3D fix at the first time. 4. Some TWN sku units can’t pass the Easy Card Bundle station at the first time. For WW 1. There is 006-D8952-00 in the 010-BOM but can’t find this in the product inventory. | the SW improvement condition will keep tracking Asia SW in PR2/WW SW in extra PR | PQE | 2021-10-28 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 24.83% - Low Power Mode Current ASSY 1. CT 15.9% - temperature 2. HT 11.31% - temperature 3. Airtight_table 16.93 % - 變形量絕對值超出規格_常壓 4. FT1 22.68 % - charging status 5. FT2 16.93 % - battery voltage 6. Compass 11.38 % - Check Unit Roll on 0 degree 7. Baro 14.74 % - 0.5 ATM diff with golden 8. Gyro 21.13 % - Gryo Data X軸檢查 | 1. ATE 24.83% - Low Power Mode Current Root cause: PCBA on ATE generate large current cause this test result is NG Action: fix bugs for PCBA on ATE in 9/28 Evidence: PR2 ASIA build retry rate 1.4% (4 out of 285) in 10/14 2. FT1 22.68 % - charging status Root cause : Burn-in cause battery voltage higher than 4V, cause (Battery) charging status is NG Action : In early of MP, discharging 30 mins after burn-in Validation : revise SOP 3. FT2 16.93 % - battery voltage Root cause : battery voltage is lower than 4V. This purpose is to make sure battery voltage is sufficient before packing. Action : check this item in product scan instead. | NPI | 2021-11-18 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 320-cable material constraint | Failure description: ‧ 320-01381-00 charging cable缺料 Root cause: ‧ Charging cables are allocated to sellable products ‧ 廠商: 正崴精密工業股份有限公司, SM : Riva Xian Action: ‧ Introduce allocation plan, allocate cables after 2021 W51, and postpone Descent G1 MP date to 2022/01/03. | PID | 2021-11-18 16:00:00.0000000 +00:00 | 2021-11-03 16:19:45.4735162 +08:00 | 1
1 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate (update on 20211013) is lower than 100 %. - ME: 56 % - Display: 43 % | @Lee, Katie ME parts estimated to completed by 10/29 @Chen, YH(Display) 470-00872-1x estimated to completed by 10/29 249-01651-00, FA completed 440-00306-10, FA completed 362-00122-00, FA completed 475-00130-00, FA completed | MFG ME/DE | 2021-10-28 16:00:00.0000000 +00:00 | 2021-12-30 15:25:00.3697823 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #1 | 2021-01-27 10:34:39.3216104 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | DPQE will finish de-panel and ASSY screwing in next build | PQE had finished strain gauge on 03/07 - @Jason Hsu | PQE | 2021-03-06 16:00:00.0000000 +00:00 | 2021-03-29 15:16:07.3421661 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 012-04166-12: 670-00334-00 max peak temp is only 240. (purchase select) | 670-00334-00 is removed from BOM by 11/26, and 670-00345-00 is used for the purchase select. | NPI | 2021-11-25 16:00:00.0000000 +00:00 | 2021-11-24 12:02:26.2604954 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No Max. peak temperature 1. Processor board 012-04188-00: 330-01933-00 2. MB 012-04163-00: 330-01933-10 / 670-00398-01 / 816-D7012-01 | 330-01933-00 – 260C 816-D7012-01 – 250C 330-01933-10 – 260C | NPI | 2021-07-01 16:00:00.0000000 +00:00 | 2021-08-02 09:20:53.4259672 +08:00 | 1
3 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Overlander: 1. Drop VT Fail 2. TST VT Fail (10/28 completed test, waiting for engineer's analysis) | 1. Drop VT fail (1/2) (Closed) -Failure description: TP broken and VT fail -Action: Due to DUT initial condition is different. Drop failed part in TWN has been tested by TST. Drop result of TWN lab was considered only for reference by Olathe. ‧122 cm: TWN tested 6 pcs and 1 failed./ OLA tested 4 pcs and all passed. ‧ 90 cm: TWN tested 2 pcs and 1 failed./ OLA tested 2 pcs and all passed. 2. TST VT Fail (1/1) - Failure description: VT failed, the value continuously came down - Root cause: Leakage came from connector door. -Action: Add a tape to increase interference and fix the gasket. Will verify in pre-MP. -Evidence: TST VT pass after adding the tape. 10/27 ECO #232300 Add 249-01509-00 tape | TWN Lab | 2021-12-02 16:00:00.0000000 +00:00 | 2022-03-16 17:19:08.2891852 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #2 | 2021-09-22 18:07:03.5597006 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 012-04305-1X (MB): 805-B7751-JC No max. peak temp definition in agile. | NPI PE is checking with OLA EE and waiting for confirmation. next check point : 10/08 | NPI | 2021-10-07 16:00:00.0000000 +00:00 | 2021-12-27 10:31:27.0343885 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | 1. SMT (1) A14000 (high voltage): 0.96 2. No ASSY cpk data in production report | There is only one outlier which within the specification. Since it is already within the specification and the number of samples is too small also, close this issue after discussing with EE. | MFG EE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 15:57:16.0352102 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | Rubber scratched (35.84%): Even 10" applies full film, it still suffers the scratch problem. This issue should be fixed before pre-MP. | Issue: Rubber scratched (35.84%) -Root cause: Rubber surface is scratched easily during production. Protect tape on one side is applied at PR build. It can only protect one side's surface. Unprotected parts still suffer scratch issues. -Action: Will apply three tapes on rubber surfaces and verify with more quantity in Pre-MP. - Evidence: No issue in MP | NPI | 2021-12-09 16:00:00.0000000 +00:00 | 2022-03-16 17:20:53.4246529 +08:00 | 1
1 | Automotive | Tread - SXS (8") | GMLA #3 | 2021-10-29 10:49:54.3807273 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Completed rate: LMS-0010462-7 (Tread) 91.67% LMS-0010462-8(Overlander) 71.43% LMS-0010462-9 (Tread) 11.76% LMS-0010462-10(Overlander) 10.81% All the tests will be completed before 11/12. | 11/22 Status LMS-0010462-7 (Tread) 100% LMS-0010462-8(Overlander) 100% LMS-0010462-9 (Tread) 100% LMS-0010462-10(Overlander) 100% | TWN Lab | 2021-11-11 16:00:00.0000000 +00:00 | 2021-11-22 13:53:02.7380899 +08:00 | 1
2 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | VT2: 94.23%: 小漏氣_超過洩漏量門檻 | VT2: 94.23% - Fail item: 小漏氣_超過洩漏量門檻 - Root cause: The new tape of TESA is used in order to pass the drop, and leak issue might result from insufficient pressure of pneumatic cylinder. But the fail rate is 10% after increasing pressure (3.3 --> 5.8kg/cm2). - Action: Use back to the old PSB tape. | NPI | 2021-11-25 16:00:00.0000000 +00:00 | 2021-11-18 13:37:58.5267639 +08:00 | 1
1 | Automotive | Tread - XL (10") | GMLA #3 | 2021-11-17 17:21:26.2189372 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate of ME parts is 82%. 18 items are ongoing. | The FA was available by 12/26. | MFG ME | 2021-12-02 16:00:00.0000000 +00:00 | 2022-02-21 10:02:56.4359718 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process validation | 2.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ ASSY/ LCM) -- Measurement position and result | Fixture ESD is incomplete | Finish ESD measurement on 6/25 and provide the result to NPI. Will add the air Ionizers in the heatsink station. | PQE | 2021-06-27 16:00:00.0000000 +00:00 | 2021-06-28 14:49:39.6157605 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #2 | 2021-09-22 18:07:03.5597006 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | 1. GPS relate test item had poor cpk result for ATE/CT/HT 2. ATE operation current Cpk 0.16 & 0.18 3. FT2 Wifi Power Cpk 0.66 & 0.68 & 0.62 | EE plan to modify test spec before PR start and test connection issue should be resolve in PR. All Cpk data will be update & review in PR. PR FRM178 pending all relate action can refer to 5" report & plan to have PR result by 1/E. (Compliance issue) | NPI | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 1. RTESN: TALK Mic Amplitudet 0.27 FFR Mic Amplitudet 0.36 FBR Mic Amplitudet 0.46 2. FT: TALK Mic Amplitudet 0.70 FFL Mic Amplitudet 0.81 FFR Mic Amplitudet 0.88 FBL Mic Amplitudet 1.03 FBR Mic Amplitudet 1.01 BT CW Medium 1.15 3. Headset_IN/OUT Check Average RD20024 0.27/ 0.19 Check Average RD20040 0.36/ 0.30 Check Average RD20056 0.29/ 0.16 Check Average RD20072 0.38/ 0.24 | 1. RTESN & 2. FT: Will provide a golden sample. The tested value will be compared with golden at the next build. (EE_Bryant) [Update] RTESN Cpk reached 0.9/FT reached 1.19 in PR. It was affected by environment due to open test condition. Keep monitoring. 3. Headset_IN/OUT: MME and DME keep discussing the solution. (ME_Angus) [Update] Reached 0.93 in PR. Will further shift spec for better Cpk in MP. | MFG EE/ME/DE | 2021-12-02 16:00:00.0000000 +00:00 | 2022-02-07 13:53:41.5313658 +08:00 | 1
1 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | 4 Issue found for appearance inspection: 1. Tape leak 100% (196 pcs) 2. Click feeling 19.39% (38 pcs) 3. Scratch 6.63% (13 pcs) 4. Dent 2.04% (4 pcs) | 1. Tape leak 100% (196 pcs): Under discussion b/w ME and MME. 2. Click feeling 19.39% (38 pcs): TBD 3. Scratch 6.63% (13 pcs): TBD 4. Dent 2.04% (4 pcs): Pending on Olathe’s comment | NPI | 2022-05-26 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 2 ELOT fail item: (1) Electrostatic Discharge (ESD) Immunity test (1/2 NG): Can’t record. (2) Mechanical Part Cycle (1/4): Weird file structure that formed | (1) EN pin short of I501. The impedance of the failed unit at "SEQ1" pin to ground is only 28 ohms, and it can be returned to normal after replacing the components Action: Cover this area with insulating tape, and it can pass the +/-30KV air test. (2) ADATA SD card could not pass read/write 10,000 cycles, EE is analyzing the root cause with ADATA FAE. We have tested another SD card supplier “Silicon Power” in FFP, result pass. | TWN Lab | 2022-01-06 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Approach G12 | GMLA #3 | 2021-03-04 11:00:32.0783377 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Assy retry rate of test station did not meet the target <10% 1. RT1=16.8% 2. FT1=18.43% 3. FT2=17.65% | In 1st MP, G12 retry rate are lower than 10% in each station. [Appendix] 1. RT1: MP 1.7%. Battery Voltage OOS which can not pass lower limit. Has already added Charging Station to Flow Chart for MP (after HT, before BI). Original no charging station during pilot run. Also the battery voltage checking will move to FT1 since RT station may be canceled after MP. 2. FT1: MP 4.0%. BOMs updated to switch to the gold-plated charge pins for Mass Production. ECO#218588 3. FT2: MP 4.0%. Production map hasn't been set up properly. The test type of vision alignment bonding station is not set up properly for FT2 to check test sequence. Update to the latest before MP. | NPI |  | 2021-03-12 13:48:49.3687124 +08:00 | 1
1 | Outdoor | Approach G12 | GMLA #3 | 2021-03-04 11:00:32.0783377 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk result review (CPK <1.33) >> SMT: - GPS sensitivity :0.81 - VEXT charge current: 0.72 >> ASSY: - RT1_GPS Radiated Sensitivity: 0.46 - HT_BLE Power Sensitivity: 0.55 | SMT: - GPS sensitivity :0.81 > 1.3 The sample mean of is 1dB lower than the performance in MP line. CPK low cause by cable difference in PR & MP. - VEXT charge current: 0.72 > 1.2 The testing CPK will be impacted by USB connect stability. After adding re-plug action, testing become stable in MP. >> ASSY: - RT1_GPS Radiated Sensitivity: 0.46 > 1.2 In FT1 the CPK of GPS signal is stable. The reason is the adhesive sealing is not implemented and not stable in RT1 - HT_BLE Power Sensitivity: 0.55 > Cancel BLE test items will be canceled in MP due to BLE will be test in RT | NPI |  | 2021-03-12 13:48:51.9938031 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing:35 items are not started. 5 items are under testing. The expected complete date:2022/1/5 | All ELOT test items were completed | TWN Lab | 2021-12-27 16:00:00.0000000 +00:00 | 2021-12-28 14:04:23.5945023 +08:00 | 1
2 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Final Yield Rate (FYR) not meet the target >=97% Light box test: 93.56% | DE will confirm final spec with designer and implement in small build | NPI | 2022-01-06 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate did not meet the target <=10% <SMT> ATE 18.75%: SD card format <Assy> (1) LightBox 33.91%: (100%)Light Value (10U-10L) (2) RST 27.67%: 1K Hz Mic Amp Diff (3) RT2 17.89%: 2.4GHz ANT Output Power (4) FT2 16.99%: WiFi功率(CH7)¦WiFi Power(CH7)* (5) FT1 11.41%:電池電壓檢查¦Battery Voltage Accuracy | - ATE Retries 1. SD card format (14.9%) -> SD card didn't insert properly. SMT PE will define the insert method and inspection more detailed in SOP. - RT2 /FT2 1. 2.4GHz ANT Output Power (RT2_6.3%, FT2_1.5%) -> Fixture issue, informed PE to improve the fixture structure. Fixture is ready, plan to verified in small build. - Light box 1. (100%) Light Value (27.3%) -> Spec. of WW / Stvzo are waiting for final defined. Optics Engineer will confirm with design team by 12/30 - RST 1. 1K Hz Mic Amp Diff (24.9%) -> MIC rubber is not hollow. ME informed vendor with 100% cosmetic check/ The function test been executed while units did not turn-on completely. Plan to add delay time for unit turn on. | NPI | 2022-01-20 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | IQC inspection VIP not ready (145-02486-00/145-03643-XX/145-03644-00...total 36 part GPN) | Track the inspection with PQE before Pre-MP start. | MFG ME/DE | 2022-01-20 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 35% (Total 37 items FA progressing) | Weekly tracking FA result after small build verification done [12/23] FA complete rate ME 37.5% PACK 71.4% [2/17] ME 98% PACK 89% Display 0% EE 0% PE 0% | MFG ME/DE | 2022-01-13 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Storage Hot/Cold Unit Performance (1/1) - FT1 C/N by ref 2. Thermal shock (1/2) - FT1 C/N by ref 3. Product Package Drop (1/1) - watch band scratched | 1. Storage Hot/Cold Unit Performance (1/1) - FT1 C/N by ref 2. Thermal shock (1/2) - FT1 C/N by ref [Problem] NG result : -2.1 db (test spec : ±1.5db) [Induction] High temp may cause solar SKU shift -1.5 db (base SKU shift only <0.5 db) [Long term action]: - applied and Tracking 1. CFT has modified auto chamber to standardize the “Cable placement”、” Absorber films” and “filters” of all 24 set chambers to accommodate the test. 2. EE has adjusted the C/No value spec: 2s solar(+/- 2dB) & 2s non-solar(+/-1.5dB) based on the chamber interference/enlarge percentage rate. 1/24 latest test result : FT1 C/No retry decreased from 15% to 1~5%, the result of long term actions seems positive and will continue monitoring/improving. 3. Product Package Drop (1/1) [Problem] side watch band scratched [Root cause] Foam and box insert are too tight to rub watch bands [Action] Loosen foam and box insert size [Validation] Retest passed, ECO#228547 | TWN Lab | 2022-02-28 16:00:00.0000000 +00:00 | 2022-03-07 09:32:02.8174710 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT still ongoing | ELOT finished | TWN Lab | 2022-02-28 16:00:00.0000000 +00:00 | 2022-03-07 09:32:58.2274892 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Product validation | 3.B-11 | CC test result | TST : FT1 CNo NG (2/10) Immersion : Baro NG (2/10) | Baro issue: will recover after settling 3days Not the real failure C/No issue : - Long term: - applied and Tracking 1. CFT has modified auto chamber to standardize the “Cable placement”、” Absorber films” and “filters” of all 24 set chambers to accommodate the test. 2. EE has adjusted the C/No value spec: 2s solar(+/- 2dB) & 2s non-solar(+/-1.5dB) based on the chamber interference/enlarge percentage rate. 1/24 latest test result : FT1 C/No retry decreased from 15% to 1~5%, the result of long term actions seems positive and will continue monitoring/improving. | PQE | 2022-02-28 16:00:00.0000000 +00:00 | 2022-03-07 09:37:58.1746114 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 805-C8560-JC have no peak temp data (component datasheet shows 260 degree, low risk, just inform Olathe component Eng to update data) | 805-C8560-JC have released peak temp : 260C | NPI |  | 2022-03-07 09:49:06.6765281 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | 1. For ASIA SKU, 006-D5459-0X in the BOM list but not show in unit inventory > By pass checking in PR, will update SW 2. For ASIA SKU 006-D8021-13 isn't in 010-BOM > will add it to BOM | 1. <Close> SW is released in 7/30 2. <Closed> 006-D8021-13 have added in BOM in 7/29 | PQE |  | 2021-08-03 11:32:07.9437773 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process development | 3.C-13 | BOM structure review (if any part needs to be added or changed after build) -- Lost parts/ wrong level/ wrong qty -- Include auxiliary material (副料) | Instruction menu (NRL)- 190-02068-65 & 190-02863-90/-91/-92/-93 | All 190- are released. | NPI |  | 2022-03-07 09:40:19.3195647 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process validation | 3.D-6 | Provide PVP (Process Verification Plan) result of critical process -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check (Preparation: define which critical process should apply SPC, ex: SPI/ voiding) | Solar SKU CPK 1. Bonding thickness : 0.58~0.83 2. Y-shift : 0.94 3. Rotation : 0.54 Non-Solar SKU CPK 1. Y-shift : 0.93 | 1. Bonding thickness : 0.58~0.83 Since instinct 2s is using domed lens, it will cause non-flatness datum when measuring. Therefore, CR PE will optimize measurement fixture and define the operation method in SOP. 2. Y-shift : 0.94 3. Rotation : 0.54 Both Y and theta are controlled by bonding equipment, CR has tightened the alignment criteria to make Cpk meet 1.33, keep tracking in ASIA build. | NPI |  | 2021-08-19 11:39:17.1572737 +08:00 | 1
2 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ASSY 1. AutoHT 17.13% - C/No BeiDou 2. RT2 14.56% - Disable BLE 5. FT2 12.07% - ANTCW TX(CW BOX) CH57 | ASSY 1. AutoHT 17.13% - C/No BeiDou [Problem] No test result returned [Root cause] Test program didn't command DUT correctly to return test result [Action] fix test program immediately Validation : Rest of results pass test in 6/15 2. RT2 14.56% - Disable BLE (see if BLE is disabled) [Problem] DUT should return 0 (disable) but test program didn't receive any data [Root cause] Test program waiting time (0sec) is too short [Action] Extend waiting time to 1.5 sec (0.5sec + 1sec guard band) [Validate] Test program have updated in 8/18 3. FT2 12.07% - ANTCW TX(CW BOX) CH57 (2.4G天線) [Problem] NG result (-10 ~ -16 db), spec : (-20 ~ -27 db) [Root cause] Antenna performance is better in new fixture than previous one, but spec did not follow up [Action] shift spec from (-20 ~ -27) db to (-8 ~ -18) db to meet real performance. [Validation] Test program have updated in 8/18 | MFG EE |  | 2021-08-19 07:52:38.7465566 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | ASSY Non-solar SKU 1. AutoCT/HT C/No by ref 0.9 2. AutoFT1 C/No by ref 0.70 Solar SKU 1. AutoFT1 C/No by ref 0.23 | @Chen, Kevin SMT 1. C/No GLONASS_65 0.784 2. C/No GLONASS_72 0.728 3. C/No GLONASS_78 0.483 1. EE verified the following two things and decided to relax the lower bound of Glonass 78 to 38.5. (1) this issue is highly related to the Signal Source used within the Garmin factory (2) this difference between GPS and Glonass cannot also be observed on other GPS Chip platform(Sony 5603) Instinct 2s Satellites FFP PR SPEC GPS 16 42.75 42.14 >40 GLONASS 65 41.88(-0.87) 41.23(-0.91) >40 GLONASS 72 41.77(-0.98) 40.98(-1.16) >40 GLONASS 78 40.92(-1.83) 39.78(-2.36) >39 ASSY Non-solar SKU 1. Auto CT/HT C/No by ref 0.9 & AutoFT1 C/No by ref 0.70 Will check if the group that is close to the lower bound actually comes from the Asia non-solar sku that has NFC antenna. Solar SKU 1. AutoFT1 C/No by ref 0.23 suspecting that if the two groups in the histogram can be easily differentiated by the gluing date or not. | NPI |  | 2021-08-19 11:40:07.7698498 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 28%, DE 17% | ME parts FA rate : 98% PACK part FA rate: 91% | MFG ME/DE | 2022-03-30 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 255S | GMLA #1 | 2021-04-19 20:41:07.0669031 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain gauge test (Router、Screw、Buckle Conn.) cannot be finished | Ongoing, aims to complete in next build since there will be PCB design change | PQE | 2021-06-04 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing. The expected complete date is 5/10. ※ 1 items under testing ※ 12 items not started yet | Completed and closed on WK22 | TWN Lab | 2022-05-11 16:00:00.0000000 +00:00 | 2022-05-28 11:33:52.3655217 +08:00 | 1
1 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process validation | 2.D-7 | FFP UPH/Capacity review -- UPH/ Capacity meet the latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | Need to update UPH and capacity of ASSY/TEST | The documentation had done the update by Dec | NPI | 2021-12-30 16:00:00.0000000 +00:00 | 2022-01-26 12:44:46.5358472 +08:00 | 1
3 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | Can't find test coverage for pilot run close phase on PRweb in 4/13 (confirmed by DPQE) | Update the test coverage progress below: ‧ Test coverage: 75%(4/16訊息) ‧ 達到100%完成日: 4/26已完成 ‧ 主要剩餘項目: all test coverage已完成100%，剩餘兩項MPS待OLA微調 | MFG EE | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-26 16:22:05.1531326 +08:00 | 1
1 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process development | 3.C-4 | Update flow chart for PR build -- key characteristic should be included and must correspond with D/PFMEA | Can't find latest version of ASSY flow chart in PR close phase on PRweb in 4/13 | @Wang, Stan(PE) will upload ASSY flow chart by 4/16. Updated on 4/16 | NPI | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-20 13:35:42.7919543 +08:00 | 1
3 | Outdoor | fenix 7S | GMLA #3 | 2021-04-13 18:44:21.5223854 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- key characteristic should be included and must correspond with D/PFMEA | Can't find Clearroom SOP in PR close phase on PRweb in 4/13 | @Tian, Ron @Cheng, James will upload to PRweb by May. confirmed by 7/16 meeting | NPI | 2021-04-29 16:00:00.0000000 +00:00 | 2021-07-16 14:10:15.9660338 +08:00 | 1
1 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | 1. SMT STD_X & STD_Z: 0.54 & 0.65 2. All FT1/FT2 CPK results cannot meet 1.33 | 1. By EE team analysis and comment, the 9-axis sensor test should be a pass/fail test item and the results should not showed normal distribution. According to the limitation setting, if the DUT is not over the maximum setting, the test result is PASS. 2.FT1/2 CPK should be monitored and recollected after the FT tank validation complete and freeze the MPS and test algorithm | NPI | 2021-12-30 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 60 items haven't update to version A, see reference | Plan to get all items partially after PR design review. Only MB & 011-05276-3X & 010 units have not get MP approve. 6/21 Items haven’t turn rev. A or get mp approval  011-05276-3X before 6/25  MB 012-04112-X0 before 7/5  Unit level 010-02541-XX before 7/12 [9/27] Get MP approval and Pre-MP Frm178 list (All items turned A) | NPI/ME/DE | 2021-07-11 16:00:00.0000000 +00:00 | 2021-09-29 09:00:42.5959788 +08:00 | 1
1 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Process development | 3.C-13 | BOM structure review (if any part needs to be added or changed after build) -- Lost parts/ wrong level/ wrong qty -- Include auxiliary material (副料) | Instruction menu- 190-02837-90/190-02837-91 drawing need to be released. | Plan to release fenix 7 QSMs before 7/14 by Cozmyer, Kari [9/27] QSM is released and confirmed with final version | NPI | 2021-07-13 16:00:00.0000000 +00:00 | 2021-09-29 09:01:19.4455419 +08:00 | 1
2 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT MB-2X 1. ATE (34.95%) - NFC 24MHz clock SMT MB-3X 2. Pre-boots (45.83%) - VSOL IN CURRENT(6.4mA) SMT Flash light board 3. ATE (12.6%) - NTC (100k//40.2k) ASSY 1. FT2 (17.4%) - Power Box Sampling BL on normal(Avg) 2. FT1 (16.6%) - GPS_ (L1 + L5) by ref 3. Compass (13.4%) - Check Unit Pitch on 45 degree 4. Airtight_table (13.2%) | 1. Pre-boots (45.83%) - VSOL IN CURRENT(6.4mA) Root cause: Power supply output resolution (0.1mA) can't meet target 6.4mA. Action plan : Introduce board level output feature high output resolution (0.01mA). Validate results by 7/E 2. ATE (34.95%) - NFC 24MHz clock Root cause : Test NFC without loading Action plan : Add a resistance in ATE as a loading Result : Re-testing 10 pcs shows no more failure. 3. FT2 (17.4%) - Power Box Sampling BL on normal(Avg) Root cause : test result is interpreted, one of factors are not applicable for Fenix 7 series Action plan : Updating SW to fix factor malfunction by 8/B | NPI | 2021-08-08 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | fenix 7X | GMLA #3 | 2021-05-24 11:20:06.6222889 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME : 55%, DE 57% (see reference) |  Some parts are under experiment for VT issue & button damage issue, keep tracking on the FA after the experiments are done. (6/M)  5/27 FA rate % ME 56% , DE 57%, EE 75%, PE 0%  6/21 FA rate % ME 75% , DE 58%, EE 100%, PE 0% | MFG ME/DE | 2021-07-01 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Product development | 3.A-10 | SW release to production line for PR build -- SMT & ASSY: Test verification result | No beeper feature in PR unit so TWN need to update the unit after assembly. OLA need to update SW in MP | Had finished SW rework for all units before shipment on 01/08 and also verified CT/HT/FT test result. | MFG EE | 2021-01-07 16:00:00.0000000 +00:00 | 2021-04-01 14:39:50.9763887 +08:00 | 1
1 | Fitness | Varia Radar Camera (RCT715) | GMLA #3 | 2021-12-16 16:58:07.4784695 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | Total 44 BOM items no turn version A on PR. (011-05439-00/011-05530-00/145-02486-00/145-0364X-XX/470-00851-00/470-00852-00...) | PR design review plan to hold on 1/12. Rev. A will be tracking after PR design review. | MFG EE/ME/DE | 2022-01-11 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | Need to finish OOB checklist before MP (Target date: 2/9) | OOB checklist document is still under preparation. Plan to release OOB document before 02/09. @Hsu, Jason(PQE) | PQE | 2021-02-08 16:00:00.0000000 +00:00 | 2021-03-26 13:59:24.1489528 +08:00 | 1
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Process validation | 3.D-7 | PR UPH/Capacity evaluation result review -- Action plan if UPH/ Capacity cannot meet latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | SMT UPH is 46 but ASSY UPH is 136. SMT Need to prepare another fixture for MP | Issue closed after clarify with planner. No need to add extra fixture. (Base on demand setting right now) | NPI | 2021-02-05 16:00:00.0000000 +00:00 | 2021-03-09 01:26:03.2500000 +00:00 | 1
2 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%. ASSY: VT1 11.39% / FT 12.5% | Although ATE & HT retry rate had been reduced in PR build. But we still have FT /VT retry rate higher than 10%. Issue keep open and monitoring in next job order. -VT retry rate over 10% : 2 main reasons cause VT retry, [1. VT machine setting [Had modified machine setting in PR. ]2. O-ring not place well. Only very few units has this issue & PE had update SOP of this station, keep monitoring] @Chen, Albert(PE) -FT retry rate over 10% : Button test – gray box cause around 5 % retry. AE had fixed it during PR. | NPI | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | SMT: Auto power-on Crnt 16V (high) Cpk 0.75 / Backlight voltage Cpk 1.27 & ASSY: Turn-on Current 12V Cpk 0.95 | After EE review all Cpk data, we decide not to modified any spec. Test result looks fine and no risk for MP. | NPI | 2021-02-05 16:00:00.0000000 +00:00 | 2021-03-09 01:27:12.4400000 +00:00 | 1
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | Need to finish ESD before MP (Target date: 2/9) | PQE is not finish all ESD test item & fixture’s measurement. Plan to finished ESD relate items before 02/09. @Hsu, Jason(PQE) | PQE | 2021-02-25 16:00:00.0000000 +00:00 | 2021-03-09 01:27:35.5833333 +00:00 | 1
1 | Marine | Malibu Display | GMLA #3 | 2021-02-03 20:53:58.3956342 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Finalize VIP is not ready for ME part. Left 6 items (011 * 2 & 145 * 4) | VIP setting had finished on 02/05. | MFG EE/ME/DE | 2021-02-24 16:00:00.0000000 +00:00 | 2021-03-09 01:27:49.7966667 +00:00 | 1
1 | Automotive | BC50 & BC50 IR | GMLA #2 | 2021-12-03 10:48:35.0451013 +08:00 | Product development | 2.A-5 | Design lockdown for 015- drawing -- Special characteristic should be included -- Process development should meet 015- drawing | Assy drawing not release and lockdown for FFP (015-05737-0X/015-05737-2X/015-05737-3X) | MME uploaded file on 12/10 . | ME | 2021-12-09 16:00:00.0000000 +00:00 | 2021-12-29 16:23:14.4458534 +08:00 | 1
1 | Automotive | BC50 & BC50 IR | GMLA #2 | 2021-12-03 10:48:35.0451013 +08:00 | Product validation | 2.B-3 | Update ASSY VIP for FFP | Need ME update the Assy VIP and provide it to NPI | MME uploaded file on 12/3. | MFG ME | 2021-12-07 16:00:00.0000000 +00:00 | 2021-12-06 10:02:21.5266409 +08:00 | 1
1 | Automotive | BC50 & BC50 IR | GMLA #2 | 2021-12-03 10:48:35.0451013 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: [non-IR SKU]10 items are not started. 2 items are under testing. The expected complete date:2021/12/13 [IR SKU] 12 items are not started.5 items are under testing. The expected complete date:2021/12/10 | All test items were complete by 12/14. | TWN Lab | 2021-12-13 16:00:00.0000000 +00:00 | 2021-12-29 16:22:34.8022612 +08:00 | 1
1 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk/ Ppk < 1.33 with action plan 1. SMT: ATE-Conducted GPS Sensitivity/VDD_OHR/VDD_1.85_AO 2. ASSY: RT1/FT1_GPS Radiated Sensitivity FT2_BLE Power Sensitivity\ALS Luminance (WLED ON) FT3_NFC Antenna Self Loop Test Tx Current | ATE-Conducted GPS Sensitivity Keep tracking on PR. ATE-VDD_OHR Will adjust the SPEC. ATE-VDD_1.85_AO Keep tracking on PR. RT1/FT1_GPS Radiated Sensitivity: Keep tracking on PR. FT2_BLE Power Sensitivity: Will adjust the SPEC. FT2_ALS Luminance (WLED ON) Keep tracking on PR. FT3_NFC Antenna Self Loop Test Tx Curren Keep tracking on PR. | NPI | 2022-05-19 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl watch | GMLA #2 | 2021-05-14 13:11:19.2001141 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | All items are not completed yet. | Due to lab insufficient capacity testing on Instinct 2/2s and Fenix 7 series, so the testing scheudle delayed. But we can finish the test by design review.(7/9) | TWN Lab | 2021-07-08 16:00:00.0000000 +00:00 | 2021-08-31 21:30:31.8486757 +08:00 | 1
1 | Automotive | dezl watch | GMLA #2 | 2021-05-14 13:11:19.2001141 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | There are 2 items of SMT and 1 item of LCM Cpk <1.33 that need to be tracked. *SMT: 1. VAFE 2. Low Power Mode Current *LCM: 1. Lens/display thickness | "Critical test items : VAFE 0.4, Low Power Mode Current 0.79 >> 4 polar in the distribution. However, retry < 1%, keep monitoring. Critical station : LCD/solar panel thickness 0.72, Lens/display thickness 0.79 >> Introduce floating fixture to cover the material tolerance" | NPI | 2021-07-08 16:00:00.0000000 +00:00 | 2021-09-03 09:24:16.7744937 +08:00 | 1
1 | Automotive | dezl watch | GMLA #2 | 2021-05-14 13:11:19.2001141 +08:00 | Supply chain/ supply of part | 2.E-2 | All material status, schedule and quantity should be reviewed | Shortage risk on Ti components (500-01224-10/500-10415-00/500-10117-00) and the design team will submit alternative PCB without Ti component solution. PM is checking this change will impact 8/30 MP date or not. | The design team will issue alternative PCB with 012-04094-FK for PR (end of June) and MP (8/9). | PID | 2021-07-08 16:00:00.0000000 +00:00 | 2021-08-31 21:31:05.1067143 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | EE confirms 004-MPS need to be updated. Spec. is under review. | MPS released on 6/29. | MFG EE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-07-02 13:42:31.5430625 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Product development | 2.A-10 | Verify the test program of SMT and ASSY station before FFP build for new SW release | M-sensor verification issue. Need SE to relesae the correct method | Same as 1st item. | MFG EE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-07-02 13:43:05.6320511 +08:00 | 1
3 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1) DEET : 5atm deflection test fail. 2) Package drop : Unit and Insert shift. 3) Tumble : OHRM puck paint peeling. | [04-28] Waive and have the MP approval start 1) DEET : 5atm VT test fail by cover lens, but there is no glue breakage or poor adhesion on both sides of the lens and the bezel, CRPE under analysis 2) Package drop : unit and insert shift: Change 174- and 171(ECO#239628) 3) Tumble : OHRM puck paint ( GPN: 013-01055-10 ) peeling: VT pass, the spacer moves to the housing by CT inspection and the peeling ink on the glue.SM_SUNYAO under analysis | TWN Lab |  | 2022-04-28 09:30:45.1652877 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | No extra units to test CC due to functional verification , national certification and multi-payment certification |  | PQE |  |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No 522-00037-04 Max peak Temp. |  | NPI |  |  | 0
2 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Product development | 3.A-14 | Receive 174- doc from Design team for packing SOP | 174- document cannot be released | 174 doc will be released after 10/29 PR design review | NPI | 2021-10-31 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Tumble failed and under analysis | 1. Tumble [Solved]  60 cycles / 100 cycles minute hand shift > Unit function is normal. Retest these units with 24 hr and it shows normal. SW has been retest and can not duplicate the fail mode. Also, ME take another turned-off normal units to do the tumble, it shows shifting with 36 degree which is accepted by Pdm. [Solved]  Some dust particles after tumble > The particles come from plastic or gluing which been determined low risk to the functionality. | TWN Lab | 2021-10-21 16:00:00.0000000 +00:00 | 2021-10-21 23:58:29.5548894 +08:00 | 1
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | 1. Unlock code(2021) did not match map files(2020)(Asia SKU) 2. All units lack 006-D9212-XX in the product inventory.(Asia SKU) 3. There some 006-D does not in the product inventory(Asia & WW) | Wait SW team released | PQE |  |  | 0
2 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 %: Top 1: AutoATE (31.81%) Top 2: FT2 (22.4%) Top 3: Auto FT1 (20.29%) | Retry Rate > 10 %: 1. AutoATE _ Solar Harvester Count VSOL(14.5mA)(8.19%) adjust Spec due to new SW match to units 2. FT2 _ WiFi Radiated File Transfer Test (3.05%) & (WiFi) Access AP (2.36%) due to Wifi status is not stable and add delay time to solve it 3: Auto FT1_ GPS_L5 by ref (8.27%) adjust Spec. due to OLA Life CN test | NPI |  |  | 0
1 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ASSY/ Testing/ Packing/ LCM) -- Measurement position and result | The cover of screw fixture ESD measure failed | Waiting for Screw fixture ready | PQE |  |  | 0
2 | Fitness | Forerunner 955 and 955 Solar | GMLA #3 | 2022-03-09 22:33:19.3642097 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 42% (see reference) DE 45% (see reference) |  | MFG ME/DE |  |  | 0
1 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Product development | 2.A-5 | Design lockdown for 015- drawing -- Special characteristic should be included -- Process development should meet 015- drawing | Assy drawing (015-05842-XX) not released | Plan to release 015- drawing by 3/25. | MFG ME | 2022-03-24 16:00:00.0000000 +00:00 | 2022-03-29 16:43:56.2401497 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process validation | 3.D-7 | PR UPH/Capacity review -- UPH/ Capacity meet the latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | SMT PR version of labor cost is not updated | SMT PE has provided PR uph | NPI | 2021-10-14 16:00:00.0000000 +00:00 | 2021-10-25 20:40:02.0796305 +08:00 | 1
2 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | High retry in ASSY are below: 1. 24hr before 13.5% 2. VT 12.4% 3. CT 12% | [Ongoing] > Asia PR retry rate 11.7% 1. 24hr before 13.5% > Backlight setting 50% still cause some display flashing, lead to the misjudgment in AOI station. SW & EE had modified new SW to address the issue in PR3. [Solved] > Asia PR retry rate 7.4% 2. VT 12.4% > Supplier prime coating method is wrong > After modifying, PR 3 150 pcs not VT failed issue [Solved] 3. CT 12%  Temperature 5.6% > cause by the insufficient temperature due to EE confirm new SW function  RGN version range check 3.2% > some units missed with programming language files. EE check RGN version | NPI | 2021-11-04 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 670-00198-02 / 464-00086-00 shortage from wk50. Need allocation since many products use these IC. | 1. 670-00198-02 / 464-00086-00 shortage from wk50. Need allocation since many products use these IC. 2. Dial 145-03631-41/ -43 are not approved for risk buy. Need to modify these 2 skus MP date. | PID | 2021-10-21 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 86%, DE 0% (see reference) | Track FA complete rate after 10/29 PR design review. Plan to complete before 11/22 MP. | MFG ME/DE | 2021-11-18 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Supply chain/ supply of part | 3.E-12 | Raw material quality issue from supplier | Gearbox VIP Axis height size Spec . need to alignment | 1. Vendor has provide improved "gearbox" with good yield rate. FR: 0.6% (6/1000) --> track scrap reason code with design team for future MP defect 2. Track the new cent card ETA at vendor site, so Garmin and Titan will align same measurement result. | MFG ME/DE | 2021-10-28 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | Not Version A 010-02604-XX 011-05631-XX 015-05631-XX | all turn Rev.A | NPI/ME/DE | 2021-10-28 16:00:00.0000000 +00:00 | 2021-12-30 15:24:19.9507040 +08:00 | 1
2 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | Not Version A 007- *1 | 007-04099-00 is updated in verA in 10/18 | MFG ME | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-26 09:10:07.0477307 +08:00 | 1
1 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004-01119-00 released to rev02. Need to add in the BOM. | Plan to update 004- by 3/25. @Tien, Howard | MFG EE | 2022-03-24 16:00:00.0000000 +00:00 | 2022-04-12 16:00:02.3484045 +08:00 | 1
1 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing. The expected complete date is 3/31 | ELOT ETC 3/24, summary report release before 3/31. @Chen, Jacob(QA) 04/13 : The ELOT test has been done on 03/31, please refer to the PID checklist for a summary report. | TWN Lab | 2022-03-30 16:00:00.0000000 +00:00 | 2022-04-06 15:04:11.3588413 +08:00 | 1
3 | Outdoor | Descent G1 | GMLA #3 | 2021-10-13 20:36:14.6136303 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | 91.59% (=98/107) 1. Solar CSA current (VEXT applied) 2. Magnetometer BIST 3. Depth Pressure Sensor Pressure Accuracy 4. Vibration Motor Driver Current when Enabled 5. Altimeter Pressure Sensor Temperature Accuracy 6. Depth Pressure Sensor Pressure Accuracy – 1atm 7. Depth Pressure Sensor Temperature Accuracy 8. Humidity Sensor Temperature Accuracy 9. Piezo Beeper Activation | Root cause: Descent G1 MPS is duplicated from Descent MK2 series, so for 3 items(1,2,4), MPS spec should be renewed to match new test method, for other 6 items, spec should be renewed to match compoent datasheet. Action: EE had informed Olathe team of these mismatches [Jeffrey]Depth pressure accuracy have not been changed / Barometer temperature does not have to be tested / Depth sensor temperature does not have to be tested / Humidity sensor test item have been removed / and the others have been revised | MFG EE | 2021-11-28 16:00:00.0000000 +00:00 | 2021-11-17 17:53:49.2580342 +08:00 | 1
1 | Fitness | Venu Sq 2(IMP) | GMLA #1 | 2021-10-26 11:19:39.0411316 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | NG items: MB: Screw OHR:De-panel / Press OHR board | 1. MB: Screw: PCB will be re-layout, keep tracking on FP1. 2. OHR: De-panel: De-panel method will change from manual to router, keep tracking on FP1. 3. Press OHR board: Consider to add underfill after FFP, keep tracking. | PQE | 2021-11-11 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Tread Audio System | GMLA #2 | 2022-01-05 16:15:40.4025766 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Finish rate: 93.75%. All the tests will be finished before 1/6. | All the tests will be finished before 1/6. | TWN Lab | 2022-01-05 16:00:00.0000000 +00:00 | 2022-01-22 17:10:31.6400240 +08:00 | 1
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #2 | 2021-03-18 19:43:09.6988554 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- document before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | 004-01098-00 is not added to BOM | IR#138807 prod released the 004 | MFG EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-05-26 15:54:19.1102569 +08:00 | 1
2 | Outdoor | Xero A1i PRO Bow Sight | GMLA #3 | 2021-07-15 11:33:41.4660021 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ASSY retry rate >10% (1) Torque_Elevation 96.64%: (R)Current Torque (2) VT2 33.04%:小漏氣_超過洩漏量門檻 (3) FT 33.06%: ALS Luminance (WLED ON/After Calibration) (4) VT1 26.15: 大漏氣_未抽至1120 (5) HT 21.88: APD Voltage Self Calibration (haptic value) (6) FT2 10.08:ButtonOK | (1) (R)Current Torque Root cause: The logic of test program is not suitable for torque measurement. Because the torque need to be adjusted a few times to let it within the spec. Action: Modify the test program to let the operator can adjust the set screw during the test. The retry rate is lower than 10% after the program modification. (2) 小漏氣_超過洩漏量門檻 Root cause: VT leak from the rubber plug. Current mount design can’t position the plug well. Action: Add a positioning fixture & lubricant for the rubber plug during assembling. The retry rate is lower than 10% after the modification. Also, the mount drawing is modified for better positioning. (3) ALS Luminance (WLED ON/After Calibration) Root cause: Incomplete shading during testing Action: Related to the test method. The test fixture should cover the lens before testing. Will add more notice in the SOP. | NPI | 2021-07-29 16:00:00.0000000 +00:00 |  | 0
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #2 | 2021-03-18 19:43:09.6988554 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | 741-31683-K4: No Max.Reflow Temperature. Need to define it | Peak temperature had been defined. | EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-29 16:01:30.2611663 +08:00 | 1
1 | Fitness | Forerunner 255 | GMLA #2 | 2021-12-21 19:46:45.2040739 +08:00 | Product development | 2.A-5 | Design lockdown for 015- drawing -- Special characteristic should be included -- Process development should meet 015- drawing | 015-05766-8X/9X are NRL | Will update next build | MFG ME/DE |  |  | 0
1 | Fitness | Forerunner 255 | GMLA #2 | 2021-12-21 19:46:45.2040739 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | No 805-C8330-JD Max peak Temp. | We have already informed component engineer to add it. And it was fixed on 12/27. | NPI | 2021-12-26 16:00:00.0000000 +00:00 | 2021-12-23 09:31:37.1579591 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 1. 105-04163-00/ 01: ATE/ ASSY screw/ ATE screw HY12000/ ASSY top case screw are incomplete 2. 105-04188-00: ATE/ PRNP/ ASSY screw are incomplete | 1. 105-04163-00 (1) ATE http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04163-00&org=T3&station=ATE (2) ASSY screw & ASSY top case screw: follow 105-03491-00 data. No need to test (3) ASSY screw HY12000: No need to test 2. 105-04188-00 (1) ATE & PRNP http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04188-00&org=T3&station=ATE (2) ASSY screw: Follow 105-03962-00 data. No need to test 3. 105-04163-01: Cancel MP. No need to test | PQE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 15:51:19.0235396 +08:00 | 1
1 | Outdoor | Instinct 2S | GMLA #3 | 2021-07-26 20:04:02.9355335 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | For 010-02563-00 012-04095-JT is ver7 | still V7 | NPI/ME/DE |  |  | 0
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process validation | 2.D-7 | FFP UPH/Capacity review -- UPH/ Capacity meet the latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | Current ASSY UPH cannot satisfy with “Aggressive plan" | Ramp up plan had adjusted from aggressive to conservative. | NPI | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 18:09:27.7522522 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | Supplier raw material issue. 3 pcs of the logo sticker isn't in the right place | The sticker passed all the test and had no quality issue on PR. | MFG ME/DE | 2021-07-22 16:00:00.0000000 +00:00 | 2021-08-02 09:21:18.9454051 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Product validation | 2.B-6 | Appearance inspection report from NPI | 1. Dent/Cosmetic/Bonding line/Uneven logo 2. Scratch: -Type C -3.5 mm -Slider: 3. Button Shift 4. Assembly gap 5. Bump | 1. Dent/Cosmetic/Bonding line/Uneven logo: Fixed by tool modification and trial shot is planned on WK47. Had been verified in PR. 1. Dent/Cosmetic/Bonding line/Uneven logo: Fixed by tool modification and had been verified in PR. 2. Scratch: ‧ Type C: Will switch test cable to plastic. ‧ 3.5 mm: Fixed by adding protection tape but cost has to be evaluated. No issue in PR. ‧ Slider: will remove burr on the side. 3. Button Shift: PCB was modified to avoid interference in PR. 4. Assembly gap: Increase hook interference in PR. 5. Bump: Root cause is still unknown. Supplier will perform visual inspection before shipping. No issue in PR. | NPI | 2021-11-25 16:00:00.0000000 +00:00 | 2022-02-07 13:41:46.0728685 +08:00 | 1
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | The complete rate is 95% on 1/27. All the tests will be finished before 2/8. | All the tests will be finished before 2/8. | TWN Lab | 2022-02-07 16:00:00.0000000 +00:00 | 2022-03-17 17:45:15.9635337 +08:00 | 1
3 | Outdoor | "Austin" | GMLA #3 | 2021-10-01 14:56:32.8208822 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | EE comment the coverage rate is 96% (confirmed by DPQE) | For uncovered items (VCCK, VDD_0.7_GPS, VDD_1.05_RP, VDD1.35_RP), other test items can detect any failures. | MFG EE | 2021-09-30 16:00:00.0000000 +00:00 | 2021-10-01 15:48:53.3783772 +08:00 | 1
2 | Outdoor | "Austin" | GMLA #3 | 2021-10-01 14:56:32.8208822 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. FT2 86.44% - Power Box Sampling BL on normal(Avg) diff with ATE 2. Airtight_table 37.97% - 連續斜率異常_負壓 3. FT1 36.05 - VEXT Current 4. RTESN 32.8% - Battery Voltage 5. Gyro 32.25% - Gyro Data X軸檢查 (CW #1) 6. HT 29.17 - GPS_L5 by ref 7. CT 21.21% - GPS_L1 8. Compass 19.27% - Heading 135 Degree 9. FT3 11.92% - LRA calibration | 1. FT2 86.44% - Power Box Sampling BL on normal(Avg) diff with ATE Root cause : Test program misread ATE data from database, so the difference is wrong. Action : fix test program Validation : No more issues(0/98) in next build in 10/13 2. Airtight_table 37.97% - 連續斜率異常_負壓 Root cause : gasket damaged after assembling Action : Arrange training for operators 3. FT1 36.05 - VEXT Current Root cause : Burn-in cause battery charging current is lower than spec (120~280mA) Action : In early of MP, discharging 30 mins after burn-in Validation : revise SOP | NPI/EE/ME/DE | 2021-10-28 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | "Austin" | GMLA #3 | 2021-10-01 14:56:32.8208822 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Maxim IC (500-10558-00) shortage risk on WK45 and WK46. Under checking pull in schedule | Failure description: ‧ Maxim IC (500-10558-00) shortage risk on WK45 and WK46 Root Cause: ‧ 全球晶片短缺 Action: ‧ Keep tracking IC pull-in schedule. @SM Willy Chang @Maxim integrated products ‧ IC allocation under checking with planners. | PID | 2021-10-07 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | "Austin" | GMLA #3 | 2021-10-01 14:56:32.8208822 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA Rate - ME: 91% - Display: 100 % | FA complete rate 99%. Only 145-03345-04 FA process on-going. | MFG ME/DE | 2021-10-14 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Total 54 items, 26 items completed, and 28 items are not completed. Completed rate 48%. | All tests were planned to be closed by 12/3 All the tests have been finished on 12/13. | TWN Lab | 2021-11-25 16:00:00.0000000 +00:00 | 2022-01-27 10:40:03.1916348 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Process validation | 2.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result | The limited position of the Headset/ Slider/ ST fixture should be modified to improve the retry rate. | 1. Headset/Slider/ANC parameters were tuned in PR and had been verified. 2. ESD result was judged pass on 1/28. | PDO/AE | 2021-12-09 16:00:00.0000000 +00:00 | 2022-02-07 13:59:16.6620511 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | There are 6 raw material issues. 1. 2% of Silvery Line of PMP from EN JINN 2. 145-03865-10 peeling issue 3. 011-05784-50 wire exposed 4. 013-01044-10 Headband curvature different from the drawing 5. 490-10041-00 speaker paragraph sink 6. 011-05784-40 the wire length outside the assembly needs to be controlled better | * * * 1 issue without action: 1. 2% of Silvery Line of PMP from EN JINN -> EN JINN made some improvement. It doesn't happen again in PR build. * * * 5 issues with action: 2. 145-03865-10 peeling issue -> Solved with designated color masterbatch 3. 011-05784-50 wire exposed -> Solved with applying heat shrinkage tube with adhesive 4. 013-01044-10 Headband curvature different from the drawing -> Vendor will send limit samples for PR reference 5. 490-10041-00 speaker paragraph sink -> Required vendor OQC 6. 011-05784-40 the wire length outside the assembly needs to be controlled better -> Added OSP vendor OQC All above issues didn't happen in PR build. (Closed) | MFG ME | 2021-12-02 16:00:00.0000000 +00:00 | 2022-01-27 17:52:01.9931824 +08:00 | 1
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Supply chain/ supply of part | 2.E-12 | Raw material quality issue from supplier | Burrs of speaker's hole need to be improved. | ME will check the mold with supplier and make the improvement. | MFG ME | 2022-03-13 16:00:00.0000000 +00:00 |  | 0
1 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | Need to update 004 to rev. 2 in BOM | The new MPS for PR build had done the update for the PR, and the team will keep collecting the data and test result in the build. | MFG EE | 2021-12-23 16:00:00.0000000 +00:00 | 2022-02-19 11:26:03.5332279 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Product development | 3.A-11 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | Customer special characteristics symbol is R in upside-down triangle not circle | EE will update the symbol "R" in 004- file, target complete by 4/8. 004-01081-00 update to Rev.0B to modify symbol "R". | EE | 2022-04-07 16:00:00.0000000 +00:00 | 2022-04-07 15:34:06.9333744 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is estimated to complete by 10/28 | ELOT is estimated to complete by 10/28 | TWN Lab | 2021-10-27 16:00:00.0000000 +00:00 | 2021-11-09 19:43:53.1272329 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process development | 3.C-1 | Any update of critical process/ equipment/ measurement method of special characteristics -- Check if DFM report updated for any process/ parameter change (ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ Displacement) | Color test process should be critical process | Add color test into DFM of critical equipment, please refer "ixww22_dfm_v3.pptx". | NPI |  | 2022-03-23 19:21:50.1691010 +08:00 | 1
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #3 | 2021-06-01 13:40:50.3197986 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 2 ELOT items are incomplete. 1. Salt fog: Testing and will complete on 6/7 2. CT scan: Not started | - Salt fog will be completed on 6/7. - CT scan will be updated @Huang, Matt(QA) | TWN Lab | 2021-06-06 16:00:00.0000000 +00:00 | 2021-06-24 23:11:08.4482288 +08:00 | 1
2 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #3 | 2021-06-01 13:40:50.3197986 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | ATE 94.19% - VBATT | LED GREEN /(PVDD Undervoltage)GREEN RED/ VBATT passed after being retested under engineering environment, the failure could be caused by MP production line equipment. Two sets of ATE fixtures will have cycle tests under mass production environment. Equipment will be adjusted accordingly at the same time. @Lin, Kevin(EE) Update: 99.55% FYR in first MP. | NPI | 2021-06-10 16:00:00.0000000 +00:00 | 2021-06-24 23:13:23.6605120 +08:00 | 1
2 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #3 | 2021-06-01 13:40:50.3197986 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ASSY (1) VT1 36.62% - 小漏氣_超過洩漏量門檻 (2) FT 20.83% - 1W Audio_L_THD+N_100Hz(BP) | - VT: The vacuum nozzle on production line didn’t fit AP-DA214;s case well. Will replace nozzle size to improve retry rate. @Chu, Allen - FT: Cable connection issue was significantly improved in PR but still have 11.11% retry rate. Even with improved cables, frequent loading/unloading could lead connection issue, AE/EE will provide spare cables to production line for replacement. | NPI | 2021-06-10 16:00:00.0000000 +00:00 | 2021-06-24 23:14:37.3462305 +08:00 | 1
2 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | 1.Modify SW to reduce defect rate. 2.Supplier supply suitable IC to Garmin | Cypress can reproduce the failure mode, expect provide the F/W in 3/25. SW will update in 3/28 for upcoming pilot run. Expect verify the BT fail/retry in 1000pcs sellable pilot run in May. [5/20] N1000 build close meeting, FYR=100% | EE | 2022-05-30 16:00:00.0000000 +00:00 | 2022-05-24 16:46:04.5781378 +08:00 | 1
2 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1.Modify SW to reduce defect rate. 2.Supplier supply suitable IC to Garmin | Cypress can reproduce the failure mode, expect provide the F/W in 3/25. SW will update in 3/28 for upcoming pilot run. Expect verify the BT fail/retry in 1000pcs sellable pilot run in May. [5/20] In N1000 build, IXWW22_iATE_BT_Auto retry rate: 2/14%. Issue close by SW solution. | EE | 2022-05-30 16:00:00.0000000 +00:00 | 2022-05-24 16:46:37.3033941 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Others | 3.F-1 | Direct labor -- Product training for PR (Training record in HR system) -- New skill requirement should be added to WH000005 (Special Job Technician Management) -- (AOEM) Training Matrix arrangement (if necessary) | Update training material | waiting C5 to provide training record. Completed. | NPI | 2022-03-23 16:00:00.0000000 +00:00 | 2022-04-07 16:23:01.5546401 +08:00 | 1
1 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #3 | 2021-06-01 13:40:50.3197986 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | 1. SMT: ATE (1) 8 items related to 1W Audio are lower than 1.33 (close to LSL) 2. ASSY: FT (1) Auto Power-On Crnt 10.8V: 1.03 (2) Auto Power-On Crnt 28.8V Remote 6V: 1.05 (3) Speaker Overload: 0.5 | - SMT: EE had tested units with lower result under engineering environment and confirmed those units are normal. This cpk shift could be caused by MP production line equipment. Two sets of ATE fixtures will have cycle tests under mass production environment. Equipment will be adjusted accordingly at the same time. @Lin, Kevin(EE) - ASSY: Three items’ Cpk were under 1.33, these items could be improved by latest published MPS. @Chang, Alex(EE-Marine) | NPI | 2021-06-10 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | inReach Messenger | GMLA #1 | 2021-09-01 16:17:13.9355925 +08:00 | Product validation | 1.B-2 | ELOT test plan | No ELOT plan (FRM064) update on LMS system. ELOT test plan still needed to discuss with Olathe Eng. | ELOT plan (LMS-0018837) has been created on LMS system | MFG ME | 2021-09-05 16:00:00.0000000 +00:00 | 2021-09-23 13:23:30.1892641 +08:00 | 1
1 | Outdoor | Descent S1 Buoy | GMLA #1 | 2021-03-04 13:32:55.3780959 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 05-03996-00/105-03996-A0/105-03996-A1 strain gauge measurement not verified yet. | o The strain gauge haven’t completed ‧ [Screwing] complete the strain gauge measurement, result: Pass ‧ [De-panel] complete the strain gauge measurement, result: Pass | PQE | 2021-03-30 16:00:00.0000000 +00:00 | 2021-04-07 13:44:45.9425822 +08:00 | 1
1 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 1. Accelerated Weathering Xenon, Accelerated Weathering UV and Chemical Resistance Test are not started 2. Salt Water Immersion Test and Validation Run-in Test are testing | Test on-going but the by review the test results are all pass for 2 months | TWN Lab | 2022-01-30 16:00:00.0000000 +00:00 | 2022-01-26 12:40:49.0255627 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Process validation | 2.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result | Need to provide the information of verification report | will complete by 11/15 | PDO/AE | 2021-11-14 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Process development | 2.C-6 | Release preliminary Control Plan (v001) -- Special characteristic should be included and must correspond with D/PFMEA -- (AOEM) Regular requalification should be included | Control Plan did not ready. | CP is planned to complete by 3/11. @Kuo, Chris -------------------------------------------------------- Update on PR Web (3/11). | PQE | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-14 10:36:25.5003708 +08:00 | 1
1 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | FFP Cpk not meet the target >=1.33 ※ SMT 1. ATE_Turn on Battery Current_3.8V: 1.01 2. ATE_MCUV18: 1.11 3. ATE_V30MCU: 1.18 4. ATE_V12GNSS: 0.93 ※ ASSY 1. FT2_USB Reverse Charge Current: 0.39 2. FT3_Iridium Tx CH120 by Ref: 0.35 3. FT3_Iridium Tx CH240 by Ref: 0.35 | Under checking with design team EE for MPS update. @Tien, Howard | NPI | 2022-03-24 16:00:00.0000000 +00:00 | 2022-04-15 10:54:34.3552216 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #2 | 2022-02-09 12:48:46.2399230 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 HT_GPS_L1 by ref_0.95 | HT_GPS_L1 by ref_0.95 - Status: The distribution is close to the lower limit, need to confirm the effect of high temperature on CN. Still under analysis, will keep tracking in next build. @Fu, Johnny | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #3 | 2022-05-17 22:03:28.6089749 +08:00 | Product validation | 3.B-4 | Release 010- unit level appearance standard for PR -- Define A/ B/ C/ D level and acceptable criteria -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) --Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | Need to update the appearance for the first MP. | MME has updated the appearance standard on 5/18 | MFG ME | 2022-05-17 16:00:00.0000000 +00:00 | 2022-05-19 13:30:28.0172142 +08:00 | 1
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #2 | 2022-02-23 10:19:51.8518228 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 590-00109-00 on 012-04166-00 is 245 degrees only. NPI will do the thermal test of PCB. | NPI and MPPE are checking re-flow temperatue with vendor, Re-flow/baking parameter will be further finalized. | NPI | 2022-03-10 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl OTR Series 2022 - 7" | GMLA #2 | 2022-01-26 17:46:50.3929354 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | The complete rate is 92.59% on 1/26. | LMS-0019600-3-TW Finished Rate: 92.59% Fail item: Mechanical Vibration Pending items: Thermal Measure and Battery Life Test Expected Completed Date: 1/29 @Wu, Steve [WK8] All testing completed on 02/11. | TWN Lab | 2022-02-15 16:00:00.0000000 +00:00 | 2022-02-17 16:11:26.0303465 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 7" | GMLA #2 | 2022-01-26 17:46:50.3929354 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33, ※SMT 1. ATE_10% BK current_1.02 2. ATE_Battery startup current 4.1V_1.04 3. ATE_Mntr Temperature_1.18 ※ASSY 1. FT_Check C/No Stable_1.29 2. FT_C/No by ref_0.7 3. ST_MIC MAX Amp.(db) - Compare with Golden_0.87 | ※SMT 1. ATE_10% BK current: 1.02 2. ATE_Battery startup current 4.1V: 1.04 3. ATE_Mntr Temperature: 1.18 - Action: Distribution is lower bound but within specification, and won’t track in next build. @Tsai, Benson(EE) ※ASSY Same as ASSY part item 2 and 3 of 2.D-9 and keep tracking in PR build. | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33: 1. 關機電流¦turn off current_0.10 2. suspend current_0.58 3. 100% SPK_1.01 4. Wifi Power_2.4G_1.17 | EE will adjust the specification for these test items. | NPI/EE/ME/DE | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl OTR Series 2022 - 6" | GMLA #2 | 2022-01-26 17:46:07.4636136 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | The complete rate is 90.91% on 1/26. | LMS-0019600-15-TW Finished Rate: 90.91% Pending items: Thermal Measure and Battery Life Test Expected Completed Date: 1/29 @Wu, Steve [WK8] All testing completed on 02/11. | TWN Lab | 2022-02-15 16:00:00.0000000 +00:00 | 2022-02-17 16:12:39.7897614 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 6" | GMLA #2 | 2022-01-26 17:46:07.4636136 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 1. CT/HT_CompenCNo _0.38/0.64 2. ST_MIC MAX Amp.(dB)-Compare with Golden_0.62 3. ST_Amp Golden Value Different_0.8 4. FT_C/No by ref_0.66 | Same as 2.D-9 and keep tracking in PR build. | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Process development | 2.C-4 | Release preliminary Flow Chart for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | OHR flow chart needs to update | Finish update | NPI |  | 2021-10-22 14:59:29.8422234 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Process development | 2.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 464-00126-00 no Max peak Temp. | 464-00126-00 Max peak Temp. need to be updated by OLA team. @Patel, Parth [10/27] updated by @Patel, Parth | NPI | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-27 11:36:24.1552401 +08:00 | 1
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | SMT: 1. Accelerometer_STD X: 0.65 2. Accelerometer_STD Z: 0.68 | By EE team analysis and commnet, the 9-axis sensor test should be a pass/fail test item and the results should not showed normal distribution. According to the limitation setting, if the DUT is not over the maximum setting, the test result is PASS. | NPI | 2021-11-29 16:00:00.0000000 +00:00 | 2021-12-22 13:44:38.4828360 +08:00 | 1
1 | Fitness | Edge Explore 2 | GMLA #2 | 2022-03-03 10:56:18.6674347 +08:00 | Product development | 2.A-8 | Unit/ Accessory: Update 004- MPS before FFP if any SPEC change -- Test program need to be adjusted accordingly -- Release to version 00X -- Add-in BOM | MPS did not release and added into the BOM. | EE will add 004-01147-00 into BOM next week. | MFG EE | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-11 14:29:51.2847384 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #2 | 2022-02-09 12:48:46.2399230 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | The complete rate is 85.19% on 2/9. All the tests will be finished before 2/11. | LMS-0019600-11-TW Finished Rate: 85.19% Fail item: Bluetooth Connection Test Pending items: Connector Engage/Disengage Durability, Tumble, Click ratio and Battery Life Test Expected Completed Date: 02/11 @Wu, Steve [WK8] LMS-0019600-11-TW Finished Rate: 88.89% Fail item: Bluetooth Connection Test Pending items: Connector Engage/Disengage Durability, Tumble and Battery Life Test Expected Completed Date: 02/25 @Wu, Steve [WK10] All testing completed on 03/03. | TWN Lab | 2022-02-15 16:00:00.0000000 +00:00 | 2022-03-03 19:41:01.7560090 +08:00 | 1
3 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #3 | 2022-03-03 16:49:41.1229176 +08:00 | Process validation | 3.D-13 | Review PR issue in PRWeb (MP block issue) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | SW issue 1. BI 24% fail 2. Wrong temperature detection issue 3. Keypad can’t light on | 1. BI issue is still under investigation by SW team. - Action: 3/23 SW release，ECO#239683. EE did the experiment (10 samples) with the same environment (25 degrees three days/ 60 degree BI for one day). There is no shut down phenomenon, but we still need time to verify for safety unitl MP 4/6. 2. Temp detection & keypad BL issue & ghost key issue had resolved. 3/23 SW release，ECO#239683 All issue had been resolved by 4/1 | NPI | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-01 13:15:53.0971880 +08:00 | 1
1 | Fitness | vivomove Trend (previously "4") | GMLA #1 | 2021-10-22 23:00:19.8693026 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | NG: ATE、PRNP、Lock Conn.、PCBA Screwing | The strain gauge of ATE and PRNP passed on FP1. The strain gauge of ASSY will be test on FFP. | PQE | 2022-01-20 16:00:00.0000000 +00:00 | 2022-03-31 17:01:55.1619634 +08:00 | 1
1 | Fitness | Forerunner 255 | GMLA #1 | 2021-04-18 23:12:11.8674891 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | ASSY : Screw 、buckle Conn are NG | Retest in next build because of new PCB version. Apply underfill as protection to the components if still fail the test. | PQE | 2021-05-31 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #2 | 2022-01-27 14:46:07.4505995 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 92.59% on 1/27. | LMS-0019600-7-TW Finished Rate: 92.59% Fail item: Bluetooth Connection Test Pending items: Thermal Measure and Battery Life Test Expected Completed Date: 1/29 @Wu, Steve [WK8] All testing completed on 02/11. | TWN Lab | 2022-02-15 16:00:00.0000000 +00:00 | 2022-02-17 16:13:37.0004621 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 440-00335-00 cannot be released to vA (ECO#228938) | 440-00335-00 has released to rev.A (ECO#228938) | NPI/ME/DE |  | 2021-10-19 18:24:48.6426035 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #2 | 2022-01-27 14:46:07.4505995 +08:00 | Process validation | 2.D-10 | FFP Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 and needs to be tracked: 1. Conducted GPS Sensitivity C/No_1.3 2. 100% SPK_0.68 | 1. Conducted GPS Sensitivity C/No: 1.3 - Action: Distribution is within specification and will be changed to the relative value with CN calibrated board, and keep tracking in next build. 2. 100% SPK: 0.68 - Action: Distribution is within specification and the lower specification limit will be adjusted to 4.4V. | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 161-01355-Y8 is not finalize | ECO #231222 is released. | MFG ME | 2021-10-14 16:00:00.0000000 +00:00 | 2021-10-25 19:11:07.2203708 +08:00 | 1
2 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process development | 3.C-2 | Review Machine/ Fixture list and ETA (need to meet build plan) -- Schedule of any modification or adjustment can meet PR build | No PR build SMT fixture list | SMT PE has provide fixture list | NPI | 2021-10-24 16:00:00.0000000 +00:00 | 2021-10-25 19:38:03.7970349 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #3 | 2022-03-03 16:51:20.9293336 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 010-0259X-XX / 012-04305-10/ 161-05801-01 / 161-05808-0X/ K00-01359-0X are still not rev. A | Same as 5" | NPI/ME/DE | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-01 13:21:20.9535748 +08:00 | 1
2 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process development | 3.C-5 | Update SOP for PR build (experimental version) -- Special characteristic should be included and must correspond with D/PFMEA | No SMT SOP for PR Build | SMT PE has provide PR SOP | NPI | 2021-10-24 16:00:00.0000000 +00:00 | 2021-10-25 19:37:51.7548321 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process development | 3.C-13 | BOM structure review (if any part needs to be added or changed after build) -- Lost parts/ wrong level/ wrong qty -- Include auxiliary material (副料) | 2 extra materials need to be introduced through TECO after PR | Have been added in BOM before PR Asia by PE Joe | NPI | 2021-10-10 16:00:00.0000000 +00:00 | 2021-10-25 20:12:15.0483737 +08:00 | 1
3 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #3 | 2022-03-03 16:51:20.9293336 +08:00 | Process validation | 3.D-13 | Review PR issue in PRWeb (MP block issue) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | SW issue 1. BI 24% fail 2. Wrong temperature detection issue 3. Keypad can’t light on | Same as 5" | NPI |  | 2022-04-01 13:21:04.4771148 +08:00 | 1
1 | Outdoor | Approach R50 | GMLA #1 | 2021-12-07 13:47:26.7286025 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain measurement of 105-04227-00 de-panel is over spec. The strain force is measured to 378 um/mm.(spec 300 um/mm) | Will change 105-04227-00 from de-panel to router process. After the design fixed, NPI will applier the fixture for router on next build. | NPI/PQE | 2022-02-27 16:00:00.0000000 +00:00 |  | 0
1 | Marine | ECHOMAP UHD2 (Touch) 6" | GMLA #1 | 2021-12-13 17:04:35.1773220 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 1. 105-04368-00 & 105-04403-00: Wait for NPI to provide the router fixture 2. 105-04267-00: ASSY screw is ongoing | 1. Will verify the strain gauge when tooling is ready. (Plan to measure on FFP) 2. The 105-04267-00 screwing process strain gauge is ongoing and will finish on 12/24. [WK1 2022] After PQE assessment there are no parts to be verified on 105-04267-00, so no testing requirement. [WK8] The strain gauge testing plan is still pending due to the FRM178 of first FP cannot be released. [WK12] 105-04368-00 & 105-04403-00 router pass. | PQE | 2022-03-13 16:00:00.0000000 +00:00 | 2022-03-14 14:14:18.8660330 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | Lock Connector I400 、 gearbox screw I601 and PCBA screw I701 are NG | These location has implement underfill gluing in PR. Detailed will be updated in SMT SOP | PQE | 2021-10-21 16:00:00.0000000 +00:00 | 2021-10-25 14:40:55.1183476 +08:00 | 1
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #2 | 2022-02-23 10:19:51.8518228 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | All the tests will be finished before 3/1. | Complete rate: 96.9% on 3/1, expecting to finish on 3/11. Completed on 3/17. | TWN Lab | 2022-03-16 16:00:00.0000000 +00:00 | 2022-03-17 18:47:43.5967613 +08:00 | 1
1 | Fitness | vivomove "Lite" | GMLA #3 | 2021-09-27 22:15:16.1890706 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | No Auto screw machine verification report | PDO plan to provide the auto screwing machine verification report after Asia PR was completed. | PDO/AE | 2021-10-31 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Product validation | 2.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 4 items are testing 1. Accelerated Weathering Xenon 2. Accelerated Weathering UV 3. Life Run-in Test 4. Validation Run-in Test | 1. Accelerated Weathering Xenon (The results showed the paint crack and the vendor is doing the analysis, the report update to be confirmed @Lin, Gilbert(ME Marine)) 2. Accelerated Weathering UV (completed and PASS) 3. Life Run-in Test ( complete date: E/Mar.2022)  Run-in test result showed positive in Dec. - Next checkpoint: JAN.3rd. @Huang, Matt(QA) 4. Validation Run-in Test ( complete date: Feb. 10th 2022)  Run-in test result showed positive in Dec. - Next checkpoint: JAN.10th. @Huang, Matt(QA) | TWN Lab | 2022-03-30 16:00:00.0000000 +00:00 |  | 0
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Process development | 2.C-6 | Release preliminary Control Plan (v001) -- Special characteristic should be included and must correspond with D/PFMEA -- (AOEM) Regular requalification should be included | Control Plan is preparing | PQE had done the control plan and completed the update to the PID checklist | PQE | 2021-11-29 16:00:00.0000000 +00:00 | 2021-12-22 13:45:15.3591521 +08:00 | 1
2 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Process validation | 2.D-8 | FFP final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 95% | Yield rate < 95% 8 CH: (1) ATE 94.92% - Open Current 14.4V (-80） (2) ATE2 91.23% - Z1L Level (BP) (3) Pre-FT 93.62% | 8 ch: (1) ATE 94.92% - Open Current 14.4V (-80) >> AE has modified the testing fixture which is the same action from the 4 CH MP type. Add the plug to simulate the speaker load. The cycling test (10 times) was passed by AE, the PR verification result was passed. (2) ATE2 91.23% (3) Pre-FT 93.62% >> Both of them were caused by contact problems on PCB and fixtures due to extra flux on test points. SOP (SP010367, v01) has been updated and PE adjusts flux amount on test program. OP needs to clean the test point after MPS. | NPI | 2021-06-24 16:00:00.0000000 +00:00 | 2021-06-25 10:34:05.0585141 +08:00 | 1
2 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate >= 10% 6 CH: (1) ATE 27.59% - Open Current 14.4V (-60) (2) ATE2 83.93% - Z1L Level (BP) (3) Pre-FT 12.2% - Z1L Level (BP) 8 CH: (1) ATE 16.95% - Open Current 14.4V (-80） (2) ATE2 71.93% - Z1L Level (BP) (3) Pre-FT 25.53% - Power On 14.4v | 6 CH : (1) ATE 27.59% - Open Current 14.4V (-60) : >> AE has modified the testing fixture which is the same action from the 4 CH MP type. Add the plug to simulate the speaker load. The cycling test (10 times) was passed by AE, and waiting for PR verification on 6/B. (2) ATE2 83.93% - Z1L Level (BP) >> Found the short circuit at RCA connector pads due to extra solder paste. PE has modified the MPS fixture and updated flux amount by test program before PR. 8 CH : (1) ATE2 71.93% - Z1L Level (BP) >> High retry is caused by contact problems on PCB and fixtures due to extra flux on test points. SOP (SP010367, v01) has been updated and PE adjusts flux amount on test program. OP needs to clean the test point before ATE test. | NPI | 2021-06-24 16:00:00.0000000 +00:00 |  | 0
2 | Marine | FUSION - Apollo Amplifiers 1 / 4 channel | GMLA #2 | 2021-02-08 16:59:07.9766140 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 012-03876-00 (1Ch) ATE 28.57% / 012-03843-00 (4Ch) ATE 14.29% | ATE: 1. Class D 420kHz LegB(-10): Was casued by BNC test cables, retest passed after changing cable. 2. Hall sensor output High Current: Caused by pogo pin’s thick wiring, can be improved by adjusting wiring inside fixture. Will run cycle test before PR. (Updated on 4/6) Cycle testing result was passed. 3. GeneralCurrent(Iin) (-40): Incorrect voltage of internal converter or bad relay, can be improved by replacing relay. Will run cycle test before PR. (Updated on 4/6) Cycle testing result was passed. | NPI | 2021-02-28 16:00:00.0000000 +00:00 | 2021-04-06 10:43:31.6977785 +08:00 | 1
2 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Reviewed in bi-weekly meeting | Issue: Solder crack issue for APIX IC component (Mainboard and IDC daughter board) after temperature cycle test. Root cause: Uneven stress/strain due to uneven solder joints. Action: PE Solution - Modify pad size to 0.3mm and via Qty to 3*3. TST initial result ETA 4/12 | NPI | 2021-04-15 16:00:00.0000000 +00:00 |  | 0
2 | OEM Auto | BMW MGU22/IDC | GMLA #2 | 2021-01-27 11:49:37.1989154 +08:00 | Process development | 2.C-5 | Release preliminary working instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Need to get latest CC/SC into flow chart and PFMEA. | SC has added to PFMEA. Release process is ongoing. | NPI | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #3 | 2021-07-15 11:33:41.4660021 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: 13 items testing: Operating Hot/Cold Unit Performance/Storage Hot/Cold Unit Performance/Thermal shock/Temperature and Humidity Cycle Test...etc. The expected complete date:2021/8/3 | ELOT in progress The expected complete date:2021/8/3 | TWN Lab | 2021-08-02 16:00:00.0000000 +00:00 | 2021-08-26 14:53:14.5886988 +08:00 | 1
2 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate >/= 10 % but with improvement plan SMT : ATE(26.92%)-Battery Voltage Measurement Accuracy,LTE CW Measure 1732.5MHz ASSY: CT(19.06%)-Compen C/No by ref、HT(12.08%)-Compen C/No by ref、RT1(21.06%)-ALS Luminance (WLED ON)、RT2(25.46%)-Touch Screen Check、DeformationVT_3bar(29.55%)-連續斜率異常、FT1(14.75%)-Battery Voltage、FT2(10.83%)-LTE Rx Value、ST(40.5%)-Play Sound File、ProdScan(50.52%)-Check Battery Voltage、Airtight_table_5bar(20.16%)-變形量絕對值超出規格 | <SMT ATE> - Misjudge/Fixtures – resolved - V1P2 SW issue, OLA will help to remove this item in MPS for PR build – closed - LTE chip pre-booting, LTE module needs to pre-boot for sure, EE will verify the LTE pre-boot combination in PRNP for PR – ongoing @Yeh, Steven <ASSY/TEST> CT(19.06%) HT(12.08%)-Compen C/No by ref – Tracking( first time we implement the auto chamber in PR) RT1(21.06%)-ALS Luminance (WLED ON) – resolved RT2(25.46%)-Touch Screen Check– resolved FT1(14.75%)-Battery Voltage : PR will charge the unit after VT and before FT1. @Wang, Annie FT2(10.83%)-LTE Rx Value – resolved ST(40.5%)-Play Sound File – resolved ProdScan(50.52%)- Battery Voltage @Wang, Annie PR will charge the unit after ST and before Product Scan. Airtight_table_5bar(20.16%)-Tracking(new membrane 5ATM implement) Need to see the action result in PR build by 6/18 | NPI | 2021-06-17 16:00:00.0000000 +00:00 | 2021-07-20 09:05:52.1007943 +08:00 | 1
1 | Outdoor | Delta Simple | GMLA #3 | 2022-04-21 17:09:58.2728035 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing. The expected completion date is 5/3. ※ 2 items under testing: Accelerated Weathering UV (UV-A/B) ※ 3 items not started yet: Connector Bending/ Shipping Vibration/ CT scan | ELOT is progressing. The expected completion date is 5/3. ※ 2 items under testing: Accelerated Weathering UV (UV-A/B) ※ 3 items not started yet: Connector Bending/ Shipping Vibration/ CT scan | TWN Lab | 2022-05-02 16:00:00.0000000 +00:00 | 2022-05-05 14:01:19.8332452 +08:00 | 1
2 | Fitness | Bounce(Waldo) | GMLA #2 | 2021-05-06 14:33:35.3773329 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | No Test coverage data upload | TW-EE MPS reviewing, estimate to complete by 5/31 @Yeh, Steven | MFG EE | 2021-05-27 16:00:00.0000000 +00:00 | 2021-07-20 09:05:08.5812266 +08:00 | 1
2 | Outdoor | Delta Simple | GMLA #3 | 2022-04-21 17:09:58.2728035 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10% issue ※SMT 1. MultiUpdater 20.92%: 5 BB Software ※Assy Testing 1. HT 19.57%: 電池溫度¦Battery Temperature 2. RTESN 13.67%: 旋鈕測試1¦Stim Dial 1 3. CT 10.14: 旋鈕測試¦Stim Dial | ※SMT 1. MultiUpdater 20.92%: 5 BB Software >> test computer issue. Will double check before PreMP. ※Assy Testing 1. HT 19.57%: Battery Temperature >> adjusted temperature. >> 65degress 2. RTESN 13.67%: Stim Dial 1>> added a rib. 3. CT 10.14%: Stim Dial>> added a rib. | NPI | 2022-05-26 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is not on schedule due to whitestone sku not provide |  | TWN Lab |  |  | 0
1 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | Will execute CC test on extra build due to previous build does not have enough units to do it |  | PQE |  |  | 0
2 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process development | 3.C-2 | Review Machine/ Fixture list and ETA (need to meet build plan) -- Schedule of any modification or adjustment can meet PR build | PCB screwing fixture, Auto chamber fixture, G-sensor fixture, SN tag pressing fixture etc are not meet schedule due to redo |  | NPI |  |  | 0
1 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | 1. Software v7.44 lack lots of font/audio files(language) 2. (WW&Asia SKU)There are some RGN86 (Text files ,006-D8579(D8581)-36/-37/-41/-42/-43) shown "missing" in the product inventory. |  | PQE |  |  | 0
1 | Outdoor | Delta Simple | GMLA #3 | 2022-04-21 17:09:58.2728035 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Inspection VIP not ready: ※ME parts 13 items not ready (011-03801-21(O)/011-05698-50(X)/115-03737-10(o)/145-03676-XX(O)/414-00281-00(O)) | All VIPs will be updated by PreMP | MFG EE/ME/DE | 2022-05-15 16:00:00.0000000 +00:00 | 2022-05-27 10:06:20.5669651 +08:00 | 1
2 | Outdoor | Delta Simple | GMLA #3 | 2022-04-21 17:09:58.2728035 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 82% - ME part 13 items not ready (011-03801-21/011-05698-50/115-03737-10/145-03676-XX/253-01441-10/414-00281-00) | Target to complete FA before 145-03676-20/145-03676-70/011-05698-50 FA checking | MFG ME/DE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Expected P/N didn't correspond with BOM | Unit SW issue- expected PN should be 006-D8422-xx that will same with BOM. Aims to fix by Pilot Run | NPI | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #3 | 2021-07-15 11:33:41.4660021 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | 117-01599-XX/125-00626-XX not define the IQC VIP. | MME will release the IQC VIP on the FA system before 7/22 | MFG ME | 2021-07-21 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 41% (see reference) DE 83% (see reference) |  | MFG ME/DE |  |  | 0
1 | Fitness | Edge Explore 2 | GMLA #1 | 2021-10-29 15:56:19.1863262 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain gauge measurement of 105-04457-00/105-03666-10 did not start yet. Will verified when tooling is ready. (plan to measure on first FP) | 1. For de-panel, will verified the strain gauge of PCBA before 11/5. 2. Will verified the screwing process strain gauge of PCBA when tooling is ready. (plan to measure on first FP) | PQE | 2021-11-29 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #3 | 2021-07-15 11:33:41.4660021 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 76%. 42 items FA still under progressing | FA complete rate is progressing. MME will push the progress to meet the 100% target before 7/28 | MFG ME | 2021-07-27 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | OHRM FPC ATE(10.13%), main board iATE(28.63%), main board preboot(18.16%) can't meet target | ATE: 1.) Fixture Alignment Improve 2.) Fixture USB Connection unstable 3.) Fixture Topgate Issue All will be fixed by PR Kickoff. OHRM: Shorten the wire length in fixture to reduce the distortion | NPI | 2021-04-15 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Venu 2 Plus | GMLA #2 | 2021-03-17 17:26:25.7157250 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | Can't find testing coverage report or any comment on PRweb | ATE 95 items (Complete Rate=100%) FT(ALL ASY Test)*54 items (Complete Rate=96%) Lacking 2 test function of ECG, complete in PR. | MFG EE | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-8 | FFP final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 95% | VT yield <95%. Improvement plan need to be tracked at next build. | Verified Pass on EPIX2 FFP2 with fixtures modified | NPI | 2021-03-09 16:00:00.0000000 +00:00 | 2021-05-19 13:02:58.4071419 +08:00 | 1
2 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | There are five station's retry rate >10%. 1. VT 120.32% 2. CT 17.86% 3. HT 17.03% 4. FT1 19.5% 5. FT2 18.67% | 1: see 2.D-8 for VT issue 2 & 3: CT/HT retry is mostly contributed by GPS_L5, which is related to instable fixtures and chamber. Expect to resolve by implementing auto chamber and will verify by PR (3/30). @Huang, Sam(EE) 4: FT1 retry is mostly caused by WiFi Power, which is relevant with poor contact of antenna, antenna design will change and will verify in PR (3/30). @Huang, Sam(EE) 5. FT2 retry is due to Power Box Sampling BL and Motor Resonant Frequency. Will modify test sequence for power box sampling and use new FPC design for motor resonant frequency, keep tracking in PR (3/30). @Huang, Sam(EE) Above can be tracking by GMLA3 | NPI | 2021-03-29 16:00:00.0000000 +00:00 | 2021-05-19 13:09:53.6516708 +08:00 | 1
2 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | 3 critical issues:1.Waterproof fail 2.ILP fail 3.I900 strain test failed | 1: see 2.D-8 for VT issue, closed. 2: ILP issue verified Pass in PR 3: see 2.D-3 for I900 strain issue, closed | NPI | 2021-03-09 16:00:00.0000000 +00:00 | 2021-05-19 13:03:51.7352269 +08:00 | 1
2 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Okay |  | NPI |  |  | 0
2 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | Need update 174 | PjM will take update ESD bad and label to update 174- packing document. 174-00514-01 update to Rev.0C in 3/27 to meet current packing status. | EPM | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-07 15:36:08.8164242 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | There are 12 components no reflow temperature. | Complete rest 12pcs parts max.reflow temperature. | NPI | 2022-03-23 16:00:00.0000000 +00:00 | 2022-03-24 10:46:42.9201341 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | Need verification report for critical machine define in DFM | Completed, verification result of color test as system attachment. | NPI/PQE |  | 2022-03-23 19:23:36.2532686 +08:00 | 1
1 | OEM Auto | IXWW22 | GMLA #3 | 2022-03-18 15:50:55.9337636 +08:00 | Process validation | 3.D-6 | Provide PVP (Process Verification Plan) result of critical process -- Refer to critical process/ equipment/ special characteristic definition -- Cpk check (Preparation: define which critical process should apply SPC, ex: SPI/ voiding) | Critical process / equipment should do PVP or verification. | NPI PE will add new color test page verification, expect complete before 4/8. Color test ITMXP updated for pixel/partical spot determine, will check the test result in PR-3 build. | NPI | 2022-04-07 16:00:00.0000000 +00:00 | 2022-04-07 16:38:48.9173074 +08:00 | 1
1 | Outdoor | inReach Messenger | GMLA #1 | 2021-09-01 16:17:13.9355925 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain gauge measurement did not start yet. Will verified when tooling is ready. (plan to measure on first FP) | The strain gauge measurement of de-panel and screwing process will be verified when sample is ready. | PQE | 2021-10-24 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GPSMAP 9000 - 24" | GMLA #1 | 2022-03-07 14:30:03.1352847 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04277-00: ASSY screw connector is not complete due to fixture is not ready | Now has two version(Rev.2 for 22”/24” and Rev.3 for 19”/27”) use in WP phase at same time. 105-04277-00 Rev.3 will wait until 19"/27" is assembled before testing. | PQE | 2022-06-22 16:00:00.0000000 +00:00 |  | 0
2 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Follow up |  | NPI |  |  | 0
2 | OEM Auto | BMW MGU22-RSE | GMLA #2 | 2021-02-06 10:10:06.5416066 +08:00 | Process development | 2.C-5 | Release preliminary working instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | comment as feedback |  | NPI |  |  | 0
2 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Black box: No ASSY and TEST SOP | Black box - NPI PE should upload SOP by 05/31. | NPI | 2021-05-30 16:00:00.0000000 +00:00 | 2021-06-22 18:58:28.3814945 +08:00 | 1
2 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT (1) 012-04060-00 ATE 218.33%: Check ESN 61.37% (2) 012-04060-D1 ATE 23.41%: V1P8 4.68% 2. ASSY (1) BB a. CT 57.89%: (No.5) Image sensor test 10.53% b. HT 78.95%: (No.1) Image sensor test 15.79% c. Acc_Calibration 39.29%: 2th Direction confirm-Y 3.57% d. Gyro_Calibration 137.5%: Y axial rotation(Script) 39.29% e. FT 89.09%: Gyroscope Calibration Matrix11 20% (2) Camera a. CT 28.35%: Temperature 22.05% b. HTMTF 263.39%: Capture image 42.52% c. Acc_Calibration: 109.45%: Max Angle Error 38.95% d. Distortion: 156.97%: Distortion Calibration 40.98% | 1. SMT: 012-04060-00 ATE ESN Root Cause: No ESN response. Caused by MPS fixture cracked component issue which makes unit fail to turn on. Action: Implement new MPS fixture & finish verified. OLA also modified the PCB layout. (Finished) 2. ASSY: Black Box: Gyro_Calibration Root Cause: SW issue. ACC_Calibration data missing. Action: OLA updates SW and EE verified pass. (Finished) 3. Camera : HTMTF Root Cause: Fail to receive the image reply stably by IOP due to SW issue. Action: OLA updated SW and verified pass in FFP2. | NPI | 2021-08-12 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Instinct 2 | GMLA #2 | 2021-05-11 17:37:50.9132378 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | 9 of 82 items were not tested. 1. VDD_1.8_WHR 2. Pressure Sensor Noise(Standard Deviation) 3. 26MHz Accuracy 4. Average External Supply Current in Test Mode 5. Pressure Sensor Temperature Accuracy 6. Pressure Sensor Pressure Accuracy – 1atm (Cold Temp) 7. Baro BIST 8. Backlight Functionality 9. NFC Inventory Check | 1. VDD_1.8_WHR (No need to be tested. A more strick test is already in MPS, MPS will be updated at PR (7/9)) (6/2:canceled) (ECO#224113) 2. Pressure Sensor Noise(Standard Deviation) (Added) (ECO#224113) 3. 26MHz Accuracy (Not suggest to add, it will affect other test item, wait for Olathe feedback(7/9)) 4. Average External Supply Current in Test Mode (Added) (6/2:canceled) (ECO#224113) 5. Pressure Sensor Temperature Accuracy(Added) (ECO#224113) 6. Pressure Sensor Pressure Accuracy – 1atm (Cold Temp)(Added) (ECO#224113) 7. Baro BIST (Added) (ECO#224113) 8. Backlight Functionality (Added) (ECO#224113) 9. NFC Inventory Check (Olathe prefer to remove, MPS will be updated at PR(7/9)) <removed on 6/14> | MFG EE | 2021-06-13 16:00:00.0000000 +00:00 | 2021-06-24 17:08:22.0144788 +08:00 | 1
2 | Outdoor | Instinct 2 | GMLA #2 | 2021-05-11 17:37:50.9132378 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Multiupdater 52.1%(MultiUpdater USB Update), ATE 18.87% (VBAT current) CT 13.17%(Language File check), HT 20.11%(GlONASS 78 CNo by ref.), RT1 27.04%(GlONASS 65 CNo by ref.), RT2 19.92%(ANTCW TX(CW BOX) CH57 solar), Solar 23.03%( Calculated Power), FT1 54.19%(GlONASS 65 CNo by ref.C/No by ref.) Gyro 10.84%(Gyro Data X軸檢查) | <Top 3 station with top 1 fail> 1.Multiupdater 52.1%(MultiUpdater USB Update 13%) Containment action : apply new SW Validation : retry rate 1.71% in PR. 5.RT1 27.04%(GlONASS 65 CNo by ref. 13%) Action : Reduce length of antenna and introduce auto chamber. Validation : Retry rate 0.46% in PR. 8.FT1 54.19%(GlONASS 65 CNo by ref.C/No by ref. 16%) Action : see above Validation : Retry rate 0.68% in PR. | MFG EE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-06 13:39:34.1801315 +08:00 | 1
2 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate not meet the target <10% 1.SMT (1) ATE 20.9%: Iridium Tx Burst CH01 diff 2.ASSY (1) FT3 21.46%: Iridium Tx CH120 by Ref (3) FT1 18.05%: BT CW High/BT CW Medium (4) VT1 12.79%:抽氣次數違反 (5) G sensor 10.73%: Z min | 1.SMT [Herry] Wait Olathe re-layout IRID to decrease short circuit. 2.ASSY (1) FT3 used old IRID power box-->fixed. FT3 fixture modification--> fixed (3) 2G4 antenna modification in next rev is not completed yet.-> design team modified. (monitor in PR build) (5) G sensor: FW + fixture modification | NPI/EE/ME/DE | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-29 20:09:29.0429544 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 014-04375-00 & 011-05745-40 & 541-B4080-00 are still v001. | 541-B4080-00 & 014-04375-00 are released on 9/15 by EE. The ELOT test of display was complete on 9/15 and 011-05745-40 was released on 9/17.-Closed | MFG EE/ME/DE | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-28 12:59:28.9927661 +08:00 | 1
2 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04149-00/02/03 is v01 and not finalized in PR | ECO released on 9/7. | MFG ME | 2021-09-08 16:00:00.0000000 +00:00 | 2021-09-09 15:31:36.6324932 +08:00 | 1
3 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Storage Hot/Cold Unit Performance (2/2 NG): Bubble found after HT 2. Thermal shock (1/2 NG): Bubble | Implement 291-00159-00 bonding glue which is used on GPSMAP 86 HT: Bubble found at 85°C on LOCA-159 Action: Relief TST test criteria from 85C to 80°C. 9/16 re-test and find minor bubble but not in active area (LMS-0018736) - Waived TST: - Relief TST test criteria from -40C~85°C to -20~60°C, same as GPSMAP 86 - ELOT TST: -20~60°C, 2 pcs PASS on 9/6. (LMS-0018736) | DE | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-27 17:07:05.4192542 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Accelerated Weathering Xenon is testing | ELOT are complete on 9/11. | TWN Lab | 2021-09-10 16:00:00.0000000 +00:00 | 2021-09-22 09:16:16.7416720 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Process development | 3.C-12 | OOB (Out of Box) checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | OOB checklist preparation is ongoing | PQE work on it, and completed by 9/24. | PQE | 2021-09-23 16:00:00.0000000 +00:00 | 2021-09-27 17:29:35.1596026 +08:00 | 1
2 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | FT 96.25% cannot meet the target (97%) | Keyboard Test: Action: Keypad had been improved by supplier. The keypad test will be implemented in RTESN to filter the fail unit._closed CNo GLONASS 65: The unit need to rework with new MT3333 chip._tracking | NPI/EE/ME/DE | 2021-09-16 16:00:00.0000000 +00:00 |  | 0
2 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 85.19%: VBATSENSE (2.35V) ASSY 1. RTESN 31.71%: Unit Temperature 2. VT1 14.63%: 抽氣次數違反 3. VT2 53.85%: 大漏氣_未抽至1120 4. CT 67.9%: CNo GPS 16 5. HT 36.25%: CNo GPS 16 6.G Sensor 15.19%: x_acc_n 7. FT 260%: flash test 8. VT3 43.84%: 大漏氣_未抽至1120 | Top3 1. FT 260% CN related test item Analysis: SG is unstable, and test would be interference by Iridium equipment. Test pass after SG calibration and remove Iridium equipment. Action: Remove Iridium to PACK station 2. ATE 85.19% VBATSENSE Action: Could be improved by modifying IOP, and V10.6 has fixed. – closed 3. CT 67.9% CNo 16 Analysis: The grounded soldering is not enough on some units from 2 lower C/No sample. Action: Add NG/GOOD unit photo in SOP. | NPI/EE/ME/DE | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-27 17:09:00.9210845 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. NMEA power on (9V) 0.71 2. USB power on (4.4V) & (5.25V) 0.56 & 0.78 3. PCB Current (USB_4.4V) 0.24 4. CNo Galileo 1 0.42 5. Battery power on (2.35V) 0.44 6. PCB Current (Battery_2.35V) 0.59 ASSY 1. Most of all CNo (GPS/GLONASS/Galileo) cannot meet the target | SMT: Modify SPEC in 004-MPS, and design team updated MPS on 9/17. ASSY: Analysis: We found the iridium on the production line would affect the test result of CN related test item. Action: Will block the iridium signal and test again to collect the test retry rate information for MP. | MFG EE | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-28 12:59:50.2393689 +08:00 | 1
1 | Marine | GPSMAP 79 Series | GMLA #3 | 2021-09-08 19:26:33.3899727 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA cannot meet 100% 1. ME FA rate: 87% 2. DE FA rate: 33% | ME will complete FA by 9/30 DE will complete FA by 9/17. | MFG ME/DE | 2021-09-29 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Instinct 2 | GMLA #2 | 2021-05-11 17:37:50.9132378 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | CC test immersion NG (3 out of 37) | We will apply 2 methods for PR build rear cases at OSP side to prevent gasket damage. <for gasket damage> 1. carry out 100% CCD scan on the gasket. 2. Improve gasket assembly method. <For HRM puck less glue > 1. Increasing weighting frequency >> to make sure glue is sufficient. 2. Carry out 100% CCD scan. >> to make sure glue spreads evenly. 3366364351 observed bubble through 5 atm test, I still doubt it might leak from charging pin and it caused the HRM puck peeling. [Alden] Gasket no damage 3367285192 passed 10 atm immersion test but it failed to 10 atm displacement tester. We use clay to seal the charger and it passed 10 atm displacement tester, so it leak from charging pin. [Alden] Gasket damaged 3367285575 leak from the housing/bezel, but it is weird that it didn’t leak when we test the first time. So I think it probably leak from other place and the internal pressure push the bezel out. [Alden] Gasket damaged Validation : CC test passed in PR. | NPI | 2021-07-08 16:00:00.0000000 +00:00 | 2021-07-06 13:52:08.6256299 +08:00 | 1
2 | Marine | GT36/GT56 UHD Transducers | GMLA #2 | 2020-12-03 18:31:46.7200000 +00:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | [5 empty] | 0
2 | Fitness | Venu H(Asia ISO13485 Certification) | GMLA #3 | 2021-01-29 23:29:59.6063595 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | Yield rate of each test station <97% ASSY : PI_UTUBE1、PS、FT_SPO2 |  |  |  |  | 0
2 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #3 | 2022-05-17 22:03:28.6089749 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME part: 45 items did not complete FA |  | MFG ME |  |  | 0
1 | Automotive | dezl OTR Series 2022-10" | GMLA #1 | 2021-11-17 19:35:10.8859599 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04456-00 de-panel NG. PCB layout will be modified in the next build. | Olathe will moving the failing parts on the next board release. [12/10] Will change de-panel manually to routing [01/25] After changing to routing, the result is pass. | PQE | 2022-01-24 16:00:00.0000000 +00:00 | 2022-02-14 10:55:09.1510890 +08:00 | 1
1 | Automotive | Tread Audio System | GMLA #3 | 2022-03-11 18:16:53.0995416 +08:00 | Product development | 3.A-6 | All ME/DE parts should be version A before PR | 161-05980-00 has not been turned A yet. | 161-05980-00 is in version A. | MFG ME | 2022-03-17 16:00:00.0000000 +00:00 | 2022-03-18 16:06:38.3701859 +08:00 | 1
3 | Automotive | Tread Audio System | GMLA #3 | 2022-03-11 18:16:53.0995416 +08:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | 1. Electrostatic Discharge (ESD) Immunity test (2/2) -Root cause: Under analysis. 2. Salt fog (2/2) -Description: ．3404539374(OP) 14.4V→24H Connection location Rust, 48H screw Rust,VT4 & light & bluetooth pass ．3404539367(Soak)→48H screw Rust & paint have bubble,VT4 & light & bluetooth pass -Action: Olathe has commented if it didn't affect the power-up effect, and the Powerswitch results are almost identical to the Blaster results at 120hrs & 168hrs. It will qualify 168hr salt fog test as PASS. It can refer to LMS-0015738-5-OE-ME. 3. Product Package Drop (2/3) Description: ．01-Tread→carton & packaging bag broken ．00-Tread+speaker→carton broken & carton rubbing marks on tread ．02-speaker→carton no defect Action: Wait for OLA's feedback. 4. Shipping Vibration (2/3) Description: ．01-Tread→carton rubbing marks ．00-Tread+speaker→carton rubbing marks on tread ．02-speaker→outward no defect Action: Wait for OLA's feedback. | [Closed] 1. Electrostatic Discharge (ESD) Immunity test (2/2) -Action: Add ESD component. MEE/DEE had checked the positive result. -The new PCB will be tested again in Pre-MP. -Evidence: ECO#239175 [Closed] 2. Salt fog (2/2) Do the test again in a vertical direction. -Description: ．Power on pass *1. ．Power off NG *1 (1/1) - Bubble after 72 hr. -Root cause: ME guessed it might be caused by the grinding process after the passivation process from the vendor side. The passivation layer might be too thin which might cause the bubble issue after the salt fog test. -Action: MME discuss with DME to check if it is possible to ask vendor do not grind from the edge 10mm. OLA comments it will not be a MP block, and it will be a running change. [Closed] 3. Product Package Drop (2/3) -Description: ．01-Tread→carton & packaging bag broken ．00-Tread+speaker→carton broken & carton rubbing marks on tread ．02-speaker→carton no defect -Action: OLA waive. [Closed] 4. Shipping Vibration (2/3) -Description: ．01-Tread→carton rubbing marks ．00-Tread+speaker→carton rubbing marks on tread ．02-speaker→outward no defect -Action: OLA waive. | TWN Lab | 2022-05-25 16:00:00.0000000 +00:00 | 2022-05-26 11:24:17.6728851 +08:00 | 1
2 | Automotive | Tread Audio System | GMLA #3 | 2022-03-11 18:16:53.0995416 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ※ASSY 1. FT(46.73%)_AMP 溫度¦Temperature of amp thermistor(C) (10.28%) 2. VT1(19.44%)_小漏氣_超過洩漏量門檻 (8.33%) 3. VT2(16.67%)_大漏氣_未抽至1120 (9.26%) ※ATE 1. Amp_Audio_(23.91%)_FM Tuner LOUTR - Vrms (6.52%) 2. Amp_ATE(16.31%)_開機電流¦open current (4.96%) 3. Proc_ATE(10.64%)_V5USB (2.13%) | 1. FT(46.73%)AMP 溫度¦Temperature of amp thermistor(C) (10.28%) -Failure description: The temperature is too low. -Root cause: 1. It is too hot for the operator to take the metal machine after the oven process. They wait for a while then do the test, which causes the failure. 2. The conveyor setting is not ready. -Action: 1. Provide hot-proof gloves. 2. If the capacity is allowed, NPI can fine-tune the conveyor speed and temperature before the PR process. 2. Amp_Audio_(23.91%)FM Tuner LOUTR - Vrms (6.52%) -Failure description: Total 3pcs retest record. One is real failed, and two pieces can pass the test after being retested. -Root cause: Under EE's analysis. AE will run a cycle test and check the result on 3/28. 3. VT1(19.44%)小漏氣_超過洩漏量門檻 (8.33%) -Root cause: 1. Flash of the bottom case. 2. The wrong screw was used. (wrong screw torque) -Action: 1. Ask the vendor to remove the flash before shipping and define the flash spec in VIP for IQC. 2. Enhance the training for the operators. | NPI |  |  | 0
1 | Automotive | Tread Audio System | GMLA #3 | 2022-03-11 18:16:53.0995416 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | 83% on 3/4. | 87% on 3/18. 11 items are under approval. | MFG ME |  |  | 0
2 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004- MPS -- Target: ≧ 90% | Test coverage rate cannot meet the 90% 1. 004-01066-00 Carrier: 81.2% 2. 004-01066-01 Camera: 86.2% | Root cause : SW issue cause test station can't finish verification in FFP1. Action : Add extra FFP2 and plan to implement new SW to finish test station verification. >> After FFP2 build, the testing coverage rate is 100% and can meet the target (90%). | MFG EE | 2021-08-12 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | Yield Rate not meet the target >= 95% 1.SMT ATE 94.03%: Iridium Tx Burst CH01 diff 2.ASSY VT1 94.52%: (1) leakage from LCM/Front case (10pcs) (2) leakage from Front case/ Rear case (2pcs) (3) leakage from antenna cap (1pcs) (4) leakage from USB port (2pcs) | SMT issue: [Herry] Wait Olathe re-layout IRID to decrease short circuit. (done) Assy VT issue: (1)(2) 145-03710-00 tooling modification completed, LCM-related dimensions are in spec (monitor in PR) (3)USB failed units are still under analyzing, suggest to apply glue at the rear side of the connector to solve the issue for good. Will discuss with PE for the new SOP. (Applied new glue on USB) (monitor in PR build especially after reflow and CT/HT test) | NPI/EE/ME/DE | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-29 20:09:20.2794554 +08:00 | 1
2 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT: AmpBD_Audio_ATE2 20.37% / ASSY: CT 14.81% & FT2 22.22% | ATE2 high retry issue is cause by flux contaminated of test point. [2pcs happened at same point and cause 9% retry] Distance between MPS & test point is under design guide line. [> 4mm] 1. Modified SOP and monitoring in PR. @Lai, Bowman 2. Evaluate tape solution to avoid contaminated. @Lai, Bowman Both CT & FT2 high retry cause by same reason. Too many cables need connect during test and OP need well trained and assembly all cables well. Need PE & EE help to discuss for further improvement plan. - Ongoing  No CT/HT/BI after MP | NPI | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT (1) PreBoot 13.15%: 待機電流 ¦ OFF Mode Current 2. ASSY (1) RT1 47.97%: GPS_L5 by ref (2) CT 31.13%: GPS_ (L1 only) by ref (3) FT1 27.85%: GPS_L5 by ref (4) FT3 20.86%: 電池百分比¦batt. percentage (5) RT2 20.60%: 與AP 連線¦(WiFi) Access AP (6) G-Sensor 16.94%: Z min (7) HT 18.2%: GPS_L5 by ref | 1. SMT (1) PreBoot 13.15%: 待機電流 ¦ OFF Mode Current Spec was too tight , already changed the spec 100->150. 2. ASSY (1) RT1 47.97%: GPS_L5 by ref (2) CT 31.13%: GPS_ (L1 only) by ref (3) FT1 27.85%: GPS_L5 by ref (7) HT 18.2%: GPS_L5 by ref 1. Fixture USB cables were not buried below chamber curtain. 2. L5 CN drop when 2.4G cable close to USB cable. 3. Some units' display does not locate tightly enough. 4. The foam on the shield lid is too thin. Adjust the testing cable position to avoid signal interference. @Lin, Andy(EE) @Wu, Joel Adjust the thickness of the foam. @Hsia, Albert Keep tracking in PR build. (4) FT3 20.86%: 電池百分比¦batt. percentage Test retry cause some unit with low battery, will set the charging station for the retry units. (5) RT2 20.60%: 與AP 連線¦(WiFi) Access AP Cycle test cannot replicate, might be WIFI AP issue and need testing support, will keep tracking. @Lin, Andy(EE) (6) G-Sensor 16.94%: Z min OP tested the pass units repeatedly cause the retry rate. will retrain the OP. | MFG EE | 2022-01-06 16:00:00.0000000 +00:00 |  | 0
2 | Marine | FUSION - RA60 | GMLA #2 | 2021-02-06 18:58:31.1933841 +08:00 | Process development | 2.C-5 | Release preliminary working instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | ASSY SOP for FFP is not fully revised. Need to update ASSY SOP before PR | Finished on 02/25 and updated in PID checklist | NPI |  | 2021-03-02 23:31:28.8900000 +00:00 | 1
2 | Automotive | DriveSmart 86 | GMLA #2 | 2021-04-09 13:23:52.4724997 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | *SMT 1. ATE 11.11% *ASSY 1. RTESN 11.5% 2. ST: 71.68% 3. FT1: 15.04% 4. FT2: 15.93% 5. ProdScan: 27.93% | Close and follow up by G3 questionnaire. - ATE retries are mainly from Wifi power_5G, which is due to the comparison with the golden sample at the initial stage of verification. Verified OK after lower limit spec modification. - RTESN: suspected to be relevant with incorrect OP testing methods, keep tracking in PR. @Chen, Leon - ST: a. Amp Golden Value Different retry (40.7%): due to the delay time difference between the test program and signal, verified OK after delay time modification. Test program modified and keep tracking in PR. @Liao, KuoChih b. MIC sealed MAX Amp (19.5%): Test program modified and keep tracking in PR @Liao, KuoChih - FT1: BT connection retries (5.49%) is due to test program setting, modified and verified OK. - FT2 battery voltage tests retries: related to OP test methods, keep tracking in PR. @Liu, Johnny - Product scan 3D fix: related to satellite signal cable looseness. After re-locking the SMA connector of the signal cable, the issue was resolved. SOP will be defined to check the equipment setting before testing on PR. | MFG EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:28:31.3770552 +08:00 | 1
2 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT: (1) BT CW Low(7.3%): has calibrated the fixture. (2) 100% BK current(2.9%): EE will modify MPS before PR. 2. ASSY: (1) RTESN(28.1%)- Speaker check: test equipment set up problem, has been solved. (2) ST(20%)-left MIC sealed MAX Amp: will add alignment in next build. (3) FT(53.2%)-(17%) Authenticate MFI IC(BT):cable not set well, has fixed. (15%) USB PwrOn Cur: we have modified the upper limit and wait for the comment from Olathe. (6.4%) Check Wifi Country Code: disconnection of factory cable. (4) ProdScan(27.8%) - 3D Fix:Operator didn't put well. | 1. SMT: (1) BT CW Low: EE has modified the uncalibrated upper limit from 4 to 5, tracking in PR. (2) 100% BK current: Need to modify the MPS. @Chen, Leon 2. ASSY: (1) RTESN-Speaker check: test equipment set up problem, has been solved. (2) ST: will add alignment in next build. @Chuang, Max(ME) (3) FT: a. Authenticate MFI IC(BT): disconnection of factory cable, it passed after the rework. PE will add “check cable connection” in SOP. @Chen, Jason(PE) b. USB PwrOn Cur: We have modified the upper limit and wait for the comment from Olathe. @Chen, Leon @Bruner, Sam c. Check Wifi Country Code: cable didn't been put well, retry pass. PE will add “check cable connection” in SOP. @Chen, Jason(PE) (4) ProdScan: We found that the satellite signal cable was loose. After re-locking the SMA connector of the signal cable, the issue was resolved. PE will add “check satellite cable connection” in SOP. @Chen, Simon(PE) | NPI | 2021-04-08 16:00:00.0000000 +00:00 | 2021-06-22 18:06:40.5618117 +08:00 | 1
2 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | SMT Yield Rate not meet the target >= 95% ATE 1st Rework yield rate: 99.13%: ATE 2st Rework yield rate: 81.6% | There were some defective PCBAs due to two times PCBA rework in FFP build. Keep tracking in PR build. | MFG EE | 2021-12-31 16:00:00.0000000 +00:00 | 2021-11-22 15:09:10.8526584 +08:00 | 1
2 | Automotive | DriveSmart 76 | GMLA #2 | 2021-03-31 19:35:43.4594342 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT ATE 18.38% 2. ASSY RTESN 11.67% / FT 25.42% / ProdScan 22.22% / ST 26.05% | Close and follow up by G3 questionnaire. - ATE retries are mainly from Wifi power_5G (6.62%), which is due to the comparison with the golden sample at the initial stage of verification. Verified OK after lower limit spec modification. - Assy RTESN: suspected to be relevant with incorrect OP testing methods, keep tracking in PR. @Chen, Leon - FT battery voltage tests retries: related to OP test methods (did not turn off units after the test). - Product scan 3D fix: related to satellite signal cable looseness. After re-locking the SMA connector of the signal cable, the issue was resolved. SOP will be defined to check the equipment setting before testing on PR. - ST Amp golden value different retry: due to the delay time difference between the test program and signal. Test program modified and keep tracking in PR. @Liao, KuoChih | MFG EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:38:53.7333736 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #3 | 2022-03-03 16:49:41.1229176 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 010-025XX-XX / 012-04305-20/ 161-05801-00 / 161-05808-0X/ K00-01359-0X are still not rev. A | Tracking design team SW issue-resolving status for 006 release target date. (Ongoing) 174 & 190 release check point will be 03/11. |  | 2022-03-10 16:00:00.0000000 +00:00 | 2022-04-01 13:16:44.3760559 +08:00 | 1
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 1. Testing (1) Thermal shock (2) Water / Dust Resistance (3) High Temp., Max Voltage Life (4) High Temp., Min Voltage Life 2. Not started (1) Temperature and Humidity Cycle Test | Lab finished and provide the testing result on 6/21. All units pass. | TWN Lab | 2021-06-20 16:00:00.0000000 +00:00 | 2021-06-29 14:18:52.6700912 +08:00 | 1
2 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. ASSY (1) HT 17.11%: Keypad ONKEY(ON) (2) VT1 19.74%: 大漏氣_未抽至1120 | ASSY (1) HT 17.11%: Keypad ONKEY(ON) The test cycle time is too short cause the operator unable to press the power bottom on time. EE already adjust the test cycle time, issue close. (2) VT1 19.74%: 大漏氣_未抽至1120 After re-calibrate the VT fixture and adjust the air pressure/current, retest 10pcs units and all of them pass the test. | NPI | 2021-06-27 16:00:00.0000000 +00:00 | 2021-06-29 15:14:17.8481355 +08:00 | 1
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | 1. SMT (1) V4P1: 0.94 2. ASSY (1) Wi-Fi Power CH1: 0.66 | 1. SMT (1) V4P1: 0.94 EE : This testing value is correspond with MPS specification, if we want to make CPK >1.33, we have to loosen the MPS spec. EE think it is not good for production quality. 2. ASSY (1) Wi-Fi Power CH1: 0.66 Testing SW issue, units passed the test after adjusted the testing SW. Issue close. | MFG EE | 2021-06-27 16:00:00.0000000 +00:00 | 2021-06-29 16:31:43.3425497 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #3 | 2022-03-03 16:49:41.1229176 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 4 items are testing and 11 items are waiting for test | same as above mitigation. | TWN Lab | 2022-03-13 16:00:00.0000000 +00:00 | 2022-04-01 13:16:52.8199853 +08:00 | 1
2 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #3 | 2022-03-03 16:49:41.1229176 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 50.23%: C/NO_GPS16 ASSY 1. VT1 12.35%: Leakage 2. CT 32.92%: Temperature 3. HT 14.91%: Internal GlONASS_65 4. FT1 49.07%: Burn-in Run time 5. VT2 19.14%: Leakage 6. FT2 28.57%: C/No 16 and Golden Diff. | 1. ATE : Retry was caused by fixture contact issue. AE had fixed fixture issue during build. Plan to fixture all duplicate fixture cycle test before MP. 2. BI : Retry was caused by SW issue & OLA SW team is still working on it. 3. EE plan to modify spec. Need keep monitoring in 1st MP order. | NPI | 2022-04-07 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Tumble Fail | Action take and will review in PR1 Close Meeting. | NPI | 2021-03-10 16:00:00.0000000 +00:00 |  | 0
2 | OEM Auto | TXTW22_Drive+3.0 (Taroko)-9 DA | GMLA #2 | 2022-03-20 17:46:41.0709626 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 10 test items retry rate more than 5%. HT_C/No GPS_16; FT_GPS_ANT_SENSE; FT_紅色R(AR-R)¦Color_Red R; FT_紅色G¦Color_Red G; FT_TPMS_UR_RX/TX Loopback (ON); FT_(2.4G) WiFi Power Level Med (channel 1); FT_紅色R(AVM-RR)¦Color_Red R; FT_Audio_USB_4G BOX TEST; FT_Audio_C/No GPS_16; FT_Audio_GLONASS_65 | PDO will optimize the tolerance and degrees of freedom of the pogo-pin fixtures. Keeping optimizing in regular meeting activity. [5/28 updated] pogo-pin optimize is not significant, will review FT/FT-audio retry in close meeting. | NPI | 2022-05-30 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | VT2 yield rate 90.45% did not meet the target(>= 95%) | Monitor in PR (1) 7.5% leakage from gluing route and close to USB side. PE will fixed the gluing fixture for better coplanarity and increased glue volume, implement in PR. (2) 2pcs leaks from USB connector & gasket > Mold modification for guide ribs. 145-03648-00 ECO#230083 (3) Modify glue volume (0.24 +- 0.2g) | NPI/ME/DE | 2021-11-18 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Assembly retry did not meet <=10% target (1) RT2 34.7%: 2.4GHz ANT Output Power (2) VT2 32.1%: 抽氣次數違反 (3) FT2 29.5%: DR SD card format (4) HT 19.4%: Temperature (5) FT1 17.1%: 電池電壓檢查¦Battery Voltage Accuracy (6) ST 13.7%: 1K Hz Mic Amp Diff | Monitor in PR (1) RT2 34.7%: 2.4GHz ANT Output Power > EE will validate the environment influence to ANT power and implement below actions (a.) FT fixture with antenna need to be modified (b.) Test inside a small shielding chamber. Also, PR will introduce a test with calibration feature that the test value should be the difference/variance with golden sample instead of an absolute power value. (2) VT2 32.1%: evacuation exceed > Most of the high retries focused in port2. PDO will help to check the stability of VT port2 rack. (3) FT2 29.5%: DR SD card format > The failure is related to the "garminexec.ash" file which we put into units on purpose in order to track the BI shut down issue. Since we already aware of the shut down relates to high temp. the file will not be implemented in PR anymore. 40C BI temperature will be implement in PR. | NPI | 2021-11-11 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% but with action plan SMT : ATE ASSY : CT、HT、RT1、RT2、FT2 | After Action take, the retry rate%: RT_ESN:4.6 / CT:4.6 /HT:.2.7/ RT1: 0.3 / RT2:6.2 / FT1:0.8 / FT2 / 29.3 | NPI | 2021-03-18 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Yield rate did not meet target (ILP failed ~6%, VT failed ~18%, M sensor failed ~10%, GPS failed 3%). But have improvement plan | RTESN 95.49%, Solar 89.45%, airtight 59.59%, CT 57.61%, 56.08%, VT 50.66%, FT1 42.55%, Gsensor 34.87%, Gyro 29.89%, compass 27.55%, FT2 18.32% , Retry rate of PR1 build are lower than FFP, will keep introduce actions in PR2 build. | NPI | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | PR critical issues have action plan but haven't verified yet | PR critical issue is screw between front case and Bezel retreated after burn in, we will glue fastened screw and verify VT in PR2 (~5/5) | NPI | 2021-05-30 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-8 | FFP final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 95% | Yield loss>5%: 1. ILP fail rate FFP1 15%, FFP2 0% 2. VT fail rate 15% | ILP [Closed] 1. Spec been updated. 2. Assembly optimization - Tape (Glass + spacer): Optimize pressing fixture - Glue (Fersnel lens + spacer): double injection - Glue (around PCB): Change glue area to avoid getting inside. Verify on Austin FFP 3. Testing fixture alignment: outsourcing, in-house fixtures should be aligned and be improved to avoid over constrain 4. Time/ temperature impact: Check FFP ELOT TST results [0319 update] No ILP related fail in Austin FFP. VT: 1. Gap between Bezel & housing (~10%): - Bezel dimension from 1 supplier: Modified Tool and 100% inspection in PR - Main sealing torque/fixture under adjustment. - Mis-judgement: VT parameter under adjustment 2. Button (~3%): Gasket damage during assembly. Will modify housing chamfer. 3. Charging pin (~1%) Implement gasket AOI checking in PR build and monitor yield rate. [0319 update] Austin FFP VT fail rate 5%. Root cause is under analysis. Charging pin leakage (2%), Baro leakage (1%) [Update PR VT result] --> Keep monitor in GMLA3 PR VT Fail 6.7% (=54/796) # 3.8% Leak between R/C and Middle frame  Inner void which close to screw hole cause the leaking path. Action 1: Light housing has more voids inside. Part weight control will be implemented for injection QC. Action 2: Tooling modification to decrease the thickness of lug. [7/7] After verification with 33pcs VT, no middle frame inner void issue cause VT fail. Middle frame turn to rev.A. #1% Lack screw  Enhance training and plus visual inspection in SOP [6/14] New fixture arrived and verified #0.5% Lens broke  Lack of “annealing” process in CW vendor. Hold the risk buy from CW and implement small build with improved lens | NPI | 2021-04-15 16:00:00.0000000 +00:00 | 2021-07-07 13:46:39.0964540 +08:00 | 1
2 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate>10%: 1.RTESN 14.59% 2. CT 21.43% 3. FlashLight 17.83% | RTESN high retry is caused by equipment setting. Already adjust setting during FFP. CT high retry rate is caused by GPS L5. Will have L5 golden and auto chamber to reduce variance in PR. Flashlight spec is still under discussion. [PR2 result] RTESN 5.8% CT 9.1% flashlight 9.4% | NPI | 2021-04-15 16:00:00.0000000 +00:00 | 2021-07-07 14:32:38.5350361 +08:00 | 1
2 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT: (1) ATE: 19.4%_Conducted GPS Sensitivity C/No L1 2. ASSY: (1) ST: 53.76%_Mic Amp Diff. with Golden (2) FT: 48.28%_外部CN值 (3) Baro: 47.09%_0.5 ATM diff with golden (4) CT: 45%_GPS_L1 by ref (5) VT2: 44.69%_小漏氣_超過洩漏量門檻 (6) VT1: 38.59%_大漏氣_未抽至1120 (7) HT: 34.64%_機台溫度 (8) Compass: 20.79%_Headeing 90 Degree (9) RTESN: 15.47%_GPS_10_L1 (10) Gsensor: 12.29%_Diff Z/Diff Y/ Positive Y | Top 3 ASSY: (1) [Close] ST: 53.76%_Mic Amp Diff. with Golden -Root cause: The value of the golden ST sample is not in the middle of the distribution. -Action: AE KuoChih provides a new golden sample on 7/28._Done -Evidence: New golden could lead to better performance in PR, retry rate was more related to the set up of ST, will add instruction in SOP. (2) [Close] FT: 48.28%_外部CN值 -Root cause: The testing fixture didn't supply power and caused the USB disconnection. - Action: Build code in fixture's iATE board to keep supplying power during FT. - Evidence: Already finished during FFP. (3) [Close] Baro: 47.09%_0.5 ATM diff with golden -Root cause: Designed Baro meter IC requires specific stable time after SMT (1~2 wks roughly). -Action: Discussed with Olathe and confirmed spec will be loosen from 150 to 300 pa as other products using this IC. -Evidence: No high retry in PR after adjusted spec | EE | 2021-10-21 16:00:00.0000000 +00:00 | 2021-10-28 11:41:12.9261555 +08:00 | 1
2 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | 1. No LCM front case SOP (working instruction) 2. ASSY SOP need to be updated because process flow is different with flow chart | NPI PE will update SOP on 9/15 | NPI | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-27 19:12:50.2171397 +08:00 | 1
2 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE MB 19.08%: Iridium Tx CH01 Golden ASSY 1. VT1 36.49%: 大漏氣_未抽至1120 2. CT 54.11%: Battery temperature 3. HT 17.24%: Battery temperature 4. VT2 51.72%: 大漏氣_未抽至1120 5. Gyro 17.01%: Gyro Data X軸檢查 (CCW #1) 6. Baro 19.73%: Pump to 0.5 ATM 7. ST 27.21%: MIC MAX Amp. (USB) 8. G Sensor 16.55%: Diff Z 9. FT 61.38%: USB PwrOn Cur. 10. FT_Iridium 21.38%: Iridium Tx CH01 by Ref | The TOP3 items are at FT/ CT/ VT1. FT: Change spec and modify testing sequence, and will define calibration procedure to OPs. OLA fixed the SW. CT: Analysis: PCBA couldn’t be PRNP due to CPU problem. Action: SE fix SW. VT1/VT2: Analysis: Unstable of air pressure when VT ongoing. Action: PE will define the air flow in SOP and inspection at the beginning of every jobs | NPI | 2021-10-19 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GMR Fantom 18x/24x | GMLA #3 | 2021-09-14 17:04:45.4560292 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 1. White sku: All complete 2. Black sku: 18x: 7 items are not complete (total 17) 24x: 6 items are not complete (total 19) | All Elot pass. | TWN Lab | 2021-09-23 16:00:00.0000000 +00:00 | 2021-09-24 10:51:04.3257823 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #3 | 2021-09-14 17:04:45.4560292 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 1. 012-04163-00 MB: 330-01933-10 & 816-D7012-01 no max temp definition in Agile on the same components which are found in GMLA 2. 2. 012-04188-00 Processor board: 330-01933-00 no max temp definition in Agile on the same component which is found in GMLA 2. | Olathe EE has provided the max temperature for 330-01933-10/00 & 816-D7012-01 | NPI | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-16 08:57:30.8386453 +08:00 | 1
2 | Marine | GMR Fantom 18x/24x | GMLA #3 | 2021-09-14 17:04:45.4560292 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT_White (1) RFIF_Sumi 59.15%: Pulse Width cfg 16 (2) ATE 22.54%: A12003 2. SMT_Black (1) RFIF_Sumi 42.5%: Pulse Width cfg 14 (2) ATE 22.5%: Turn On Current 3. ASSY_White (1) CT 55.56%: Pulse Width cfg 18(CH4) (2) VT2 20.45%: 小漏氣_超過洩漏量門檻 4. ASSY_Black (1) VT2 25%: 小漏氣_超過洩漏量門檻 (2) FT_00 37.5%: RF board Temperature | 1. SMT (1) RFIF_Sumi 59.15%: Pulse Width cfg 16 Cause by RF board slightly deformed after reflow. No retry after adjust the ATE fixture pressing force. (2) ATE 22.54%: A12003: OLA had modified MPS SPEC, all units passed the test after modified. - resolved 2. ASSY (1) CT 55.56%: Pulse Width cfg 18(CH4) Low failed rate at CT, already solved the issue by ECO#227965. (2) VT2 25%: 小漏氣_超過洩漏量門檻 Cause by OP incorrect operation (3) FT_00 37.5%: RF board Temperature The temperature of the machine is too high cause after BI. Change the SOP: Conduct FT after 30 minutes from BI. | NPI | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-16 08:57:50.0889883 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #3 | 2021-09-14 17:04:45.4560292 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | SMT 1. A14000 & A14000 (high voltage) ASSY 1. HT_Sensitivity cfg 20 2. FT_Amplitude cfg 14 | 1. SMT (1)A14000 & A14000( high volyage) Cpk value just for reference due to strict upper and lower limitations. 2.ASSY (1) HT_Sensitivity cfg 20 The Cpk value is already bigger than 1.33. (2) FT_Amplitude cfg 14 As this item has no lower limit, the Cpk value is just for reference. | NPI | 2021-09-16 16:00:00.0000000 +00:00 | 2021-09-17 14:02:10.8132286 +08:00 | 1
1 | Marine | GMR Fantom 18x/24x | GMLA #3 | 2021-09-14 17:04:45.4560292 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME FA rate cannot reach the target 100%. Now, it's 97%. 4 items are not complete 1. 145-01804-01 2. 145-01804-11 3. 145-04018-00 4. 320-01038-03 | 1. 145-01804-01 - Done 2. 145-01804-11 - Done 3. 145-04018-00 - Done 4. 320-01038-03 - Done | MFG ME | 2021-10-07 16:00:00.0000000 +00:00 | 2021-10-08 14:44:55.7519834 +08:00 | 1
1 | Outdoor | Instinct Hybrid Analog/Digital(Ripley) | GMLA #1 | 2021-11-08 18:33:22.1539934 +08:00 | Process validation | 1.D-1 | Strain Gauge request input (at least de-panel process & screwing process, WQ000211) | SMT: Since router software and fixture are unfinished, in Strain Gauge input would be provided on next build. ASSY: Pending. | PE has input the stain gauge | NPI | 2021-11-08 16:00:00.0000000 +00:00 | 2021-11-09 14:30:35.7652541 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #3 | 2022-03-03 16:51:20.9293336 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 4 items are testing and 11 items are waiting for test | Same as 5" | TWN Lab |  | 2022-04-01 13:21:28.0970188 +08:00 | 1
2 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #3 | 2022-03-03 16:51:20.9293336 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 18.83%: V3P0ON (UNIT on) ASSY 1. VT1 15.70%: Leakage 2. CT 15.52%: 77K TX Frequency 3. HT 10.34%: 77K TX Frequency 4. FT1 25.86%: Burn-in Run time 5. VT2 36.78%: Leakage 6. FT2 22.41%: Wifi Power CH1 | Same as 5" | NPI |  |  | 0
2 | Outdoor | Delta Simple | GMLA #2 | 2021-12-02 17:27:57.0174302 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004- MPS -- Target: ≧ 90% | Need Designer help to ECO the MPS(004-01063-00) for Tx current before Pilot Run. Still need more data from the small build to set the Tx power specification and update the specification on MPS. | Small Build has confirmed that the Performance has met the TX specification after fine-tune the Antenna. Double-Verified in PR Build. ECO#238071 released | MFG EE | 2022-01-06 16:00:00.0000000 +00:00 | 2022-02-17 09:01:50.7230833 +08:00 | 1
2 | Outdoor | Delta Simple | GMLA #2 | 2021-12-02 17:27:57.0174302 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Assy retry rate not meet the target (<10%) (1) HT 17.27%: 旋鈕測試Stim Dial (2) FT 12.73%: Calibration Status | [Monitor in PR] HT Stim dial --> after verified in small build, there is no fail SMP been found. As conclusion, we set it as handling issue in FFP, PE will define more specific handling process and method in SOP. FT1 Calibration sratus --> Suspect USB wasn't plugged firmly cause high retry in certain time zone. Keep monitoring in PR. | NPI/ME/DE | 2022-02-17 16:00:00.0000000 +00:00 | 2022-03-03 13:58:14.0362315 +08:00 | 1
2 | Outdoor | Approach G12 | GMLA #2 | 2020-12-25 09:13:44.4670000 +00:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | The retry rate did not meet the 10% target >>ATE: 27.94% >>FT: 31.54% | Additional cycle test 100 times with PR SW shows fail 1/100 . High retry in ATE  verify 100  Keypad DOWN 6.9%, All fail units are distributed in the same fixture. Action: Replace this probe/line/iATE with the new one and make sure the stability by cycle test before releasing to the mass production.  Check PID 5.9%, PID setting error (testing set the APAC version) when transferring to the automatic ATE test by using 012-GPN. Action: It could be solved after fixing by Testing.  VEXT Charge Current (Universal USB) 3%, Fail value 0 and occurred at the same port. Action: Ask AE to review the probe/line/iATE and use cycle test to make sure the stability. Update PR ATE result: Total Retry 4.6%, 1st YR 95.4% | NPI |  | 2021-02-06 13:49:21.9604849 +08:00 | 1
2 | Outdoor | fenix 7S | GMLA #2 | 2020-12-28 06:54:32.4700000 +00:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | Can't find testing coverage file in PID check list | updated on 1/8 on PR web , 4/26 check test coverage = 100% | MFG EE | 2021-01-07 16:00:00.0000000 +00:00 | 2021-04-26 16:25:31.0302363 +08:00 | 1
2 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | There are two high risk issue: 1. FFP1 VT2 9.85% 2. ILP test 15.1% Both issue are with action. | ILP [Closed ] 1. Spec been updated 2. Assembly optimization - Tape (Glass + spacer): Optimize pressing fixture - Glue (Fersnel lens + spacer): double injection - Glue (around PCB): Change glue area to avoid getting inside. Verify on Austin FFP 3. Testing fixture alignment: outsourcing, in-house fixtures should be aligned and be improved to avoid over constrain 4. Time/ temperature impact: Check FFP ELOT TST results VT: 1. Gap between Bezel & housing (~10%): -bezel dimension from 1 supplier: Modified Tool and 100% inspection in PR -Main sealing torque/fixture under adjustment. - mis-judgement: VT parameter under adjustment 2. Button (~3%): Gasket damage during assembly. Will modify housing chamfer. 3. Charging pin (~1%) Implement gasket AOI checking in PR build and monitor yield rate [Update PR VT result] --> Keep monitor in GMLA3 PR VT Fail 6.7% (=54/796) # 3.8% Leak between R/C and Middle frame  Inner void which close to screw hole cause the leaking path. Action 1: Light housing has more voids inside. Part weight control will be implemented for injection QC. Action 2: Tooling modification to decrease the thickness of lug. [7/7] After verification with 33pcs VT, no middle frame inner void issue cause VT fail. Middle frame turn to rev.A. #1% Lack screw  Enhance training and plus visual inspection in SOP [6/14] New fixture arrived and verified #0.5% Lens broke  Lack of “annealing” process in CW vendor. Hold the risk buy from CW and implement small build with improved lens | NPI | 2021-04-18 16:00:00.0000000 +00:00 | 2021-07-07 13:47:46.1188215 +08:00 | 1
2 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% Top1. AutoCT(75.28%) Top2. RTESN (42.98%)Top3. AutoHT(39.45%) | CT CN Retry: 1.4% / FT: 8.27% HT 5.28% | NPI |  | 2022-03-30 15:54:47.3135473 +08:00 | 1
1 | Outdoor | Instinct Hybrid Analog/Digital(Ripley) | GMLA #1 | 2021-11-08 18:33:22.1539934 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | SMT: Since router software and fixture are unfinished, in Strain Gauge input would be provided on next build. ASSY: Pending. | Strain Gage test will be performed after FFP close. | PQE | 2022-05-30 16:00:00.0000000 +00:00 |  | 0
1 | Marine | ECHOMAP UHD2 (Touch) 7" | GMLA #1 | 2021-12-13 17:05:12.3412286 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 1. 105-04368-00 & 105-04403-00: Wait for NPI to provide the router fixture 2. 105-04267-00: ASSY screw is ongoing | 1. Will verify the strain gauge when tooling is ready. (Plan to measure on FFP) 2. After PQE assessment there are no parts to be verified on 105-04267-00, so no testing is required. | PQE |  |  | 0
2 | Outdoor | Descent G1 | GMLA #2 | 2021-06-29 16:44:14.7262153 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 34.68% - Low Power Mode Current (AVR) ASSY 1. CT 13.77% - Depth Pressure 2. HT 15.46% - Humidity Value 3. Airtight 15.69% - 連續斜率異常_負壓 4. FT1 11.46% - Charging Status 5. FT2 23.75% - ANTCW TX(CW BOX) CH57 6. Compass 13.95% - Check Unit Roll on 0 degree 7. Dive 15.94% - Level11壓差 | 1. ATE 34.68% - Low Power Mode Current > current out of USL (0.35mA) Root cause : The current resolution power supply observed is low (0.1mA) Action plan : Introduce iATE which resolution is (0.01mA) Validation : Plan to implement by 9/E. 2. FT2 23.75% - ANTCW TX(CW BOX) CH57 > test result out of spec root cause : current spec can't cover assembly variance Action : Loose current spec from (-27~ -14) to MPS spec (-33 ~ -10) Validation : All NG units passed while applying MPS spec. Updated test spec in 7/26. 3. Dive 15.94% - Depth sensor can't output correct pressure difference in 1.3 bar after dive test. Root cause : raw material issue (Nozzle crack pads on chips) Action : replace dive sensor with new batch | MFG EE | 2021-08-11 16:00:00.0000000 +00:00 | 2021-08-10 11:18:45.4606347 +08:00 | 1
3 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | The test coverage rate is 76% with 004_001 version. Some items and spec. needs to be modified before MP. | RevA SW released on 2/18. Test station is under finalization, checkpoint will be 2/25 | MFG EE | 2022-02-24 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Product Package Drop (2/2)_Mic deformed, carton damaged. ME Aries provided a new designed box to retest. 2. Electrostatic Discharge (ESD) Immunity test (2/2)_MEE discuss with OLA EE to check the charging status. Lab will test it again by CLA charging. | 1. Package drop/transportation fail issue. (2/18 closed) Action: - #1 Add protection foam as a damper but would add additional cost - #2 Change method to bending mic boom along headband direction as competitors. Try 2 type insert on 2/17. Evidence: -OLA agree to one of #2 on 2/18 but will keep monitoring improvement with running change. -Track 174-00541-00 and 171-01672-00 modified. -171-01672-00: ECO#237864 on 2/22. -174-00541-00: ECO#238229 on 2/23. 2. ESD (2/16 Closed) Root cause: -V6 PCB failed at ESD with charging cable Action: -Resistance was modified to one with a higher voltage value. Evidence: -Completed TPR-20220209018 for replacing ESD parts on MB. The ESD result on 2/15 is Class C and judged as pass. ECO#237950 was released on 2/17. | TWN Lab | 2022-02-17 16:00:00.0000000 +00:00 | 2022-02-23 10:10:07.3845402 +08:00 | 1
2 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | Gap: Trim ring gap is under discussion. | Trim ring assembly issue. Verification of sample with all solutions will be available on 2/18 (2/21 closed) Action: - Modified part has a smaller gap - Checked baking and UV parameters on 2/11, reported OK. - Add 5 tapes can improve the gap issue Evidence: -2/18 TST pass. OLA gets the package and agree to close this issue on 2/21. ->Pre-MP will do ELOT mechanical vibration check. | MFG ME | 2022-03-17 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-7 | PR UPH/Capacity review -- UPH/ Capacity meet the latest forecast -- (AOEM) Capacity flexibility and maximum capacity review -- (AOEM) Production line extend evaluation | UPH in PR2 cannot meet MP demands due to insufficient equipment. The second set of ST and ANC will be ready by 3/17. Initial MP UPH and weekly demands will be adjusted accordingly. | Test equipment was pulled-in to 3/7 and could meet MP date, keep tracking. | NPI | 2022-02-28 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Yield rate < 97%: 1. ATE (95.52%)_BT 低頻測試¦BT CW Low 2. HingeMain (93.62%)_RD MR20200 | 1. ATE: Total of 5 pcs failed at BT CW and were determined as I400 failure. No update from vendor yet. -EE Bryant 2. HingeMain: Will adjust spec after receiving broken torque measurement. - MME Angus | NPI | 2022-02-20 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%: ※dezl headset (-00) 1. SoundCheck (31.91%)_critical ALL RESULT 3.5 2. HingeMain (25.53%)_Group 5 Test Result Pass/Fail (RD MR20200) 3. ANC_FT (24.47%)_[ANST][AUTOIT] GET RESULT ANC LEFT 4. HeadSet_IN (14.89%)_RD MR20112 ※dezl headset mono (-10) 1. SoundCheck (50%)_Get('Result.Margin', '1k-SPL R') 2. SliderVice (32.35%)_Peak Result Pass / Fail(RD MR20111) 3. RTESN (32.35%)_TALK Mic loop back test mono 4. FT2(F) (17.65%)_FBR Mic Amplitudet mono 5. SliderMain (14.71%)_Peak Result Pass / Fail(RD MR20111) | Retry > 10% Top 3: ※dezl headset (-00) 1. SoundCheck (31.91%)_critical ALL RESULT 3.5 Root cause: ‧3.5mm cable isn't fixed well. It will pass the test after retest. NPI found there is some contact issue of the cable. Action: ‧OLA remove the 3.5mm test of ST. 3.5mm test items will be moved to FT2. Evidence: ‧2/14 FT2 test box and program are ready and verified by NPI. There is no 3.5mm cable contact issue. 2. HingeMain (25.53%)_Group 5 Test Result Pass/Fail (RD MR20200) ‧Same as yield < 97% item 2 3. ANC_FT (24.47%)_[ANST][AUTOIT] GET RESULT ANC LEFT Failure description: ‧Peak at 300Hz Root cause: ‧Still under analysis. NPI provided all the ESN of TW units to the acoustic engineer to do the ANC cycle test on 2/9._@KuoChich ※dezl headset mono (-10) 1. SoundCheck (50%)_MemoryList.Get('Result', 'THD R margin [Ear Sim R]') Failure description: ‧THD has abnormal peaks Root cause: ‧ 2/7 run 100 cycle test without abnormal issue ‧ 2/9 add ITMXP fail retry ‧ Still under analysis by acoustic engineer @KuoChih. 2. SliderVice (32.35%)_Peak Result Pass / Fail(RD MR20111) Failure description: ‧Peak is almost out of spec. Root cause: ‧It is the first time to collect mass data at PR build. The maximum is near to the upper spec which causes high retry. Action: ‧ME Angus will adjust the spec. 3. RTESN (32.35%)_TALK Mic loop back test mono Root cause: ‧ Big noise of the environment. Action: ‧Still wait for acoustic engineer's analysis. | NPI | 2022-02-20 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33: ※Mechanical item: 1. Hinge main 2. Slider main/vice 3. Headset Clamping ※FT1_Power Box Sampling (Avg_Avg) ANC電流 ※ST_MIC Sensitivity | Cpk < 1.33: ※Mechanical item: @Angus 1. Hinge main -ME will check the broken torque whether loosen the torque or not. 2. Slider main/vice -ME is still discussing with OLA to check whether add the tape or not. The spec. might change after the design change. 3. Headset Clamping -ME will test the new sample of the headband on 2/8 and check the spec. ※FT1_Power Box Sampling (Avg_Avg) ANC電流 @Bryant -The USL and LSL will be adjusted. ※ST_MIC Sensitivity -The USL and LSL will be adjusted to -15.5~-26dB. | NPI | 2022-02-24 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ASSY/ Testing/ Packing/ LCM) -- Measurement position and result | The new force fixture is not ready yet. | Hinge/ Slider/ Clamping force test equipment is expected to be released on 2/22. PQE will measure the new equipment when the fixture is released. -2/22 test the new fixture pass. | PQE | 2022-02-21 16:00:00.0000000 +00:00 | 2022-02-22 11:18:01.5738315 +08:00 | 1
3 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Process validation | 3.D-13 | Review PR issue in PRWeb (MP block issue) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | 1. Package drop/transportation fail issue. 2. Trim ring assembly issue. | 1. Package drop/transportation fail issue. (2/18 closed) Action: - #1 Add protection foam as a damper but would add additional cost - #2 Change method to bending mic boom along headband direction as competitors. Try 2 type insert on 2/17. Evidence: -OLA agree to one of #2 on 2/18 but will keep monitoring improvement with running change. -Track 174-00541-00 and 171-01672-00 modified. -171-01672-00: ECO#237864 on 2/22. -174-00541-00: ECO#238229 on 2/23. 2. Trim ring assembly issue. Verification of sample with all solutions will be available on 2/18 (2/21 closed) Action: - Modified part has a smaller gap - Checked baking and UV parameters on 2/11, reported OK. - Add 5 tapes can improve the gap issue Evidence: - 2/18 TST pass. OLA gets the package and agree to close this issue on 2/21. ->Pre-MP will do ELOT mechanical vibration check. | NPI | 2022-02-17 16:00:00.0000000 +00:00 | 2022-02-23 10:11:08.1261697 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | FA rate: ME 29%. 101 items without VIP. (check by 1/25) | FA rate: ME 42%, deadline is 3/4 (checked on 2/14) | MFG ME | 2022-03-03 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | Parts with design change after PR need to be further monitored. 1. Headband 2. Trim Ring 3. Packing box | 1. Headband: New tooled parts was measured and judged pass on 1/28 (closed) 2. Trim ring assembly issue. Verification of sample with all solutions will be available on 2/18 (2/21 closed) Action: - Modified part has a smaller gap - Checked baking and UV parameters on 2/11, reported OK. - Add 5 tapes can improve the gap issue Evidence: -2/18 TST pass. OLA gets the package and agree to close this issue on 2/21. ->Pre-MP will do ELOT mechanical vibration check. 3. Packing box (Design fixed on 2/18): Action: - #1 Add protection foam as a damper but would add additional cost - #2 Change method to bending mic boom along headband direction as competitors. Evidence: -OLA agree to one of #2 on 2/18 but will keep monitoring improvement with running change. -Track 174-00541-00 and 171-01672-00 modified. -171-01672-00: ECO#237864 on 2/22. -174-00541-00: ECO#238229 on 2/23. | PID | 2022-02-17 16:00:00.0000000 +00:00 | 2022-02-23 10:11:36.7551985 +08:00 | 1
2 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate: ME 29% (check by 1/25) | FA rate: ME 42%, deadline is 3/4 (checked on 2/14) | MFG ME | 2022-03-03 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Supply chain/ supply of part | 3.E-12 | Raw material quality issue from supplier | 310-00179-20 appeared pin disengagement. 1. 100% fixture check on vendor side 2. Review vendor fixture to ensure no snap exist It should be kept tracking. | Root cause: -Wire is too short. -Supplier's process problem. Action: 1. Design: Modify wire length 2. Supplier: -Modified test fixture to prevent hooking the cable during removing DUT from the test fixture. -Change the process procedure. Cut the cable before pressing the cable into the connector. -100% inspected before shipping. - First and last article pulling inspection. - Detach force for the connector will be updated by the supplier. The actions will be verified in Pre-MP | MFG ME | 2022-03-10 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ATE: Retry <10% Testing: FT2=13.3% FT3=21.3% Recheck=18.84% | 1. Mapping Laser (15.94) – Laser wasn’t adjusted into spec, need manual adjustment. 2. HUD backlight_Green current: PE suggested to keep this item with a wider test range. If TWN EE remove this test item, new inspection method should be defined. 3. ButtonOK: Fail value is -999, passed on different port. Could be caused by cables., will change cables first in the next build. PR update 1.SMT retry rate all meet the target <10% 2.ASSY retry rate >10% (1) Torque_Elevation 89.66%: (R)Current Torque (2) VT2 33.04%:小漏氣_超過洩漏量門檻 (3) FT 29.41%: ALS Luminance (WLED ON/After Calibration) | NPI | 2021-03-18 16:00:00.0000000 +00:00 | 2021-08-06 22:47:15.7409109 +08:00 | 1
1 | Outdoor | Xero A1i PRO Bow Sight | GMLA #3 | 2021-07-15 11:33:41.4660021 +08:00 | Process development | 3.C-13 | BOM structure review (if any part needs to be added or changed after build) -- Lost parts/ wrong level/ wrong qty -- Include auxiliary material (副料) | 171-01418-04/14 was wrong and missed in BOM. New part was designed and ETA is TBC. | Packing parts for pic sku will arrive on 7/23, ELOT result will be updated by 7/30. [Update_0806] Completed and passed on 7/22 | NPI | 2021-07-29 16:00:00.0000000 +00:00 | 2021-08-26 14:53:31.9369219 +08:00 | 1
3 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | TST / Tumble are NG | [04-28] Waive and have the MP approval start 1. FT2 failed after TST :known Gen4 issue that FSP/ILP related SPECs are being evaluated.checked that this pcs is limit sample and Biosensor team's working with design team to loosen the spec. 2. VT_5 atm failed after Vibration and ME is under analysis 3. 1 unit can't turn on after tumble 10 cycles due to pSRAM issue and already solve it 4. Bad GPS signal for Operating Hot/Cold Unit Performance、Storage Hot/Cold Unit Performance、TST、Temperature and Humidity Cycle Test. 、Tumble 、Mechanical Vibrationand and tracking by Asia build and Pre MP build | TWN Lab |  | 2022-04-28 09:28:58.9558027 +08:00 | 1
1 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | Need to provide report for verification. |  | PDO/AE |  |  | 0
2 | Outdoor | Instinct 2S | GMLA #2 | 2021-05-12 14:49:06.6247015 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | Test coverage is 89% (73/82) | @Chen, Kevin complete the test coverage>90% by 5/27 | MFG EE | 2021-05-30 16:00:00.0000000 +00:00 | 2021-05-31 09:07:11.9559332 +08:00 | 1
2 | Outdoor | Instinct 2S | GMLA #2 | 2021-05-12 14:49:06.6247015 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Multiupdater 12.84%(MultiUpdater USB Update), ATE 24.97%(VBAT current), HT 12.44%(GlONASS 78 CNo by ref.), ProdScan 13.44(Check Battery Voltage), RTESN 10.2% (Antenna Self-Test Tx Current), Gyro 14.8%(Check Airtight Test Data), RT1 18.39%(GlONASS 65 CNo by ref.), Solar 23.3%(Calculated Power) | Retry with actions: ATE 24.97%(VBAT current) – ongoing RTESN 10.2% (Antenna Self-Test Tx Current) – Tracking HT 12.44%(GlONASS 78 CNo by ref.) – Resolved RT1 18.39%(GlONASS 65 CNo by ref.) – Tracking Solar 23.3%(Calculated Power) – Resolved Gyro 14.8%(Check Airtight Test Data) – Resolved ProdScan 13.44(Check Battery Voltage) – ongoing ATE: Fixture& test program misjudged, AE/EE continue to finetune before PR @Chen, Kevin @Tsai, Eason RTESN: EE will adjusted WW/Asia skus separately after the software released to avoid retry% @Chen, Kevin RT1: GPS antenna design lockdown & verified pass, tracking the PR result. ProdScan: will adding the charging station and re-calculate the charging time @Chen, Eason Will verify in PR by 6/30 | NPI | 2021-06-29 16:00:00.0000000 +00:00 | 2021-07-20 09:04:35.2765898 +08:00 | 1
2 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Process validation | 2.D-8 | FFP final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 95% | SMT ATE: 93.75% | 1. Auto Power-On Crnt 32V: raw material issue, part is not within the spec. Besides to control vendor quality, will adjust resistor range to avoid this issue. 2. VBATT_LIM: Part has short problem. Cannot replicate this issue after replacing component. Haven’t found issue thru cycle test. Keep tracking in PR. Update: Reached FYR 99.95% in first MP. | MFG EE | 2021-05-13 16:00:00.0000000 +00:00 | 2021-06-24 23:15:41.9847923 +08:00 | 1
2 | Marine | FUSION - AP-DA214 (Zone Amplifier) | GMLA #2 | 2021-04-13 15:01:41.9158928 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT ATE 10.42% / 2. ASSY HT 42.86% / FT 76.19% | SMT 1. Auto Power-On Crnt 28.8V: Will adjust MPS specification. ASSY: Mostly contributed by connection issue. 1. Short term: relax THD+N spec in FT 2. Long term: Verified reworked cable can improve audio connection. Will add dummy terminals with wires in FT jig cable and verify it in PR. Upaate: improved in PR and MP | MFG ME | 2021-05-13 16:00:00.0000000 +00:00 | 2021-06-24 23:16:08.2550314 +08:00 | 1
2 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | 1. VT still has ~5% fail rate 2. false touch issue to be resolved by PR | - Charging pin VT issue: Gasket molding defects lead to charging pin VT fail (fail rate: 2.1%). Have implemented AOI for gaskets and use thicker charging pins to verify on F7 series PR build. F7s PR completed and no charging pin VT issue was found. SOP updated by 2/26. - Barometer VT fail: barometer VT fail (fail rate: 0.9%) is due to dust / fiber on O-ring. Will modify O-ring assembly process from 011-05275-5x to 011-05275-3x to reduce air exposure time. SOP updated. - For the leak from main gasket and rear gasket, found dust/fiber. Clean and re-assemble then tested OK. - False touch issue: SW updated and verified OK in FFP2, close. | MFG ME/DE | 2021-05-20 16:00:00.0000000 +00:00 | 2021-06-23 18:03:38.7835464 +08:00 | 1
3 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | T sharp FPC sku was achieved 100% L bend FPC sku was estimated 80% The array testing fixture wasn’t ready to adopt in the PR build phase. | ATE2 testing fixture will be ready by 4/29 | MFG EE | 2022-04-28 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | FYR < 97% : FT_R/C (95.26%)、 CT (96.21%)、HT(93.45%)、RT1(96.51%)、FT1(88.41%) due to Antenna issue | 1. CT / HT / RT1 failed issues are GPS items, will add spacer and verify at Asia PR build. 2. FT_R/C is ILP alignment issue ,will add AOI inspection after Lens bonding to R/C station (Done) [04/27] Latest Update Fail rate: CT 1.21% (18/1493), HT 0.78% (11/1415) Potential Cause: incorrect SPEC (EE provide the new golden with production line, but do not modify the SPEC) Action: EE modified the SPEC and have the production line to retest all the units (that using incorrect SPEC to do the test). We will keep tracking the actual fail rate. | NPI |  | 2022-04-27 14:29:39.8101489 +08:00 | 1
2 | OEM Auto | IXWW22 | GMLA #2 | 2021-12-20 18:48:32.4156611 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Unit temperature retry, caused by HT oven speed and temperature setting on-going. FT BT level test item retry. | PE will tune the oven speed setting, verify in 2022/Jan PR build. | NPI | 2022-01-20 16:00:00.0000000 +00:00 |  | 0
2 | OEM Auto | IXWW22 | GMLA #2 | 2021-12-20 18:48:32.4156611 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Unit temperature retry, caused by HT oven speed and temperature setting on-going. FT BT level test item retry. | EE send the calibrated golden sample on 12/23, verify in 2022/Jan PR build. PR-1/PR-2 BT verification are still fail, issue not solven. Keeps open. | MFG EE | 2022-03-03 16:00:00.0000000 +00:00 |  | 0
2 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | FT2 89.62%: Target Max 2 | Same as retry rate item | NPI | 2022-04-24 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process development | 2.C-5 | Release preliminary working instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | SMT preliminary working instruction is not released | SMT SOP of FFP have been updated on 5/4 in attached | NPI | 2021-05-03 16:00:00.0000000 +00:00 | 2021-05-19 15:06:32.4983193 +08:00 | 1
2 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate >= 10 % but with improvement plan 1. SMT : ATE(12.74%) 2. ASSY : (1) RTESN(13.53%) (2) RT1(12.3%) (3) RT2_ALS(58.23%) - 開機電流 (4) FT2_ALS(35.42%) - (Discharge)電池電壓¦(Discharge)Battery Voltage (5) Airtight_table(10.48%) (6) FT1(16.15%) (7) 24hBefore(51.74%) - Hour Angle (0) diff (8) 24hAfter(33.2%) (9) FT4(12.9%) | ASY : [Monitor in PR result] (1) RT2_ALS(58.23%) - 開機電流 Root Cause : Boot current 10.9% Action: The upper spec will be modified from 115 to 117 mA [Solved] (2) 24hBefore(51.74%) - Hour Angle (0) diff Root Cause : SW cause hands can not back to default 19:30 after 24 hr. Action: Plan to verify 20 pcs with latest SW to retest 24 hrs. Validation: 20 pcs units back to default 19:30 after new SW. [Monitor in PR] (3) FT2_ALS(35.42%) - (Discharge)Battery Voltage Root Cause : The low power mode have not been justified well in FFP build which cause batt voltage drop quickly. Action : Modify Low power mode in next build and implement charging station after RTESN & before 24 hrs. | NPI | 2021-08-29 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Red light issue*2 : 1. gearbox-related issue (8%) 2. High retest rate at 24 Hr ( after ) testing station. (33.2%) | 1. Gearbox (370-00043-00)–related issue (1) Pad / Ground short (3.1%) Provide Testing Fixture to inspect Gearbox on next build (5/17) (2) Coil resistance abnormal (1.9%) (3) Rotation abnormal (1.9%) (4) Warpage (1.2%) 2. High retest rate at 24 Hr ( after ) testing station Modify SW to drive watch hand running abnormal issue and will execute on 5/E [6/21] After verified in 20pcs small build, new wave form of gearbox & new screw result positive. Plan to verified in PR with large amount | NPI | 2021-05-26 16:00:00.0000000 +00:00 | 2021-06-29 17:13:27.4100012 +08:00 | 1
2 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME parts 95% 6 items are ongoing 1. 115-03929-00 2. 145-03886-00 & -10 & -50 & -51 3. 717-00196-01 | MME will complete all FA next week. 4/27: FA rate 97%. 4 items are ongoing. 1. 115-03929-00 2. 145-03886-50 3. 145-03886-51 4. 717-00196-01 Plan to finish FA by 5/6 | MFG ME | 2022-04-21 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01094-00 did not production release (still on the experiment version) | The ECO is processing, and estimated complete date was on 3/7. | MFG EE | 2022-03-07 16:00:00.0000000 +00:00 | 2022-03-07 14:07:08.2685150 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (tolerances need to be well defined in the drawing as well) | Drawing or related 015 is not released. Drawing ECO R&R discussion between Olathe ME and Tacx ME is ongoing. | As a MP transfer product, no 105 drawings were received. Will be followed-up in Olathe/TWN weekly meeting for future quality control. | MFG ME | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design, and release 174- document -- Customer/ Garmin requirement need to be included | This is MP transfer product. Packing information is defined in SOP. | SOP was uploaded in ISO system on 3/31 | MPPE | 2021-03-30 16:00:00.0000000 +00:00 | 2021-04-21 15:50:19.1967556 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- document with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | There is no 004 document in BOM. Test program is released by Tacx. Specifications are defined in the test program. | As a MP transfer product, all test program was developed by TACX so no 004 document is available. | MFG EE | 2021-04-14 16:00:00.0000000 +00:00 | 2021-04-20 20:02:27.2623233 +08:00 | 1
3 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT issue ※ Non IR SKU 1. Product Package Drop (1/1) ※ IR SKU 1. Salt Fog (1/1) 2. Product Package Drop (1/1) 3. Shipping Vibration (1/1) | (1) Salt Fog: Analysis: The failure phenomenon only occur on the IR SKU. The unit power was turned on during the test. It caused IR LED turned on and had a high temperature on the unit. Action: Waive to 144hr on the salt fog at initial MP and improve the powder coat salt fog performance as a design running change after MP. -Closed (2) Product Package Drop: Analysis: Front side: carton damaged. Action: The test item is waived with normal units after test. -Closed (3) Shipping Vibration: Analysis: Manual damaged Action: There will be a polybag to protect in MP phase. -Closed | TWN Lab | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-21 09:03:24.8267490 +08:00 | 1
1 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing. The expected complete date is 3/8 | ELOT is progressing. The complete date is 3/11. | TWN Lab | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-21 09:03:44.0019842 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-1 | Any update of critical process/ equipment/ measurement method of special characteristics -- Special characteristics flow down from drawing/ top area concern -- ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ Displacement ruler -- Check if DFM report updated and prototype report for any process/ parameter change | There is no drawing and DFM report. | Uploaded PFMEA document in GMLA attachment. | NPI | 2021-04-19 16:00:00.0000000 +00:00 | 2021-04-20 20:15:25.0479692 +08:00 | 1
2 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-2 | Review Machine/ Fixture list and ETA (need to meet build plan) -- Schedule of any modification or adjustment can meet PR build -- (New equipment) Defined operation/ maintenance SOP and official release before PR | PDO has not provided equipment operation manual yet. | Operation manual of the automatic screw machine will be provided before 4/30. | PDO | 2021-04-29 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-8 | Check traceability resolution setup -- Program setup status review | PCBA tracebility need to be recorded. | ESN wil be recorded in learning, calibration and final test station. | NPI | 2021-04-08 16:00:00.0000000 +00:00 | 2021-04-21 16:51:21.1802132 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-9 | Review IQC fixture preparation status -- Fixture readiness -- Fixture working instruction -- Spare fixture preparation -- Finalize IQC inspection VIP base on latest material version | Wait for NG product test result to check which part is abnormal and need to be measured by IQC. Already know metal frame fixture is needed. | 1. Metal frame for vibration improvement: TWN parts can improve vibration issue significantly, MME will define VIP for IQC inspection. 2. 2. 117-01574-02 dimension deviation during PR1-2: Will have VIP and IQC inspection in MP. | MFG ME | 2021-04-27 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-10 | Review FQC fixture/ test equipment preparation status -- Fixture/ equipment readiness -- Fixture/ equipment working instruction -- Spare fixture/ equipment preparation -- Added maintenance SOP of test equipment in PNPMS system | Some fixture under going: test bike, simulation tool for turning the axle. | Undergoing, will be completed by 4/29. | PQE | 2021-04-28 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | SW revision cannot be checked due to no TACX related program to read out. | Not available. | PQE | 2021-04-15 16:00:00.0000000 +00:00 | 2021-04-21 16:54:58.5349774 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-12 | OOB checklist preliminary release -- Are the new features/ quality concern included? ( Refer to owner manual or UX document) -- Accessory compatibility review (EX: phone) | The basic check items of OOB are arranged (cosmetic / packing materials/ accessory/ labels/ wings open and close/ screw status). Simulation test of bike/turning axle is undergoing. | Completed on 3/19. | PQE | 2021-03-18 16:00:00.0000000 +00:00 | 2021-04-21 09:25:29.1780142 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process development | 3.C-13 | BOM structure review if any part needs to be added or changed after build -- Lost parts/ wrong level/ wrong qty | 012-04181-00/011-05408-01/011-05415-03/011-05369-00/011-05417-01 wait for modified. Additionally, 004/006/015 should be set in BOM. | PE reviewed correctness already quantity will be checked by Kenny | NPI | 2021-04-22 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process validation | 3.D-5 | Check verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine -- Action plan if verification result fail | Completed verification, the result is as attached file. | Completed verification, the result is as attached file. | PDO/AE | 2021-05-30 16:00:00.0000000 +00:00 | 2021-04-21 09:20:45.9371103 +08:00 | 1
2 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process validation | 3.D-8 | PR final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 97% | 1. Learning: Stator and Cooling unit cable damaged during assembly. NPI defines a new way for arranging wires in SOP and makes fixtures. 2.Calibration: Vibration NG, wait for ME to clarify metal frame problem. | 1. Learning: Improved by changing wiring method which had been defined in SOP and been verified in PR1-2. 2.Calibration: Metal frame for vibration improvement: TWN parts can improve vibration issue significantly, MME will define VIP for IQC inspection before 5/15. | NPI | 2021-04-27 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Final Yield Rate(FYR) not meet the target >= 97% ※Non-IR Testing 1. CCM_W (95.96%) ※ IR Testing 1. CCM_W (92.23%) 2. HTMTF (93.57%) | CCM_W Analysis: Pollution in the camera lens. Action: DE and PE will add the inspection of the lens pollution in CR process and sort the polluted lens before jobs. -Closed HTMTF Analysis: The MTF test passed after first AA, but the MTF test failed after baking on the nearly SPEC limit sample. Action: DE is check the SPEC how to be adjusted if need with design team before Pre-MP started. -Closed | NPI | 2022-03-30 16:00:00.0000000 +00:00 | 2022-04-07 15:17:31.3136095 +08:00 | 1
3 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process validation | 3.D-13 | PR critical issue (marked by red light) action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | There are 7 PR issues. 1. Incorrect screw/Cosmetic issue/Internal cable issue will be tracked. 2. Metal frame/ Cooling unit housing are expected to be solved by MIT parts. 3. Vibration/ Bumpy issue are waiting for Tacx、EE、PTE reply. | 1. Incorrect screw: PI has added this program and will be confirmed for the next production. Cosmetic issue: Modified fixtures had been verified in PR2, no scratch was found. Internal cable issue: After modifying wiring method, this issue was fixed. 2. MIT parts had been verified and will set corresponding VIP dimension and have specific inspection fixture at supplier site. 3. Vibration: MIT parts will set corresponding VIP dimension and have specific inspection fixture at supplier site and IQC. ETA 5/15. Bumpy: Root cause: Big voltage deviation among three sets of resistances which causes unbalance of motors. Short term: Test unit of 16hz after assembly. If NG, change 0.1% resistance of the PCBA. Long term: Supplier HEAD changes 1% resistance to 0.1% resistance and uses the detection program provided by Tacx before shipping. | NPI | 2021-04-27 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | 1st PR parts are from Tacx. Inspection VIP will be passed to TW supplier before MP. | Inspection VIP will be evaluated based on PR2 result and be ready before MP. | MFG ME | 2021-05-27 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | PR 1 Tacx sent wrong 117-01568-06 with small hole opening. PR 1-2 60 units will be postponed to 4/6 due to delayed shipment of 145-03541-00 screw cap cadance sprint. | PR1-2 was postponed to 4/6 due to delayed 145-03541-00. PR2 started from 4/14. | PID | 2021-04-14 16:00:00.0000000 +00:00 | 2021-04-20 22:36:12.2206616 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | There is no Taiwan parts for 1st PR. | No action should be taken. This item will be reviewed in PR2. | MFG ME | 2021-04-14 16:00:00.0000000 +00:00 | 2021-04-20 22:35:34.3497465 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Others | 3.F-1 | Direct labor -- Training has been taken within schedule and should be completed before MP -- (AOEM) Update Training Matrix if any new training requirement from CFT/ customer -- (AOEM) The record should be updated in HR system | Will be completed by 4/1 | Completed on April 1st. | NPI/PQE | 2021-03-31 16:00:00.0000000 +00:00 | 2021-04-20 22:34:34.1473880 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Others | 3.F-2 | Indirect labor -- Training has been taken within schedule and should be completed before MP -- (AOEM) Update Training Matrix if any new training requirement from CFT/ customer -- (AOEM) The record should be updated in HR system (EE product introduction | Will be completed by 4/1 | Completed on April 1st. | NPI/PQE | 2021-03-31 16:00:00.0000000 +00:00 | 2021-04-20 22:33:50.2826214 +08:00 | 1
2 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate not meet the target <10% ※Non-IR Testing 1. VT2 (13.99%)_小漏氣_超過洩漏量門檻 2. FT (12.69%)_Turn on current 12V (for SB 10) 3. RTESN (11.56%)_Turn on current 12V 4. HTMTF (10.61%)_MTFV8-Collimator9 5. VT1 (10.45%)_小漏氣_超過洩漏量門檻 ※IR Testing 1. HTMTF (21.64%)_MTFV8-Collimator9 2. CCM_W (17.62%)_影像檢查¦Check Image 3. CT (11.22%)_Turn on current 12V (for SB 20) | TOP3 issue: ASSY: Non-IR: (1) VT2: Cable sealing fixture can't seal the fixture efficiently, the fixture is under adjustment. -Closed (2) FT: The test started before units were connected, EE had modified the ITMXP to show the alarm notification and reboot sensor board, and tracking on pre-MP build. -Tracking (3) RTESN: The failed units weren’t soldering well, PE will training operator again with SOP. -Tracking IR: (1) HTMTF: DE is check the SPEC how to be adjusted if need with design team before Pre-MP started. -Closed (2) CCM_W: Pollution in the camera lens. DE and PE will add the inspection of the lens pollution in CR process. -Closed (3) CT: Operator with improper test method result in IR LED was turned on, EE had added alarm notification in script. -Tracking | NPI | 2022-03-30 16:00:00.0000000 +00:00 | 2022-04-07 15:18:08.7301575 +08:00 | 1
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #1 | 2021-10-08 16:00:55.0658912 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04450-00 V1 de-panel failed. It will be changed to the router for the next build. The strain of routing will be tested when the fixture is ready. | 105-04450-00 router strain gauge pass on 12/16. http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04450-00 | PQE | 2021-12-15 16:00:00.0000000 +00:00 | 2022-01-06 18:03:29.7881142 +08:00 | 1
2 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | ※Assy Testing 1. FT1 60.08% 2. HTMTF 88.93% 3. RT1 91.67% | 1. FT1 60.08%: SW issue, resulting WiFi/BLE/LRE failure. 2. HTMTF 88.93%: Unit crashed during test. Could be contributed by unstable SW or test current. 3. RT1 91.67%: SW issue, resulting WiFi/BLE/LRE failure. | NPI | 2022-05-16 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10% issue ※SMT 1. ATE 39.74%: Wi-Fi Power Level Med (channel 6) ※Assy Testing 1. FT1 55.04%: Normal Battery Voltage 2. RT1 38.24%: Main LTE Band12 RX 737.5 MHz Msg (A) 3. HTMTF 29.51: Image sensor temperature 4. RTESN 24.62: LTE Module Software Version Msg 5. CT 14.18: Temperature 6. FT2 13.95: BLE LESC test¦藍芽LESC測試 7. ST 12.4: 1K Hz microphone amplitude difference | ※SMT [Closed, not occurred in FFP2]1. ATE 39.74%: Wi-Fi Power Level Med (channel 6): Could be caused by unstable SW. Had provided error log to Olathe, pending on new SW solution ※Assy Testing [Closed] 1. FT1 55.04%: Normal Battery Voltage: Units have been shipped to T2 before tested FT1. We tested FT1 several days after assembly, so the battery voltage is low 2. RT1 38.24%: Main LTE Band12 RX 737.5 MHz Msg (A): SW issue, Some units didn't show TX signal while testing FT1. 3. [Closed] HTMTF 29.51: Image sensor temperature 4. RTESN 24.62: LTE Module Software Version Msg: SW issue, It cost about 20 sec to get LTE Module Software Version Msg. Sometime, it would failed due to mis-judgement or long test time. 5. [Closed] CT 14.18: Temperature 6. FT2 13.95: BLE LESC test¦藍芽LESC測試: SW issue, unstable connection. 7. ST 12.4: 1K Hz microphone amplitude difference: Gasket was missed in assembly. | NPI | 2022-06-16 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | Xero A1i PRO Bow Sight | GMLA #2 | 2021-01-08 17:17:54.4251773 +08:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | There is 5 red light issue on PR Web: 1) Gyro test not been verified in FFP yet. 2) The feeling of windage & elevation knob is not smooth and easy to get stuck after tight the set screw. 3) The shaft curved after assembly 011-05466-00 4) Wrong dimension on 117-01599-10 5) 011-05466-00 Screw is too tight and hard to screw to the end even use large torque | Action Plan 1) Received Gyro SW and had verified fixture on 12/31, will keep track on next build. 2) MME is evaluating applying oil or POM+screw for this issue. 3) OLA & MME is discussing to adding the positive interference to solve this issue. 4) Model was updated, and already asked supplier should check the fitting before deliver 5) MME will adjust the Nylock amount on screw and cover the screwing hole during painting. Keep tracking. Action Plan 1) [Closed] Received Gyro SW and had verified fixture on 12/31, will keep track on next build. [Closed] 2) MME is evaluating applying oil or POM+screw for this issue. [4/14 Update] Olathe had design lock down on 4/9. 3) [Closed] OLA & MME added the positive interference to solve this issue. 4) [Closed] Model was updated, and already asked supplier should check the fitting before deliver 5) [Closed] Most screws have improved by adjusting Nylock amount on screw. | NPI | 2021-03-18 16:00:00.0000000 +00:00 | 2021-08-26 14:50:59.7573377 +08:00 | 1
2 | Fitness | Forerunner 255S | GMLA #2 | 2021-12-22 20:32:55.7975659 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 %: Top 1: CT = 133.33 %, Top 2: RTESN = 89.62 Top 3: RT2 / HT = 60.86 % | 1. CT/HT : low antenna contact , Will ask supplier to improve and inspect the appearance before ASSY 2. RTESN: Display FPC was tore issue,will remove display hard coat next build. 3. RT2: Modify Spec. due to different material | EE | 2021-12-27 16:00:00.0000000 +00:00 | 2021-12-27 14:35:38.7077344 +08:00 | 1
2 | Outdoor | Approach G12 | GMLA #2 | 2020-12-25 09:13:44.4670000 +00:00 | Process validation | 2.D-13 | PR critical issue (marked by red light) list action plan and resolve status review -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | There is 1 critical issue: ->Charging current can not meet the spec | - In RT1/FT1 station, 47.5% units (=58/122) cannot pass the lower spec of VEXT current (85mA) - Root cause: The charging current will be impacted by the contact resistance between housing, cable and board. - Action: Apply modified pins for PR build and compare results with FFP build. Final decision will be determined in PR review. - PR result update ＞ Improved SS charge pins showed a 20% failure rate, and gold-plated charge pins showed a 0% failure rate; BOMs updated to switch to the gold-plated charge pins for Mass Production. | NPI |  | 2021-02-06 13:49:27.7743666 +08:00 | 1
2 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process validation | 2.D-8 | FFP final yield rate (FYR) review of each test station and improvement plan -- Target of each station: ≥ 95% | Watch_ClickTest : 90.3% | Click test results are only for reference. Not a judgment method. | MFG ME | 2021-03-29 16:00:00.0000000 +00:00 | 2021-03-30 14:50:14.7882637 +08:00 | 1
2 | Outdoor | "Austin" | GMLA #2 | 2021-03-26 09:36:28.6821203 +08:00 | Process validation | 2.D-9 | FFP retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | displacement : 354.4%, CT: 54.7%, ProdScan : 41.4%, GSensor : 35.3%, Compass : 33.2%, Baro : 22.5%, FT1 : 20.1%, HT : 17.1%, FT2 : 15.8%, Gyro : 13.6% | ‧ CT: GPS_L5 retries (34.88%) are related to improper assembly of the small antennas. No GPS_L5 retry in FFP2. ‧ HT: GPS_L5 retries (7.13%) are related to the test angle in auto-chamber, will follow Fenix 7's action on GPS testing in auto chamber and validate in FFP2. Validate OK. ‧ FT2 retries are due to test equipment settings. Verified OK after modification. ‧ G-sensor X heading retries (13.92%) are suspected to be relevant with abnormal angles from test equipment. Both test program and spec are updated and validated OK. Will have test equipment fine-tuned for PR validation, keep tracking PR status. ‧ M-sensor “unit pitch on 45 degree” and “unit roll on 45 degree”: Verified PR candidate SW, which refreshes its data better than FP, so it looks good that unit can report its pitch & roll as expect. This will be further monitored in PR, but note that pitch and roll in M station is a fool proof item rather than test item so it will rely more on the unit orientation to be correct and G sensor data to be correct. Both test program and spec are updated and validated OK. Will have test equipment fine-tuned for PR validation, keep tracking PR status. ‧ Baro retries (13.47%): FFP validated PASS with new SW. ‧ VT retries are due to multiple times tests arranged in FFP. See 2.D-13 for the test results. | MFG EE | 2021-09-06 16:00:00.0000000 +00:00 |  | 0
2 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT (1) ATE 10.81%: USB 連線¦USB Connection 2. ASSY (1) RTESN 45.05%: Flash test (2) VT1 54.05%: 小漏氣_超過洩漏量門檻 (3) VT2 21.62%: 大漏氣_未抽至1120 (4) VT3 36.36%: 漏氣_測試中壓降低於1070 (5) CT 13.51%: Flash test (6) HT 40.54%: Flash test (7) G sensor 38.53%: x_acc_n | 1. SMT (1) Power supply input switch unstable, so EE fix the input sequence in time._Done 2. ASSY (1)(5)(6) SD read bug in test station, implement IOP to turn off unit before taking off SD._Done (2) VT1: The gasket are contaminated. Implement clean process in SOP and procced 100% rear case VT in OSP side._Done (3) VT2: One screw was missed in the assembly process but pass the VT1. Modify SOP to inspect the screws are assembled in VT station._Done (4) VT3: The test item will be bypass on MP._Done (7) PR version SW release on 6/25, validation is positive in cycling test._Done | NPI/EE/ME/DE | 2021-07-14 16:00:00.0000000 +00:00 | 2021-08-03 12:45:14.7269103 +08:00 | 1
2 | Automotive | Tread Audio System | GMLA #2 | 2022-01-05 16:15:40.4025766 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | Yield < 95% : 1. SMT_Amp_Audio_ATE (91.82%)_Zone1 Speaker Out L - Frequency 2. ASSY_FT (93.41%)_BT Radiated Output Power@2441MHz | 1. SMT_Amp_Audio_ATE (91.82%)_Zone1 Speaker Out L - Frequency -Root cause: ‧ Interval between command and command is too short. ‧ SMA contact issue. - Action: ‧Modified the command timing and improve the Fixture stability. -Evidence: ‧ Cycle test result is good. Keep monitoring in PR. 2. ASSY_FT (93.41%)_BT Radiated Output Power@2441MHz -Root cause: ‧ There is a latency after BT IOP sending. -Action: ‧ Modified the command timing. -Evidence: ‧ Cycling result is good. Keep monitoring in PR. | NPI |  | 2022-03-08 09:14:46.9520560 +08:00 | 1
2 | Automotive | Tread Audio System | GMLA #2 | 2022-01-05 16:15:40.4025766 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%: ※SMT 1. Amp_Audio_ATE (65.45%)_Zone1 Speaker Out L - Vrms 2. Amp_ATE (13.91%)_開機電流¦open current 3. Proc_ATE (10.92%)_V5USB ※ASSY 1. CT (11.7%)_開機電流¦open current 2. HT (15.96%)_AMP 溫度¦Temperature of amp thermistor(C) 3. FT (16.48%)_BT Radiated Output Power@2441MHz | Top 3: 1. SMT_Amp_Audio_ATE (65.45%)_Zone1 Speaker Out L - Vrms -Same as yield rate < 95% item 1. 2. FT (16.48%)_BT Radiated Output Power@2441MHz -Same as yield rate < 95% item 2. 3. HT (15.96%)_AMP 溫度¦Temperature of amp thermistor(C) -Failure description: ‧ After units come out of the chamber, the temperature is lower than 50 degrees. -Root cause: ‧ DUTs need to stay in the HT chamber longer. -Action: ‧ Verified the conveyor speed to check the temperature degree after DUTs come out of the HT chamber at PR build. | NPI |  |  | 0
2 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #2 | 2021-03-18 19:43:09.6988554 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004-MPS - Target: ≧ 90% | 004-01098-00 is not released (NRL) so test coverage rate cannot be evaluated | IR#138807 prod released the 004 | MFG EE | 2021-06-03 16:00:00.0000000 +00:00 | 2021-05-26 15:54:29.5734300 +08:00 | 1
2 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04050-70 is still ver.002. OLA is expected to update before MP. | Failure description: ‧ 007-04050-70 is still ver.002. OLA is expected to update before MP. Action: ‧ Update from the packaging team regarding the 007. Date moved out with our schedule push of MP now starting on 12/13. ‧ Packaging ‧ Targeting 11/22 for release of Mass Production Packaging ‧ Only waiting on updated PFJ logo for box artwork, email has been sent to request updated logo | MFG ME | 2021-11-21 16:00:00.0000000 +00:00 | 2021-11-23 09:03:11.5473518 +08:00 | 1
1 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Inspection VIP not ready: ※non-IR SKU -DE part: 013-00701-04 ※IR SKU -ME part: 115-03762-20 -DE part: 013-00701-03/470-00906-00 2 part GPN | Inspection VIP were available by 3/18. | MFG ME/DE | 2022-03-17 16:00:00.0000000 +00:00 | 2022-04-07 15:16:27.0164372 +08:00 | 1
2 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | FT1(95.7%)_NFC Antenna Self-test Tx Current | FT1 (95.7%) Failure description: -NFC Antenna Self-test Tx Current Root cause: -EE checked one unit without gluing and found LCM connector disconnected. The other three gluing units pass RT1, and FT1 fail. EE estimates all the units suffer the same problem. (Process flow: RT1-> Disconnect LCM connector -> Gluing -> Assemble LCM connector -> FT1) Action: -NPI will disassemble the gluing units to confirm the root cause. [11/26] will check fixture highness and prevent to tear down the NFC trace. [1/3] No similar issue found in PreMP build. [Closed] | NPI | 2021-12-09 16:00:00.0000000 +00:00 | 2022-01-03 15:13:58.5880110 +08:00 | 1
2 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE (49.59%)_Keypad Up 2. Multiupdater (22.31%)_MultiUpdater USB Update ASSY 1. FT1 (115.05%)_C/No by ref. (Non Solar) 2. Gyro (103.37%)_Gyro Data X軸檢查 (CW #1) 3. Compass (93.26%)_Check Unit Roll on 0 degree 4. FT2 (94.38%)_電池電壓¦Battery Voltage 5. Baro (74.16%)_fail retry 0% (not real retry) 6. VT (69.89%)_INI壓力超出規格,變形量絕對值超出規格_正/負壓 7. Gsensor (67.42%)_fail retry 0% (not real retry) 8. HT (60%)_GlONASS 78 CNo by ref. 9. RT1 (31.18%)_(ILP LED ON) LED2C_PD4 AVG 10. RT2 (26.88%)_ANTCW TX(CW BOX) CH57 11. ProdScan (26.25%)_Software Version 12. RTESN (17.89%)_RGN version range check | Only show the percentage without fail unit retry rate. 1. FT1 (41.95%)>>[[11/26]21.1% [12/10] 設備理線後重測有改善 close Failure description: -C/No by ref. (Non Solar) Root cause: -The test environment wasn’t ready yet. The cable in the chamber isn't fixed well. After fixing the cable, the same DUT's tested value is from -4.82 (out spec.) to -1.5db (in spec.). Action: -AE adjusted the test environment. Fix the cable in the chamber. Evidence: -Retry decreased to less than 2% in the following Instinct 2 orders. 2. Gyro (23.6%) >> [11/26]2.19% Failure description: -Gyro Data X軸檢查 (CW #1) Root cause: -Testing value is mostly zero. Temporarily judge to be a test equipment issue. Action: -Inform OP to notify PE when the issue happened again. 3. Compass (22.47%)>>[11/26]1.7% Failure description: -Check Unit Roll on 0 degree Root cause: -G-sensor fixture issue. Stepping motor causes g-sensor unprecise calibrated environment for Compass test. Action: -PDO will change the stepping motor firmware on 10/25. | NPI | 2021-12-09 16:00:00.0000000 +00:00 | 2021-12-10 17:45:32.9871898 +08:00 | 1
1 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 1. SMT - C/No GLONASS_78_0.83 - ANT功率(CH57)¦ANT Power(CH57)_0.94 - C/No GLONASS_72_1.06 2. ASSY - ANTCW TX(CW BOX) CH57_0.72 - (ILP LED ON) LED2C_PD4 AVG_0.79 | 1. SMT 1)C/No GLONASS_78_0.83 -Will provide a golden PCBA to T2 AE for the verification of equipment. [Closed] 2)ANT功率(CH57)¦ANT Power(CH57)_0.94 -Need AE's help in reducing the variance caused by the testing equipment. [Closed] 3)C/No GLONASS_72_1.06 -Need AE's help in reducing the variance caused by the testing equipment. [Closed] 2. ASSY 1)ANTCW TX(CW BOX) CH57_0.72 -NG Units come from the same port. [Closed] 2)(ILP LED ON) LED2C_PD4 AVG_0.79 -Wait EE check.[Closed] | NPI | 2021-12-09 16:00:00.0000000 +00:00 | 2022-01-03 15:14:34.9702028 +08:00 | 1
2 | Automotive | BC50 & BC50 IR | GMLA #3 | 2022-03-02 17:29:06.1781979 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 94.12% ※ Non-IR SKU - ME part 2 items not ready(320-01532-00/320-01532-10) - DE part 1 items not ready(013-00701-04) ※ IR SKU - ME part 4 items not ready(115-03762-20/320-01532-00/320-01532-10/320-01532-20) - DE part 2 items not ready(013-00701-04/470-00906-00) | The FA was complete by 3/18. | MFG ME/DE | 2022-03-17 16:00:00.0000000 +00:00 | 2022-04-07 15:16:43.1490287 +08:00 | 1
2 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #2 | 2021-09-22 18:04:20.4510995 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 29.37%: C/NO_GPS16 ASSY 1. VT1 15.05% 2. RTESN 13.54%: Check Bundle ESN1 3. CT 92.71%: C/No 16 and Golden Diff & Temperature 4. HT 23.96%: Internal GlONASS_65 5. VT2 11.58%: 小漏氣_超過洩漏量門檻 6. FT1 39.58%: CPU_temperature 7. FT2 17.02%: Wifi Power CH1 | 1. ATE: C/NO_GPS16 Poor contact with antenna on ATE fixture cause most of retry. Need AE & EE provide fixture modification estimate date. 2. CT: C/No 16 and Golden Diff & Temperature GPS relate test item had unstable test result ; Temperature is the critical factor for GPS test and all relate test spec are still under EE discussion 3. FT1: Most of retry was cause by connection issue and it is hard to judge actual cycle time & other retry issue in FFP. [ME had modified tooling and change gasket hardness, will have new test result in PR] All actions are pending, because of PR FRM178 delay. (Compliance issue) | NPI | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Edge 540 840 | GMLA #1 | 2021-12-06 14:51:45.6789038 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Need to verify 105-04394-00 strain when the Router fixture is ready. | The fixture was available by 2/23. The strain gauge had be complete on 2/24 | NPI/PQE | 2022-02-24 16:00:00.0000000 +00:00 | 2022-02-24 13:32:57.8456427 +08:00 | 1
2 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #2 | 2021-09-22 18:07:03.5597006 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | SMT 1. ATE 26.77%: Power Key Turn-On Current 9V ASSY 1. CT 14.58%: 77K TX Frequency 2. HT 20.83%: C/No 16 and Golden Diff. 3. VT2 12.37%: 大漏氣_未抽至1120 4. FT1 16.67%: Unit_temperature 5. FT2 31.25%: Wifi Power CH1 | 1. ATE: Power Key Turn-On Current 9V OP did not assemble cable well and cause retry. Need to update Sop and train OP to assemble cable in right position. 2. HT: C/No 16 and Golden Diff. Under analysis 3. FT2: Wifi Power CH1 Under analysis PR FRM178 pending all relate action can refer to 5" report & plan to have PR result by 1/E. (Compliance issue) | NPI | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
2 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. SMT (1) ATE 15.73%: A14000(high voltage) 2. ASSY - White (1) CT_01 31.25%: Main board Temperature (2) HT_01 37.5%: Calibration index 0 (3) VT2 12.12%: 大漏氣_未抽至1120 (4) FT_00 29.41%: Amplitude cfg 14 (5) CT_00 23.53%: Main board Temperature (6) HT_00 41.18%: Amplitude cfg 14 3. ASSY - Black (1) CT_01 63.64%: Amplitude cfg 14 | 1. SMT ATE 15.73%: A14000(high voltage) Cause by the SW setting issue, after reset the SW and all units pass the test. -- 2. ASSY - White CT_01 31.25%: Main board Temperature CT_00 23.53%: Main board Temperature All the temperature retry were failed by the temperature of the unit were not enough hot/cold. As the units are big that sometimes can't reach the temperature target under the testing time. All units pass the test after the temperature reach the test standard. -- HT_01 37.5%: Calibration index 0 HT_00 41.18%: Amplitude cfg 14 Cause by the SW setting issue, after reset the SW and all units pass the test. -- FT_00 29.41%: Amplitude cfg 14 The original fixture was broken. All units passed the test after change to another fixture. -- VT2 12.12%: 大漏氣_未抽至1120 All HT/CT VT fail machine have passed IPX6 and he external mechanical parts are the same as previous model so the design team believes that the risk is small. We have closed this issue base on above evidence. 3. ASSY - Black CT_01 63.64%: Amplitude cfg 14 The actual retry rate are 27% Cause by the SW setting issue, after reset the SW and all units pass the test. | NPI | 2021-07-01 16:00:00.0000000 +00:00 | 2021-07-05 11:36:01.2929569 +08:00 | 1
2 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004- MPS -- Target: ≧ 90% | Test coverage rate still under EE analysis. Can be evaluated before PR. | Test coverage rate still under EE analysis. Can be evaluated before PR. | MFG EE | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% 1. MicBoom: 77.17% 2. SoundCheck: 30.43% 3. SliderMain: 29.07% 4. SliderVice: 23.46% 5. RTESN: 20.99% 6. FT: 11.11% | 1. [Fixed in PR, no retry] MicBoom (77.17%) -Root cause: Not real retry. The high retry rate is due to duplicate ESN being posted on different MIC Boom. NPI provided two labels of one ESN to the MIC boom outsourcer. Outsourcer misunderstood and attached duplicate ESN labels on different units. -Action: NPI will provides only one piece for each ESN. 2. [Still remained 8.5% in PR, was caused by unstable test fixture, will modify connection method in MP] SoundCheck (30.43%)_ critical ALL RESULT 3.5 -Root cause: The headset isn't placed well. Limited position on the fixture should be improved. -Action: Acoustic engineer Henry will add more limited position and check it won't deform the earcup cushion. (Under discussion) 3. [Fixed in PR, no retry] SliderMain (29.07%)_ RDS MR20100 8 -Root cause: Unclear fixture limitation leads to a high retest rate. DUT will pass the test after being replaced. -Action: NPI will discuss with PDO to modify the fixture to fix the DUT well. (Under discussion) | NPI | 2022-01-19 16:00:00.0000000 +00:00 | 2022-02-07 13:57:44.6713647 +08:00 | 1
2 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | 1. No Pre-assembly (Dicing) and Test SOP 2. ACF bonding and main assembly SOP need to be updated because the content is not for LVS62 | The SOP has done the updated and uploaded to the Web | NPI | 2021-12-23 16:00:00.0000000 +00:00 | 2021-12-27 09:56:09.9787965 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #1 | 2021-05-17 15:06:13.9266871 +08:00 | Product validation | 1.B-2 | ELOT test plan | ELOT test plan is not ready | ELOT plan has been created as eFRM064 (LMS0017078) | MFG EE/ME/DE | 2021-05-18 16:00:00.0000000 +00:00 | 2021-05-20 10:13:57.2419696 +08:00 | 1
1 | Fitness | Venu H(Asia ISO13485 Certification) | GMLA #3 | 2021-01-29 23:29:59.6063595 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- SMT VIP -- New component design review (refer to DFM report) -- Minimum component review | Max. Reflow Temp of 805-C8560-JD (MB)need to be confirmed MB : 012-03645-10 Gen3 : 012-03548-17 |  |  |  |  | 0
2 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | FT2 60%: Max Side Lobe2 | - Root cause: Reflection in FT2 tank - Action: The design team asked EE had done the validation by adding the metal panel in the FT tank for reducing the reflection. The validation results showed positive | NPI | 2021-12-23 16:00:00.0000000 +00:00 | 2022-01-26 12:46:44.8388891 +08:00 | 1
2 | Fitness | Venu H(Asia ISO13485 Certification) | GMLA #3 | 2021-01-29 23:29:59.6063595 +08:00 | Process validation | 3.D-9 | PR retry rate review and action plan for high retry rate station or test item -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate >10% but with action plan to improved SMT: PRNP、AutoATE ASSY: RTESN、iFT2、Easycard、FT1、FT_SPO2 |  |  |  |  | 0
1 | Fitness | Venu H(Asia ISO13485 Certification) | GMLA #3 | 2021-01-29 23:29:59.6063595 +08:00 | Process validation | 3.D-10 | PR Cpk result review of critical testing item/ station -- Action plan for Cpk improvement | Cpk/ Ppk < 1.33 with action plan to improved ASSY : GIONASS、C/No |  |  |  |  | 0
1 | Fitness | vivosmart 5 (Franklin) | GMLA #1 | 2021-05-17 15:06:13.9266871 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | ASSY: screwing、Locking Connectors are NG | Adding PCB support structure improved the strain but still fail on FP1. Will apply underfill on I501/I601/I208 on FFP for relevant tests and keep tracking. | PQE | 2021-10-14 16:00:00.0000000 +00:00 |  | 0
1 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Product validation | 3.B-4 | Release 010- unit level appearance standard for PR -- Define A/ B/ C/ D level and acceptable criteria -- Check if special requirement of appearance standard for critical parts (IIS/ 001-/ 005- document) --Release 001-/ 005- document -- (AOEM) Customer approval for appearance standard | Not defined the unit level appearance standard. | Latest housing samples sent to Olathe ID Michael on 5/16. Once ID confirmed, the appearance standard can be defined. Update: ID designer had confirmed. | MFG ME | 2022-05-26 16:00:00.0000000 +00:00 | 2022-06-06 15:26:03.2159532 +08:00 | 1
3 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ※ ELOT issue found 1. Product Package Drop (2/2) Inner Box New Design - 1 1)The unit was shifted after the drop test(The inner box can't fix the unit well.) and the appearance was minor scratched. ) _ESN: 3415914074 Inner Box New Design - 2 2)The inner box cracks._ESN: 3415914047 | 05/30 Update : MPM has updated the final conclusion(waive), and the issue has closed. 05/27 Update : The Olathe team has waived the issue, the reason shown below : (By Stephen) Here are my thoughts. As long as the inReach Messenger device doesn’t show any issues (i.e. scratches, dings, cracks, etc.)…, I think the slight damage to the packaging insert after the vibe/drop tests is OK to be waived. If the device is OK…, the box insert did its job by protecting the device during the vibe/drop tests. Inner Box New Design - 1 : 1)The unit was shifted after the drop test(The inner box can't fix the unit well.) and the appearance was minor scratched. ) _ESN: 3415914074 Update: The packaging team and the production line decided not to use this design. Inner Box New Design - 2 : 2)The inner box cracks._ESN: 3415914047 Update : Jasmine is confirming the test criteria with the Olathe team to decide whether the inner box's crack can be accepted or not. https://etrex8.garmin.com:8888/LMS/ResultPageInit.action?resultItemId=325869 | TWN Lab | 2022-06-09 16:00:00.0000000 +00:00 | 2022-05-30 11:32:14.5235871 +08:00 | 1
2 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Product validation | 3.B-6 | Appearance inspection report from NPI | Issue found on rear & front case: 1. Rear case surface damage(scratch and nail marks) during transportation. Defect rate: 36% (82/277) 2. Front case surface damage from molding process/Clean Room ,scratch, nail marks, flow marks. Defect rate: 29% (66/277) | Modify the tray design to prevent scratches  New tray samples will be ready next week and run transportation and drop tests. Evaluate the protective film.  Supplier has sent out the samples on 5/16 | NPI | 2022-05-26 16:00:00.0000000 +00:00 |  | 0
2 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. FT2 152.5%: Max Side Lobe2 2. RT 10.47%: STDImage0 | - Root cause: Reflection in FT2 tank - Action: The design team asked EE had done the validation by adding the metal panel in the FT tank for reducing the reflection. The validation results showed positive | NPI | 2021-12-23 16:00:00.0000000 +00:00 | 2022-01-26 12:47:33.6297275 +08:00 | 1
2 | Automotive | BC50 & BC50 IR | GMLA #2 | 2021-12-03 10:48:35.0451013 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | 011-05738-00 VT1 final yield rate 94.94% not meet the target (3 pcs fail. One unit leak from the cable, the others leak from the RC) | Analysis: All the leakage are come from PW connector and units can PASS after sealed PW cable Action: Add glue on the connectors & also coaxial cable. -Tracking on PR build. | NPI/ME/DE | 2022-01-27 16:00:00.0000000 +00:00 | 2022-02-21 10:03:43.5640291 +08:00 | 1
2 | Automotive | BC50 & BC50 IR | GMLA #2 | 2021-12-03 10:48:35.0451013 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry not meet 10% target TOP3 issue SMT (1) IR Sensor Head_ATE 19.46%: Sensor board current(disable IR) (2) Tx board PRNP 14.5%: Wi-Fi Power Level Diff. CH11_CCK_11M Assy (Non_IR SKU) (1) RTMTF 99.24%: Move fixutre (2) VT1 55.8%: 漏氣_測試中壓降低於1070 (3) VT2 50%:小漏氣_超過洩漏量門檻 Assy (IR SKU) (1) RTMTF 102.56%: Turn on current 12V (for SB 20) (2) HT 91.79%: Turn on current 12V (for SB 20) (3) VT1 86.08: 小漏氣_超過洩漏量門檻 | SMT: (1) Suspect to I102 component issue, and track on PR build. – Closed (2) Power is abnormal due to RF probe touch the L301 at ATE test, and DEE moved the L301 position to fixed the layout on V4 version.-Closed ASSY: Non-IR/ IR RTMTF: The HTMTF test program didn’t be set up well by DE, so the units went through HTMTF test at RTMTF station on FP build. DE will provide the test program before next build. VT1/VT2: The sealing fixture is available to seal the end of the connector, and the verification pass on 11/18 HT: The metal head of the test cable is compressed to fix the electrical wire, which can provide stable connection. This solution has also been confirmed in the low retry rate of FT (2.24%) | NPI/EE/ME/DE | 2022-01-27 16:00:00.0000000 +00:00 | 2022-02-21 10:04:26.0524748 +08:00 | 1
1 | Marine | ECHOMAP UHD2 (Touch) 9" | GMLA #1 | 2021-12-13 17:05:51.8887607 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 1. 105-04368-00 & 105-04403-00: Wait for NPI to provide the router fixture 2. 105-04267-00: ASSY screw is ongoing | 1. Will verify the strain gauge when tooling is ready. (Plan to measure on FFP) 2. After PQE assessment there are no parts to be verified on 105-04267-00, so no testing is required. | PQE |  |  | 0
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ Packing material…) | 2 items are not ver. A+. 010-02642-00: v009 012-03545-90: v001 | Both have updated to ver.A | PID | 2021-06-27 16:00:00.0000000 +00:00 | 2021-08-02 09:22:52.4984156 +08:00 | 1
2 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Product development | 3.A-14 | Receive 174- doc from Design team for packing SOP | 174-pack instruction is not released | Keep tracking with PE/PjM. | NPI | 2021-06-27 16:00:00.0000000 +00:00 | 2021-07-05 11:23:50.8544937 +08:00 | 1
1 | Marine | GPSMAP 9000 - 19" | GMLA #1 | 2022-05-09 15:33:04.7405657 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 1. 105-04277-00: ASSY screw connector is waiting for the fixture. NPI will provide it by 6/B. 2. 105-04458-00: De-panel NG. NPI will change it to the router. Keep tracking the router result | 105-04277-00 Rev.3 de-panel will start in first FP, because the fixture is not ready yet. @Cheng, Derek @Hsu, Jason(PQE) | PQE | 2022-06-22 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GPSMAP 9000 - 22" | GMLA #1 | 2021-12-09 15:38:58.2593981 +08:00 | Product development | 1.A-2 | Define critical parts/ component for BOM material (Input from design team; output is critical parts list) -- Critical patrs list have been well defined and review by CFT in DFM meeting (maintained in MPM system) -- (AOEM) AOER requirement review for critical parts | Critical part is not ready. Need to define and maintain the critical part in MPM system | MME: 330-01996-00 USB C connector and 145-03898-00 front case. DE: 440-00349-00/439-00187-00. ENG list the parts first, will upload to MPM system until project BOM implement. | MFG ME/DE | 2021-12-13 16:00:00.0000000 +00:00 | 2021-12-13 11:30:51.5220208 +08:00 | 1
1 | Marine | GPSMAP 9000 - 22" | GMLA #1 | 2021-12-09 15:38:58.2593981 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04277-00/ 105-04458-00/ 105-04022-00: De-panel and ASSY screw are ongoing | De-panel and ASSY screw testing are ongoing. [12/17] 105-04277-00 V3/ 105-04022-00 V2 de-Panel pass, but the ASSY screw test of 105-04022-00 will not be tested until the tolerance problem on the RC is resolved. | PQE | 2022-06-22 16:00:00.0000000 +00:00 |  | 0
1 | Marine | GPSMAP 9000 -27" | GMLA #1 | 2022-05-09 15:34:40.7338135 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 1. 105-04277-00: ASSY screw connector is waiting for the fixture. NPI will provide it by 6/B. 2. 105-04458-00: De-panel NG. NPI will change it to the router. Keep tracking the router result | 105-04277-00 Rev.3 de-panel will start in first FP, because the fixture is not ready yet. @Cheng, Derek @Hsu, Jason(PQE) | PQE | 2022-06-22 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | Do not have SOP for SMT process. | Completed on 4/15. | NPI | 2022-04-14 16:00:00.0000000 +00:00 | 2022-04-18 14:08:20.7055198 +08:00 | 1
1 | Marine | WDU Cost down (EmpirBus Low cost web server solution) | GMLA #3 | 2021-06-16 16:38:15.6544801 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | 10 GPNs without VIP: 211-/251-/252-/310-/335-/336- | 211-/251-/252-/310-/335-/336- FA had been approved and followed CLx, no new change request, issue closed. | MFG ME | 2021-06-16 16:00:00.0000000 +00:00 | 2021-06-17 18:37:18.6118496 +08:00 | 1
2 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | FYR of Airtight_table station is lower than 95%. | Failure Description: Airtight table station fail. Root Cause: Dispensing equipment tilted, cause glue overflow. Action: Dispensing equipment has been recalibrated for levelness. Evidence: TBD | NPI | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
3 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #3 | 2022-03-03 16:49:41.1229176 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | High Temp., Min Voltage Life (1/1 NG): Testing under 85 deg and 9V power for 1 week. Display pass but VT fail | NPI PE had provided improvement samples and all 3pcs passed after baking. 03/14 will finish lab test. All passed after re-test. | TWN Lab | 2022-03-13 16:00:00.0000000 +00:00 | 2022-03-23 13:17:25.3267364 +08:00 | 1
2 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | FYR of Airtight_table station is lower than 95%. |  | NPI |  |  | 0
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #1 | 2021-11-17 19:31:27.1080132 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | 105-04455-00 de-panel fail. OLA will modify the layout in the next revision. | Olathe will moving the failing parts on the next board release. [WK2] After moving the failing parts on 105-04455-00, de-panel pass on 2021/12/24. http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04455-00 | PQE | 2022-01-13 16:00:00.0000000 +00:00 | 2022-01-04 17:04:04.5315070 +08:00 | 1
2 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%, ※SMT 1. ATE (26.75)_NFC Antenna Self Loop Test Tx Current ※ASSY 1.RT1 (28.24)_Motor Vibration Z 2.RT2_ALS (23.65)_Power Box Sampling (Norm) | ※SMT 1. ATE (26.75)_NFC Antenna Self Loop Test Tx Current Not able to detect by ATE, only able to detect in assembly testing, the failed unit can not rework and need to be scrapped. Keep tacking on PR. ※ASSY 1.RT1 (28.24)_Motor Vibration Z Will bypass after PR. 2.RT2_ALS (23.65)_Power Box Sampling (Norm) Happened on the rework units in FFP. Keep tacking in PR. | NPI | 2022-05-19 16:00:00.0000000 +00:00 |  | 0
4 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | Strain gauge test failed by screw but underfill it | Strain gauge test failed by screw but underfill it | PQE | 2022-03-29 16:00:00.0000000 +00:00 | 2022-03-30 15:18:57.1741905 +08:00 | 1
1 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | Need to provide report for verification. | Verified partial fixtures before Asia PR and will complete rest of verification before MP. | PDO/AE | 2022-04-17 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezl watch | GMLA #2 | 2021-05-14 13:11:19.2001141 +08:00 | Product development | 2.A-9 | Unit/ Accessory: Test coverage rate evaluation based on 004- MPS -- Target: ≧ 90% | 9 of 82 items were not tested. 1. VDD_1.8_WHR 2. Pressure Sensor Noise(Standard Deviation) 3. 26MHz Accuracy 4. Average External Supply Current in Test Mode 5. Pressure Sensor Temperature Accuracy 6. Pressure Sensor Pressure Accuracy – 1atm (Cold Temp) 7. Baro BIST 8. Backlight Functionality 9. NFC Inventory Check | 6 items are added in test, 3 items wait for MPS updated. 1. VDD_1.8_WHR (No need to be tested. A stricker test is already in MPS, MPS will be updated at PR (7/9)) 2. Pressure Sensor Noise(Standard Deviation) (Added) 3. 26MHz Accuracy (Not suggest to add, it will affect other test item, wait for Olathe feedback(7/9)) 4. Average External Supply Current in Test Mode (Added) 5. Pressure Sensor Temperature Accuracy(Added) 6. Pressure Sensor Pressure Accuracy – 1atm (Cold Temp)(Added) 7. Baro BIST (Added) 8. Backlight Functionality (Added) 9. NFC Inventory Check (Olathe prefer to remove, MPS will be updated at PR(7/9)) | MFG EE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-08-31 21:30:04.6468941 +08:00 | 1
2 | Automotive | dezl watch | GMLA #2 | 2021-05-14 13:11:19.2001141 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | 1. ATE: 10.83% ->VBAT current (GNSS on BL off): 5.83% 2. CT: 12.04% ->M-Sensor BIST 9.26% 3. HT: 12.04% ->M-Sensor BIST 6.48% 4. RT1:13.89% ->GlONASS 78 CNo by ref. 7.41% 5. 10 atm: 22.22% ->Consecutive slope abnormal under negative pressure 7.41% 6. Compass: 12.04% ->Check Unit Roll on 0 degree 10.19% 7. Gyro: 10.19% ->Check Airtight Test Data 5.56% | <Top 4 stations with top 1 fail item> 2. CT: 12.04% ->M-Sensor BIST 9.26% >> Power rail issue, it will be solved on V5 PCB and checked at PR build._EE Kevin (7/9) <Closed> 4. RT1:13.89% ->GlONASS 78 CNo by ref. 7.41% >> Will check in PR build with the new length of antenna._EE Kevin (7/9) <keep monitoring PreMP> 5. 10 atm: 22.22% ->Consecutive slope abnormal under negative pressure 7.41% >> fail concentrated on 2 NG units with less glue. We will carry out 100% weighting for PR build units. (no change on glue volume for PR build)_NPI Daniel (7/9)<Closed> 6. Compass: 12.04% ->Check Unit Roll on 0 degree 10.19% >> Stepping motor causes g-sensor unprecise calibrated environment for Compass test. Improving the motor is under discussion._EE Kevin (7/9)<keep monitoring PreMP> | MFG EE | 2021-07-08 16:00:00.0000000 +00:00 | 2021-10-07 11:34:48.5676930 +08:00 | 1
2 | Fitness | Forerunner 255 | GMLA #2 | 2021-12-21 19:46:45.2040739 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 %: Top 1: ProdScan_Pack = 96.86 %, Top 2: AutoATE = 31.94 % Top 3: RT2 = 26.23 % | 1. ProdScan: Manifest Check issue due to software behavior, will discuss with SW team 2. AutoATE: Modify Spec. due to different PCBA type(Alt type) solution, will update 004 Spec. 3. RT2: ‧ SW issue due to calibration reading error , will update SNS FW to v13. to solve the issue | EE | 2022-01-04 16:00:00.0000000 +00:00 | 2021-12-27 14:36:14.5697460 +08:00 | 1
2 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ProdScan (21.9%)、 VT (18.7%)、RT2(12.1%) | ATE: 1.“32K” (3%) [closed]: spec has been adjusted considering the variance of component. 2.“Low Power Mode Current” (1.5%) [closed]: spec has been adjusted due to design changes. Assy: 1. VT related retry [closed]: caused by test parameter setting on the 1st jobs, verified OK after modification. 2. RT2 Battery Volt (6%) [closed]: confirmed as insufficient charging during test process, keep tracking in PR. 3. Product scan [closed]: TE helped to adjust battery voltage to 3.8~4.4 V.(Follow MPS) | NPI | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-27 11:37:21.4203615 +08:00 | 1
2 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Process development | 2.C-2 | Review Machine/ Fixture list and ETA for FFP build | FT2 tank readiness need to be tracked | According to the EE additional validation requirement, the PDO team had done the fixture to installation with the metal penal and created the different sizes of the metal ball for testing. | NPI | 2021-12-20 16:00:00.0000000 +00:00 | 2021-12-22 13:52:34.5216691 +08:00 | 1
2 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | No SMT/Cleanroom SOP. | SMT SOP ETC 3/11. @Chen, Andy(PE) CR SOP ETC 3/25 (after LOCA leakage small build issue validation complete). @Lee, Allenjt | NPI | 2022-03-30 16:00:00.0000000 +00:00 | 2022-03-30 10:48:23.5257801 +08:00 | 1
2 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | FFP Retry not meet 10% target ※SMT 1. PRNP (42.42%): 14 SYSTEM SOFTWARE ※Assy 1. VT1 (12.94%): 抽氣次數違反 2. FT_iridium_Test (12.89%): Start to Read RSSI | 1. PRNP retry: not actual fail, but SW behavior caused SW version could not be checked. Will discuss SW update schedule with design team. @Tien, Howard 2. VT: The smaller gasket sample ETA 3/9. Plan to complete validation by WK11. @Kuo, Kuo 3. FT iridium retry: mainly from Rx related tests: verified OK after test sequence modification. | NPI | 2022-04-14 16:00:00.0000000 +00:00 | 2022-05-12 09:40:24.6091783 +08:00 | 1
2 | Automotive | dezl OTR Series 2022-10" | GMLA #2 | 2022-02-09 12:48:46.2399230 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ※SMT 1. ATE (17.39%)_LDO24 ※ASSY 1.ST (40.71%)_Mic Amp Diff. with Golden 2. HT (12.28%)_機台溫度 3. GSensor (10.62%)_Negative X | Top3 retry rate: 1. ST (40.71%)_Mic Amp Diff. with Golden -Failure description: Mic Amp Diff. with Golden -Root cause: The fixture speaker's volume is a little low at the beginning. Mic gets the initial volume to compare with golden. -Action: The problem is solved by adjusting the test program with retry times to get the correct volume. 2. ATE (17.39%)_LDO24 -Failure description: LDO24 voltage abnormal -Root cause: Test program’s problem causes the wrong value of DUT. -Action: Modify the program of the test timing to get the corrective LDO voltage value. -Evidence: Retest the unit with modified program pass. 3. HT (12.28%)_機台溫度 -Failure description: DUT's temperature is not high enough. -Root cause: DUT didn't stay in the chamber with enough time. Operators take the unit out of the heating chamber too early. -Action: Ask the operator in the PR line to follow the set time to take the DUT out. In addition, it will be improved by MP line with heating conveyor. | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | Tread 8" OEM w/ CAN | GMLA #2 | 2022-02-23 10:19:51.8518228 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10% 1.FT3_Others(F)_35.56%_Mount Status 2.VT2(.501)_33.33%_大漏氣_未抽至1120 3.Baro(B)_31.11%_Wait for the pressure stable 4.ST(.161)_31.11%_喇叭頻率(1K)¦Speaker Freq.(1K) 5.RTESN(.183)_26.67%_GPS_10_L1 6.ATE_25.93%_100% SPK 7.CT(C)_20%_機台溫度 8.HT(H)_13.33%_機台溫度 9.Compass(R)_13.33%_[Compass]Vector Error 10.VT1(.101)_11.11%_小漏氣_超過洩漏量門檻 | 1.FT3_Others(F)_35.56%_Mount Status -Failure description: ‧ Mount was not well-locked. -Root cause: ‧ Mount was not locked well due to the operator and the fixture. Some fixtures may need to change to a new pin. -Action: ‧ Modify ITMXP for mount locked alarm. ‧ Check if it happened on the identical fixture, AE will modify the fixture. -Evidence: ‧ Modified ITMXP had been verfied on Tread SXS MP job 15770102 and 15770139 (700 pcs), retry rate of Mount status reduced to 2.5% 2.VT2(.501)_33.33%_大漏氣_未抽至1120 -Failure description: ‧ VT failed -Root cause: ‧ SD door wasn't closed -Action: ‧ Ask the operator to follow SOP to check SD door closed. After new operator completed learning cureve, retry of Tread SXS MP job 15770102 and 15770139 (700 pcs) had reduced to 4.2%. 3. Baro(B)_31.11%_Wait for the pressure stable -Failure description: ‧ USB Connection is not stable. -Root cause: ‧ Test cable is clamped by door and chamber. -Action: ‧ Add request for check cable status before the test in the SOP. After new operator completed learning cureve, retry of Tread SXS MP job 15770102 and 15770139 (700 pcs) had reduced to 1.4%. | NPI | 2022-02-28 16:00:00.0000000 +00:00 | 2022-03-01 19:22:05.5957303 +08:00 | 1
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | For 010-02727-00/ 010-02728-00/ 010-02729-00, there are 21 items that haven't been turned A. 011-05879-00, 011-05879-01, 011-05879-10, 011-05879-20, 011-05879-21, 011-05879-30, 011-05879-40, 011-05879-50, 011-05879-52, 011-05879-55, 011-05879-60, 011-05879-70, 011-05879-71, 011-05879-80, 012-04450-JT, 015-05879-6X, 145-03955-00, 145-03956-00, 145-03956-01, 145-03957-00, 145-04038-00. |  | NPI/ME/DE |  |  | 0
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04285-00, 007-04286-00, and 007-04287-00 haven't been turned A yet. | ECO#242942 was released on 5/21. ECO#242940 was released on 5/23. | MFG ME | 2022-05-23 16:00:00.0000000 +00:00 | 2022-05-24 18:01:09.4257794 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | Waiting for ECO #237506 release | ECO was released on 2/10 | MFG ME | 2022-02-09 16:00:00.0000000 +00:00 | 2022-02-15 15:51:18.4309490 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 010-02581-00: There are 41 items not turned A yet. 010-02581-10: There are 35 items not turned A yet. (2/8) | 5 items remain in both 010-02581-00 and 010-02581-10 004-01114-00: ECO#236858 was effective on 2/15. 006-B3962-00: RevA released on 2/18 012-04335-JT: Debug purpose 170-02463-63: New packing solution passed on 2/21. ECO#238229 was relased. 171-01672-00: New packing solution passed on 2/21. ECO#238229 was relased. | NPI/ME/DE | 2022-02-20 16:00:00.0000000 +00:00 | 2022-02-23 13:17:42.7083255 +08:00 | 1
2 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 170-02463-63/171-01672-00 hasn't turned A yet. | Two packing parts are pending on ELOT drop failure issue, deadline is 2/18. 1. 170-02463-63 has already turned A on 2/16. 2. 171-01672-00 is waiting for the package design fixed (ECO#237864 on 2/22). | MFG ME | 2022-02-17 16:00:00.0000000 +00:00 | 2022-02-23 10:09:20.8154939 +08:00 | 1
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | Some fixtures would need to be modified. 1. Battery pressure fixture will remove battery PCB area to prevent breaking battery. 2. Modify unit holder to prevent tilt during assembly. 3. Change DA5x RTESN rack to share with dezlcam. 4. Modify MTF fixture to fit hot unit. | The expected release date is as below. 1. Battery pressure fixture will remove battery PCB area to prevent breaking battery. (6/6) 2. Modify unit holder to prevent tilt during assembly. (6/10) 3. Change DA5x RTESN rack to share with dezlcam. (6/6) 4. Modify MTF fixture to fit hot unit. (6/6) | PDO/AE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Yield < 97%: HTMTF (84.79%) 1. Start preview (15.21% 20pcs) 2. Transfer file(Raw to JPG) (8.76% 9pcs) 3. MTFH0-Collimator1 (0.92% 2pcs) 4. Lock AE AWB (0.46% 1pcs) | -Description: 1. Start preview (15.21% 20pcs) 2. Transfer file(Raw to JPG) (8.76% 9pcs) 3. MTFH0-Collimator1 (0.92% 2pcs) 4. Lock AE AWB (0.46% 1pcs) -Root cause: Item 1&2&4 is related to the SW communication. Item 3 is waiting for the optical engineer's analysis. -Action: Item 1&2&4 : SW V1.15 can fix the issue. It is verified by the next job order with 100% yield rate. (Job order: 15903220/15903225/15903427) -Evidence: Item 1&2&4 : wait for ECO released. | NPI |  |  | 0
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%: ※SMT: 1. ATE (20.9%)_C/No¦Snr (15.79%) 2. SB_ATE (19.17%)_Stop Video Recording (8.21%) ※ASSY: 1. HTMTF (104.61%)_Start preview (37.33%) 2. CT (78.54%)_C/No by ref (11.87%) 3. ProdScan (60.69%)_3D Fix (12.41%) 4. HT_CCM_B (48.85%)_Temperature (13.36%) 5. RTESN (45.66%)_電池電壓¦Battery Volt. (9.13%) 6. ST (23.53%)_(PND Mic) MAX Amp Diff (4.9%) 7. FT (25%)_Manifest Event Test (8%) 8. CCM_3in1 (20%)_Vignette calibration (3.41%) | Retry > 10% Top 3, 1. HTMTF (104.61%)_Start preview (37.33%) -Description: Communication with DUT camera fail. -Root cause: The software is not ready yet. -Action: SW V1.15 can fix the issue. -Evidence: It is verified by the next job order with 0% start preview retry rate. (Job order: 15903220/15903225/15903427) 2. CT (78.54%)_C/No by ref (11.87%) -Root cause: It is related to equipment verification. The equipment is not verified before PR production. -Action: EE asks AE to verify all the equipment before the production date. -Evidence: It is verified by the next job order (- SKU) with 0% CN-related retry rate at CT. (Job order: 15903220/15903225/15903427) 3. HT_CCM_B (48.85%)_Temperature (13.36%) -Root cause: Retry too many times of DPC calibration which causes low temperature. (DPC calibration retry 11.06%) -Action: FPC is not fully inserted. ME already asked OLA to add a white line for checking the inserted status. -Evidence: Wait for ECO. | NPI |  |  | 0
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk < 1.33 items are listed in the attachment. Following item: FT_G Sensor Resultant_0.66: MEE will discuss with DEE if it needs to modify the spec. | G Sensor Resultant is expected to be confirmed before 6/6. @Yeh,Richard、Broady, Eric | MFG EE | 2022-06-05 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Process validation | 3.D-13 | Review PR issue in PRWeb (MP block issue) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | Mechanical vibration failed | Refer to 3.B-5. | MFG ME | 2022-06-02 16:00:00.0000000 +00:00 | 2022-06-01 10:05:00.6562919 +08:00 | 1
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate: DE_100%. ME_83%. Not up-to-date: 11 items. | There are 6 items undergoing. 145-03955-00, 145-03956-00, 145-03956-01, 145-03957-00, 145-04038-00, 330-01916-02 All the items will be completed before 6/3. | MFG ME/DE | 2022-06-02 16:00:00.0000000 +00:00 |  | 0
1 | OEM Auto | IMWW23 | GMLA #1 | 2021-12-14 15:14:25.6513114 +08:00 | Process validation | 1.D-3 | Strain Gauge measurement result of latest PCB version -- De-panel/Screwing process measurement if tooling pats/ mock-up parts are ready | Strain gauge evaluation has been completed in 12/9, and the verification is expected to be completed before 12/23 | PQE will work with NPI PE to check strain gauge in router station, the result would expect in Jan/B. | PQE | 2022-01-03 16:00:00.0000000 +00:00 | 2022-01-04 10:35:47.8027381 +08:00 | 1
1 | Automotive | Dezl Headset | GMLA #3 | 2022-02-08 13:12:11.5392024 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01114-00 hasn't turned A yet. | ECO#236858 was effective on 2/15. | MFG EE | 2022-02-14 16:00:00.0000000 +00:00 | 2022-02-15 15:52:01.6236488 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 7" | GMLA #2 | 2022-01-26 17:46:50.3929354 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%, ※SMT 1. ATE (53.39%)_常溫充電電流¦Room temperature charging current ※ASSY 1. CT (12.37%)_機台溫度 2. HT (11.34%)_機台溫度 3. ST (10.53%)_MIC MAX Amp.(dB) - Compare with Golden 4. FT (35.42%)_C/No by ref | ※SMT 1. ATE: 15.25%_ Room temperature charging current - Root Cause: MPS does not have this test item and it’s additional test item for EE. - Action: Remove this test item in ITMXP. ※ASSY 1. CT/HT: 12.37%/11.34%_Unit Temperature - Root Cause: DUT didn't stay in chamber with enough time. Operators take the unit out of the cooling chamber too early. - Action: Ask operator in PR line to follow setting time to take the DUT out. In addition, it will be improved by MP line with cooling conveyor. 2. ST: 10.53%_MIC MAX Amp.(dB) - Compare with Golden - Root Cause: The samples don’t put in the right position. - Action: Will actually implement the SOP and keep tracking in next build. 3. FT: 35.42%_C/No by ref - Root Cause: The spec is change to +/- 1.5. Some units’ test results are closed but out the spec. - Action: PR will separate to FT1 and FT2 to verify new FT fixture can efficiently avoid noise. @Tsai, Benson(EE) | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | Yield rate < 95% 1. HTMTF (90.4%)_Start preview (photo) 2. CCM_3in1 (94.84%)_Check DPC status | 1. HTMTF (90.4%)_Start preview (photo) -Failure description: ‧ SW issue. -Root cause: ‧ OLA and TW S/W team are working on it. 2. CCM_3in1 (94.84%)_Check DPC status -Failure description: ‧ Check DPC status -Root cause: ‧ DUT must pass CCM_B before testing CCM_3in1, these failed units didn't pass that first. | NPI/EE/ME/DE | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10% 1. FT (88.89%)_DR SD Card Status 2.ProdScan (81.48%)_電池電壓¦Battery Volt. 3.HT_CCM_B (38.43%)_Start photo preview 4.ST (30.56%)_Start Preview 5.HTMTF (21.21%)_Start preview(photo) 6.CCM_3in1 (19.72%)_Check DPC status 7.RTESN (17.97%)_C/No值¦C/No | 1. FT (88.89%)_DR SD Card Status -Failure description: ‧ SD card can't be read. It will pass after insert the card again. -Root cause: ‧ OLA is analyzing this problem 2.ProdScan (81.48%)_電池電壓¦Battery Volt. -Failure description: ‧ Battery voltage too high or too low. -Root cause: ‧ Charging station hasn't been fixed at FFP. -Action: ‧ NPI will set the charging process after HT during manifest. 3.HT_CCM_B (38.43%)_Start photo preview -Failure description: ‧ Same as yield rate < 95% issue 1. | NPI/EE/ME/DE | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezl OTR Series 2022 - 6" | GMLA #2 | 2022-01-26 17:46:07.4636136 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%, 1. RTESN (17.07%)_C/No值¦C/No 2. ST (31.71%)_MIC MAX Amp.(dB) - Compare with Golden 3. FT (18.29%)_C/No by ref | 1. RTESN: 17.07%_ C/No - Status: It may be the equipment is not set up well, and this problem has not been found in DriveSmart 66. Still under analysis, will keep tracking in next build. @Tsai, Benson(EE) 2. ST: 31.71%_MIC MAX Amp.(dB) - Compare with Golden - Root Cause: The testing program has problem when choosing golden sample let ST golden is lower 10 dB than other units. - Action: Will select a new golden before PR. 3. FT: 18.29%_C/No by ref - Root Cause: The spec is change to +/- 1.5. Some units’ test results are closed but out the spec. - Action: PR will separate to FT1 and FT2 to verify new FT chamber can efficiently avoid noise. @Tsai, Benson(EE) | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
2 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | FT2 85% Max Side Lobe0 | - Failure description: Black box/Cable damage by electric short - Root cause: Issue found: the connector touch the water - Action: PDO will redesign the cable holder to avoid the same happen during the movement or testing. - Update: Due to the robot motion change, the cable directly to be redefined, the team decide to fix the cable by short-term method, by monitoring the stability with robot path, the PDO team will provide the design to fix the cable. | NPI | 2021-12-30 16:00:00.0000000 +00:00 |  | 0
2 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | FT2 37.5% Max Side Lobe0 & Delta IQ0 | - Failure description: Black box/Cable damage by electric short - Root cause: Issue found: the connector touch the water - Action: PDO will redesign the cable holder to avoid the same happen during the movement or testing. - Update: Due to the robot motion change, the cable directly to be redefined, the team decide to fix the cable by short-term method, by monitoring the stability with robot path, the PDO team will provide the design to fix the cable. | NPI | 2021-12-30 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Edge Explore 2 | GMLA #2 | 2022-03-03 10:56:18.6674347 +08:00 | Process validation | 2.D-8 | FFP Final Yield Rate (FYR) review -- Target of each station: ≥ 95% | Baro final yield rate 92.19% not meet the target | The breathable membrane is contaminated, caused the ventilation rate decrease. Enlarge the vent hole to reduce the risk of contaminant blockage (ECO#238062_2/23 completeD) Still see 2 pcs in PR build but fail rate is lower than 1%. Will modify the PTFE process to outsourced process for improvement. | MFG ME | 2022-04-14 16:00:00.0000000 +00:00 | 2022-05-04 15:46:14.1119877 +08:00 | 1
2 | Fitness | Edge Explore 2 | GMLA #2 | 2022-03-03 10:56:18.6674347 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate not meet the target <10% ※SMT 1. ATE (16.79%)_Suspend Current ※ASSY 1.Baro (15.63%)_0.5 ATM diff with golden | ATE: Some units have the opportunity to pass the retest. Will start the break down test next week. -> closed and tracking by GMLA3 Baro: The breathable membrane is contaminated, caused the ventilation rate decrease. Enlarge the vent hole to reduce the risk of contaminant blockage -> already modified PTFE process to outsourced parts. Will validate in PR | NPI | 2022-04-14 16:00:00.0000000 +00:00 | 2022-05-04 15:39:31.5540196 +08:00 | 1
2 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04214-00 is not finalize | Need PjM's help to check the packing status. @Wang, Liz | MFG ME | 2022-01-06 16:00:00.0000000 +00:00 | 2022-01-24 12:46:42.9467676 +08:00 | 1
2 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Product development | 3.A-10 | Verify the test program of SMT and ASSY station before PR build for new SW release | 1. CT/HT ”Temperature” 2. Charging status | CT/HT ”Temperature” & RT2 "Charging status" have been verified OK with updated SW (1.06) in PR2 (20pcs). | MFG EE | 2022-01-02 16:00:00.0000000 +00:00 | 2022-01-05 12:52:19.7823790 +08:00 | 1
3 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Elot failed are show below : 1. High Temp., Min Voltage Life 2. Tumble | 1. Display screen shift after tumble/HT: Verified with the updated SW (1.06) in PR2 (20 pcs) without issues. Keep tracking Pre-MP status. 2. One unit SN tag drops after 20 cycle tumble: Caused by venting hold glue overflow. SOP updated to add twice inspection after venting hole gluing and SN tag pressing. | TWN Lab | 2022-01-03 16:00:00.0000000 +00:00 | 2022-01-05 12:51:26.9505205 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT items not be completed | Completed by 1/3. | TWN Lab | 2022-01-02 16:00:00.0000000 +00:00 | 2022-01-05 12:52:44.7382010 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | Those issue will modify 1. R/C vibrator dispensing 2. RT/FT fixture 3. cleaniness before Display bonding | 1. FT3 noise after immersion: leaning LRA on nearby-ribs. Will modify R/C vibrator dispensing. @Shih, Denzel 2. VT fail after HT & TST: misjudgment from fixture issue. Retest OK after fixture modification. 3. Display bubble after Drop: particle in LOCA. Will reinforce cleaning process and inspection after bonding. Keep tracking in Pre-MP. @Chang, Hunhua | PQE | 2022-02-10 16:00:00.0000000 +00:00 |  | 0
4 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | Lock LCM Connector failed | Plan to apply underfill on I601. | PQE | 2022-01-02 16:00:00.0000000 +00:00 | 2022-01-05 12:52:30.8572618 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Process validation | 3.D-5 | Provide verification result of critical equipment/ fixture -- Refer to critical process/ equipment/ special characteristic definition -- Verification result of ATE/ Auto screw machine/ Display pressing machine/ Auto machine/ ESD result/ PNPMS maintenance SOP | PDO will provide the modified fixtures for verification | The updated fixture has been verified OK. | PDO/AE | 2022-01-03 16:00:00.0000000 +00:00 | 2022-01-05 12:51:40.8745667 +08:00 | 1
2 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 %: Top 1: RT1 (22.31%) Top 2: Pack (19.28%) Top 3: RT2 (18.11%) | 1. RT1_ILP (10.2%) & External Current(3.7%): caused by fixture instability. The updated fixture has been verified OK. 2. Pack_Check Pass Record: Not real issue but a normal control system that is caused by units not being fully tested. 3. RT2_Charging status (6.3%): confirmed as SW issue. Verified OK with the updated SW (1.06). | NPI | 2022-01-03 16:00:00.0000000 +00:00 | 2022-01-05 12:51:54.7647304 +08:00 | 1
1 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review (refer to WQ000329 5.1 ESD < 100V) -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ASSY/ Testing/ Packing/ LCM) -- Measurement position and result | ASSY_Screw fixture up cover ESD measure is failed | An updated fixture is planned to verify by 1/14. Retest pass on 1/24 | PQE | 2022-01-13 16:00:00.0000000 +00:00 | 2022-01-24 18:51:38.0498600 +08:00 | 1
3 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 012-04352-F2 will arrive on 1/26 | 012-04352-F2 ETA pull in to 1/12 (*2k pcs). MP date has been updated to 2/21 and under evaluation to pull in to 2/14. | PID | 2022-01-02 16:00:00.0000000 +00:00 | 2022-01-05 12:52:54.3956528 +08:00 | 1
2 | Fitness | vivosmart 5 (Franklin) | GMLA #3 | 2021-12-27 20:23:35.9823217 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 46% (see reference) | FA is estimated to complete by 1/28. @Lin, Susan | MFG ME/DE | 2022-01-27 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezl OTR Series 2022 - 8" | GMLA #2 | 2022-01-27 14:46:07.4505995 +08:00 | Process validation | 2.D-9 | FFP Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%, ※SMT 1. RB_ATE (47.89)_USB連線¦USB Connection 2. ATE (17.33)_產品檢查¦Product Check ※ASSY 1. ProdScan (93.55%)_PID檢查¦PIDCheck 2. ST (54.76%)_Mic Amp Diff. with Golden 3.FT2_Others (19.2%)_USB開機電流¦USB PwrOn Cur. | ※SMT 1. RB_ATE: 47.89%_ USB Connection - Root Cause: The MB in the ATE fixture is unstable, all boards can pass after retest ATE. - Action: Will change the MB of fixture and modify the retry times of program. Also, make a cycling test before PR and keep tracking in next build. 2. ATE: 17.33%_ Product Check - Root Cause: SW is not ready. - Action: It was resolved after changing to SW 0.22. - Evidence: This issue is solved by verifying with RV/Camper project. ※ASSY 1. ProdScan: 93.55%_ PIDCheck - Root Cause: SW is not ready. - Action: It was resolved after changing to SW 0.22. - Evidence: This issue is solved by verifying with RV/Camper project. 2. ST: 54.76%_ Mic Amp Diff. with Golden - Root Cause: The sound of DUT is too low. - Action: After modifying the test program then pass, and keep tracking in next build. 3. FT2_Others: 19.2%_ USB PwrOn Cur. - Root Cause: The OP boot the unit unexpectedly causing low battery. - Action: Will try to add a mechanism which can only boot when cable is connected to avoid unexpected boot, and keep tracking in next build. | NPI | 2022-03-31 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 %: Top1: FR255s_CT(114.2%) Top2: FR255s_HT(88.82%) Top3: FR255s_RT1(80.7%) | All failed issues are GPS items, will add spacer and verify at Asia PR build. [04/27] Latest Data: Fail rate: CT 1.21% (18/1493), HT 0.78% (11/1415) Potential Cause: Material tolerance (quality) Action: (Short-term) ME/MPPE: Use clip to fix the antenna with the rear case in certain shape to have the gap in-spec (Will divide one job to validate the new process in this week) (Long-term) ME: Have the material quality be stable (ME will validate the new antenna in May/M) | NPI |  | 2022-04-27 14:28:26.1844039 +08:00 | 1
1 | Fitness | Forerunner 255S | GMLA #3 | 2022-03-31 21:11:19.7851428 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk result < 1.33: Top1:LRA Freq. (0.56) Top2: GPS L1 by ref (CT/HT/RT1/FT1) Top3: GPS L5 by ref (CT/HT/RT1/FT1) |  | NPI |  |  | 0
1 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | CC test is complete but still wait for FT to check the test result | 8 pcs CC test samples had done and passed the FT test on W15 | PQE | 2022-04-11 16:00:00.0000000 +00:00 | 2022-04-14 14:13:04.6195514 +08:00 | 1
2 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ASSY 1. Array 10.26%: RX90(800 KHz) 2. IR 20.06%: 確認 array 有沒有斷面 heating 50s 3. FT2 61.32: Target Max 2 | The test items will be adjusted, the detail shown below 1. Target Max: Add the delay time. EE will do the test data collection and provide it to the design team 2. IR test: OP judgment issue. PE will keep reinforcing the OP inspection skill. 3. Array ATE: By reviewing the data, the results showed a bit lower with the spec, the team will discuss with EE if have any possibility to adjust the limit. | NPI | 2022-04-24 16:00:00.0000000 +00:00 |  | 0
1 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | ASSY 1. Target Max 1: 0.76 2. Target Max 2: 0.44 3. Delta IQ0: 0.65 4. Bottom IQ0: 0.42 5. Bottom IQ1: 0.5 | 1. The target Max was commented by EE and will do the test data collection by releasing the new SW/ test criteria. @Chiu, Kev@Coleman, Aaron 2. Delta IQ/Bottom IQ CpK only for reference. | NPI | 2022-04-24 16:00:00.0000000 +00:00 |  | 0
3 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Process validation | 3.D-13 | Review PR issue in PRWeb (MP block issue) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | OLA find the ghost dot issue in lake test | 1. Testing - Add the Bottom IQ in FT2 for inspecting the failure. 2. The design team created a dicing validation with the single blade setting and a new dicing fixture for investigating the root cause. | NPI | 2022-04-26 16:00:00.0000000 +00:00 |  | 0
0 | Marine | Panoptix PS70 - (SSMB) | GMLA #1 | 2021-12-23 14:17:03.0942310 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | Need to release the 004-MPS and add in BOM |  | MFG EE |  |  | 0
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #3 | 2022-01-26 10:15:34.6385814 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Life Run-in Test/ Salt Fog Test/ Salt Water immersion Test/ Validation Run-in Test are testing | 1. Salt Fog Test and Salt Water immersion Test are completed on 2/12 2. Life Run-in Test and Validation Run-in Test are testing. Expected completion date is 5/E | TWN Lab |  |  | 0
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #3 | 2022-01-26 10:15:34.6385814 +08:00 | Process development | 3.C-4 | Update Flow Chart for PR build -- Special characteristic should be included and must correspond with D/PFMEA | No ASSY flow chart | ASSY Flow chart had done the review and update | NPI |  | 2022-02-18 08:29:39.0547688 +08:00 | 1
2 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #3 | 2022-01-26 10:15:34.6385814 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | FT2 24.88%: m10db Beamwidth Degree0 | The test criteria were redefined and updated to the MPS | NPI |  | 2022-02-18 09:01:01.0112032 +08:00 | 1
2 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #3 | 2022-01-26 10:15:34.6385814 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME FA rate is 83% | 2/15: FA 91% ME will finish it before 2/25 | MFG ME | 2022-02-24 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Product development | 3.A-9 | Unit/ Accessory: Update test coverage rate evaluation based on 004-MPS - Target: 100% | Test coverage can't be evaluated because Tacx doesn't provide 004 document. | As a MP transfer product, all test program was developed by TACX so no 004 document is available. | MFG EE | 2021-04-14 16:00:00.0000000 +00:00 | 2021-04-20 20:12:51.3266752 +08:00 | 1
0 | Marine | GT36/GT56 UHD Transducers | GMLA #1 | 2020-12-03 18:26:36.2100000 +00:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 456 |  |  |  |  | 0
3 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Product validation | 3.B-5 | DVP&R/ ELOT report summary (result review) -- Action plan for test fail items | For ANT+ signal loss issue, lab will arrange more test. | After 4 hours long duration Ant+ connection test, there are not Ant+ lose signal phenomenon, Ant+ lose should be beta user Edge hardware issue. | TWN Lab | 2021-03-30 16:00:00.0000000 +00:00 | 2021-04-01 13:47:59.1985050 +08:00 | 1
0 | Fitness | Edge 1040 | GMLA #1 | 2021-02-19 17:29:48.3957364 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | There is no preliminary 004-document release to the BOM. | Updated | MFG EE | 2021-03-11 16:00:00.0000000 +00:00 | 2021-04-19 15:21:25.1547847 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Process validation | 3.D-11 | Fixture ESD protection review -- Remeasurement is any modification to fixture -- Fixture is made by anti-ESD material -- ESD voltage measurement result -- Production related fixtures (SMT/ Assy/ Testing/ Packing/ LCM) -- Measurement position and result | 1. Air ionizer and ESD vehicle will be ready before 4/5. 2. Material trolley is expected to be be improved when air ionizer is ready. | Air ionizer can work, confirmed ESD passed. | PQE | 2021-04-07 16:00:00.0000000 +00:00 | 2021-04-20 23:27:23.5667060 +08:00 | 1
2 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #2 | 2021-11-23 19:05:05.8673113 +08:00 | Process development | 2.C-5 | Release preliminary Working Instruction for FFP build -- Special characteristic should be included and must correspond with D/PFMEA | 1. No Pre-assembly (Dicing) and Test SOP 2. Main assembly SOP is for LVS32 so it needs to be updated | The SOP will be done and updated by Dec.9th | NPI | 2021-11-29 16:00:00.0000000 +00:00 | 2021-12-22 13:42:25.4172484 +08:00 | 1
1 | Fitness | NEO 2T Taiwan Production | GMLA #3 | 2021-03-31 18:51:43.0407068 +08:00 | Others | 3.F-3 | Define skill requirements (defined in WH000005) of each station -- Any update for the skill that needed in each station | CFT should discuss whether the high torque process needs to be defined in WH0000005. | Will be covered by general screw driver training. | NPI | 2021-04-19 16:00:00.0000000 +00:00 | 2021-04-20 22:32:39.6984563 +08:00 | 1
1 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT hasn't been started yet. | ELOT starts from 10/29 | TWN Lab | 2021-11-18 16:00:00.0000000 +00:00 | 2021-11-10 10:20:40.4235465 +08:00 | 1
1 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | BOM not turn version A: ※ ME part: - 145-03939-00/145-03939-10/145-03939-20/145-03939-30/145-03939-40/145-03939-50 - 117-01867-00/117-01867-01 - 700-00182-00/700-00182-01 ※ EE part - 012-04457-JT | Target to release all drawings by 5/9. @Zheng, Eason 012-04457-JT has been removed from BOM. | NPI/ME/DE | 2022-05-08 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | 249-01662-00 VIP will be ready when FA status completes. Before FA is finished, there will be a temporary VIP for IQC. | [DE] 249-01662-00 VIP has been sent to supplier and temp VIP has been set for Garmin IQC | MFG EE/ME/DE | 2021-11-28 16:00:00.0000000 +00:00 | 2021-10-21 17:52:21.4811659 +08:00 | 1
3 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ※1 ELOT issue found 1. Body and Wearable Chemicals(1/1) | [Non-power SKU] No VT fail issue and is confirmed this issue can be waived. | TWN Lab | 2022-05-03 16:00:00.0000000 +00:00 | 2022-05-04 19:26:10.5972136 +08:00 | 1
1 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | ELOT is progressing: ※1 item did not start: RF Immunity Conducted ※4 items under testing: Accelerated Weathering Xenon/UV-A/UV-B/Salt Fog. The expected complete date:2022/5/13 | Estimated to complete by 5/6. @Wu, Steve | TWN Lab | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Process validation | 3.D-8 | PR Final Yield Rate (FYR) review -- Target of each station: ≥ 97% | Yield Rate not meet the target >= 97% ※SMT 1. ATE 96.26% ※Assy Testing 1. RT3 94.74% | 1. Suspend current: suspected to be caused by SW behavior, under further analysis. @Liu, Nathan 2. FYR of RT3 is actually 99.24% and no specific failures to highlight. | NPI | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10% issue ※SMT 1. ATE 39.88%: Power path selection 1_VUSB ※Assy Testing 1. RT1 23.36%_Check Map Checksum 2. VT 14.89%_開始密氣測試 3. CT 11.31%_充電狀態¦Charging Status 4. HT 10.22%_Temperature | 1. RT2 checksum: Will modify to manifest for MP to avoid potential operational error. @Liu, Nathan 2. ATE_Power path selection 1_VUSB: Caused by poor contact of fixture test points. Plan to modify on powered SKU SMT build on 5/10. @Cheng, Danny(PE) 3. RT1 ESN check in: Auto Check out by test program, need to Check in by manual before testing. | NPI | 2022-05-09 16:00:00.0000000 +00:00 |  | 0
1 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Process validation | 3.D-10 | PR Cpk result review -- Target of each item: ≥ 1.33 | Cpk not meet the target <1.33 1.SMT (1) ATE_BAT3.8V開機電流¦BAT3.8V startup current: 0.62 (2) ATE_BAT4.2V開機電流¦BAT4.2V startup current: 0.99 (3) ATE_Suspend Current: 1.13 (4) ATE_待機電流¦OFF Current: 0.64 (5) ATE_Fuel Gauge Battery Current Accuracy: 0.69 (6) ATE_PMIC Fuel Gauge battery charging Voltage: 0.61 2.No Cpk review on Assy Testing | 1. ATE_BAT startup current: All pass lower limits, confirmed as low risk. 2. Suspend current: suspected to be caused by SW behavior, under further analysis. @Liu, Nathan 3. Off current: spec will be modified. Will monitor powered SKU SMT result (5/10) for further assessment. @Liu, Nathan | NPI | 2022-05-09 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl watch | GMLA #3 | 2021-10-20 18:19:12.8896539 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | Display FA ratio 50%. 249-01662-00 and 470-00902-11 are ongoing. | [DE] FA data has been uploaded. Target complete date 11/30 | MFG ME/DE | 2021-11-29 16:00:00.0000000 +00:00 | 2021-12-08 14:28:00.2255292 +08:00 | 1
0 | Marine | BlueNET Gateway | GMLA #1 | 2021-09-23 14:42:14.5550785 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004-MPS preliminary release to the BOM | Olathe has released 004-01137-00 and added it to the BOM on ECO#230862. | EE | 2022-02-15 16:00:00.0000000 +00:00 | 2021-10-14 09:51:14.5690671 +08:00 | 1
3 | Marine | FUSION - Apollo Amplifiers 6 / 8 channel | GMLA #2 | 2021-05-13 19:27:09.9899413 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | ELOT fail 6 CH (1) Drop fail (1/1 NG): Screw loose 8 CH (1) Salt Fog fail (1/1 NG): Cannot turn on | 6 CH 1. Drop >> After retested with right Dim. screw part, result is passed. 8 CH 1. Salt fog >> After Fusion EE's analysis, the testing result could be acceptable. | MFG ME | 2021-06-10 16:00:00.0000000 +00:00 | 2021-06-25 10:30:21.7338690 +08:00 | 1
3 | Outdoor | fenix 7 | GMLA #2 | 2021-01-11 16:05:07.3150054 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | Failed item: 1. Drop 2. Mechanical vibration 3. Wear resistance test 4. Scratch resistance test 5. Shock resistance | 1. Units heat up after drop tests, no water leakage. Verified with new SW w/o issue. 2. No button board pop out issue in PR, close. 3. for reference only 4. for reference only 5. units heat up after shock resistance tests. Verified with new SW w/o issue. | TWN Lab | 2021-03-09 16:00:00.0000000 +00:00 | 2021-05-19 13:08:43.2150935 +08:00 | 1
3 | Marine | Surround View Camera System | GMLA #2 | 2021-05-25 19:33:14.2680667 +08:00 | Process validation | 2.D-13 | Review MP block issue (PR issue in PRWeb) -- Issue severity review -- Progress of failure analysis -- Schedule of action plan | MP blocker issue : SW (ESD/ D3) | 1. ESD fail at Rogers lab (external lab) Root Cause: Need SW update to resolved this issue. Should auto-reset when camera streaming crash. Action: SW updated. ESD re-test pass at Rogers lab on 6/24. TWN lab will also test ESD on WK28. ELOT : 高溫/鹽霧測試需等待PR機台確認 2. CCMW issue (D3) Root Cause: SW delay due to supplier Action: Add extra FFP2 build and verified new SW. Still need to key in command manually. Keep tracking new SW release. | NPI | 2021-08-12 16:00:00.0000000 +00:00 |  | 0
3 | Outdoor | inReach Mini 2 | GMLA #2 | 2021-06-25 15:56:03.0851231 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 2 ELOT items failed: (1) Electrostatic Discharge (ESD) Immunity test (1/2 NG): AC charger -25KV on VT's hole causes the display without image. (2) Drop (1/4 NG): Can not turn on after 90 cm drop | <ESD> Waiting Yarmouth to provide to GPN of IRmini2 optional adapter (362-00112-00) so QA lab could do ESD test again. <7/8> test again with 362-00112-00 and passed <Drop> After replacing the failed unit PCB with another one, the unit appeared functional(could be turned on). We found soldering damaged after drop and will do red ink test on I100 for double check. Raw material analysis: found crack symptom at less than 250 degree. Next analysis will go for hot stress. (no similar symptom on Venu 2) [0929]摔了10台都pass | NPI/EE/ME/DE | 2021-09-14 16:00:00.0000000 +00:00 | 2021-09-29 22:16:15.7708926 +08:00 | 1
0 | Marine | BlueNET Switch | GMLA #1 | 2021-09-23 14:42:22.7081766 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004-MPS preliminary release to the BOM | Olathe has released 004-01137-00 and added it to the BOM on ECO#230862. | EE | 2022-02-15 16:00:00.0000000 +00:00 | 2021-10-14 09:50:44.3590744 +08:00 | 1
0 | Outdoor | Marq (Gen 2) | GMLA #1 | 2022-02-10 07:38:57.7929389 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004- is NRL and not added in BOM | 這個請@Dorris David -Cooper |  |  |  | 0
2 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | No 174-packing instruction released on BOM | SOP updated(ECO#242876), will initiate ECO to update the BOM. Update: ECO#243004 submitted. | NPI | 2022-05-26 16:00:00.0000000 +00:00 | 2022-05-19 09:54:58.7215300 +08:00 | 1
2 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | ※SMT_ATE 10.07%: Iridium Tx Burst CH01 diff | Change the golden samples from PR and result pass by verified in small build. | NPI | 2022-06-02 16:00:00.0000000 +00:00 | 2022-05-24 15:41:59.7931605 +08:00 | 1
0 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #1 | 2021-07-12 15:01:33.0485318 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | Preliminary 004-01118-00 has been released. Need to add to the BOM. | Preliminary 004-01118-00 has been released. Need Olathe help to add in the BOM. -->PjM will get the 004 MPS in the system by WK31. after confirmed no change is required by the Electrical Engineer. | MFG EE |  |  | 0
1 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | Inspection VIP not ready: - ME part 12 items not ready: 115-03872-0X/115-03873-00/115-03889-00/115-03906-0X/145-03912-XX/253-01437-00/253-01456-00/253-01485-00 - DE part 3 items not ready: 249-01648-00/249-01726-00/470-00922-00 | <ME> Already informed the suppliers to start FA process. Schedule to finish all FA before 6/10 <DE> Estimated Completion Date for 249-01648-00/249-01726-00 : 5/27 Estimated Completion Date for 470-00922-00 : 5/20 | MFG EE/ME/DE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
2 | Outdoor | inReach Messenger | GMLA #3 | 2022-05-16 10:16:27.7824598 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 53% - ME part 12 items not ready: 115-03872-0X/115-03873-00/115-03889-00/115-03906-0X/145-03912-XX/253-01437-00/253-01456-00/253-01485-00 - DE part 3 items not ready: 249-01648-00/249-01726-00/470-00922-00 | <ME> Already informed the suppliers to start FA process. Schedule to finish all FA before 6/10 <DE> Estimated Completion Date for 249-01648-00/249-01726-00 : 5/27 Estimated Completion Date for 470-00922-00 : 5/20 | MFG ME/DE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Edge 1040 | GMLA #2 | 2021-11-16 13:26:53.3160674 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1 ELOT fail items (1) Tumble (1/1 NG): The DUT can not turn on under 20 drops | 1. Some units were using the wrong connector in FFP. Will use the right (JST) connector in PR build. 2. RTV glue will be used to fix the connector in PR build. | TWN Lab | 2022-01-06 16:00:00.0000000 +00:00 | 2022-03-28 17:11:03.2832536 +08:00 | 1
3 | Fitness | Forerunner 55 | GMLA #2 | 2021-02-02 22:59:55.0071821 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | Tumble (100 drop, 1m) Fail but without action plan -Black / Whitestone / Aqua / Grey | Action take and will review in PR1 Close Meeting. Button no feeling: Process + Fixture revise and will have further ELOT tumble test to verify. Lens Leak: Bezel Shelf enlarge and verify in PR2 >> Result is pass | TWN Lab | 2021-03-18 16:00:00.0000000 +00:00 | 2021-04-23 14:07:12.9784648 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | 015-05934-2X needs to add tape instruction on the mic. | Expect to ECO on 04/14. @Chen, Mac [4/15] ECO#239301. | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-15 13:20:55.5581258 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 005-01556-00/011-05927-03/012-04456-21/012-04456-90/012-04456-93/012-04456-99/012-04456-JT/017-04456-00 012-04456-D3/012-04456-G5/012-04456-89/161-05927-00/190-02947-03 haven't turned A yet. | After ECO#240890, remaining GPN: 005-01556-00, 011-05927-03, 012-04456-JT, 017-04456-00, 161-05927-00, 190-02947-03 haven't turned A yet. | NPI/ME/DE |  |  | 0
2 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04206-00 hasn't turned A yet. | Please convert to version A. @Sattler, Karl [4/19] ECO#240723 | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-19 10:43:08.1457871 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01142-00_002、004-01142-50_001 haven't turned A yet. | Please convert to version A. @Sattler, Karl [4/13] ECO#238723. | MFG EE | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-13 10:49:56.7714344 +08:00 | 1
0 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #1 | 2021-02-01 15:45:14.4727398 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 004 is not added to BOM | EE still push Olathe LED backlight test methodology for 004- MPS. | MFG EE | 2021-03-04 16:00:00.0000000 +00:00 |  | 0
0 | Outdoor | Xero C1 Chronograph | GMLA #1 | 2022-01-13 11:16:49.4306781 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01139-00 (version 01) not released to and need to add in BOM | The 004-MPS is uploaded into the BOM by FP1 build. | MFG EE | 2022-03-14 16:00:00.0000000 +00:00 | 2022-03-21 09:19:45.0071993 +08:00 | 1
2 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%: 1. ST (31.4%)_麥克風頻率¦MIC Freq. (10.74%) 2. FT2_Others (24.17%)_Touch Panel DND Check (5%) 3. ATE (18.18%)_快充電流 (4.55%) 4. CT (15.45%)_GPS_L1 by ref (8.13%) | 1. ST (31.4%)_麥克風頻率¦MIC Freq. (10.74%) -Root cause: Mic didn't get the sound from the fixture's speaker. -Action: 1). Add fail retry. Let the speaker make a sound again. 2). The ST fixture is the same as dezl 1000. NPI will take dezl 1000 and dezl 1010 to check the fixture. -Evidence: Need to track the result after modification. 2. FT2_Others (24.17%)_Touch Panel DND Check (5%) -Root cause: This is redundant code. -Action: EE compared the test program with dezl 810 and found it is redundant code. EE already removed the code. 3. ATE (18.18%)_快充電流 (4.55%) -Root cause: Fixture pin issue. It focused on fixture ID=255. -Action: EE will keep tracking and doing cycle tests before Pre-MP | NPI |  |  | 0
3 | Automotive | DriveSmart 66 | GMLA #2 | 2021-03-19 09:16:08.7996452 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | Fail item: 1. HT---wait for Olathe checking SW. 2. Thermal shock---wait for DE analysis. 3. Mechanical Vibration---wait for EE analysis. 4. Power On / Off test---wait for EE analysis. | 1. HT: has passed on 4/9. 2. Thermal shock: has passed on 4/9. 3. Mechanical Vibration: unit cannot power on sometimes. (1) Connection is good based on the CT scanning result. EE found there are scratches on the FPC, and it gets short with the PCB. (2) Reworked units to add foam to prevent the short and rerun the test Pass. 4. Power On/Off test: same with TST, test Pass. | TWN Lab | 2021-03-29 16:00:00.0000000 +00:00 | 2021-06-22 18:03:43.5195104 +08:00 | 1
3 | Automotive | DriveSmart 76 | GMLA #2 | 2021-03-31 19:35:43.4594342 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | 1. Drop (70 cm): 4 units. Six side display fail / 2. Tumble: 1 unit. Display broken after tumble 16 cycles. | - Drop fail is due to particles on the tested concrete floor. Retested PASS from both TWN and Olathe sides. Before each drop, the floor was checked to make sure no large particles on the floor. Confirmed with design team that this issue can be closed. - Tumble fail: confirmed as a reference test. | MFG ME | 2021-04-07 16:00:00.0000000 +00:00 | 2021-04-08 09:45:05.3861248 +08:00 | 1
3 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | TST & Tumble & High Temp., Max Voltage Life are NG | [04-28] Waive and have the MP approval start 1 Bad GPS signal for Operating Hot/Cold Unit Performance、Storage Hot/Cold Unit Performance、TST、High Temp., Max Voltage Life. and tracking by Asia build and Pre MP build 2. Start/Stop no function after tumble 50 times but OLA waive due to RMA rate is acceptable 3. 5atm deflection test fail after tumble due to button leakage but OLA waive due to The button hole diameter/ button pin diameter are all in spec | TWN Lab | 2022-04-10 16:00:00.0000000 +00:00 | 2022-04-28 09:29:59.1769221 +08:00 | 1
3 | Automotive | DriveSmart 86 | GMLA #2 | 2021-04-09 13:23:52.4724997 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | Fail item: 1. Thermal shock._wait for ME check. 2. Bluetooth connection test._wait for EE check. 3. Drop test. 4. Shock test._New mount wait for re-test. 5. Vibration test._wait for new SW. | 1 & 2. Thermal shock & shock test fail (4/4 NG): Material change from POM to PC and test PASS. 3. BT connection fail (2/2 NG): 100% fail for Android phone but PASS for IOS. SW1.22 fixed. 4. Drop fail (4/4 NG): Due to uneven concrete floor. Re-test 4 units pass on 3/31. 5. Vibration test fail (2/2 NG]: Instantaneous power test fail during vibration test. Cable SR modified and verified PASS. | MFG ME | 2021-06-03 16:00:00.0000000 +00:00 | 2021-06-24 09:19:25.6568133 +08:00 | 1
1 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Process development | 3.C-11 | Packing parameter/ program setup (Product scan/ packing/ unlock/ UPC/…) a. Parameter setup base on latest BOM version b. Check if all SW elements (version and checksum) being checked at product scan c. Check if safe power off IOP (10,83,2)_ AOEM only/ factory reset IOP(10,39,2) workable? | 1. Software v7.44 lack lots of font/audio files(language) 2. (WW&Asia SKU)There are some RGN86 (Text files ,006-D8580-36/-37/-41/-42/-43) shown "missing" in the product inventory. | MP SW candidate v9.09 is undergoing ECO#. EE team is verifying. Would keep updated once done. | PQE | 2022-04-10 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry Rate > 10 % : Top1 : FR255_ProdScan_Pack ( 28.24 %) Top2 : FR255_AutoRT1 (22.65%) Top3 : FR255_AutoCT (12.96%) | Higher retry rate concludes in GPS item and Gyro SW issue (already fixed). GPS issue is addressed with stronger spring force while screwing [04/27] The latest test rate is only with 8.32% retry rate and no further failure in following test, also after the CC test. | NPI | 2022-04-10 16:00:00.0000000 +00:00 | 2022-04-27 14:24:07.8352767 +08:00 | 1
2 | Fitness | Forerunner 255 | GMLA #3 | 2022-03-30 10:14:23.1055637 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME 45% (see reference) | The FA process should be ready before 4/30. The blocker is the ANT design change/ housing design change/ rubber pad solution are defined lately. | MFG ME/DE | 2022-04-17 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Product development | 3.A-5 | Update drawing version if any design change (Tolerances need to be well defined in the drawing as well) | 015-05933-2X needs to add tape on Mic. | Expect to ECO on 04/14. @Chen, Mac [4/15] ECO#239301. | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-15 13:20:26.7143295 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 005-01556-00、011-05926-03、012-04455-21、012-04455-90、012-04455-93、012-04455-99、012-04455-JT、017-04455-00、012-04455-D3、012-04455-G5、012-04455-89、161-05926-00 haven't turned A yet. | After ECO#240890 & #240816, remaining GPN: 005-01556-00、012-04455-JT、017-04455-00、161-05926-00 haven't turned A yet. | NPI/ME/DE |  |  | 0
2 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04205-00 hasn't turned A yet, | Please convert to version A. @Sattler, Karl [4/19] ECO#240723 | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-19 10:42:35.0782440 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Product development | 3.A-8 | Unit/ Accessory: Update 004- MPS with final SPEC -- Test program need to be adjusted accordingly -- Release to version 0A -- Add-in BOM | 004-01142-00_002、004-01142-50_001 haven't turned A yet. | Please convert to version A. @Sattler, Karl [4/13] ECO#238723. | MFG EE | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-13 10:49:36.4160651 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 91.67% on 4/9. All the tests will be finished before 4/14. Not finished: 1. Drop 2. Battery disconnect drop | All the tests will be finished before 4/14. [4/15] All the tests are completed on 4/11. | TWN Lab | 2022-04-13 16:00:00.0000000 +00:00 | 2022-04-15 09:26:01.6718287 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 500-10780-00/500-10781-00/590-00109-00 max reflow temp. are less than 250°C | The components less than 250 degrees have been checked by the reflow profile board. The test result passed. The information had been added to SMT VIP. | NPI | 2022-04-11 16:00:00.0000000 +00:00 | 2022-04-12 11:23:46.8521576 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | 105-04455-00 ATE 2.0 is waiting for the fixture ready. | The ATE2.0 fixture will be finished on 04/15, and will do the strain gauge test on 04/18 and cycle test before Pre-MP. @Ho, Tony @Wu, Iris @Ni, Wendy [4/17] ATE 2.0 strain gauge pass. 105-04455-00: De-panel/ ATE 2.0/ Lid assembly/ Screw pass.? (http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04455-00) 105-04455-10: De-panel/ ATE 2.0/ Lid assembly/ Screw pass.? (http://peweb/home/smtvip/vip_StrainGauge.aspx?gpn=105-04455-10) | NPI/PQE | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-17 14:23:39.1116273 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%: 1. ATE (42.63%)_常溫充電電流 (14.21%) 2. ST (26.84%)_Mic Amp Diff. with Golden (10.39%) 3. GSensor (13.1%)_Y max (2.18%) 4. RTESN (12.93%)_GPS_10_L1 (10.78%) 5. FT1_GPS (11.26%)_Check ProductionMap (2.6%) | 1. ATE (42.63%)_常溫充電電流 (14.21%) -Root cause: The unit didn't respond immediately when the iATE board make the order. Thus, ITMXP got the wrong value. -Action: Modify the ATE testing program (add delay time 1s) -Evidence: It performs well after adding delay time 1s. 2. ST (26.84%)_Mic Amp Diff. with Golden (10.39%) -Root cause: Due to the mic loose -Action: NPI will add the procedure of pressing The mic after connecting The Mic cable to The PCB in The SOP. -Evidence: It will be tracking in Pre-MP 3. GSensor (13.1%)_Y max (2.18%) -Root cause: The fixture direction in PR line and MP line is different which causes the wrong output data. -Action: EE modified the program with the correct direction. -Evidence: DUT output the right data after the modification. | NPI |  |  | 0
1 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Process validation | 3.D-14 | Golden sample and bad sample ready and registered in internal system -- Expired date set-up for golden sample and bad sample | 1. CT/HT/FT*2 for CN_not provided yet. 2. ST*2_not provided yet. | All the golden samples will be provided before 4/15. | MFG EE/ME/DE | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezl OTR Series 2022 - 8" | GMLA #3 | 2022-04-11 18:37:17.4136198 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME: 94% (not up-to-date * 5), DE: 100% | MME will complete FA on 04/26. @Chen, Mac | MFG ME | 2022-04-26 16:00:00.0000000 +00:00 |  | 0
0 | Automotive | Dash Cam Live (LTE) | GMLA #1 | 2021-01-18 10:07:42.9713788 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01090-00 not release the preliminary version on the BOM | [Update] 004-01090-00 has been released under 010-02619-00 and 010-02619-10 | MFG EE | 2021-07-11 16:00:00.0000000 +00:00 | 2021-07-11 19:02:23.2459575 +08:00 | 1
3 | Automotive | Tread - XL (10") | GMLA #2 | 2021-09-07 19:18:09.4652294 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Operating Hot/cold performance (2/2 NG): Found the TP function can't work.. 2. Salt fog (1/1 NG): Found some pins rust after test. 3. IPX6 (1/1 NG): Found the TP fails after the test. 4. Accelerated Weathering Xenon (Q sun) (1/1 NG): Found the display bubble. 5. Tumble test (1/1 NG): Found the TP broken. (70 cycles). | Fail Item (1) (3): TP function fail Analysis: Poor FPC contact is caused by the wrong FPC thickness design Action: S/T: Stick mylar film on FPC, re-test pass. L/T: ME modify the FPC size from 0.2mm to 0.3mm for MP. ECO#229287 Fail Item (2): Some pins rust. Analysis: Some pads on units for antenna without protection are rust after 168h test. Action: The criteria of salt fog should be 48h, 168h for reference, and also the coating thickness will be checked. Fail Item (4): Display bubble Analysis: The bubble was found after 624 hours but didn't become serious. Low risk. Fail Item (5): TP broken. (70 cycles) The test item is for reference. Low risk | ME/DE | 2021-09-29 16:00:00.0000000 +00:00 | 2021-10-01 10:33:12.2320934 +08:00 | 1
0 | Automotive | BC50 & BC50 IR | GMLA #1 | 2021-06-09 15:55:16.3554894 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No preliminary 004-MPS released and not added to the BOM since the core IC will be EOL that causes the large re-design on the v2 board. | Plan to complete before WP design review- 7/23 | MFG EE | 2021-07-22 16:00:00.0000000 +00:00 | 2022-04-13 09:45:34.6363902 +08:00 | 1
3 | Fitness | Varia Radar Camera (RCT715) | GMLA #2 | 2021-09-23 16:20:34.9451728 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 5 ELOT fail items (1) Thermal shock (1/2 NG): Recording quality get fuzzy (2) Accelerated Weathering UV (1/1 NG): No sound during recording (3) Body and Wearable Chemicals (1/4 NG): VT fail. 470-00851-00 peeling with Front case. (4) Mechanical Part Cycle (2/2 NG): weather cap cannot sealed perfectly (5) Tumble (2/2 NG): SD Card tenon loose, can't record (50 cycles & 80 cycles) | [Monitor in PR, design team has changed MPS, retest pass] 1. After TST > recording quality get fuzzy *1 - Analysis: Wrong testing specification set by Design team. - Camera temperature resistance: -20 ~ 60, TST pass after retest with -20 ~60C. - Follow up: The fail unit cannot recover after return normal temperature, confirming the analysis with design team. (PND product temp spec: -40 ~ 85C) [Monitor in PR, Define cleaning method] 2. After UVB > no sound in recording*1 - Acoustic engineer is checking the micro condition with tearing units apart - Root cause: particles attache on membrane while cleaning. [Closed] 3. Sunscreen > Camera lens peeling and fail at VT8 - Analysis: Confirmed that this failure was seen on previous products - Action: Design team accept it and proceed with no changes [Monitor in PR] 4. Weather cap 3,000 cycle > weather cap cannot seal perfectly - Action: Weather cap is under tooling modification. 145-03649-00 ECO#: 230083 9/16 [Retest pass with adding foam] 5. Tumble & Vibration > SD Card tenon loose, can't record (SD卡槽鬆脫無法錄影) *2 (Tumble fail at 50 cycles & 80 cycles) - Action1: Add foam thickness from 0.75m to 1.35mm to increase compression on the SD card connector. Retest tumble and pass. - Action2: Modify the SD card connector with 0.2mm to prevent the door from causing the SD card holder to be partially unlocked. ECO#230550,9/25 | TWN Lab | 2021-10-31 16:00:00.0000000 +00:00 | 2021-11-30 10:07:09.8981739 +08:00 | 1
3 | Outdoor | fenix 7X | GMLA #2 | 2021-01-15 14:36:26.0851051 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | *Under analysis: 1. Operating Hot/Cold Unit Performance(revealed by 1/14) *Failed item with action: 1. Wear Resistance test 2. Scratch Resistance Test 3. Shock resistance | Operating Hot/Cold Unit Performance -> wait ME to analyze. This result just revealed on 1/14 [0121 update] leak from charging pin gasket. This is a known issue from HDC bezel chamfer manufacturing, and already been solved. | TWN Lab | 2021-02-09 16:00:00.0000000 +00:00 | 2021-02-03 08:48:58.1766667 +00:00 | 1
3 | Automotive | Tread - SXS (8") | GMLA #2 | 2021-07-26 09:04:50.6196716 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Failed item: 1. Thermal shock (4/4) - VT2 fail. 2. High temp,. Max Voltage Life (1/1) - Can't power on. 3. High temp,. Min Voltage Life (1/1) - VT2 fail. 4. Drop (1/4) - Screen broken. 5. Salt fog (1/1) - Pogo pin rust. 6. Accelerated Weathering Xenon (1/1) - VT fail 7. Accelerated Weathering UV(1/1) - VT fail 8. Tumble (1/1) - VT fail 9. Mechanical Vibration - VT fail 10. Water / Dust Resistance (4/4) | 1. Thermal shock/ High temp,. Min Voltage Life/ Accelerated Weathering Xenon/ Accelerated Weathering UV/ Mechanical Vibration - VT2 fail. - Root cause: Leakage point caused by the case gap which between soft and hard case material. - Action: Add glue and re-do the test. Will do tool modification and test in PR build. - Evidence: 7/23 test result of unit with glue pass. 2. High temp,. Max Voltage Life (1/1) - Can't power on. - Root cause: Buck has bad transferred efficiency which causes the surge. It probably causes capacity shorted with ground suddenly and PCB burned out. - Change the PCB circuit in PR build to reduce the ascending temperature from the voltage in. The switch frequency of a buck resistance change from 2100 kHz to 400 kHz. It will be verified in PR build. 3. Drop (1/4) - Screen broken (TP function is okay). - Root cause: Failure could be caused by the foreign object, the risk is judged as low. - Action: Test 2 more units. - Evidence: Units pass the test on 7/29. 4. Salt fog (1/1) - Pogo pin rust. (VT PASS) - Unit failed under 168hrs 5% Sol w/o power on. - Action: Re-test unit with power on. - Evidence: Unit with power on pass 168hr test on 8/10. 5. Tumble (1/1) - VT fail - Issue: Antenna fell apart. - Action: Change the glue of antenna from RTV 179 to epoxy 203. - Evidence: Verification was completed and passed VT. 6. Water / Dust Resistance (4/4) - unit turned on during test - IPX6 failure is under analysis by MME & OLA. - MME modify mount pogo pin rubber . It is expected to be re-tested on 8/20. | TWN Lab | 2021-09-07 16:00:00.0000000 +00:00 | 2021-10-28 11:35:53.1570766 +08:00 | 1
2 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | There is no 174- in the BOM. | Pending on packing SOP review, targeting to complete review in end-May. | NPI | 2022-05-30 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Thermal Shock (1/2)_GPS failed 2. Tumble (1/1)_display abnormal 3. High Temp., Min Voltage Life (1/1)_display abnormal | 1. Thermal Shock (1/2)_GPS failed -Failure description: GPS fail -Root cause: After IOP 10/515 to restart GPS, GPS function normally. EE doubts it is related to the unit hardware. -Action: Lab arranged TST test again (LMS-0021562-2-TW) with the same unit, and will check the GPS status after TST. The result is pass. This issue will be tracked in PR2 ELOT. (PR CC TST 10 units all pass) (ELOT: -40℃ to 85℃ dwell time 1hour 50 cycles) (CC: -40℃ to 85℃,dwell time 1 hour 6 cycles) 2. Tumble (1/1)_display abnormal [Close] -Failure description: Abnormal display after tumble 60 cycles. The other functions pass. -Action: DE's comment: tumble test for PND display is only for reference. It's over display spec and would not have the solution. 3. High Temp., Min Voltage Life (1/1)_display abnormal [Close] -Failure description: 144hrs found the display screen abnormal. Display function recovery at room temperature. -Root cause: The unit has been shipped to OLA. If the unit function normally at room temperature, it should be pass (the criteria defined in ENG 0072). This unit is pass of this ELOT. | TWN Lab | 2022-05-19 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Product validation | 3.B-11 | CC test result (if PR have CC test requirement) | TST fail *1. It is caused by the battery connector loosening. | -Root cause: This shop order is assembled by new operators. -Action: Operators will be well trained. It will be tracked at pre-MP shop order's CC test. | PQE |  |  | 0
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 500-02020-01, 500-10780-00, 500-10781-00, 590-00109-00 on 012-04166-00 is 245 degrees only. NPI will do the thermal test of PCB. | SMT NPI and MPPE arrange the PCB thermal test for components with max reflow temp 245 degrees. The thermal test result will be provided before W19. @Derek, Weiting | NPI | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Process validation | 3.D-3 | Strain Gauge measurement result of latest PCB version -- All process including de-panel, SMT, PCBA version, ASSY | Check RF screw solution with DME. Screw sequence MB -> RF with new screw 211-71260-40 in 1.6 kgf-cm torque. Wait for DME's reply. | 1.6 kgf-cm | PQE | 2022-05-12 16:00:00.0000000 +00:00 | 2022-05-13 16:52:11.5305370 +08:00 | 1
2 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10%: 1. VT1(76.27%)_大漏氣_未抽至1120 (25.42%) 2. ATE (47.83%)_100% SPK (14.49%) 3. RTESN(35.59%)_機台溫度 (13.56%) 4. FT2_GPS(18.64%)_GPS_L5 by ref (8.47%) 5. GSensor(18.64%)_Diff Y (5.08%) 6. Gyro(16.95%)_Gyro Data X軸檢查 (CCW #1) (10.17%) 7. CT(13.56%)_Check ProductionMap (5.08%) 8. Baro(11.86%)_0.5 ATM diff with golden (5.08%) 9. FT3_Others(10.17%)_Touch Panel DND Check (3.39%) | 1. VT1(76.27%)_大漏氣_未抽至1120 (25.42%) -Root cause: Assembly problem / connector door is not closed. -Action: This build is executed by new employees. They are not familiar with the process. NPI will well train new employees during the next production. -Evidence: Tracking by Tread 8" shop order. Job 15899157 (4/E), VT1 retry 10.63%, 大漏氣_未抽至1120 2.99% 2. ATE (47.83%)_100% SPK (14.49%) -Root cause: Should be CPU soldering issue -Action: The same issue as Tread 8". It is solved by reflow temperature modification. 3. RTESN(35.59%)_機台溫度 (13.56%) -Root cause: The battery connector is not fully plugged in. -Action: This build is executed by new employees. They are not familiar with the process. NPI will well train new employees during the next production. -Evidence: Tracking by Tread 8" shop order. Job 15899157 (4/E), RTESN retry 5.32%, 機台溫度 2.99% | NPI | 2022-05-26 16:00:00.0000000 +00:00 | 2022-05-12 11:32:06.2511991 +08:00 | 1
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Supply chain/ supply of part | 3.E-1 | Supplier inspection preparation -- Finalize VIP should deliver to supplier (including test fixture/ test jig) -- Align Garmin IQC inspection VIP with supplier's IPQC/ OQC plan -- Check if Garmin provide our own test jig/ equipment/ gauges to supplier (need to provide verification report and working instruction) | FA rate is 93%. There are still 10 items waiting for FA process. | Cables (320-01597-00/01/02) are new designed, sample will be available in end-May. FA activity will be triggered after cable review completion. | MFG EE/ME/DE | 2022-06-30 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Supply chain/ supply of part | 3.E-2 | All material status, schedule and quantity should be reviewed | 500-11029-00 had shortage without ETA. Keep tracking with purchaser. | Has enough 500-11072-00 in stock as purchase select. | PID | 2022-05-03 16:00:00.0000000 +00:00 | 2022-05-04 17:52:08.0818568 +08:00 | 1
2 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA rate 93%. Not up-to-date: 10 items. | Cables (320-01597-00/01/02) are new designed, sample will be available in end-May. FA activity will be triggered after cable review completion. | MFG ME/DE | 2022-06-30 16:00:00.0000000 +00:00 |  | 0
0 | Marine | GPSMAP 79 Series | GMLA #1 | 2021-03-03 16:17:51.6189192 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 004 is not added to BOM. | 004-s has been added in BOM as attached. | MFG EE | 2021-03-16 16:00:00.0000000 +00:00 | 2021-05-06 16:32:02.1583939 +08:00 | 1
3 | Outdoor | Descent G1 | GMLA #2 | 2021-06-29 16:44:14.7262153 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. TST NG (1/2) > USB communication malfunction 2. button drop test NG (1/1) > Menu button malfunction 3. Accessory Impact test NG (1/1) > start button malfunction in top angle 35 degree 4. Tumble NG (1/1) > rattling vibration in FT3 | 1. TST NG (1/2) > USB communication malfunction Root cause : flux remain on charging pin cap while soldering battery Action : Have added fixture cover on charging pin area Validation : Update fixture picture in SOP by 8/17 2. button drop NG (1/1) > Menu button malfunction 3. Accessory Impact test NG (1/1) > start button malfunction in top angle 35 degree Root cause : spring on button board deformed Action : adding 0.2mm stop rib on housing Validation : 1 unit pass 10 cycle test, release ECO#226170 4. Tumble NG (1/1) > rattling vibration in FT3 Root cause : LRA peeled-off from the rear case Action : Add pressing force <50N, 10sec to active LRA tape correctly by 8/17 | MFG EE/ME/DE | 2021-07-22 16:00:00.0000000 +00:00 | 2021-07-20 09:07:10.1662796 +08:00 | 1
3 | Outdoor | Approach G12 | GMLA #2 | 2020-12-25 09:13:44.4670000 +00:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | 2 ELOT fail item: 1. Electrostatic Discharge (ESD) Immunity test 2. Drop (belt off) | 1. ESD fail in air 110V -25KV  Add foam on PCB in PR and verify in PR. 2. Belt clip came off in drop test. MME modified tooling, plan to verify in PR. 3. Sunscreen & DEET etching (Waive by Olathe due to the PC 141R material limitation is known) 4. Lens abrasion fail in unit level (Waive) --> Issue waive, abrasion test pass with raw material due to too much variety may cause fail in unit level. 5. IPX7 leakage after UVA --> Improve vendor cleaning process and gluing adhesive parameter in PR. Verify result in PR. see GMLA 3 | TWN Lab |  | 2021-02-06 13:49:11.6364839 +08:00 | 1
3 | Fitness | Forerunner 955 and 955 Solar | GMLA #2 | 2021-11-15 23:49:38.6146296 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Elot failed are show below : 5.2.4 : Temperature and Humidity Cycle Test 5.4.2 : Electrostatic Discharge (ESD) Immunity test 6.6.1 :Button focused drop test | 1.) Temperature and Humidity Cycle Test: CN Failure Retest is pass. Double confirmed by Live CN is also qualified. 2.) Electrostatic Discharge (ESD) Immunity test(Class D): After Air +25KV with charge cable, the unit touch panel some area is no work. (ESN: 3388322698)，EE is under analysis. >> Wait for thicker 1.3T verified in PR 3.) Button test: Observe in PR Build, OLA test is pass and TWN is reference only. All items will be double confirmed in PR build | TWN Lab | 2022-01-27 16:00:00.0000000 +00:00 | 2022-03-30 15:01:20.6386477 +08:00 | 1
3 | Outdoor | Delta Simple | GMLA #2 | 2021-12-02 17:27:57.0174302 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 2 ELOT fail items (1) Accelerated Weathering UV (1/1 NG): Case discolor (2) Tumble (1/1 NG): Shell crack | (1) Action: Discoloring is acceptable given that UVB is not present in the Solar spectrum. (2) Root cause: Insufficient design strength to do the strict experiment. Action: Will adjust the tooling and retest tumble before PR. passed with 1414T antenna shell cap + 121 glue Milestone: 1/14 Tooling trial shot 1/21 trail shot sample ready 1/28 Assemble with sample 2/9 Retest Tumble get result (ID color confirmed) 2/25 Tooling textured complete 3/4 PR mechanic parts ready 3/7 PR SMT start 3/14 PR ASSY start (3/7~3/14 OSP) | TWN Lab | 2022-01-20 16:00:00.0000000 +00:00 | 2022-02-16 16:19:53.2115395 +08:00 | 1
3 | Fitness | Tacx NEO Bike Plus_Shifter | GMLA #2 | 2022-02-07 17:57:04.0806893 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1 ELOT issue found (Button force test 5000 cycles ): abnormal click ratio | - The root cause of this failure was attributed to raw material or the limitation of equipment, so MME and Lab decided to improve both sides and retest again. - Snaptron has provided a 2nd batch of samples and the glue dispensing process should be modified. - Lab modified the test equipment with a 800g spring indenter. This will help fix the pushing force. - RTL has adjusted the cycle machine with a 800g spring intender, which helped control the maximum force. - MME assembled four units with Snaptron and Shanyo’s domes for RTL to verify the cycles. - Shanyo dome array verify – completed  Shanyo’s 200sets has arrived and the verification result is positive – Pass the cycle test (decided to set Shanyo as main source, ) | TWN Lab | 2022-03-06 16:00:00.0000000 +00:00 | 2022-04-29 10:13:09.7683081 +08:00 | 1
3 | Fitness | vivomove "Lite" | GMLA #2 | 2021-05-03 22:13:00.4262280 +08:00 | Product validation | 2.B-5 | DVP&R/ ELOT report summary (progress review) -- Action plan for test fail items | Elot NG and no action Plan*8 1. Temperature and Humidity Cycle Test (8/8 NG) 2. Salt Fog ( 1/8 NG) 3. Drop (2/2 NG) 4. Q-sun (4/4 NG) 5. UV-B (3/4 NG) 6. Tumble (10/12 NG) | [Closed] 1. Temperature and Humidity Cycle Test > Display haze*4 [Monitor PR ELOT result] > no reveal in PR ELOT Analysis: Cannot duplicate failure, retest 4 pcs test result was PASS. Action: In PR, lens thickness will be modified from 1.4t to 1.5t with better condensation resistance which may helped with solving haze issue. Keep tracking PR ELOT. [Closed] 2. Q-sun [Monitor PR ELOT] > no display yellowing in PR ELOT, only rear case yellowing and has been confirmed acceptable by design team. 2.1 Display yellowing*4 > DE analyze yellowing cause by display polarizer damage. Retest with display level, result pass. Retest 4pcs black SKU & 2pcs sunstone, result pass. DE refer this yellowing issue to a special case and keep watching this phenomenon at next phase. [Solved] 2.2 After Q-sun can’t boot*1 + 2.3 After Q-sun batt voltage drop quick*1 Root Cause: unit wake up under HT cause battery capacity been damaged by over discharge Action: Modify new software & layout to solved wake up issue. Test UV-B 4 pcs pass, Q-sun 3 pcs pass on 6/15. 3. UV-B [Solved] 3.1 Back shell yellowing*3 Root cause: discoloring cause by material limitation (XE 11107) > ID team & Design team consider as low risk after checking the discolor shell. [Solved] 3.2 After UV-B can’t charge*3 Root Cause: unit wake up under HT cause battery capacity been damaged by over discharge Action: Modify new software & layout to solved wake up issue. Test UV-B 4pcs pass, Q-sun 3pcs pass on 6/15. 4. Drop > Lens crack*1 [Solved] Root Cause: Due to the Lens is higher than housing Action: Increase the height of housing to decrease the gap between lens & housing. (Gap: 0.3mm > 0.02mm) Validation: New height housing 10 pcs drop pass & 10 pcs tumble/ 1 pc fail, fail at 70~80 cycle. Design team consider as low risk. 5. Tumble [Monitor PR ELOT] > PR ELOT tumble fail*3, further analysis tracking in GMLA3. 5.1 Hand shift*3 5.2 Units shut down & reboot during cycles*4 Root Cause: units appear step loss in user mode with high speed Counter/CCW turning even without tumbling. Action: EE & SW improve SW stability and gearbox driving waveform to solve step loss. Validation: New waveform and SW been applied in 20pcs experiment, result shows no step loss or unexpected shut down. Keep monitoring with PR result. [Monitor PR ELOT] > no reveal in PR ELOT 5.3 Abnormal sound*5 Analysis: Unit function normal, CT scan shows no component damage. The fail mode cannot be duplicated after retest. Keep monitoring the result in PR. [Solved] 5.4 TP malfunction*2 Root Cause: TP touch invalid due to I601 IC crack during tumble Action: Apply underfill on 4 units and retest result pass [Solved] 5.5 Lens drop*3 Root Cause: Due to the Lens is higher than housing Action: Increase the height of housing to decrease the gap between lens & housing. (Gap: 0.3mm > 0.02mm) Validation: New height housing 10 pcs drop pass & 10 pcs tumble/ 1 pc fail, fail at 70~80 cycle. Design team consider as low risk. | TWN Lab | 2021-08-26 16:00:00.0000000 +00:00 | 2021-10-21 13:37:02.8038965 +08:00 | 1
3 | Marine | GPSMAP 79 Series | GMLA #2 | 2021-06-16 17:17:01.6269250 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 6 fail items (1) Water / Dust Resistance (2/2 NG): The machine was water ingress fail (2) Accelerated Weathering Xenon (1/1 NG): 72 hrs screen burn & 120 hrs bubble (3) Accelerated Weathering UV (1/1 NG): 120H bubble & yellowing (4) Body and Wearable Chemicals (2/3 NG): Yellowing (5) High Temp., Max Voltage Life (1/1 NG): Display bubble & discolor (6) High Temp., Min Voltage Life (1/1 NG): Bubble fail after 48H | Fail item (1) : IPX6 fail – low risk Analysis: Unit + Mount: IPX7 Pass, but IPX6 Fail because water comes from the battery cap which connects to mount. LAB re-test unit level and result is pass. Action: Need to define the "IPX6 is for unit level only" in website/gift box/manual. -Closed Fail item (2)(3)(5)(6) : LOCA peeling & Yellowing – high risk a. LOCA peeling Action: The verifications of LOCA 153 and 180 are positive with adding glue 53 on front case after 336h Q-sun. -Closed b. Yellowing Analysis: suspect to the much liquid crystal of display. Action: decrease the thickness of liquid crystal from supplier, and validation on PR build. The improved display is under UVB testing for 200h, and the MP and improved display are yellowing in the test. DE will apply the improved display to MP and keep the display improving. -Closed Fail item (4): White part Chemicals fail – medium risk Analysis: The material of white part is same with watchband which passed on Body and Wearable Chemicals in past products. Action: Re-test ELOT had passed. -Closed | NPI/EE/ME/DE | 2021-07-14 16:00:00.0000000 +00:00 | 2021-08-16 11:35:51.9872011 +08:00 | 1
2 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Product development | 3.A-10 | Verify the test program of SMT and ASSY station before PR build for new SW release | PR SW has an issue with HTMTF station. SE has a solution but still needs to wait for the cycle test result with the latest release patch. | Wait for SW 1.15 released. | MFG EE |  |  | 0
2 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry > 10%: 1. ST (14.47%)_MIC MAX Amp.(dB) - Compare with Golden (7.89%) 2. FT2_GPS (14.47%)_C/No by ref (3.95%) | 1. ST (14.47%)_MIC MAX Amp.(dB) - Compare with Golden (7.89%) -Root cause: The fixture is unstable. ITMXP records the unstable amp. during golden sample calibration. -Action: Add the spec in the calibration program. ITMXP will show fail if golden calibration failed. -Evidence: Acoustic engineer already adds spec. in the calibration program. 2. FT2_GPS (14.47%)_C/No by ref (3.95%) -Root cause: EE assumes that the absorber material peels off. -Action: Add absorber material to the chamber -Evidence: EE will compare the result between after the modification. | NPI | 2022-05-26 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT failed: 1. Mechanical vibration_Automotive profile (2/2): Auto power off at the fore/side axis 2. Mechanical vibration_Performance profile (2/2): One unit cable is disconnected at the fore/side axis, and the other cable is disconnected at the fore axis. | 1. Mechanical vibration_Automotive profile (2/2) -Failure description: ‧Auto power off at the fore/side axis -Root cause: The cable abrased after the vibration test. -Action: OLA test 76% automotive profile 60hr for each axis. The first two axes pass the test, which means it can pass 6000 user experiences. Even though it failed at the third axis, the DUT can function after changing a new cable. It is not a device issue. OLA agrees with this result and waives the failed result of TWN's test. 2. Mechanical vibration_Performance profile (2/2) -Failure description: One unit cable is disconnected at the fore/side axis, and the other cable is disconnected at the fore axis. -Root cause: The cable abrased after the vibration test. -Action: OLA test 76% automotive profile 60hr for each axis. The first two axes pass the test, which means it can pass 6000 user experiences. Even though it failed at the third axis, the DUT can function after changing a new cable. It is not a device issue. OLA agrees with this result and waives the failed result of TWN's test. | TWN Lab | 2022-06-02 16:00:00.0000000 +00:00 | 2022-06-01 10:04:52.4868865 +08:00 | 1
3 | Marine | GMR Fantom 18x/24x | GMLA #2 | 2021-06-22 16:37:00.6313327 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. 18" white (1) Thermal shock (1/1 NG): VT fail 2. 24" white (1) Operating Hot/Cold Unit Performance (1/1 NG): VT fail from HT (2) Thermal shock (1/1 NG): VT fail 3. 18"/24" black Wait for ELOT test so there is no fail item | All HT/CT VT fail machine have passed IPX6 and he external mechanical parts are the same as previous model so the design team believes that the risk is small. We have closed this issue base on above evidence. | TWN Lab | 2021-06-28 16:00:00.0000000 +00:00 | 2021-06-29 17:43:55.1511217 +08:00 | 1
3 | Automotive | Dash Cam Live (LTE) | GMLA #2 | 2022-04-26 13:30:35.4785799 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ※ 10 ELOT issues found 1. Operating Hot/Cold Unit Performance (2/2) 2. Storage Hot/Cold Unit Performance (1/2) 3. High Temp., Max Voltage Life (1/1) 4. High Temp., Min Voltage Life (1/1) 5. Bluetooth Connection Test (1/1) 6. High temp life recording (1/1) 7. Tumble (1/1) 8. Drop (1/1) 9. Magnetic Field (1/1) 10. Abrasion Test (1/1) | [On-going] 1. Operating Hot/Cold Unit Performance - Root cause: High temperature inside the unit. Found 1 pcs white line & 1 pcs cross talk & 1 pcs unit shut down. - Action: (1) White line is under EE analysis. (changing sensor IC) (2) Cross talk: Implement new SW to add a High temp time-out mechanism for PR build (3) Shut down is under EE analysis. 2. Bluetooth Connection Test (1/1) - Root cause: FFP did not support the Bluetooth connection function. - Action: Update SW v0.41 can fix this issue. 3. Drop - Root cause: Insufficient mechanical strength - Action: Display crack: Modify 145-03730-00 to protect cover lens and improve lens positioning. Separated cases: Modify 145-03730-10 to increase hook engagement Keep re-test the ELOT result on FFP2 [Close] 1. Storage Hot/Cold Unit Performance (1/2) 2. High Temp., Max Voltage Life (1/1) 3. High Temp., Min Voltage Life (1/1) 4. High temp life recording (1/1) - Root cause: Unstable SW. - Action: Re-test and update SW 006-B4143-00 from v0.28 to v0.38, all units were passed under high temperature. 5. Tumble (For reference only.) 6. Magnetic Field (Waived, for reference only in PND) 7. Abrasion (Can be waive.) | TWN Lab | 2022-06-16 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Forerunner 255S | GMLA #2 | 2021-12-22 20:32:55.7975659 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Elot failed are show below : 1. Drop failed 2.Tumble failed | The IC has been replaced. Issue 1. Drop failed (1)Can't turn on due to I 102 (570-00050-00) thermal ball crack, will replace 570-00037-01 (2) Olathe not willing to change the design, they can accept for the click feeling decay after drop. Issue 2. Tumble failed (1) Can't turn on due to I 102 (570-00050-00) thermal ball crack, will replace 570-00037-01 (2) Display FPC was tore due to the hard coating on the JDI Display once manufacturing process (like as attach, soldering,and lock connector) | TWN Lab | 2022-01-27 16:00:00.0000000 +00:00 | 2022-03-30 15:58:47.1256777 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 6" | GMLA #3 | 2022-04-08 11:13:56.5468443 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 002-S0033-00/ 161-05924-00/ 007-04203-00 haven't been turned A yet. | Please convert to version A. @Sattler, Karl [WK18] ECO#240723, ECO#241091 and ECO#241196 have been submitted. | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-27 22:06:26.7090777 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 6" | GMLA #3 | 2022-04-08 11:13:56.5468443 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04203-00 hasn't been turned A yet. | Please convert to version A. @Sattler, Karl [4/19] ECO#240723 | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-19 10:43:36.4502433 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 6" | GMLA #3 | 2022-04-08 11:13:56.5468443 +08:00 | Process validation | 3.D-9 | PR Retry Rate review -- (Consumer) Target of each station: < 10% -- (AOEM) Check if meet customer requirement , if no customer requirement, internal target of each station: < 5% | Retry rate > 10% 1. ST (42.74%)_MIC MAX Amp.(dB) - Compare with Golden (29.91%) 2. FT2_GPS (11.67%)_C/No by ref (10%) | 1. ST (42.74%)_MIC MAX Amp.(dB) - Compare with Golden (29.91%) -Root cause: ‧ It seems that the chamber is not stable and don't calibrate well when op test the first four job (15832339; 15832340; 15832342; 15832344). Retest rate for job (15833038; 15833039; 15833040; 15834215) was decreased after calibration. -Action: ‧ Acoustic engineer adds chamber calibration spec. to make sure that the chamber is well calibrated. -Evidence: ‧ ITMXP modified on 4/6. 2. FT2_GPS (11.67%)_C/No by ref (10%) -Root cause: ‧ The CN value of the redesign PCB is weaker about 2 db than the original PCB. May need a new golden for the redesign unit. -Action: ‧ It is the first build for redesign. EE will provide separated golden for dezl 610 & redesign. | NPI | 2022-05-19 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezlCam OTR710 & RV 795 | GMLA #3 | 2022-05-24 17:53:04.8934419 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | The completed rate is 34.48% on 5/24. The ELOT result is expected to be released on 5/30. | The ELOT result is expected to be completed on 5/30. | TWN Lab | 2022-05-29 16:00:00.0000000 +00:00 |  | 0
0 | Automotive | Dezl Headset | GMLA #1 | 2021-05-25 17:12:15.1357351 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-MPS is not added in BOM, and not be released. | Received MPS draft for FP1 build. 004 document will be updated after FP1. Updated: 004-01114-00 has been released under 010-02581-00 on 6/17 | MFG EE | 2021-09-29 16:00:00.0000000 +00:00 | 2021-06-27 23:29:29.8758512 +08:00 | 1
0 | Fitness | Forerunner 255S | GMLA #1 | 2021-04-19 20:41:07.0669031 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01086-00 is NRL | Ongoing, aims to complete by WK20 | MFG EE | 2021-05-13 16:00:00.0000000 +00:00 | 2021-05-18 11:51:55.4607666 +08:00 | 1
3 | Fitness | Venu Sq 2(IMP) | GMLA #2 | 2022-04-08 09:36:28.3314319 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Failed Item: Accelerated Weathering Xenon (2/5)_ESN3410112159 Lens floating, ESN3410112297 Water leakage leads the LCM iodine release. After Q sun immersion (no pressure 5atm) 3pcs:5ATM→No water leakage. | (Closed) *Accelerated Weathering Xenon Fail (1/5) - Failure Description: After accelerated weathering xenon test, water flow into HRM glass and LCM is discolored. - Root Cause: The based plate of Dispensing equipment is tilted around 0.2 mm and cause based plate cannot fit fixture correctly. - Action: See 2.D-8 | TWN Lab | 2022-05-05 16:00:00.0000000 +00:00 | 2022-04-29 16:00:53.8530888 +08:00 | 1
3 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1 ELOT NG found: Body and Wearable Chemicals (2/2) DEET caused the rear case crack and VT Fail. | Since the materials have been adopted from inReach mini series and no RMA issue was reported. Will discuss with design team ME to waive the issues. @Hsu, Alvin [0321] confirmed the issue can be waived. 04/13 Lab : FA Result : ME Confirmed with DME Curt that since it's inevitable for this kind of PC material to be damaged after chemical test, this issue is as expected and can be waived. | TWN Lab | 2022-03-20 16:00:00.0000000 +00:00 | 2022-03-21 13:48:31.2648895 +08:00 | 1
3 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Product package drop (1/2 fail): Paper insert and Polybag are broken | [Result] The unit had no damage after the drop test, but the carton and plastic bag were found 2cm of length damage. [Mitigation] 1. T3 recommended that the accessory bag can be changed to bubble bag and OLA accept this change. 2. Change bag from 172-00021-26 zipper bag to 172-00036-00 bubble bag. 4/20 Re-test pass. ECO#241394 | TWN Lab | 2022-04-21 16:00:00.0000000 +00:00 | 2022-04-27 11:09:30.3793385 +08:00 | 1
1 | Marine | LiveScope XR | GMLA #3 | 2022-04-07 18:24:15.3535665 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | Salt Water Immersion Test and Validation Run-in Test are testing | 1. Salt water immersion test: 4/14 PASS 2. Validation run-in test: Run test for 3 months. 1st month's test is PASS. We change 2~3 month test result to LMS ID 21700 for tracking. Original LMS ID will be closed. The expected test complete date is 6/26 | TWN Lab | 2022-06-26 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Dezl Headset | GMLA #2 | 2021-11-18 15:40:02.6868420 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Failed item: 1. Mechanical vibration (2/2) - Unit sloped to the table. MIC and slider were broken. 2. Mechanical shock (2/2) - Unit popped out from the shelf. | 1. Mechanical vibration Z axis (Vertical) failed (2/2) -Description: Unit sloped to the table. MIC and slider were broken. -Root cause: The loosen slider caused it to slope to the table. -Action: 1). Add 0.3mm mylar on the slider (145-03865-20 or 145-03865-60) 2). Hinge cushion material change (silicone-> rubber) (253-01425-10) 3) Still fail the test with parts changing. Olathe accepted running truck profile with a constrained headset instead of the MOPAR profile. -Evidence: 1. Machined sample passed truck profile. 2. PR1 unit passed ELOT vibration test. (Closed) 2. Mechanical shock Z axis (Vertical) failed (2/2) -Failure description: Unit popped out from the shelf. -Root cause: 20G vertical shock is not user mode. MME is discussing with DME about the vertical shock spec. (Under discussion)(ME_Angus) -Evidence: 1. OLA test 12G (Same as dezl OTR 10") and pass. In the reality, if it’s more than 12G, the PND will fall first. 2. Moreover, tumble and drop test pass. Even if the headset fell down, there won't be any damage on it. (Closed) | TWN Lab | 2021-11-25 16:00:00.0000000 +00:00 | 2022-01-27 10:47:35.9122885 +08:00 | 1
3 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | NG *1 and EE under analysis : High temp and humidity | The reset mechanism design is imperfect, will remove IC (670-00198-xx) next build | TWN Lab | 2021-10-28 16:00:00.0000000 +00:00 | 2021-10-25 23:18:45.9025050 +08:00 | 1
3 | Marine | LiveScope XR | GMLA #2 | 2021-12-06 18:30:15.8208834 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Pendulum impact test (barrel mount): 45 degree fail due to mount damage | Pendulum impact test passed, The ME team has done the optimization and the tooling modification and the material way will be used with GVN-5H (impact resistance additive) | TWN Lab | 2021-12-30 16:00:00.0000000 +00:00 | 2022-01-26 12:41:55.9471545 +08:00 | 1
1 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #3 | 2022-01-26 10:15:34.6385814 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 214-10025-00 is still v001, not ver. 0A | 214-10025-00 is released to v0A on 2/12 | MFG ME | 2022-02-11 16:00:00.0000000 +00:00 | 2022-02-18 08:59:24.6578042 +08:00 | 1
0 | Marine | ECHOMAP UHD2 (Keyed) 5" | GMLA #1 | 2021-01-27 10:34:39.3216104 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- document from OLA for WP -- Release to version 001 -- Add-in BOM | 004-MPS is not added to BOM | OLA EE needs more time for design verification and plan to add 004 into BOM before FP1. (04/09) 2 main design issue under checking: Sonar testing & GPS antenna | MFG EE | 2021-04-08 16:00:00.0000000 +00:00 |  | 0
0 | Outdoor | Instinct Hybrid Analog/Digital(Ripley) | GMLA #1 | 2021-11-08 18:33:22.1539934 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | FP1 will released verison 001. | Keep contact with PM and target to release before FP1 build. | MFG EE | 2022-01-09 16:00:00.0000000 +00:00 | 2022-01-11 16:00:02.8816220 +08:00 | 1
3 | Fitness | Edge Explore 2 | GMLA #2 | 2022-03-03 10:56:18.6674347 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT 7 items fail 1. Accelerated Weathering UV (1/1) 2. Body and Wearable Chemicals (1/1) 3. Electrostatic Discharge (ESD) Immunity test (1/1) 4. Drop 90cm (1/1) 5. Mechanical Vibration_Motorcycle (1/1) 6. Mechanical Vibration_Recreation/Fitness(1/2) 7. Tumble (1/1) | [Power SKU issue] Accelerated Weathering UV: Design team agreed to bypass this item. Body and Wearable Chemicals: The DEET test will be removed after discussed with the design team. PR ELOT Pass - Issue closed Electrostatic Discharge (ESD) Immunity test No ESD issue with standard SKU, will keep tracking this issue on powered SKU. Drop 90cm: Modify the mold to increase the thickness of the plastic. New housing had passed the preliminary validation test, keep tracking on PR. PR ELOT Pass - Issue closed Mechanical Vibration_Motorcycle: Will start the new tooling for powered SKU on 3/7. The MP date of powered SKU is on 8/15. Mechanical Vibration_Recreation/Fitness: Will start the new tooling for powered SKU on 3/7. The MP date of powered SKU is on 8/15. Tumble: Modify the mold to increase the thickness of the plastic. New housing had passed the preliminary validation test, keep tracking on PR. | TWN Lab | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
3 | Fitness | Forerunner 255 | GMLA #2 | 2021-12-21 19:46:45.2040739 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Elot failed are show below : 1. Drop failed 2. Tumble failed | Issue 1. Drop failed (1) Olathe not willing to change the design, they can accept for the click feeling decay after drop. Issue 2. Tumble failed (1) Display FPC was tore due to the hard coating on the JDI Display once manufacturing process (like as attach, soldering,and lock connector) (2) Can't turn on due to I 102 (570-00050-00) thermal ball crack, will replace 570-00037-01 (3)5 atm failed : PR no same failure (3)-1: Main sealing: some bubble be inspected by CT (NPI analysis) (3)-2: Len/Bezel : Low adhesion on bezel and glue, CR is evaluating the plasma process. | TWN Lab | 2022-01-27 16:00:00.0000000 +00:00 | 2022-03-30 16:01:52.5987550 +08:00 | 1
3 | Automotive | dezl OTR Series 2022 - 8" | GMLA #2 | 2022-01-27 14:46:07.4505995 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Bluetooth Connection Test (2/2)_Garmin dezl APP failed connection. | [Closed] Bluetooth Connection Test fail (2/2). - Failure description: dezl DUT can be paired with the mobile by BT, but it won't automatically reconnect after disconnection by the isolated box. - Status: EE discussed with OLA SW, possibly related to App issue. Use the new app released by OLA still failed, and still under analysis. @Werling, Brett @Ho, Tony -DUT pass the test by new SW on 3/15. -Evidence: LMS-0019600-8-TW PR build pass. | TWN Lab | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-01 10:57:43.7258013 +08:00 | 1
2 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Product development | 3.A-14 | Receive 174- packing instruction from Design team for packing SOP | No 174-packing instruction released on BOM | Need @Lee, Milly’s advice for release schedule. | NPI | 2022-05-05 16:00:00.0000000 +00:00 |  | 0
2 | Fitness | Edge Explore 2 | GMLA #3 | 2022-05-03 11:11:09.4079014 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | FA completed rate is 60% - ME part 33 items not ready - DE part 9 items not ready (Detail list as attached) | ME parts FA is planned to complete before 5/23. @Zheng, Eason DE parts FA is planned to complete by 5/16 due to Kapton tape ECO. @Chien, Mike(Display) | MFG ME/DE | 2022-05-22 16:00:00.0000000 +00:00 |  | 0
0 | Fitness | vivomove Trend (previously "4") | GMLA #1 | 2021-10-22 23:00:19.8693026 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004 is not added-in BOM and not released (NRL) | 004 had be released on 11/4. | MFG EE | 2021-11-04 16:00:00.0000000 +00:00 | 2022-03-31 17:00:43.7917722 +08:00 | 1
0 | Fitness | Forerunner 255 | GMLA #1 | 2021-04-18 23:12:11.8674891 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01086-00 is NRL | MPM and TW EE will push the design team for the first version release this week. | MFG EE | 2021-04-22 16:00:00.0000000 +00:00 | 2021-05-18 11:51:10.6036715 +08:00 | 1
0 | Fitness | vivosmart 5 (Franklin) | GMLA #1 | 2021-05-17 15:06:13.9266871 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004 is not added-in BOM | Need PjM to add 004- doc in BOM. 004- has been updated in BOM by 9/15 | MFG EE | 2021-06-24 16:00:00.0000000 +00:00 | 2021-09-28 13:34:57.5860699 +08:00 | 1
0 | Outdoor | eTrex SE | GMLA #1 | 2021-12-20 16:53:27.9827922 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01133-00 not released to version 001 and not release to the BOM | OLA EE has added the MPS to the BOM on the last release, and it is at rev. 1. | MFG EE | 2022-04-14 16:00:00.0000000 +00:00 | 2022-04-11 08:11:37.5835114 +08:00 | 1
0 | Marine | GPSMAP 9000 - 24" | GMLA #1 | 2022-03-07 14:30:03.1352847 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01152-00 is added in BOM but not released (NRL). Need to release it to v001. | ECO#234993 was released on 2021/12/14, but 004-01152-00(it will be based on the 86xx) still NRL. @Eugene.Li@garmin.com @Goughnour, Kevin | MFG EE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
0 | Fitness | Edge Explore 2 | GMLA #1 | 2021-10-29 15:56:19.1863262 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | This is TWN design project. the MPS is planed to IR before FP1 start. This project design is similar with Edge 1030+. | EE will release the initial MPS before 1st FP start. | MFG EE | 2021-11-29 16:00:00.0000000 +00:00 |  | 0
0 | Marine | GPSMAP 9000 - 19" | GMLA #1 | 2022-05-09 15:33:04.7405657 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01152-00 is not released (NRL) | ECO#234993 was released on 12/14, but 004-01152-00 still NRL. @Li, Eugene @Goughnour, Kevin | MFG EE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | Tread 8" OEM w/ CAN | GMLA #2 | 2022-02-23 10:19:51.8518228 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | ELOT failed: 1. Thermal shock (1/2)_DUT reboot. 2. High Temp., Min Voltage Life (1/1)_Screen flicker. 3. Battery connector drop (1/1)_display broken | [Closed] 1. Thermal shock (1/2)_DUT reboot. -Root cause: ‧ PCB had a repair record. It is related to the empty soldering issue as Tread 8". -Action: ‧ This issue is the same as Tread 8" OEM solder empty issue. It will be tracked by the Tread 8". -Evidence: ‧ 3/1 new DUT pass the ELOT. [Closed] 2. High Temp., Min Voltage Life (1/1)_Screen flicker. -Root cause: ‧ The screen flicker issue follows the scene. It will be fixed after replacing the screen. The high temp. 85-degree excesses the IIS spec. (80 degrees). -Action: ‧ Do the test again with a new DUT in 80 degrees then check the status. -Evidence: ‧ 3/15 2 DUTs pass the test. (LMS-0021562-1-TW) [Closed] 3. Battery connector drop (1/1)_display broken -Root cause: ‧ DE checks there is a cracking point on the display. DE doubt there is a small stone or uneven floor. -Action: ‧ 90cm drop test pass. OLA pass this test. | TWN Lab | 2022-03-10 16:00:00.0000000 +00:00 | 2022-03-17 17:55:14.5064576 +08:00 | 1
3 | Automotive | dezlCam OTR710 & RV 795 | GMLA #2 | 2022-01-27 13:27:53.8448397 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | 1. Mechanical vibration (4/4)_power off (4/4), suction cap bracket broken (3/4) | -Failure description: ‧ Y axix (vertical) power off ‧ X axis 3pcs mount broken ‧ Z axis power off ‧ 4/4 Powe off , 3/4 suction cup racket broken -Root cause: ‧ Suction cap arm strength is not enough to support. -Action: 1. Change material to PC + glass fiber 2. Wide the suction cup arm to strengthen the stiffness. 3. Tune the mount/rear case fitting tighter. Vibration test result: -Power off (4/4) -Wide arm + material change to PC+GF*2pcs: Pass -Same arm + material change to PC+GF*1pcs: Fail →OLA did the same material with a wide arm test pass. →Take the action: Wide arm + same material + modified mount It will be test at the PR build. | MFG ME | 2022-02-06 16:00:00.0000000 +00:00 | 2022-03-17 17:44:53.3729083 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 88.00% on 4/11. All the tests will be finished before 4/15. Not finished: 1. Product package drop 2. Shipping vibration 3. XRF | All the tests will be finished before 4/15. [4/15] All the tests are completed on 4/13. | TWN Lab | 2022-04-14 16:00:00.0000000 +00:00 | 2022-04-15 09:27:14.6321806 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Process development | 3.C-7 | SMT process readiness review (need to check the available SMT equipments on the MP production line, ex: soldering printing/ pick & place/ AOI/..) -- Peak temperature review of new component -- Smart factory (105 Control setting) -- New component design review (refer to DFM report) -- Minimum component review | 500-10780-00/500-10781-00/590-00109-00 max reflow temp. are less than 250°C | The components less than 250 degrees have been checked by the reflow profile board. The test result passed. The information had been added to SMT VIP. | NPI | 2022-04-11 16:00:00.0000000 +00:00 | 2022-04-12 11:23:56.3893207 +08:00 | 1
1 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Process validation | 3.D-14 | Golden sample and bad sample ready and registered in internal system -- Expired date set-up for golden sample and bad sample | CT/HT/FT*2 for CN_not provided yet. ST*2_not provided yet. | All the golden samples will be provided before 4/15. | MFG EE/ME/DE | 2022-04-14 16:00:00.0000000 +00:00 |  | 0
2 | Automotive | dezl OTR Series 2022-10" | GMLA #3 | 2022-04-11 18:52:35.0545771 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME: 94% (not up-to-date * 5), DE: 100% | MME will complete FA on 04/26. @Chen, Mac | MFG ME | 2022-04-26 16:00:00.0000000 +00:00 |  | 0
0 | Marine | GPSMAP 9000 - 22" | GMLA #1 | 2021-12-09 15:38:58.2593981 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004- MPS in BOM. Need to release 004 and add it to BOM | Please confirm 004- MPS released date. [12/14] ECO#234993 was released on 12/14, but 004-01152-00 still NRL. | MFG EE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
3 | Automotive | dezl OTR Series 2022 - 7" | GMLA #2 | 2022-01-26 17:46:50.3929354 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Vibration test failed (2/2)_film abrasion after Vertical axis | [Closed] Mechanical Vibration fail (2/2). - Failure description: After vibration test found the LCM showed white mark(mura). - Root Cause: Supplier found particle between the diffuser and the LGP/Frame, but this display is corresponding with IIS spec.. However, the UPBEF is scratched due to the particle pressing the B/L film. - Action: Suppliers will improve the cleaning process of 440-00311-01 to ensure quality. Need DE discuss with OLA for ELOT fail results. @Lin, Austin(Display) - Evidence: PR build mechanical vibration pass. (LMS-0019600-4-TW) | TWN Lab | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-01 13:56:38.8217842 +08:00 | 1
3 | Automotive | dezl OTR Series 2022-10" | GMLA #2 | 2022-02-09 12:48:46.2399230 +08:00 | Product validation | 2.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Fail item: 1. Bluetooth Connection Test (2/2) | [Closed] Bluetooth Connection Test fail. - Failure description: dezl DUT can be paired with the mobile by BT, but it won't automatically reconnect after disconnection by the isolated box. - Status: EE discussed with OLA SW, possibly related to App issue. Use the new app released by OLA still failed, and still under analysis. @Werling, Brett @Fu, Johnny -DUT pass the test by new SW on 3/15. -Evidence: LMS-0019600-12-TW PR build pass. | TWN Lab | 2022-03-31 16:00:00.0000000 +00:00 | 2022-04-01 10:59:31.4060861 +08:00 | 1
4 | Marine | ECHOMAP UHD2 (Keyed) 7" | GMLA #2 | 2021-09-22 18:07:03.5597006 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | 105-04305-10: ASSY Screw (front case & rear case) is incomplete. Wait for NPI to provide the press fixture. | Had finished and passed. | PQE | 2021-09-28 16:00:00.0000000 +00:00 | 2021-09-29 14:17:21.7411472 +08:00 | 1
4 | Fitness | Forerunner 255S | GMLA #2 | 2021-12-22 20:32:55.7975659 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | HRM : I101/ I103 failed MB: I101/ I103 / I601 failed | Dispensing underfill for strain gauge failed IC. | PQE | 2021-12-22 16:00:00.0000000 +00:00 | 2021-12-23 11:37:29.5451186 +08:00 | 1
1 | Automotive | Tread 8" OEM w/ CAN | GMLA #3 | 2022-04-26 16:31:47.4910762 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | There are 22 items haven't turned A yet. 010-02507-70, 010-02507-93, 011-05922-00, 011-05922-10, 011-05922-20, 011-05922-30, 011-05922-40, 011-05961-00, 011-06088-01, 011-06088-11, 011-06096-00, 015-05922-0X, 015-05922-0X, 015-05922-1X, 015-05922-2X, 015-05922-3X, 015-05922-4X, 015-06088-0X, 145-03659-B2, 145-03659-C0, 320-01597-01, K00-01378-00 | Cables (320-01597-00/01/02) are new designed, sample will be available in end-May. Version will be finalized after cable verification. | NPI/ME/DE | 2022-06-30 16:00:00.0000000 +00:00 |  | 0
1 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Product development | 3.A-6 | All BOM parts should be version A before PR (Except for 006-/ 174- Packing instruction/ 190-0 User manual…) | 002-S0033-00, 011-05925-00, 011-05948-T9, 012-04158-T9, 017-04158-00, 161-05925-00 hasn't turned A yet. | Please convert to version A. @Sattler, Karl ECO#240576 has been released. [WK18] All GPNs have been converted to version A. | NPI/ME/DE | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-27 23:01:08.8117389 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Product development | 3.A-7 | Finalize unit level packaging design -- Customer/ Garmin requirement need to be included | 007-04204-00 hasn't turned A yet. | Please convert to version A. @Sattler, Karl [4/19] ECO#240723 | MFG ME | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-19 10:44:05.4302616 +08:00 | 1
3 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Product validation | 3.B-5 | (Consumer) Review ELOT result (AOEM) Review DVP&R result -- Action plan for test fail items | Drop (1/1)_front case and back shell separated. | Drop (1/1)_front case and back shell separated. -Root cause: There are only four screws for the front case and rear case assembly. After the drop test, the case may be squeezed. -Action: 1. Press the case, and it can be assembled as the appearance before. 2. ME checks the components inside are without damage. 3. MME will discuss with DME. (2022/04/12) There is no components damage inside the unit and after press the case all the functions are work. MME has discuss with DME, this issue can be closed. | TWN Lab | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-12 09:25:14.2956004 +08:00 | 1
1 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Product validation | 3.B-8 | (Consumer) Review ELOT completed status (AOEM) Review DVP&R schedule | 82.35% on 4/11. All the tests will be finished before 4/15. Not finished: 1. Product package drop 2. Shipping vibration 3. XRF | All the tests will be finished before 4/15. [4/15] All the tests are completed. | TWN Lab | 2022-04-17 16:00:00.0000000 +00:00 | 2022-04-15 09:24:30.6322810 +08:00 | 1
2 | Automotive | dezl OTR Series 2022 - 7" | GMLA #3 | 2022-04-11 17:27:32.0898730 +08:00 | Supply chain/ supply of part | 3.E-4 | Material PPAP/ FA (in MPM system) should be ready (FA Percentage should be provided by QE. FA Percentage: %) (phase#1 modification is under discussion by SM team) | ME: 96% (not up-to-date *2), DE: 100% | 92% on 5/23. Only left CLA and accessaries. Accessary MP date will be 6/6. | MFG ME/DE | 2022-06-05 16:00:00.0000000 +00:00 |  | 0
0 | Marine | GPSMAP 9000 -27" | GMLA #1 | 2022-05-09 15:34:40.7338135 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004-01152-00 is not released (NRL) | ECO#234993 was released on 12/14, but 004-01152-00 still NRL. @Li, Eugene @Goughnour, Kevin | MFG EE | 2022-06-09 16:00:00.0000000 +00:00 |  | 0
4 | Outdoor | inReach Messenger | GMLA #2 | 2022-03-03 18:25:02.0953748 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | Strain guage NG on install battery connector. Cause the strain force up to 715 um/m on I205. (spec: 350) | ELOT pass and designer agree to apply underfill. @Chen, Andy(PE) | NPI/PQE | 2022-03-24 16:00:00.0000000 +00:00 | 2022-04-15 09:52:18.3864603 +08:00 | 1
4 | Fitness | vivosmart 5 (Franklin) | GMLA #2 | 2021-10-18 16:23:43.7458162 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | NG : PRNP、lock LCM connector、Press Batt. | Failure description: ‧ NG station : PRNP、lock LCM connector、Press Batt. Root cause: ‧ Board thickness is too thin Action: ‧ Apply underfill next build | PQE | 2021-10-27 16:00:00.0000000 +00:00 | 2021-10-25 23:20:39.2773459 +08:00 | 1
4 | Fitness | Forerunner 255 | GMLA #2 | 2021-12-21 19:46:45.2040739 +08:00 | Process validation | 2.D-3 | Strain Gauge measurement result of latest PCB version (all process including de-panel, SMT, PCBA version, ASSY) | HRM : I101/ I103 failed MB: I101/I103/I601/ I603 / I500 failed | Dispensing underfill for strain gauge failed IC. | PQE | 2021-12-22 16:00:00.0000000 +00:00 | 2021-12-23 09:33:29.1412644 +08:00 | 1
0 | Marine | Panoptix LiveScope HD (LVS34HD Transducer) | GMLA #1 | 2021-07-29 16:16:11.7866974 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004- MPS release and not in BOM | EE team and Design team to review and release the document to the BOM | MFG EE | 2021-10-14 16:00:00.0000000 +00:00 | 2021-10-14 09:15:21.9659953 +08:00 | 1
0 | Marine | RV Fixed Displays - 7" | GMLA #1 | 2022-03-01 17:19:42.3144265 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004-MPS in BOM | Waiting for design team release MPS plan. | MFG EE | 2022-04-17 16:00:00.0000000 +00:00 |  | 0
0 | Marine | RV Fixed Displays - 10" | GMLA #1 | 2022-03-01 17:18:23.0112740 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | No 004-MPS in BOM |  | MFG EE |  |  | 0
0 | Marine | GMR xHD3 Magnetron Open Arrays | GMLA #1 | 2022-04-28 16:09:30.5529512 +08:00 | Product development | 1.A-8 | Unit: Review preliminary 004- MPS from OLA for WP -- Release to version 001 -- Add-in BOM | 004 is not released and added in BOM |  | MFG EE |  |  | 0